## Sheet1
Scheduled Period | Priority | Revision | Order Type | Main WorkCtr | Oper.WorkCenter | Order | Description | Opr. short text | System status | User status | Work | Actual work | Unloading Point | Bas. start date | Basic fin. date | Earl.start date | Latst Allowd.FinDate | Earliest StrDate | Activity | Op.SystemStatus | Oper.UserStatus | Functional Loc. | Description.1 | Subnetwork of | SystemCondition | MaintenancePlan | Planner group | MaintPlant | PM Collective | Room | Start Day
0 | 4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100074609 | ANOS Timerelay for door closing defect ( | Scaffold assistance/step-up scaff. | REL GMPS MANC PRC SETC | APPR WTA SMAT AWDO RDBL RFRZ ROUT | 8 | 0 | W09-W10 | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2025-08-25 | 2023-03-09 | 10 | REL | APPR OPND | HD /B /02/HDBF-FID-64207 | FIRE DOOR |  | A |  | MEL | DK60
0 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100074609 | ANOS Timerelay for door closing defect ( | Replce Door Time-delay Vlv. | REL GMPS MANC PRC SETC | APPR WTA SMAT AWDO RDBL RFRZ ROUT | 8 | 0 | W09-W10 | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2025-08-25 | 2023-03-09 | 20 | REL | APPR OPND | HD /B /02/HDBF-FID-64207 | FIRE DOOR |  | A |  | MEL | DK60
2024-W37-38 | 3 | NE | WDF | MTN-INST | MTN-INST | 2100098684 | Online vibration data collection stopped | Online vibration data collection stopped | REL MANC PRC SETC | APPR WTA RDBL | 32 | 0 |  | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-03-16 | 2023-11-02 | 10 | REL | APPR OPND | HB /D /08/HBDC-OS-7250 | VIBRATION MONITOR PC |  | A |  | MIN | DK50
0 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007060 | Handheld vib meas. on rotating Equipment | Handheld vib meas. on rotating Equipment | REL PCNF MANC PRC SETC | APPR WTA RDBL | 0 | 0 |  | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-06-21 | 2021-05-12 | 10 | PCNF REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK60
0 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007060 | Handheld vib meas. on rotating Equipment | Make sure equipment is operating stable | REL PCNF MANC PRC SETC | APPR WTA RDBL | 12 | 0 |  | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-06-21 | 2021-05-12 | 20 | PCNF REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK60
0 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007060 | Handheld vib meas. on rotating Equipment | Take vib meas with handheld data collect | REL PCNF MANC PRC SETC | APPR WTA RDBL | 24 | 112 |  | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-06-21 | 2021-05-12 | 30 | PCNF REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK60
0 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007060 | Handheld vib meas. on rotating Equipment | Data Analysis, db optimization | REL PCNF MANC PRC SETC | APPR WTA RDBL | 0 | 0 |  | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-06-21 | 2021-05-12 | 40 | PCNF REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK60
0 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007060 | Handheld vib meas. on rotating Equipment | Additional measurements | REL PCNF MANC PRC SETC | APPR WTA RDBL | 0 | 0 |  | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-06-21 | 2021-05-12 | 50 | PCNF REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK60
0 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007818 | Handheld vib meas. on rotating Eq R2 | Handheld vib meas. on rotating Eq R2 | REL MANC PRC SETC | APPR WTA RDBL | 0 | 0 |  | 2023-03-27 | 2023-04-02 | 2023-03-27 | 2021-12-15 | 2021-09-16 | 10 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK60
0 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007818 | Handheld vib meas. on rotating Eq R2 | Make sure equipment is operating stable | REL MANC PRC SETC | APPR WTA RDBL | 0 | 0 |  | 2023-03-27 | 2023-04-02 | 2023-03-27 | 2021-12-15 | 2021-09-16 | 20 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK60
0 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007818 | Handheld vib meas. on rotating Eq R2 | Take vib meas with handheld EX data coll | REL MANC PRC SETC | APPR WTA RDBL | 50 | 0 |  | 2023-03-27 | 2023-04-02 | 2023-03-27 | 2021-12-15 | 2021-09-16 | 30 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK60
0 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007818 | Handheld vib meas. on rotating Eq R2 | Data analysis, db optimization | REL MANC PRC SETC | APPR WTA RDBL | 10 | 0 |  | 2023-03-27 | 2023-04-02 | 2023-04-01 | 2021-12-15 | 2021-09-16 | 40 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-PIPF | 2100023866 | 2 stk HCV L.G. blowdown line HDA29 | Spool og Erct finde frem og tjekkes. | REL MANC PRC SETC | APPR WMAT RDBL | 2.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2018-05-06 | 2017-12-07 | 10 | REL | APPR OPND | HD /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | F |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-SCAF | 2100023866 | 2 stk HCV L.G. blowdown line HDA29 | Stillads/skamle stilles til rådighed | REL MANC PRC SETC | APPR WMAT RDBL | 6.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2018-05-06 | 2017-12-07 | 20 | REL | APPR OPND | HD /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | F |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-SCAF | 2100023866 | 2 stk HCV L.G. blowdown line HDA29 | Rigger ass ophæng af spool/ventiler | REL MANC PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2018-05-06 | 2017-12-07 | 25 | REL | APPR OPND | HD /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | F |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | PRODTECH | 2100023866 | 2 stk HCV L.G. blowdown line HDA29 | Safing udføres. Prod tilstede ved Flg ad | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2018-05-06 | 2017-12-07 | 30 | REL | APPR OPND | HD /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | F |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-PIPF | 2100023866 | 2 stk HCV L.G. blowdown line HDA29 | Ventiler udskiftes til nye. Vær agtpågiv | REL MANC PRC SETC | APPR WMAT RDBL | 6.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2018-05-06 | 2017-12-07 | 40 | REL | APPR OPND | HD /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | F |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | PRODTECH | 2100023866 | 2 stk HCV L.G. blowdown line HDA29 | Desafing/Leaktest udføres. | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2018-05-06 | 2017-12-07 | 50 | REL | APPR OPND | HD /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | F |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-SCAF | 2100023866 | 2 stk HCV L.G. blowdown line HDA29 | Stillads/skamle/rigger udstyr demonteres | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2018-05-06 | 2017-12-07 | 60 | REL | APPR OPND | HD /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | F |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-PIPF | 2100023866 | 2 stk HCV L.G. blowdown line HDA29 | Området opryddes. | REL MANC PRC SETC | APPR WMAT RDBL | 1.3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2018-05-06 | 2017-12-07 | 70 | REL | APPR OPND | HD /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | F |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | CON-WELD | 2100023866 | 2 stk HCV L.G. blowdown line HDA29 | new valve orded | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2018-05-06 | 2017-12-07 | 80 | REL | APPR OPND | HD /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | F |  | MMS | DK60
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-INST | 2100043868 | HCV upstream PIT-30106 is blocked | HCV upstream PIT-30106 is blocked | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-02-20 | 2021-01-11 | 10 | REL | APPR OPND | HB /A /10/HBAA-PIT-30106 | WELL FLUID FLOWLINE WELL 10 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | PRODTECH | 2100043868 | HCV upstream PIT-30106 is blocked | Isolate the line | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 1 | 0 | Oceam team do the job | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-02-20 | 2021-01-11 | 20 | REL | APPR OPND | HB /A /10/HBAA-PIT-30106 | WELL FLUID FLOWLINE WELL 10 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-INST | 2100043868 | HCV upstream PIT-30106 is blocked | Isolate Pressure transmitter | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-02-20 | 2021-01-11 | 30 | REL | APPR OPND | HB /A /10/HBAA-PIT-30106 | WELL FLUID FLOWLINE WELL 10 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-MECH | 2100043868 | HCV upstream PIT-30106 is blocked | Install new SDBB valve | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 2.5 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-02-20 | 2021-01-11 | 40 | REL | APPR OPND | HB /A /10/HBAA-PIT-30106 | WELL FLUID FLOWLINE WELL 10 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-INST | 2100043868 | HCV upstream PIT-30106 is blocked | De-Isolate Pressure transmitter | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-02-20 | 2021-01-11 | 50 | REL | APPR OPND | HB /A /10/HBAA-PIT-30106 | WELL FLUID FLOWLINE WELL 10 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-INST | 2100043868 | HCV upstream PIT-30106 is blocked | Test Pressure transmitter | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-02-20 | 2021-01-11 | 60 | REL | APPR OPND | HB /A /10/HBAA-PIT-30106 | WELL FLUID FLOWLINE WELL 10 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | PRODTECH | 2100043868 | HCV upstream PIT-30106 is blocked | De-isolate line | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-02-20 | 2021-01-11 | 70 | REL | APPR OPND | HB /A /10/HBAA-PIT-30106 | WELL FLUID FLOWLINE WELL 10 |  | E |  | MIN | DK50
0 | 4 | HDADEG A | WDF | MTN-MECH | MTN-SCAF | 2100050877 | HCV to LT upper seal stuck in open pos. | Prepare permit/rectify Scaffolding | REL MANC PRC SETC | APPR WMAT RDBL | 24 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2022-09-23 | 2021-11-27 | 10 | REL | APPR OPND | HD /A /27/SYSTEM-27-MANUAL-VALVES | SYSTEM-27-MANUAL-VALVES |  | F |  | MMS | DK60
0 | 4 | HDADEG A | WDF | MTN-MECH | MTN-MECH | 2100050877 | HCV to LT upper seal stuck in open pos. | Prepare matr/tools/permit | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2022-09-23 | 2021-11-27 | 20 | REL | APPR OPND | HD /A /27/SYSTEM-27-MANUAL-VALVES | SYSTEM-27-MANUAL-VALVES |  | F |  | MMS | DK60
0 | 4 | HDADEG A | WDF | MTN-MECH | PRODTECH | 2100050877 | HCV to LT upper seal stuck in open pos. | Production Isolation/Permit | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2022-09-23 | 2021-11-27 | 30 | REL | APPR OPND | HD /A /27/SYSTEM-27-MANUAL-VALVES | SYSTEM-27-MANUAL-VALVES |  | F |  | MMS | DK60
0 | 4 | HDADEG A | WDF | MTN-MECH | MTN-MECH | 2100050877 | HCV to LT upper seal stuck in open pos. | Replace 2" valve | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2022-09-23 | 2021-11-27 | 40 | REL | APPR OPND | HD /A /27/SYSTEM-27-MANUAL-VALVES | SYSTEM-27-MANUAL-VALVES |  | F |  | MMS | DK60
0 | 4 | HDADEG A | WDF | MTN-MECH | MTN-INST | 2100050877 | HCV to LT upper seal stuck in open pos. | Recalibrate ESD LIT-50166A | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2022-09-23 | 2021-11-27 | 50 | REL | APPR OPND | HD /A /27/SYSTEM-27-MANUAL-VALVES | SYSTEM-27-MANUAL-VALVES |  | F |  | MMS | DK60
0 | 4 | HDADEG A | WDF | MTN-MECH | PRODTECH | 2100050877 | HCV to LT upper seal stuck in open pos. | Production Deisolate w leak/test | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-04 | 2022-09-23 | 2021-11-27 | 60 | REL | APPR OPND | HD /A /27/SYSTEM-27-MANUAL-VALVES | SYSTEM-27-MANUAL-VALVES |  | F |  | MMS | DK60
0 | 4 | HDADEG A | WDF | MTN-MECH | MTN-MECH | 2100050877 | HCV to LT upper seal stuck in open pos. | Housekeeping | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2022-09-23 | 2021-11-27 | 70 | REL | APPR OPND | HD /A /27/SYSTEM-27-MANUAL-VALVES | SYSTEM-27-MANUAL-VALVES |  | F |  | MMS | DK60
0 | 4 | HDADEG A | WDF | MTN-MECH | MTN-SCAF | 2100050877 | HCV to LT upper seal stuck in open pos. | Scaffold removal | REL MANC PRC SETC | APPR WMAT RDBL | 18 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2022-09-23 | 2021-11-27 | 80 | REL | APPR OPND | HD /A /27/SYSTEM-27-MANUAL-VALVES | SYSTEM-27-MANUAL-VALVES |  | F |  | MMS | DK60
2026-W13-14 | 3 | HBA09-GL | WDF | MTN-INST | PRODTECH | 2100063712 | Cable and Glant is not connect proberly | Isolate the well and CVA valve | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-06-15 | 2022-03-17 | 10 | REL | APPR OPND | HB /A /10/HBAA-CVA-30096 | CHOKE VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HBA09-GL | WDF | MTN-INST | MTN-INST | 2100063712 | Cable and Glant is not connect proberly | Replace cable glands | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-06-15 | 2022-03-17 | 20 | REL | APPR OPND | HB /A /10/HBAA-CVA-30096 | CHOKE VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HBA09-GL | WDF | MTN-INST | PRODTECH | 2100063712 | Cable and Glant is not connect proberly | De-isolate the valve | REL MANC PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-06-15 | 2022-03-17 | 30 | REL | APPR OPND | HB /A /10/HBAA-CVA-30096 | CHOKE VALVE | 99000119 | E |  | MIN | DK50
2024-W23-24 | 3 | HBA23-GL | WDF | MTN-INST | MTN-INST | 2100064728 | Synergi 650656 FIT-29233 bolt failure | Synergi 650656 FIT-29233 bolt failure | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-04-02 | 2022-03-13 | 10 | REL | APPR OPND | HB /A /37/HBAA-FIT-29233 | FLOW INDICATOR TRANSMITTER (METERING) |  | A |  | MIN | DK50
2024-W23-24 | 3 | HBA23-GL | WDF | MTN-INST | MTN-INST | 2100064728 | Synergi 650656 FIT-29233 bolt failure | Isolate transmitter | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 4 | 0 | W45-46 BL-Team | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-04-02 | 2022-03-13 | 30 | REL | APPR OPND | HB /A /37/HBAA-FIT-29233 | FLOW INDICATOR TRANSMITTER (METERING) |  | A |  | MIN | DK50
2024-W23-24 | 3 | HBA23-GL | WDF | MTN-INST | MTN-INST | 2100064728 | Synergi 650656 FIT-29233 bolt failure | Replace faulty bolts | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 8 | 0 | W45-46 BL-Team | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-04-02 | 2022-03-13 | 40 | REL | APPR OPND | HB /A /37/HBAA-FIT-29233 | FLOW INDICATOR TRANSMITTER (METERING) |  | A |  | MIN | DK50
2024-W23-24 | 3 | HBA23-GL | WDF | MTN-INST | MTN-INST | 2100064728 | Synergi 650656 FIT-29233 bolt failure | Test/calibrate transmitter | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 2 | 0 | W45-46 BL-Team | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-04-02 | 2022-03-13 | 45 | REL | APPR OPND | HB /A /37/HBAA-FIT-29233 | FLOW INDICATOR TRANSMITTER (METERING) |  | A |  | MIN | DK50
2024-W23-24 | 3 | HBA23-GL | WDF | MTN-INST | MTN-INST | 2100064728 | Synergi 650656 FIT-29233 bolt failure | De-isolate transmitter | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 2 | 0 | W45-46 BL-Team | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-04-02 | 2022-03-13 | 50 | REL | APPR OPND | HB /A /37/HBAA-FIT-29233 | FLOW INDICATOR TRANSMITTER (METERING) |  | A |  | MIN | DK50
2024-W23-24 | 3 | HBA23-GL | WDF | MTN-INST | VEN-INST | 2100064728 | Synergi 650656 FIT-29233 bolt failure | order transmitter | REL MANC PPRT PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2022-04-02 | 2022-03-13 | 60 | REL | APPR OPND | HB /A /37/HBAA-FIT-29233 | FLOW INDICATOR TRANSMITTER (METERING) |  | A |  | MIN | DK50
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065796 | SYNC_R HDB - Repair of Helideck Surface | 2100065796-0002-COATING | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2022-06-16 | 2022-06-22 | 2022-06-16 | 2022-11-13 | 2022-06-16 | 2 | REL | APPR OPND | HD /B /86/HELIDECK - PRIM AND SEC STRUCT | HELIDECK PRIMARY STRUCTURE |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065796 | SYNC_R HDB - Repair of Helideck Surface | 2100065796-0003-CONSUMABLES | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2022-06-16 | 2022-06-22 | 2022-06-16 | 2022-11-13 | 2022-06-16 | 3 | REL | APPR OPND | HD /B /86/HELIDECK - PRIM AND SEC STRUCT | HELIDECK PRIMARY STRUCTURE |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065796 | SYNC_R HDB - Repair of Helideck Surface | 2100065796-0004-RENT-ALTRAD | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2022-06-16 | 2022-06-22 | 2022-06-16 | 2022-11-13 | 2022-06-16 | 4 | REL | APPR OPND | HD /B /86/HELIDECK - PRIM AND SEC STRUCT | HELIDECK PRIMARY STRUCTURE |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065796 | SYNC_R HDB - Repair of Helideck Surface | 210006579-0005-DRAFT-RENT-MOURITSEN | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2022-06-16 | 2022-06-22 | 2022-06-16 | 2022-11-13 | 2022-06-16 | 5 | REL | APPR OPND | HD /B /86/HELIDECK - PRIM AND SEC STRUCT | HELIDECK PRIMARY STRUCTURE |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065796 | SYNC_R HDB - Repair of Helideck Surface | HDB - Repair of Helideck Surface | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2022-06-16 | 2022-06-22 | 2022-06-16 | 2022-11-13 | 2022-06-16 | 10 | REL | APPR OPND | HD /B /86/HELIDECK - PRIM AND SEC STRUCT | HELIDECK PRIMARY STRUCTURE |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065796 | SYNC_R HDB - Repair of Helideck Surface | Paint; Prep/Team/Gear/Barrier+POST | REL MACM PRC SETC | APPR WMAT RDBL | 48 | 0 |  | 2022-06-16 | 2022-06-22 | 2022-06-16 | 2022-11-13 | 2022-06-16 | 20 | REL | APPR OPND | HD /B /86/HELIDECK - PRIM AND SEC STRUCT | HELIDECK PRIMARY STRUCTURE |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065796 | SYNC_R HDB - Repair of Helideck Surface | Paint; Clean, SB, Inspect, Prime Surface | REL MACM PRC SETC | APPR WMAT RDBL | 48 | 0 |  | 2022-06-16 | 2022-06-22 | 2022-06-17 | 2022-11-13 | 2022-06-16 | 30 | REL | APPR OPND | HD /B /86/HELIDECK - PRIM AND SEC STRUCT | HELIDECK PRIMARY STRUCTURE |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065796 | SYNC_R HDB - Repair of Helideck Surface | Paint; QC, Repaint to Spec. | REL MACM PRC SETC | APPR WMAT RDBL | 60 | 0 |  | 2022-06-16 | 2022-06-22 | 2022-06-19 | 2022-11-13 | 2022-06-16 | 40 | REL | APPR OPND | HD /B /86/HELIDECK - PRIM AND SEC STRUCT | HELIDECK PRIMARY STRUCTURE |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065796 | SYNC_R HDB - Repair of Helideck Surface | Paint; Clean-Up, Waist, Backload | REL MACM PRC SETC | APPR WMAT RDBL | 36 | 0 |  | 2022-06-16 | 2022-06-22 | 2022-06-21 | 2022-11-13 | 2022-06-16 | 50 | REL | APPR OPND | HD /B /86/HELIDECK - PRIM AND SEC STRUCT | HELIDECK PRIMARY STRUCTURE |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065796 | SYNC_R HDB - Repair of Helideck Surface | Additional materials Stencils | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2022-06-16 | 2022-06-22 | 2022-06-22 | 2022-11-13 | 2022-06-16 | 60 | REL | APPR OPND | HD /B /86/HELIDECK - PRIM AND SEC STRUCT | HELIDECK PRIMARY STRUCTURE |  | A |  | MFM | DK60
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100073752 | Change motor HBCM-PM-5732 | Isolate and prove dead | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-02-22 | 2022-10-10 | 10 | REL | APPR OPND | HB /C /71/HBCM-PM-5732 | DIESEL TRANSFER PUMP (DUTY) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073752 | Change motor HBCM-PM-5732 | Disconnect motor | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-02-22 | 2022-10-10 | 20 | REL | APPR OPND | HB /C /71/HBCM-PM-5732 | DIESEL TRANSFER PUMP (DUTY) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100073752 | Change motor HBCM-PM-5732 | Diconnect coupling | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-02-22 | 2022-10-10 | 30 | REL | APPR OPND | HB /C /71/HBCM-PM-5732 | DIESEL TRANSFER PUMP (DUTY) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100073752 | Change motor HBCM-PM-5732 | Change out motor | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-02-22 | 2022-10-10 | 40 | REL | APPR OPND | HB /C /71/HBCM-PM-5732 | DIESEL TRANSFER PUMP (DUTY) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073752 | Change motor HBCM-PM-5732 | Change out motor | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-02-22 | 2022-10-10 | 50 | REL | APPR OPND | HB /C /71/HBCM-PM-5732 | DIESEL TRANSFER PUMP (DUTY) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073752 | Change motor HBCM-PM-5732 | Connect coupling | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-02-22 | 2022-10-10 | 60 | REL | APPR OPND | HB /C /71/HBCM-PM-5732 | DIESEL TRANSFER PUMP (DUTY) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073752 | Change motor HBCM-PM-5732 | Connect motor | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-02-22 | 2022-10-10 | 70 | REL | APPR OPND | HB /C /71/HBCM-PM-5732 | DIESEL TRANSFER PUMP (DUTY) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100073752 | Change motor HBCM-PM-5732 | De-isolate and test | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-28 | 2023-02-22 | 2022-10-10 | 80 | REL | APPR OPND | HB /C /71/HBCM-PM-5732 | DIESEL TRANSFER PUMP (DUTY) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100076233 | Cracked 1"valve on utility air S-HBBA-04 | Isolation of valves | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-04-11 | 2022-11-27 | 10 | REL | APPR OPND | HB /B /07/SYS-07-INST-AIR-MANUAL-VALVES | SYSTEM 07 INST AIR MANUAL VALVES |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100076233 | Cracked 1"valve on utility air S-HBBA-04 | Dismantle old Valve | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-04-11 | 2022-11-27 | 20 | REL | APPR OPND | HB /B /07/SYS-07-INST-AIR-MANUAL-VALVES | SYSTEM 07 INST AIR MANUAL VALVES |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100076233 | Cracked 1"valve on utility air S-HBBA-04 | Install New Valve | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-04-11 | 2022-11-27 | 30 | REL | APPR OPND | HB /B /07/SYS-07-INST-AIR-MANUAL-VALVES | SYSTEM 07 INST AIR MANUAL VALVES |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100076233 | Cracked 1"valve on utility air S-HBBA-04 | Deisolation | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2023-04-11 | 2022-11-27 | 40 | REL | APPR OPND | HB /B /07/SYS-07-INST-AIR-MANUAL-VALVES | SYSTEM 07 INST AIR MANUAL VALVES |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076238 | Flange on flowglass | Isolate HBAA-P-3904 | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-04-11 | 2022-11-27 | 20 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076238 | Flange on flowglass | Replace sight glass/kit HBAA-P-3904 | REL MANC PRC SETC | APPR WMAT RDBL | 10 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-04-11 | 2022-11-27 | 30 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076238 | Flange on flowglass | De-Isolate/Test HBAA-P-3904 | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-28 | 2023-04-11 | 2022-11-27 | 40 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078390 | Block defect for 4 accumulators | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2023-05-22 | 2023-01-07 | 10 | REL | APPR OPND | HB /B /07/HBBB-FP-5942 | LP ACCUMULATOR PANEL |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078390 | Block defect for 4 accumulators | Replace Safety Block/PRV | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2023-05-22 | 2023-01-07 | 20 | REL | APPR OPND | HB /B /07/HBBB-FP-5942 | LP ACCUMULATOR PANEL |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078390 | Block defect for 4 accumulators | Production deisolation w leak test | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2023-05-22 | 2023-01-07 | 30 | REL | APPR OPND | HB /B /07/HBBB-FP-5942 | LP ACCUMULATOR PANEL |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100079015 | HBB07 prod.man. valve internally leaking | Isolation of valves | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-06-02 | 2023-01-18 | 10 | REL | APPR OPND | HB /B /10/HBBB-XCV-300704 | CONTROL VALVE WELL 07 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-RIGG | 2100079015 | HBB07 prod.man. valve internally leaking | Prepare Rigging Equipment | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-06-02 | 2023-01-18 | 20 | REL | APPR OPND | HB /B /10/HBBB-XCV-300704 | CONTROL VALVE WELL 07 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100079015 | HBB07 prod.man. valve internally leaking | Dismantle Plug Valve | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-06-02 | 2023-01-18 | 30 | REL | APPR OPND | HB /B /10/HBBB-XCV-300704 | CONTROL VALVE WELL 07 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-RIGG | 2100079015 | HBB07 prod.man. valve internally leaking | Riggout Plug Valve | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2023-06-02 | 2023-01-18 | 40 | REL | APPR OPND | HB /B /10/HBBB-XCV-300704 | CONTROL VALVE WELL 07 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-RIGG | 2100079015 | HBB07 prod.man. valve internally leaking | Rigg in New Valve | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2023-06-02 | 2023-01-18 | 50 | REL | APPR OPND | HB /B /10/HBBB-XCV-300704 | CONTROL VALVE WELL 07 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100079015 | HBB07 prod.man. valve internally leaking | Install New Valve | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2023-06-02 | 2023-01-18 | 60 | REL | APPR OPND | HB /B /10/HBBB-XCV-300704 | CONTROL VALVE WELL 07 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100079015 | HBB07 prod.man. valve internally leaking | De-isolate | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-11 | 2023-06-02 | 2023-01-18 | 70 | REL | APPR OPND | HB /B /10/HBBB-XCV-300704 | CONTROL VALVE WELL 07 |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100079536 | 26-12-2023 Gheorghe Micu L1096015 | Isolation | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-06-28 | 2024-06-29 | 2024-06-28 | 2023-06-13 | 2023-01-29 | 10 | REL | APPR OPND | HB /D /09/HBDB-P-1296 | CHILLED WATER PUMP (STANDBY) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079536 | 26-12-2023 Gheorghe Micu L1096015 | Dismantle pump | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-06-28 | 2024-06-29 | 2024-06-28 | 2023-06-13 | 2023-01-29 | 20 | REL | APPR OPND | HB /D /09/HBDB-P-1296 | CHILLED WATER PUMP (STANDBY) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079536 | 26-12-2023 Gheorghe Micu L1096015 | Install New Pump | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-06-28 | 2024-06-29 | 2024-06-28 | 2023-06-13 | 2023-01-29 | 30 | REL | APPR OPND | HB /D /09/HBDB-P-1296 | CHILLED WATER PUMP (STANDBY) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100079536 | 26-12-2023 Gheorghe Micu L1096015 | De-isolate | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-06-28 | 2024-06-29 | 2024-06-29 | 2023-06-13 | 2023-01-29 | 40 | REL | APPR OPND | HB /D /09/HBDB-P-1296 | CHILLED WATER PUMP (STANDBY) |  | A |  | MMS | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081882 | Leak from seawater filter motor 5370 | put Materials on Stock offshore | REL PCNF MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-07-25 | 2023-03-12 | 110 | REL | APPR OPND | HB /D /51/HBDB-XM-5370 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK | 2024-05-23
2024-W21-22 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081883 | Leak from seawater filter motor 5373 | put Materials on Stock offshore | REL PCNF MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-07-25 | 2023-03-12 | 110 | REL | APPR OPND | HB /D /51/HBDB-XM-5373 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK | 2024-05-26
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084635 | LOTI: HBAA-P-5914 is very noisy | Isolate HBAA-P-5914 | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W09-W10 | 2024-09-03 | 2024-09-06 | 2024-09-03 | 2023-07-31 | 2023-03-18 | 20 | REL | APPR OPND | HB /A /07/HBAA-P-5914 | HYDRAULIC PUMP |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084635 | LOTI: HBAA-P-5914 is very noisy | Exchange HBAA-P-5914 | REL MANC PRC SETC | APPR WMAT RDBL | 8 | 0 | W09-W10 | 2024-09-03 | 2024-09-06 | 2024-09-03 | 2023-07-31 | 2023-03-18 | 30 | REL | APPR OPND | HB /A /07/HBAA-P-5914 | HYDRAULIC PUMP |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084635 | LOTI: HBAA-P-5914 is very noisy | De-isolate HBAA-P-5914 | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W09-W10 | 2024-09-03 | 2024-09-06 | 2024-09-05 | 2023-07-31 | 2023-03-18 | 40 | REL | APPR OPND | HB /A /07/HBAA-P-5914 | HYDRAULIC PUMP |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084635 | LOTI: HBAA-P-5914 is very noisy | Test HBAA-P-5914 | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W09-W10 | 2024-09-03 | 2024-09-06 | 2024-09-05 | 2023-07-31 | 2023-03-18 | 50 | REL | APPR OPND | HB /A /07/HBAA-P-5914 | HYDRAULIC PUMP |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084635 | LOTI: HBAA-P-5914 is very noisy | Backload old P-5914 for repair / stock | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W09-W10 | 2024-09-03 | 2024-09-06 | 2024-09-06 | 2023-07-31 | 2023-03-18 | 60 | REL | APPR OPND | HB /A /07/HBAA-P-5914 | HYDRAULIC PUMP |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085371 | Change of defect position indicator - HB | Change of defect position indicator | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2023-08-11 | 2023-03-29 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-B02-01 | INCOMER MAIN UPS UNIT B |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085371 | Change of defect position indicator - HB | Sitevisit - TBT. | REL MANC PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2023-08-11 | 2023-03-29 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-B02-01 | INCOMER MAIN UPS UNIT B |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100085371 | Change of defect position indicator - HB | Isolate accordingly | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2023-08-11 | 2023-03-29 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-B02-01 | INCOMER MAIN UPS UNIT B |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085371 | Change of defect position indicator - HB | Change of defect position indicator | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2023-08-11 | 2023-03-29 | 40 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-B02-01 | INCOMER MAIN UPS UNIT B |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100085371 | Change of defect position indicator - HB | De-isolate accordingly. | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2023-08-11 | 2023-03-29 | 50 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-B02-01 | INCOMER MAIN UPS UNIT B |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085371 | Change of defect position indicator - HB | Test - Check up - Clean up. | REL MANC PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2023-08-11 | 2023-03-29 | 55 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-B02-01 | INCOMER MAIN UPS UNIT B |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085371 | Change of defect position indicator - HB | Matrials added to WO | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2023-08-11 | 2023-03-29 | 60 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-B02-01 | INCOMER MAIN UPS UNIT B |  | C |  | MEL | DK50 |  | PROK
2024-W23-24 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086714 | Trip on power to cont. HBC Roof | Trip on power to cont. HBC Roof | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2023-08-31 | 2023-04-18 | 10 | REL | APPR OPND | HB /C /05/HBCA-LP-1838-QF03-S | POWER SOCKET 16A (SO13) OUTDOOR |  | A |  | MEL | DK50 |  |  | 2024-05-31
2024-W23-24 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086714 | Trip on power to cont. HBC Roof | Replace cable.. | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2023-08-31 | 2023-04-18 | 20 | REL | APPR OPND | HB /C /05/HBCA-LP-1838-QF03-S | POWER SOCKET 16A (SO13) OUTDOOR |  | A |  | MEL | DK50 |  |  | 2024-06-01
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100088922 | Replace filter housing for breathing air | Replace filter housing for breathing air | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2023-10-02 | 2023-05-20 | 10 | REL | APPR OPND | HB /D /84/WORKSHOP-EQUIPMENT | WORKSHOP EQUIPMENT |  | A |  | MIN | DK50 |  |  | 2024-05-22
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-SCAF | 2100091979 | Cooling fan trips, E-1701-11M5 | Built scaffolding and hoist | REL PCNF MANC PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-12-01 | 2023-07-19 | 50 | PCNF REL | APPR OPND | HB /C /05/HBCA-E-1702 | AIR COOLER EMG GEN. HBCM-E-1760/1761) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100091979 | Cooling fan trips, E-1701-11M5 | Isolate Circuit 11M5 for blower | REL PCNF MANC PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-12-01 | 2023-07-19 | 60 | PCNF REL | APPR OPND | HB /C /05/HBCA-E-1702 | AIR COOLER EMG GEN. HBCM-E-1760/1761) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100091979 | Cooling fan trips, E-1701-11M5 | Replace motor, fan and cable | REL PCNF MANC PRC SETC | APPR WMAT RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-12-01 | 2023-07-19 | 70 | PCNF REL | APPR OPND | HB /C /05/HBCA-E-1702 | AIR COOLER EMG GEN. HBCM-E-1760/1761) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100091979 | Cooling fan trips, E-1701-11M5 | Adjust overload protection relay | REL PCNF MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2023-12-01 | 2023-07-19 | 80 | PCNF REL | APPR OPND | HB /C /05/HBCA-E-1702 | AIR COOLER EMG GEN. HBCM-E-1760/1761) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100091979 | Cooling fan trips, E-1701-11M5 | De-Isolate circuit 11M5 | REL PCNF MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2023-12-01 | 2023-07-19 | 90 | PCNF REL | APPR OPND | HB /C /05/HBCA-E-1702 | AIR COOLER EMG GEN. HBCM-E-1760/1761) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100091979 | Cooling fan trips, E-1701-11M5 | Test run with the production | REL PCNF MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2023-12-01 | 2023-07-19 | 100 | PCNF REL | APPR OPND | HB /C /05/HBCA-E-1702 | AIR COOLER EMG GEN. HBCM-E-1760/1761) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-SCAF | 2100091979 | Cooling fan trips, E-1701-11M5 | Remove scaffolding / hoist | REL PCNF MANC PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2023-12-01 | 2023-07-19 | 110 | REL | APPR OPND | HB /C /05/HBCA-E-1702 | AIR COOLER EMG GEN. HBCM-E-1760/1761) |  | A |  | MEL | DK50 |  | PROK
2024-W27-28 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094953 | Defekt volt & amp. meter DP-1832 | Defekt volt & amp. meter DP-1832 | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2026-07-04 | 2024-01-16 | 10 | REL | APPR OPND | HB /C /05/HBCA-LP-1832-01 | VOLTMETER |  | A |  | MEL | DK50 |  |  | 2024-06-02
2024-W27-28 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094953 | Defekt volt & amp. meter DP-1832 | Isolate | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2026-07-04 | 2024-01-16 | 20 | REL | APPR OPND | HB /C /05/HBCA-LP-1832-01 | VOLTMETER |  | A |  | MEL | DK50 |  |  | 2024-06-03
2024-W27-28 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094953 | Defekt volt & amp. meter DP-1832 | Replace defect meters | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2026-07-04 | 2024-01-16 | 30 | REL | APPR OPND | HB /C /05/HBCA-LP-1832-01 | VOLTMETER |  | A |  | MEL | DK50 |  |  | 2024-06-05
2024-W27-28 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094953 | Defekt volt & amp. meter DP-1832 | De isolate and test | REL MANC PRC SETC | APPR WMAT RDBL | 1.5 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2026-07-04 | 2024-01-16 | 40 | REL | APPR OPND | HB /C /05/HBCA-LP-1832-01 | VOLTMETER |  | A |  | MEL | DK50 |  |  | 2024-06-07
2024-W27-28 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095238 | Defect amp/volt display HBCC-LP-1833 | Defect amp/volt display HBCC-LP-1833 | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2026-07-10 | 2024-01-22 | 10 | REL | APPR OPND | HB /C /05/HBCB-LP-1833-01 | VOLTMETER |  | C |  | MEL | DK50
2024-W27-28 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095238 | Defect amp/volt display HBCC-LP-1833 | Isolate | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2026-07-10 | 2024-01-22 | 20 | REL | APPR OPND | HB /C /05/HBCB-LP-1833-01 | VOLTMETER |  | C |  | MEL | DK50
2024-W27-28 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095238 | Defect amp/volt display HBCC-LP-1833 | Replace defect meters | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2026-07-10 | 2024-01-22 | 30 | REL | APPR OPND | HB /C /05/HBCB-LP-1833-01 | VOLTMETER |  | C |  | MEL | DK50
2024-W27-28 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095238 | Defect amp/volt display HBCC-LP-1833 | De isolate and test | REL MANC PRC SETC | APPR WMAT RDBL | 1.5 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2026-07-10 | 2024-01-22 | 40 | REL | APPR OPND | HB /C /05/HBCB-LP-1833-01 | VOLTMETER |  | C |  | MEL | DK50
2024-W27-28 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095238 | Defect amp/volt display HBCC-LP-1833 | Add materilas | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2026-07-10 | 2024-01-22 | 50 | REL | APPR OPND | HB /C /05/HBCB-LP-1833-01 | VOLTMETER |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100095242 | Rusted solenoid on HBAA-CVA-30136 | Well SD state prep. | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-09-08 | 2023-07-25 | 10 | REL | APPR OPND | HB /A /10/HBAA-CVA-30136 | CHOKE VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100095242 | Rusted solenoid on HBAA-CVA-30136 | Isolate valve control panel | REL MANC PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-09-08 | 2023-07-25 | 20 | REL | APPR OPND | HB /A /10/HBAA-CVA-30136 | CHOKE VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100095242 | Rusted solenoid on HBAA-CVA-30136 | Replace valve control panel | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-09-08 | 2023-07-25 | 30 | REL | APPR OPND | HB /A /10/HBAA-CVA-30136 | CHOKE VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100095242 | Rusted solenoid on HBAA-CVA-30136 | De-isolate valve control panel/Test with | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-09-08 | 2023-07-25 | 40 | REL | APPR OPND | HB /A /10/HBAA-CVA-30136 | CHOKE VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100095242 | Rusted solenoid on HBAA-CVA-30136 | Well is back to service | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-09-08 | 2023-07-25 | 50 | REL | APPR OPND | HB /A /10/HBAA-CVA-30136 | CHOKE VALVE |  | E |  | MIN | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096926 | Hydraulic leak PRV accumulator | Hydraulic leak PRV accumulator | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-02-24 | 2023-10-12 | 10 | REL | APPR OPND | HB /B /07/HBBB-PRV-59054B | PRESSURE RELIEF VALVE |  | A |  | MMS | DK50 |  | PROK | 2024-05-25
2024-W21-22 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096926 | Hydraulic leak PRV accumulator | Isolate, verify isolation | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-02-24 | 2023-10-12 | 20 | REL | APPR OPND | HB /B /07/HBBB-PRV-59054B | PRESSURE RELIEF VALVE |  | A |  | MMS | DK50 |  | PROK | 2024-05-26
2024-W21-22 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096926 | Hydraulic leak PRV accumulator | Replace PRV | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-02-24 | 2023-10-12 | 30 | REL | APPR OPND | HB /B /07/HBBB-PRV-59054B | PRESSURE RELIEF VALVE |  | A |  | MMS | DK50 |  | PROK | 2024-05-27
2024-W21-22 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096926 | Hydraulic leak PRV accumulator | De-isolate, check for leak | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-02-24 | 2023-10-12 | 40 | REL | APPR OPND | HB /B /07/HBBB-PRV-59054B | PRESSURE RELIEF VALVE |  | A |  | MMS | DK50 |  | PROK | 2024-05-28
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098853 | PRV-300101 calibration date expired | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 10 | REL | APPR OPND | HB /B /07/HBBB-PRV-300101 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-22
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098853 | PRV-300101 calibration date expired | Replace PRV | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 20 | REL | APPR OPND | HB /B /07/HBBB-PRV-300101 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-23
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098853 | PRV-300101 calibration date expired | Production deisolation w function test | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2023-11-09 | 2023-09-25 | 30 | REL | APPR OPND | HB /B /07/HBBB-PRV-300101 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-24
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098854 | PRV-300301 calibration date expired | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 10 | REL | APPR OPND | HB /B /07/HBBB-PRV-300301 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-22
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098854 | PRV-300301 calibration date expired | Replace PRV | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 20 | REL | APPR OPND | HB /B /07/HBBB-PRV-300301 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-23
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098854 | PRV-300301 calibration date expired | Production deisolation w function test | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2023-11-09 | 2023-09-25 | 30 | REL | APPR OPND | HB /B /07/HBBB-PRV-300301 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-24
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098855 | PRV-300401 calibration date expired | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 10 | REL | APPR OPND | HB /B /07/HBBB-PRV-300401 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-22
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098855 | PRV-300401 calibration date expired | Replace PRV | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 20 | REL | APPR OPND | HB /B /07/HBBB-PRV-300401 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-23
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098855 | PRV-300401 calibration date expired | Production deisolation w function test | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2023-11-09 | 2023-09-25 | 30 | REL | APPR OPND | HB /B /07/HBBB-PRV-300401 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-24
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098856 | PRV-300501 calibration date expired | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 10 | REL | APPR OPND | HB /B /07/HBBB-PRV-300501 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-25
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098856 | PRV-300501 calibration date expired | Replace PRV | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 20 | REL | APPR OPND | HB /B /07/HBBB-PRV-300501 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-26
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098856 | PRV-300501 calibration date expired | Production deisolation w function test | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2023-11-09 | 2023-09-25 | 30 | REL | APPR OPND | HB /B /07/HBBB-PRV-300501 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-27
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098857 | PRV-300601 calibration date expired | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 10 | REL | APPR OPND | HB /B /07/HBBB-PRV-300601 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-24
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098857 | PRV-300601 calibration date expired | Replace PRV | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 20 | REL | APPR OPND | HB /B /07/HBBB-PRV-300601 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-25
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098857 | PRV-300601 calibration date expired | Production deisolation w function test | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2023-11-09 | 2023-09-25 | 30 | REL | APPR OPND | HB /B /07/HBBB-PRV-300601 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-27
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098858 | PRV-300701 calibration date expired | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 10 | REL | APPR OPND | HB /B /07/HBBB-PRV-300701 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-24
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098858 | PRV-300701 calibration date expired | Replace PRV | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 20 | REL | APPR OPND | HB /B /07/HBBB-PRV-300701 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-26
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098858 | PRV-300701 calibration date expired | Production deisolation w function test | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2023-11-09 | 2023-09-25 | 30 | REL | APPR OPND | HB /B /07/HBBB-PRV-300701 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-27
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098859 | PRV-300801 calibration date expired | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 10 | REL | APPR OPND | HB /B /07/HBBB-PRV-300801 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-25
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098859 | PRV-300801 calibration date expired | Replace PRV | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 20 | REL | APPR OPND | HB /B /07/HBBB-PRV-300801 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-26
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098859 | PRV-300801 calibration date expired | Production deisolation w function test | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2023-11-09 | 2023-09-25 | 30 | REL | APPR OPND | HB /B /07/HBBB-PRV-300801 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-27
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098860 | PRV-301001 calibration date expired | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 10 | REL | APPR OPND | HB /B /07/HBBB-PRV-301001 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-21
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098860 | PRV-301001 calibration date expired | Replace PRV | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-11-09 | 2023-09-25 | 20 | REL | APPR OPND | HB /B /07/HBBB-PRV-301001 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-23
2024-W21-22 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100098860 | PRV-301001 calibration date expired | Production deisolation w function test | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2023-11-09 | 2023-09-25 | 30 | REL | APPR OPND | HB /B /07/HBBB-PRV-301001 | PRESSURE RELIEF VALVE |  | C |  | MMS | DK50 |  |  | 2024-05-24
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099383 | Drawer trips for HDBM-A-1206 | Isolate Circuit for HDBM-A-1206 | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-05-06 | 2024-05-07 | 2024-05-06 | 2024-03-30 | 2023-11-16 | 20 | REL | APPR OPND | HD /B /85/HDBM-A-1206 | CONDENSER PACKAGE |  | A |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099383 | Drawer trips for HDBM-A-1206 | Replace Breaker | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-05-06 | 2024-05-07 | 2024-05-07 | 2024-03-30 | 2023-11-16 | 30 | REL | APPR OPND | HD /B /85/HDBM-A-1206 | CONDENSER PACKAGE |  | A |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099383 | Drawer trips for HDBM-A-1206 | De-Isolate Circuit for HDBM-A-1206 | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-05-06 | 2024-05-07 | 2024-05-07 | 2024-03-30 | 2023-11-16 | 40 | REL | APPR OPND | HD /B /85/HDBM-A-1206 | CONDENSER PACKAGE |  | A |  | MEL | DK60
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-INST | 2100099732 | Hydraulic PRV-30081 is internal leaking | Hydraulic PRV-30081 is internal leaking | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-04-03 | 2023-11-20 | 10 | REL | APPR OPND | HB /A /07/HBAA-PRV-30081 | PRESSURE RELIEF VALVE |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100099732 | Hydraulic PRV-30081 is internal leaking | Production isolate, verify isolation | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-04-03 | 2023-11-20 | 20 | REL | APPR OPND | HB /A /07/HBAA-PRV-30081 | PRESSURE RELIEF VALVE |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100099732 | Hydraulic PRV-30081 is internal leaking | Replace PRV | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-04-03 | 2023-11-20 | 30 | REL | APPR OPND | HB /A /07/HBAA-PRV-30081 | PRESSURE RELIEF VALVE |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100099732 | Hydraulic PRV-30081 is internal leaking | Production to de-isolate, check for leak | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2024-04-03 | 2023-11-20 | 40 | REL | APPR OPND | HB /A /07/HBAA-PRV-30081 | PRESSURE RELIEF VALVE |  | A |  | MMS | DK50 |  | PROK
2024-W23-24 | 3 | HBDSW | WDF | MTN-TELE | MTN-ELEC | 2100099738 | PSU fault in HBD-N-1852B | Set SW board to MANUAL mode | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-03-26 | 2023-11-12 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-B | SECTION B |  | A |  | MIN | DK50
2024-W23-24 | 3 | HBDSW | WDF | MTN-TELE | MTN-TELE | 2100099738 | PSU fault in HBD-N-1852B | Replace power modules | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-03-26 | 2023-11-12 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-B | SECTION B |  | A |  | MIN | DK50
2024-W23-24 | 3 | HBDSW | WDF | MTN-TELE | MTN-ELEC | 2100099738 | PSU fault in HBD-N-1852B | Set SW AUTO mode/Set switches/Check with | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2023-11-12 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-B | SECTION B |  | A |  | MIN | DK50
2024-W27-28 | 4 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100099739 | Replace Multi inst. LCD HBCA-N-1840B-02 | Replace Multi inst. LCD HBCA-N-1840B-02 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-04-07 | 2024-04-08 | 2024-04-07 | 2026-09-24 | 2024-04-07 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-02 | SECTION NO.02 |  | A |  | MEL | DK50 |  | PROK
2024-W27-28 | 4 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100099739 | Replace Multi inst. LCD HBCA-N-1840B-02 | Isolate Equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-07 | 2024-04-08 | 2024-04-07 | 2026-09-24 | 2024-04-07 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-02 | SECTION NO.02 |  | A |  | MEL | DK50 |  | PROK
2024-W27-28 | 4 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100099739 | Replace Multi inst. LCD HBCA-N-1840B-02 | Replace defective parts | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-07 | 2024-04-08 | 2024-04-07 | 2026-09-24 | 2024-04-07 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-02 | SECTION NO.02 |  | A |  | MEL | DK50 |  | PROK
2024-W27-28 | 4 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100099739 | Replace Multi inst. LCD HBCA-N-1840B-02 | De-isolate Equipment | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-07 | 2024-04-08 | 2024-04-08 | 2026-09-24 | 2024-04-07 | 40 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-02 | SECTION NO.02 |  | A |  | MEL | DK50 |  | PROK
2024-W27-28 | 4 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100099739 | Replace Multi inst. LCD HBCA-N-1840B-02 | Test & put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-07 | 2024-04-08 | 2024-04-08 | 2026-09-24 | 2024-04-07 | 50 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-02 | SECTION NO.02 |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100100017 | Backwash scraper external leaking | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-08-22 | 2024-08-27 | 2024-08-22 | 2023-11-26 | 2023-10-12 | 10 | REL | APPR OPND | HB /D /51/HBDB-XM-5370 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100100017 | Backwash scraper external leaking | Rigger assistance | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-08-22 | 2024-08-27 | 2024-08-23 | 2023-11-26 | 2023-10-12 | 20 | REL | APPR OPND | HB /D /51/HBDB-XM-5370 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100100017 | Backwash scraper external leaking | Replace Scanner shaft | REL MANC PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-08-22 | 2024-08-27 | 2024-08-23 | 2023-11-26 | 2023-10-12 | 30 | REL | APPR OPND | HB /D /51/HBDB-XM-5370 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100100017 | Backwash scraper external leaking | Production deisolation w Leak/func. test | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-08-22 | 2024-08-27 | 2024-08-26 | 2023-11-26 | 2023-10-12 | 40 | REL | APPR OPND | HB /D /51/HBDB-XM-5370 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102029 | LOTI: Water inside terminal box. | water inside terminal box. | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-06-26 | 2024-06-27 | 2024-06-26 | 2024-05-13 | 2023-12-30 | 10 | REL | APPR OPND | HB /D /72/HBDB-A-1150 | HOT WATER UNIT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100102029 | LOTI: Water inside terminal box. | Isolate heater and prove dead | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-26 | 2024-06-27 | 2024-06-26 | 2024-05-13 | 2023-12-30 | 20 | REL | APPR OPND | HB /D /72/HBDB-A-1150 | HOT WATER UNIT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100102029 | LOTI: Water inside terminal box. | disconnect cables | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-26 | 2024-06-27 | 2024-06-26 | 2024-05-13 | 2023-12-30 | 30 | REL | APPR OPND | HB /D /72/HBDB-A-1150 | HOT WATER UNIT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100102029 | LOTI: Water inside terminal box. | Replace old heater with new heater | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-06-26 | 2024-06-27 | 2024-06-26 | 2024-05-13 | 2023-12-30 | 40 | REL | APPR OPND | HB /D /72/HBDB-A-1150 | HOT WATER UNIT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100102029 | LOTI: Water inside terminal box. | Connect cables in new heater | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-26 | 2024-06-27 | 2024-06-26 | 2024-05-13 | 2023-12-30 | 50 | REL | APPR OPND | HB /D /72/HBDB-A-1150 | HOT WATER UNIT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100102029 | LOTI: Water inside terminal box. | De-Isolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-26 | 2024-06-27 | 2024-06-27 | 2024-05-13 | 2023-12-30 | 60 | REL | APPR OPND | HB /D /72/HBDB-A-1150 | HOT WATER UNIT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100102029 | LOTI: Water inside terminal box. | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-26 | 2024-06-27 | 2024-06-27 | 2024-05-13 | 2023-12-30 | 70 | REL | APPR OPND | HB /D /72/HBDB-A-1150 | HOT WATER UNIT |  | C |  | MEL | DK50
2024-W23-24 | 3 | HBB04-GL | WDF | MTN-INST | MTN-INST | 2100102280 | HBB04 intern leaking SOV to DH ESDV | Isolate solenoid valve | REL MANC PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-05-08 | 2023-12-25 | 10 | REL | APPR OPND | HB /B /75/HBBB-ESDV-390408 | EMERGENCY SHUTDOWN VALVE (WS) |  | E |  | MIN | DK50
2024-W23-24 | 3 | HBB04-GL | WDF | MTN-INST | MTN-INST | 2100102280 | HBB04 intern leaking SOV to DH ESDV | Replace solenoid valve | REL MANC PRC SETC | APPR WMAT RDBL | 2.5 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-05-08 | 2023-12-25 | 20 | REL | APPR OPND | HB /B /75/HBBB-ESDV-390408 | EMERGENCY SHUTDOWN VALVE (WS) |  | E |  | MIN | DK50
2024-W23-24 | 3 | HBB04-GL | WDF | MTN-INST | MTN-INST | 2100102280 | HBB04 intern leaking SOV to DH ESDV | Deisolate/Test with CCR | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-05-08 | 2023-12-25 | 30 | REL | APPR OPND | HB /B /75/HBBB-ESDV-390408 | EMERGENCY SHUTDOWN VALVE (WS) |  | E |  | MIN | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100103422 | PIT-575001 no signal to scada | Inhibit signals | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-05-22 | 2024-01-08 | 10 | REL | APPR OPND | HB /D /34/HBDB-PIT-575001 | PRESSURE INDIC.TRANSMITTER (METERING) |  | A |  | MIN | DK50 |  |  | 2024-05-27
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100103422 | PIT-575001 no signal to scada | Investigate/replace Hart-09 module | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-05-05 | 2024-05-06 | 2024-05-06 | 2024-05-22 | 2024-01-08 | 20 | REL | APPR OPND | HB /D /34/HBDB-PIT-575001 | PRESSURE INDIC.TRANSMITTER (METERING) |  | A |  | MIN | DK50 |  |  | 2024-05-28
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100103424 | Glycol pump P-4163 oil leak | Prepare for rigging | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-05-20 | 2024-05-25 | 2024-05-20 | 2024-06-03 | 2024-01-20 | 10 | REL | APPR OPND | HB /D /30/HBDB-P-4163 | GLYCOL CIRCULATION PUMP (110%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100103424 | Glycol pump P-4163 oil leak | Isolate Pump P-4163 | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-05-20 | 2024-05-25 | 2024-05-20 | 2024-06-03 | 2024-01-20 | 20 | REL | APPR OPND | HB /D /30/HBDB-P-4163 | GLYCOL CIRCULATION PUMP (110%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100103424 | Glycol pump P-4163 oil leak | Replace Seals | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-05-20 | 2024-05-25 | 2024-05-21 | 2024-06-03 | 2024-01-20 | 30 | REL | APPR OPND | HB /D /30/HBDB-P-4163 | GLYCOL CIRCULATION PUMP (110%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100103424 | Glycol pump P-4163 oil leak | Rigging assistance | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-05-20 | 2024-05-25 | 2024-05-22 | 2024-06-03 | 2024-01-20 | 40 | REL | APPR OPND | HB /D /30/HBDB-P-4163 | GLYCOL CIRCULATION PUMP (110%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100103424 | Glycol pump P-4163 oil leak | Alignment of pump - if required | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-05-20 | 2024-05-25 | 2024-05-23 | 2024-06-03 | 2024-01-20 | 50 | REL | APPR OPND | HB /D /30/HBDB-P-4163 | GLYCOL CIRCULATION PUMP (110%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100103424 | Glycol pump P-4163 oil leak | Cleanup | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-05-20 | 2024-05-25 | 2024-05-23 | 2024-06-03 | 2024-01-20 | 60 | REL | APPR OPND | HB /D /30/HBDB-P-4163 | GLYCOL CIRCULATION PUMP (110%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100103424 | Glycol pump P-4163 oil leak | Deisolate Pump | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-05-20 | 2024-05-25 | 2024-05-24 | 2024-06-03 | 2024-01-20 | 70 | REL | APPR OPND | HB /D /30/HBDB-P-4163 | GLYCOL CIRCULATION PUMP (110%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100103424 | Glycol pump P-4163 oil leak | Removal of rigging equipment | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-05-20 | 2024-05-25 | 2024-05-24 | 2024-06-03 | 2024-01-20 | 80 | REL | APPR OPND | HB /D /30/HBDB-P-4163 | GLYCOL CIRCULATION PUMP (110%) |  | A |  | MMR | DK50
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100103804 | DWEA insufficient light inCCR/ office | DWEA insufficient light inCCR/ office | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-06-04 | 2024-01-21 | 10 | REL | APPR OPND | HD /B /62 | LIGHTING |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100103804 | DWEA insufficient light inCCR/ office | Take down old difussers | REL MANC PRC SETC | APPR WMAT RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-06-04 | 2024-01-21 | 20 | REL | APPR OPND | HD /B /62 | LIGHTING |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100103804 | DWEA insufficient light inCCR/ office | Install new difussers | REL MANC PRC SETC | APPR WMAT RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-06-04 | 2024-01-21 | 30 | REL | APPR OPND | HD /B /62 | LIGHTING |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100103804 | DWEA insufficient light inCCR/ office | Test equipment. | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-06-04 | 2024-01-21 | 40 | REL | APPR OPND | HD /B /62 | LIGHTING |  | A |  | MEL | DK60 |  | PROK
2024-W31-32 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100104719 | Pump is making Noise when running | Pump is making Noise when running | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-06-21 | 2024-02-07 | 10 | REL | APPR OPND | HB /D /27/HBDB-P-3456 | SPENT H2S SCAVENGER WATER PUMP (100%) |  | A |  | MMR | DK50 |  |  | 2024-05-22
2024-W23-24 | 3 | HBA06-WI | WDF | MTN-INST | MTN-INST | 2100104720 | Indication for HBA06 choke | Check / adjust pos transmitter's axle | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-04-17 | 2024-04-17 | 2024-04-17 | 2024-07-01 | 2024-02-17 | 10 | REL | APPR OPND | HB /A /55/HBAA-CVA-30066 | CHOKE VALVE |  | E |  | MIN | DK50
2024-W23-24 | 4 |  | WDF | MTN-MECH | MTN-MECH | 2100104725 | Chemical hose damaged on T-3953 | Chemical hose damaged on T-3953 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-06-22 | 2024-06-23 | 2024-06-22 | 2026-12-09 | 2024-06-22 | 10 | REL | APPR OPND | HB /D /75/HBDD-T-3953 | WATER CLARIFIER TYPE 1 TANK, TRANSPORTAB |  | A |  | MMS | DK50
2024-W23-24 | 4 |  | WDF | MTN-MECH | MTN-MECH | 2100104725 | Chemical hose damaged on T-3953 | Replace hose. Re-use flange and coupling | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-06-22 | 2024-06-23 | 2024-06-22 | 2026-12-09 | 2024-06-22 | 20 | REL | APPR OPND | HB /D /75/HBDD-T-3953 | WATER CLARIFIER TYPE 1 TANK, TRANSPORTAB |  | A |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104960 | Back wash XCV-536453 can't close | Production isolation | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-03-25 | 2024-03-28 | 2024-03-25 | 2024-02-22 | 2024-01-08 | 10 | REL | APPR OPND | HB /D /51/HBDB-XCV-536453 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100104960 | Back wash XCV-536453 can't close | Rigger assistance | REL MACM PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-03-25 | 2024-03-28 | 2024-03-25 | 2024-02-22 | 2024-01-08 | 20 | REL | APPR OPND | HB /D /51/HBDB-XCV-536453 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-INST | 2100104960 | Back wash XCV-536453 can't close | Instrument assistance | REL MACM PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-03-25 | 2024-03-28 | 2024-03-25 | 2024-02-22 | 2024-01-08 | 30 | REL | APPR OPND | HB /D /51/HBDB-XCV-536453 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104960 | Back wash XCV-536453 can't close | Replace XCV Valve/Actuator | REL MACM PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-03-25 | 2024-03-28 | 2024-03-26 | 2024-02-22 | 2024-01-08 | 40 | REL | APPR OPND | HB /D /51/HBDB-XCV-536453 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104960 | Back wash XCV-536453 can't close | Production deisolation w Leak/func. test | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-03-25 | 2024-03-28 | 2024-03-27 | 2024-02-22 | 2024-01-08 | 50 | REL | APPR OPND | HB /D /51/HBDB-XCV-536453 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104961 | Back wash XCV-536454 internal leaking | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-02-22 | 2024-01-08 | 10 | REL | APPR OPND | HB /D /51/HBDB-XCV-536454 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100104961 | Back wash XCV-536454 internal leaking | Rigger assistance | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-02-22 | 2024-01-08 | 20 | REL | APPR OPND | HB /D /51/HBDB-XCV-536454 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-INST | 2100104961 | Back wash XCV-536454 internal leaking | Instrument assistance | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-02-22 | 2024-01-08 | 30 | REL | APPR OPND | HB /D /51/HBDB-XCV-536454 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104961 | Back wash XCV-536454 internal leaking | Replace XCV Valve | REL MANC PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-31 | 2024-02-22 | 2024-01-08 | 40 | REL | APPR OPND | HB /D /51/HBDB-XCV-536454 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104961 | Back wash XCV-536454 internal leaking | Production deisolation w Leak/func. test | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-08-01 | 2024-02-22 | 2024-01-08 | 50 | REL | APPR OPND | HB /D /51/HBDB-XCV-536454 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2024-W21-22 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104962 | Back wash XCV-536455 internal leaking | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-02-22 | 2024-01-08 | 10 | REL | APPR OPND | HB /D /51/HBDB-XCV-536455 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK | 2024-05-29
2024-W21-22 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104962 | Back wash XCV-536455 internal leaking | Rigger assistance | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-02-22 | 2024-01-08 | 20 | REL | APPR OPND | HB /D /51/HBDB-XCV-536455 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK | 2024-05-30
2024-W21-22 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104962 | Back wash XCV-536455 internal leaking | Instrument assistance | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-02-22 | 2024-01-08 | 30 | REL | APPR OPND | HB /D /51/HBDB-XCV-536455 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK | 2024-05-31
2024-W21-22 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104962 | Back wash XCV-536455 internal leaking | Replace XCV Valve | REL MANC PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-31 | 2024-02-22 | 2024-01-08 | 40 | REL | APPR OPND | HB /D /51/HBDB-XCV-536455 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK | 2024-06-01
2024-W21-22 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104962 | Back wash XCV-536455 internal leaking | Production deisolation w Leak/func. test | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-08-01 | 2024-02-22 | 2024-01-08 | 50 | REL | APPR OPND | HB /D /51/HBDB-XCV-536455 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK | 2024-06-03
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104965 | Back wash XCV-536555 can't close | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-02-22 | 2024-01-08 | 10 | REL | APPR OPND | HB /D /51/HBDB-XCV-536555 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100104965 | Back wash XCV-536555 can't close | Rigger assistance | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-02-22 | 2024-01-08 | 20 | REL | APPR OPND | HB /D /51/HBDB-XCV-536555 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-INST | 2100104965 | Back wash XCV-536555 can't close | Instrument assistance | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-02-22 | 2024-01-08 | 30 | REL | APPR OPND | HB /D /51/HBDB-XCV-536555 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104965 | Back wash XCV-536555 can't close | Replace XCV Valve | REL MANC PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-31 | 2024-02-22 | 2024-01-08 | 40 | REL | APPR OPND | HB /D /51/HBDB-XCV-536555 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104965 | Back wash XCV-536555 can't close | Production deisolation w Leak/func. test | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-08-01 | 2024-02-22 | 2024-01-08 | 50 | REL | APPR OPND | HB /D /51/HBDB-XCV-536555 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104966 | Leak from seawater filter motor XM-5372 | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-22 | 2024-02-22 | 2024-01-08 | 10 | REL | APPR OPND | HB /D /51/HBDB-XM-5372 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100104966 | Leak from seawater filter motor XM-5372 | Rigger assistance | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-23 | 2024-02-22 | 2024-01-08 | 20 | REL | APPR OPND | HB /D /51/HBDB-XM-5372 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104966 | Leak from seawater filter motor XM-5372 | Replace Scanner shaft | REL MANC PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-23 | 2024-02-22 | 2024-01-08 | 30 | REL | APPR OPND | HB /D /51/HBDB-XM-5372 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104966 | Leak from seawater filter motor XM-5372 | Production deisolation w Leak/func. test | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-25 | 2024-02-22 | 2024-01-08 | 40 | REL | APPR OPND | HB /D /51/HBDB-XM-5372 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104967 | Leak from seawater filter motor XM-5371 | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-22 | 2024-02-22 | 2024-01-08 | 10 | REL | APPR OPND | HB /D /51/HBDB-XM-5371 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100104967 | Leak from seawater filter motor XM-5371 | Rigger assistance | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-23 | 2024-02-22 | 2024-01-08 | 20 | REL | APPR OPND | HB /D /51/HBDB-XM-5371 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104967 | Leak from seawater filter motor XM-5371 | Replace Scanner shaft | REL MANC PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-23 | 2024-02-22 | 2024-01-08 | 30 | REL | APPR OPND | HB /D /51/HBDB-XM-5371 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104967 | Leak from seawater filter motor XM-5371 | Production deisolation w Leak/func. test | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-25 | 2024-02-22 | 2024-01-08 | 40 | REL | APPR OPND | HB /D /51/HBDB-XM-5371 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50
2024-W21-22 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105038 | Leak from seawater filter motor XM-5366 | Production isolation | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-02-23 | 2024-01-09 | 10 | REL | APPR OPND | HB /D /51/HBDB-XM-5366 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50 |  |  | 2024-05-28
2024-W21-22 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105038 | Leak from seawater filter motor XM-5366 | Rigger assistance | REL MANC PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-02-23 | 2024-01-09 | 20 | REL | APPR OPND | HB /D /51/HBDB-XM-5366 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50 |  |  | 2024-05-29
2024-W21-22 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105038 | Leak from seawater filter motor XM-5366 | Replace Scanner shaft | REL MANC PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-02-23 | 2024-01-09 | 30 | REL | APPR OPND | HB /D /51/HBDB-XM-5366 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50 |  |  | 2024-05-30
2024-W21-22 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105038 | Leak from seawater filter motor XM-5366 | Production deisolation w Leak/func. test | REL MANC PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-25 | 2024-02-23 | 2024-01-09 | 40 | REL | APPR OPND | HB /D /51/HBDB-XM-5366 | SEAWATER FILTER FILTER MOTOR |  | C |  | MMS | DK50 |  |  | 2024-06-01
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106306 | CCR heater issue HBDC-HE-12251 | Isolate Heater | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-07-02 | 2024-02-18 | 20 | REL | APPR OPND | HB /D /09/HBDC-HE-12251 | CCR HEATER |  | A |  | MEL | DK50 |  | PROK | 2024-06-02
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106306 | CCR heater issue HBDC-HE-12251 | Replace thermostat | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-07-02 | 2024-02-18 | 30 | REL | APPR OPND | HB /D /09/HBDC-HE-12251 | CCR HEATER |  | A |  | MEL | DK50 |  | PROK | 2024-06-04
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106306 | CCR heater issue HBDC-HE-12251 | De-Isolate Heater | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-07-02 | 2024-02-18 | 40 | REL | APPR OPND | HB /D /09/HBDC-HE-12251 | CCR HEATER |  | A |  | MEL | DK50 |  | PROK | 2024-06-06
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106306 | CCR heater issue HBDC-HE-12251 | Test/Calibration | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-07-02 | 2024-02-18 | 50 | REL | APPR OPND | HB /D /09/HBDC-HE-12251 | CCR HEATER |  | A |  | MEL | DK50 |  | PROK | 2024-06-08
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107157 | EMG light HBD Lev 1 LP-1811-Q01 | EMG light HBD Lev 1 LP-1811-Q01 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-08-09 | 2024-03-27 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-01 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-02
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107157 | EMG light HBD Lev 1 LP-1811-Q01 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-08-09 | 2024-03-27 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-01 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-03
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107157 | EMG light HBD Lev 1 LP-1811-Q01 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 1.5 | 0 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-08-09 | 2024-03-27 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-01 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-05
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107157 | EMG light HBD Lev 1 LP-1811-Q01 | De-Isolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-08-09 | 2024-03-27 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-01 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-07
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107157 | EMG light HBD Lev 1 LP-1811-Q01 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-08-09 | 2024-03-27 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-01 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-09
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107158 | EMG light HBD Lev 1 LP-1811-Q02 | EMG light HBD Lev 1 LP-1811-Q02 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-07-11 | 2024-07-12 | 2024-07-11 | 2024-08-09 | 2024-03-27 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-02 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-02
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107158 | EMG light HBD Lev 1 LP-1811-Q02 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-11 | 2024-07-12 | 2024-07-11 | 2024-08-09 | 2024-03-27 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-02 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-03
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107158 | EMG light HBD Lev 1 LP-1811-Q02 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-07-11 | 2024-07-12 | 2024-07-11 | 2024-08-09 | 2024-03-27 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-02 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-04
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107158 | EMG light HBD Lev 1 LP-1811-Q02 | De-Isolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-07-11 | 2024-07-12 | 2024-07-12 | 2024-08-09 | 2024-03-27 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-02 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-06
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107158 | EMG light HBD Lev 1 LP-1811-Q02 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-11 | 2024-07-12 | 2024-07-12 | 2024-08-09 | 2024-03-27 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-02 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-08
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107159 | EMG light HBD Lev 1 LP-1811-Q03 | EMG light HBD Lev 1 LP-1811-Q03 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-06-10 | 2024-06-11 | 2024-06-10 | 2024-08-09 | 2024-03-27 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-03 | EMERG. LIGHTING AIR COMPRESSOR RM LVL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100107159 | EMG light HBD Lev 1 LP-1811-Q03 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-10 | 2024-06-11 | 2024-06-10 | 2024-08-09 | 2024-03-27 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-03 | EMERG. LIGHTING AIR COMPRESSOR RM LVL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107159 | EMG light HBD Lev 1 LP-1811-Q03 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 5 | 0 |  | 2024-06-10 | 2024-06-11 | 2024-06-10 | 2024-08-09 | 2024-03-27 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-03 | EMERG. LIGHTING AIR COMPRESSOR RM LVL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107159 | EMG light HBD Lev 1 LP-1811-Q03 | De-Isolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-06-10 | 2024-06-11 | 2024-06-11 | 2024-08-09 | 2024-03-27 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-03 | EMERG. LIGHTING AIR COMPRESSOR RM LVL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100107159 | EMG light HBD Lev 1 LP-1811-Q03 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-10 | 2024-06-11 | 2024-06-11 | 2024-08-09 | 2024-03-27 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-03 | EMERG. LIGHTING AIR COMPRESSOR RM LVL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107160 | EMG light HBD Lev 1 LP-1811-Q04 | EMG light HBD Lev 1 LP-1811-Q04 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-08-09 | 2024-03-27 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-04 | EMERG. LIGHTING AIR COMPRESSOR RM LVL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100107160 | EMG light HBD Lev 1 LP-1811-Q04 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-08-09 | 2024-03-27 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-04 | EMERG. LIGHTING AIR COMPRESSOR RM LVL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107160 | EMG light HBD Lev 1 LP-1811-Q04 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 6 | 0 |  | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-08-09 | 2024-03-27 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-04 | EMERG. LIGHTING AIR COMPRESSOR RM LVL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107160 | EMG light HBD Lev 1 LP-1811-Q04 | De-Isolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-16 | 2024-07-18 | 2024-07-17 | 2024-08-09 | 2024-03-27 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-04 | EMERG. LIGHTING AIR COMPRESSOR RM LVL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100107160 | EMG light HBD Lev 1 LP-1811-Q04 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1.5 | 0 |  | 2024-07-16 | 2024-07-18 | 2024-07-17 | 2024-08-09 | 2024-03-27 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-04 | EMERG. LIGHTING AIR COMPRESSOR RM LVL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107161 | EMG light HBD Lev 1 LP-1811-Q06 | EMG light HBD Lev 1 LP-1811-Q06 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-07-22 | 2024-07-23 | 2024-07-22 | 2024-08-09 | 2024-03-27 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-06 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100107161 | EMG light HBD Lev 1 LP-1811-Q06 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-22 | 2024-07-23 | 2024-07-22 | 2024-08-09 | 2024-03-27 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-06 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107161 | EMG light HBD Lev 1 LP-1811-Q06 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-07-22 | 2024-07-23 | 2024-07-22 | 2024-08-09 | 2024-03-27 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-06 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107161 | EMG light HBD Lev 1 LP-1811-Q06 | De-Isolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-22 | 2024-07-23 | 2024-07-22 | 2024-08-09 | 2024-03-27 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-06 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100107161 | EMG light HBD Lev 1 LP-1811-Q06 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-22 | 2024-07-23 | 2024-07-23 | 2024-08-09 | 2024-03-27 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-06 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107163 | EMG light HBD Lev 0 LP-1811-Q38 | EMG light HBD Lev 0 LP-1811-Q38 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-03-26 | 2024-03-27 | 2024-03-26 | 2024-08-08 | 2024-03-26 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-38 | EMERG. LIGHTING PLATFORM LEVEL 0 |  | C |  | MEL | DK50 |  |  | 2024-05-28
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107163 | EMG light HBD Lev 0 LP-1811-Q38 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-26 | 2024-03-27 | 2024-03-26 | 2024-08-08 | 2024-03-26 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-38 | EMERG. LIGHTING PLATFORM LEVEL 0 |  | C |  | MEL | DK50 |  |  | 2024-05-29
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107163 | EMG light HBD Lev 0 LP-1811-Q38 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 6 | 0 |  | 2024-03-26 | 2024-03-27 | 2024-03-26 | 2024-08-08 | 2024-03-26 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-38 | EMERG. LIGHTING PLATFORM LEVEL 0 |  | C |  | MEL | DK50 |  |  | 2024-05-30
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107163 | EMG light HBD Lev 0 LP-1811-Q38 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-03-26 | 2024-03-27 | 2024-03-27 | 2024-08-08 | 2024-03-26 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-38 | EMERG. LIGHTING PLATFORM LEVEL 0 |  | C |  | MEL | DK50 |  |  | 2024-06-01
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107163 | EMG light HBD Lev 0 LP-1811-Q38 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-26 | 2024-03-27 | 2024-03-27 | 2024-08-08 | 2024-03-26 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-38 | EMERG. LIGHTING PLATFORM LEVEL 0 |  | C |  | MEL | DK50 |  |  | 2024-06-02
2026-W13-14 | 3 | HBDIGF2 | WDF | MTN-ELEC | MTN-ELEC | 2100107274 | Motor heater defect IGF PM-5076 | Motor heater defect IGF PM-5076 | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-28 | 2024-08-10 | 2024-03-28 | 10 | REL | APPR OPND | HB /D /27/HBDB-PM-5076 | ELECTRIC PUMP MOTOR |  | D |  | MEL | DK50
2026-W13-14 | 3 | HBDIGF2 | WDF | MTN-ELEC | MTN-ELEC | 2100107274 | Motor heater defect IGF PM-5076 | Material | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-28 | 2024-08-10 | 2024-03-28 | 20 | REL | APPR OPND | HB /D /27/HBDB-PM-5076 | ELECTRIC PUMP MOTOR |  | D |  | MEL | DK50
2026-W13-14 | 3 | HBDIGF2 | WDF | MTN-ELEC | PRODTECH | 2100107274 | Motor heater defect IGF PM-5076 | Isolate equipment and prove dead. | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-29 | 2024-08-10 | 2024-03-28 | 30 | REL | APPR OPND | HB /D /27/HBDB-PM-5076 | ELECTRIC PUMP MOTOR |  | D |  | MEL | DK50
2026-W13-14 | 3 | HBDIGF2 | WDF | MTN-ELEC | MTN-ELEC | 2100107274 | Motor heater defect IGF PM-5076 | Disconnect cables from defect | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-29 | 2024-08-10 | 2024-03-28 | 40 | REL | APPR OPND | HB /D /27/HBDB-PM-5076 | ELECTRIC PUMP MOTOR |  | D |  | MEL | DK50
2026-W13-14 | 3 | HBDIGF2 | WDF | MTN-ELEC | MTN-ELEC | 2100107274 | Motor heater defect IGF PM-5076 | Replace old motor with new motor. | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-29 | 2024-08-10 | 2024-03-28 | 50 | REL | APPR OPND | HB /D /27/HBDB-PM-5076 | ELECTRIC PUMP MOTOR |  | D |  | MEL | DK50
2026-W13-14 | 3 | HBDIGF2 | WDF | MTN-ELEC | MTN-ELEC | 2100107274 | Motor heater defect IGF PM-5076 | Connct cables to new motor. | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-30 | 2024-08-10 | 2024-03-28 | 60 | REL | APPR OPND | HB /D /27/HBDB-PM-5076 | ELECTRIC PUMP MOTOR |  | D |  | MEL | DK50
2026-W13-14 | 3 | HBDIGF2 | WDF | MTN-ELEC | PRODTECH | 2100107274 | Motor heater defect IGF PM-5076 | De-Isolate and put back in service | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-30 | 2024-08-10 | 2024-03-28 | 70 | REL | APPR OPND | HB /D /27/HBDB-PM-5076 | ELECTRIC PUMP MOTOR |  | D |  | MEL | DK50
2026-W13-14 | 3 | HBDIGF2 | WDF | MTN-ELEC | MTN-ELEC | 2100107274 | Motor heater defect IGF PM-5076 | Test equipment. | REL MANC PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-30 | 2024-08-10 | 2024-03-28 | 80 | REL | APPR OPND | HB /D /27/HBDB-PM-5076 | ELECTRIC PUMP MOTOR |  | D |  | MEL | DK50
2024-W31-32 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107893 | EMG light HBD Lev 1 LP-1811-Q05 | EMG light HBD Lev 1 LP-1811-Q05 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-08-09 | 2024-03-27 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-05 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-02
2024-W31-32 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107893 | EMG light HBD Lev 1 LP-1811-Q05 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-08-09 | 2024-03-27 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-05 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-03
2024-W31-32 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107893 | EMG light HBD Lev 1 LP-1811-Q05 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-08-09 | 2024-03-27 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-05 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-05
2024-W31-32 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107893 | EMG light HBD Lev 1 LP-1811-Q05 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-05-13 | 2024-05-14 | 2024-05-14 | 2024-08-09 | 2024-03-27 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-05 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-07
2024-W31-32 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107893 | EMG light HBD Lev 1 LP-1811-Q05 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-05-13 | 2024-05-14 | 2024-05-14 | 2024-08-09 | 2024-03-27 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-05 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-09
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107894 | EMG light HBD Lev 1 LP-1811-Q07 | EMG light HBD Lev 1 LP-1811-Q07 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2024-08-09 | 2024-03-27 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-07 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-02
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107894 | EMG light HBD Lev 1 LP-1811-Q07 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2024-08-09 | 2024-03-27 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-07 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-03
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107894 | EMG light HBD Lev 1 LP-1811-Q07 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2024-08-09 | 2024-03-27 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-07 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-05
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107894 | EMG light HBD Lev 1 LP-1811-Q07 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-04-22 | 2024-04-23 | 2024-04-23 | 2024-08-09 | 2024-03-27 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-07 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-07
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107894 | EMG light HBD Lev 1 LP-1811-Q07 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-22 | 2024-04-23 | 2024-04-23 | 2024-08-09 | 2024-03-27 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-07 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-08
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107895 | EMG light HBD Lev 1 LP-1811-Q08 | EMG light HBD Lev 1 LP-1811-Q08 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-08-09 | 2024-03-27 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-08 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-02
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107895 | EMG light HBD Lev 1 LP-1811-Q08 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-08-09 | 2024-03-27 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-08 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-03
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107895 | EMG light HBD Lev 1 LP-1811-Q08 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-08-09 | 2024-03-27 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-08 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-04
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107895 | EMG light HBD Lev 1 LP-1811-Q08 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-08-09 | 2024-03-27 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-08 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-06
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107895 | EMG light HBD Lev 1 LP-1811-Q08 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-08-09 | 2024-03-27 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-08 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-08
2024-W29-30 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100107896 | EMG light HBD Lev 1 LP-1811-Q09 | EMG light HBD Lev 1 LP-1811-Q09 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-08-10 | 2024-03-28 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-09 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | A |  | MEL | DK50 |  |  | 2024-06-02
2024-W29-30 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100107896 | EMG light HBD Lev 1 LP-1811-Q09 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-08-10 | 2024-03-28 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-09 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | A |  | MEL | DK50 |  |  | 2024-06-03
2024-W29-30 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100107896 | EMG light HBD Lev 1 LP-1811-Q09 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-08-10 | 2024-03-28 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-09 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | A |  | MEL | DK50 |  |  | 2024-06-05
2024-W29-30 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100107896 | EMG light HBD Lev 1 LP-1811-Q09 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-05 | 2024-06-06 | 2024-06-06 | 2024-08-10 | 2024-03-28 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-09 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | A |  | MEL | DK50 |  |  | 2024-06-07
2024-W29-30 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100107896 | EMG light HBD Lev 1 LP-1811-Q09 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-05 | 2024-06-06 | 2024-06-06 | 2024-08-10 | 2024-03-28 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-09 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | A |  | MEL | DK50 |  |  | 2024-06-09
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107897 | EMG light HBD Lev 1 LP-1811-Q10 | EMG light HBD Lev 1 LP-1811-Q10 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-08 | 2024-08-10 | 2024-03-28 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-10 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-02
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107897 | EMG light HBD Lev 1 LP-1811-Q10 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-08 | 2024-08-10 | 2024-03-28 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-10 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-03
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107897 | EMG light HBD Lev 1 LP-1811-Q10 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 5 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-08 | 2024-08-10 | 2024-03-28 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-10 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-05
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107897 | EMG light HBD Lev 1 LP-1811-Q10 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-09 | 2024-08-10 | 2024-03-28 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-10 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-07
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107897 | EMG light HBD Lev 1 LP-1811-Q10 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-09 | 2024-08-10 | 2024-03-28 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-10 | EMERG. LIGHTING PLATFORM LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-09
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107898 | EMG light HBD Lev 1 LP-1811-Q11 | EMG light HBD Lev 1 LP-1811-Q11 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-06-24 | 2024-06-25 | 2024-06-24 | 2024-08-10 | 2024-03-28 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-11 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-02
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107898 | EMG light HBD Lev 1 LP-1811-Q11 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-24 | 2024-06-25 | 2024-06-24 | 2024-08-10 | 2024-03-28 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-11 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-03
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107898 | EMG light HBD Lev 1 LP-1811-Q11 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 5 | 0 |  | 2024-06-24 | 2024-06-25 | 2024-06-24 | 2024-08-10 | 2024-03-28 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-11 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-04
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107898 | EMG light HBD Lev 1 LP-1811-Q11 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-24 | 2024-06-25 | 2024-06-25 | 2024-08-10 | 2024-03-28 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-11 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-06
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107898 | EMG light HBD Lev 1 LP-1811-Q11 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-24 | 2024-06-25 | 2024-06-25 | 2024-08-10 | 2024-03-28 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-11 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-08
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107899 | EMG light HBD Lev 1 LP-1811-Q12 | EMG light HBD Lev 1 LP-1811-Q12 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-08-10 | 2024-03-28 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-12 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-02
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107899 | EMG light HBD Lev 1 LP-1811-Q12 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-08-10 | 2024-03-28 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-12 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-03
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107899 | EMG light HBD Lev 1 LP-1811-Q12 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-08-10 | 2024-03-28 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-12 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-05
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107899 | EMG light HBD Lev 1 LP-1811-Q12 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-08-10 | 2024-03-28 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-12 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-07
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107899 | EMG light HBD Lev 1 LP-1811-Q12 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-08-10 | 2024-03-28 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-12 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50 |  |  | 2024-06-09
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107900 | EMG light HBD Lev 1 LP-1811-Q13 | EMG light HBD Lev 1 LP-1811-Q13 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-06-24 | 2024-06-25 | 2024-06-24 | 2024-08-13 | 2024-03-31 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-13 | EMERG. LIGHTING SIGN BOARD LEVEL 1 |  | C |  | MEL | DK50
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107900 | EMG light HBD Lev 1 LP-1811-Q13 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-24 | 2024-06-25 | 2024-06-24 | 2024-08-13 | 2024-03-31 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-13 | EMERG. LIGHTING SIGN BOARD LEVEL 1 |  | C |  | MEL | DK50
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107900 | EMG light HBD Lev 1 LP-1811-Q13 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 4.5 | 0 |  | 2024-06-24 | 2024-06-25 | 2024-06-24 | 2024-08-13 | 2024-03-31 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-13 | EMERG. LIGHTING SIGN BOARD LEVEL 1 |  | C |  | MEL | DK50
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107900 | EMG light HBD Lev 1 LP-1811-Q13 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-06-24 | 2024-06-25 | 2024-06-25 | 2024-08-13 | 2024-03-31 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-13 | EMERG. LIGHTING SIGN BOARD LEVEL 1 |  | C |  | MEL | DK50
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107900 | EMG light HBD Lev 1 LP-1811-Q13 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-24 | 2024-06-25 | 2024-06-25 | 2024-08-13 | 2024-03-31 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-13 | EMERG. LIGHTING SIGN BOARD LEVEL 1 |  | C |  | MEL | DK50
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107901 | EMG light HBD Lev 1 LP-1811-Q14 | EMG light HBD Lev 1 LP-1811-Q14 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-08-13 | 2024-03-31 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-14 | EMERG. LIGHTING SIGN BOARD LEVEL 1 |  | C |  | MEL | DK50
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107901 | EMG light HBD Lev 1 LP-1811-Q14 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-08-13 | 2024-03-31 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-14 | EMERG. LIGHTING SIGN BOARD LEVEL 1 |  | C |  | MEL | DK50
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107901 | EMG light HBD Lev 1 LP-1811-Q14 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-08-13 | 2024-03-31 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-14 | EMERG. LIGHTING SIGN BOARD LEVEL 1 |  | C |  | MEL | DK50
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107901 | EMG light HBD Lev 1 LP-1811-Q14 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-08-13 | 2024-03-31 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-14 | EMERG. LIGHTING SIGN BOARD LEVEL 1 |  | C |  | MEL | DK50
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107901 | EMG light HBD Lev 1 LP-1811-Q14 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-08-13 | 2024-03-31 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-14 | EMERG. LIGHTING SIGN BOARD LEVEL 1 |  | C |  | MEL | DK50
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107902 | EMG light HBD Lev 4 LP-1811-Q34 | EMG light HBD Lev 4 LP-1811-Q34 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-34 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-02
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107902 | EMG light HBD Lev 4 LP-1811-Q34 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-34 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-03
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107902 | EMG light HBD Lev 4 LP-1811-Q34 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-34 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-05
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107902 | EMG light HBD Lev 4 LP-1811-Q34 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-09 | 2024-08-19 | 2024-04-06 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-34 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-07
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107902 | EMG light HBD Lev 4 LP-1811-Q34 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-09 | 2024-08-19 | 2024-04-06 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-34 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-09
2024-W31-32 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107903 | EMG light HBD Lev 4 LP-1811-Q35 | EMG light HBD Lev 4 LP-1811-Q35 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-35 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50
2024-W31-32 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107903 | EMG light HBD Lev 4 LP-1811-Q35 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-35 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50
2024-W31-32 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107903 | EMG light HBD Lev 4 LP-1811-Q35 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-35 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50
2024-W31-32 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107903 | EMG light HBD Lev 4 LP-1811-Q35 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-35 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50
2024-W31-32 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107903 | EMG light HBD Lev 4 LP-1811-Q35 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-35 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107904 | EMG light HBD Lev 4 LP-1811-Q36 | EMG light HBD Lev 4 LP-1811-Q36 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-04-03 | 2024-04-04 | 2024-04-03 | 2024-08-16 | 2024-04-03 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-36 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-02
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107904 | EMG light HBD Lev 4 LP-1811-Q36 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-03 | 2024-04-04 | 2024-04-03 | 2024-08-16 | 2024-04-03 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-36 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-03
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107904 | EMG light HBD Lev 4 LP-1811-Q36 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-04-03 | 2024-04-04 | 2024-04-04 | 2024-08-16 | 2024-04-03 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-36 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-05
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107904 | EMG light HBD Lev 4 LP-1811-Q36 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-04-03 | 2024-04-04 | 2024-04-04 | 2024-08-16 | 2024-04-03 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-36 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-06
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107904 | EMG light HBD Lev 4 LP-1811-Q36 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-03 | 2024-04-04 | 2024-04-04 | 2024-08-16 | 2024-04-03 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-36 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-08
2024-W35-36 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100107905 | EMG light HBD Lev 1 LP-1814-Q1 | EMG light HBD Lev 1 LP-1814-Q1 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-08-13 | 2024-03-31 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1814-01 | EMERG. LIGHTING EXIT DELUGE VLV RM LVL 1 |  | A |  | MEL | DK50 |  |  | 2024-05-28
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107906 | EMG light HBD Lev 4 LP-1814-Q16 | EMG light HBD Lev 4 LP-1814-Q16 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1814-16 | EMERG. LIGHTING EXIT EM GEN RM LVL 4 |  | A |  | MEL | DK50 |  |  | 2024-05-28
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107906 | EMG light HBD Lev 4 LP-1814-Q16 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1814-16 | EMERG. LIGHTING EXIT EM GEN RM LVL 4 |  | A |  | MEL | DK50 |  |  | 2024-05-29
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107906 | EMG light HBD Lev 4 LP-1814-Q16 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1814-16 | EMERG. LIGHTING EXIT EM GEN RM LVL 4 |  | A |  | MEL | DK50 |  |  | 2024-05-30
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107906 | EMG light HBD Lev 4 LP-1814-Q16 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-09 | 2024-08-19 | 2024-04-06 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1814-16 | EMERG. LIGHTING EXIT EM GEN RM LVL 4 |  | A |  | MEL | DK50 |  |  | 2024-06-01
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107906 | EMG light HBD Lev 4 LP-1814-Q16 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-09 | 2024-07-09 | 2024-08-19 | 2024-04-06 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1814-16 | EMERG. LIGHTING EXIT EM GEN RM LVL 4 |  | A |  | MEL | DK50 |  |  | 2024-06-02
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107907 | EMG light HBD Lev 4 LP-1814-Q17 | EMG light HBD Lev 4 LP-1814-Q17 | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1814-17 | EMERG. LIGHTING EXIT WKSH LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-02
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107907 | EMG light HBD Lev 4 LP-1814-Q17 | Isolate equipment and prove dead. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1814-17 | EMERG. LIGHTING EXIT WKSH LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-03
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107907 | EMG light HBD Lev 4 LP-1814-Q17 | Replace defect parts | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1814-17 | EMERG. LIGHTING EXIT WKSH LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-05
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107907 | EMG light HBD Lev 4 LP-1814-Q17 | Deisolate and put back in service | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1814-17 | EMERG. LIGHTING EXIT WKSH LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-07
2024-W29-30 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107907 | EMG light HBD Lev 4 LP-1814-Q17 | Test equipment. | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-08-19 | 2024-04-06 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1814-17 | EMERG. LIGHTING EXIT WKSH LEVEL 4 |  | C |  | MEL | DK50 |  |  | 2024-06-09
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100107908 | Temp transmitter on High pressure washer | Empty tank | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-05-31 | 2024-06-01 | 2024-05-31 | 2024-08-13 | 2024-03-31 | 10 | REL | APPR OPND | HB /D /72/HBDB-A-1150 | HOT WATER UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100107908 | Temp transmitter on High pressure washer | Isolate temp. sensor | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-05-31 | 2024-06-01 | 2024-05-31 | 2024-08-13 | 2024-03-31 | 20 | REL | APPR OPND | HB /D /72/HBDB-A-1150 | HOT WATER UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100107908 | Temp transmitter on High pressure washer | Replace temp. sensor PT100 | REL MACM PRC SETC | APPR WMAT RDBL | 2.5 | 0 |  | 2024-05-31 | 2024-06-01 | 2024-05-31 | 2024-08-13 | 2024-03-31 | 30 | REL | APPR OPND | HB /D /72/HBDB-A-1150 | HOT WATER UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100107908 | Temp transmitter on High pressure washer | De-isolate sensor / Change set point | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-05-31 | 2024-06-01 | 2024-05-31 | 2024-08-13 | 2024-03-31 | 40 | REL | APPR OPND | HB /D /72/HBDB-A-1150 | HOT WATER UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100107908 | Temp transmitter on High pressure washer | De-isolate tank / Test | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-05-31 | 2024-06-01 | 2024-05-31 | 2024-08-13 | 2024-03-31 | 50 | REL | APPR OPND | HB /D /72/HBDB-A-1150 | HOT WATER UNIT |  | C |  | MIN | DK50
0 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100107921 | Deacification filter needs cleaning HDB | Isolate | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-05-13 | 2024-05-16 | 2024-05-13 | 2024-08-14 | 2024-04-01 | 10 | REL | APPR OPND | HD /B /85/HDBM-A-1060 | FRESH WATER PLANT |  | C |  | MMS | DK60
0 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100107921 | Deacification filter needs cleaning HDB | Cleaning deacification filters | REL MACM PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-05-13 | 2024-05-16 | 2024-05-13 | 2024-08-14 | 2024-04-01 | 20 | REL | APPR OPND | HD /B /85/HDBM-A-1060 | FRESH WATER PLANT |  | C |  | MMS | DK60
0 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100107921 | Deacification filter needs cleaning HDB | De-isolate, test | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-05-13 | 2024-05-16 | 2024-05-15 | 2024-08-14 | 2024-04-01 | 30 | REL | APPR OPND | HD /B /85/HDBM-A-1060 | FRESH WATER PLANT |  | C |  | MMS | DK60
2024-W23-24 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100108302 | R.O. Element replacement HBDB-X-1060 | Isolate | REL PCNF MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-15 | 2024-04-18 | 2024-04-15 | 2024-08-24 | 2024-04-11 | 10 | PCNF REL | APPR OPND | HB /D /85/HBDB-X-1060 | RO MODULES |  | C |  | MMS | DK50 |  |  | 2024-05-22
2024-W23-24 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100108302 | R.O. Element replacement HBDB-X-1060 | De-isolate | REL PCNF MANC PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-15 | 2024-04-18 | 2024-04-18 | 2024-08-24 | 2024-04-11 | 30 | PCNF REL | APPR OPND | HB /D /85/HBDB-X-1060 | RO MODULES |  | C |  | MMS | DK50 |  |  | 2024-05-24
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100108489 | Findings after synergi 672065 | Install new drain and vent valves | REL MACM PRC SETC | APPR WMAT RDBL | 3.5 | 0 |  | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-08-28 | 2024-04-15 | 10 | REL | APPR OPND | HB /A /28/HBAA-LIT-50011 | LEVEL INDICATOR TRANSMITTER (SCADA) |  | A |  | MIN | DK50 |  |  | 2024-05-20
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100108493 | Findings after Synergi 672065 | Isolate / Drain the tank | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-05-16 | 2024-05-17 | 2024-05-16 | 2024-08-29 | 2024-04-16 | 10 | REL | APPR OPND | HB /D /50/HBDB-LIT-536101 | LEVEL INDICATOR TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100108493 | Findings after Synergi 672065 | Install DBB valves | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-05-16 | 2024-05-17 | 2024-05-16 | 2024-08-29 | 2024-04-16 | 20 | REL | APPR OPND | HB /D /50/HBDB-LIT-536101 | LEVEL INDICATOR TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100108493 | Findings after Synergi 672065 | De-isolate tank | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-05-16 | 2024-05-17 | 2024-05-16 | 2024-08-29 | 2024-04-16 | 30 | REL | APPR OPND | HB /D /50/HBDB-LIT-536101 | LEVEL INDICATOR TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100108495 | Findings after Synergi 672065 | Install new drain and vent valves | REL MACM PRC SETC | APPR WMAT RDBL | 3.5 | 0 |  | 2024-05-16 | 2024-05-17 | 2024-05-16 | 2024-08-29 | 2024-04-16 | 10 | REL | APPR OPND | HB /D /77/HBDE-LIT-106301 | LEVEL INDICATOR TRANSMITTER |  | A |  | MIN | DK50 |  |  | 2024-05-20
2024-W21-22 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100108496 | Findings after Synergi 672065 | Isolate line | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2027-02-15 | 2024-08-29 | 10 | REL | APPR OPND | HB /D /05 | EMERGENCY POWER GENERATION/DISTRIBUTION |  | A |  | MIN | DK50 |  |  | 2024-05-24
2024-W21-22 | 4 | NOSD | WDF | MTN-INST | MTN-MECH | 2100108496 | Findings after Synergi 672065 | Remove remote seal | REL MACM PRC SETC | APPR WMAT RDBL | 1.5 | 0 |  | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2027-02-15 | 2024-08-29 | 20 | REL | APPR OPND | HB /D /05 | EMERGENCY POWER GENERATION/DISTRIBUTION |  | A |  | MIN | DK50 |  |  | 2024-05-25
2024-W21-22 | 4 | NOSD | WDF | MTN-INST | MTN-MECH | 2100108496 | Findings after Synergi 672065 | Install flush ring | REL MACM PRC SETC | APPR WMAT RDBL | 0.5 | 0 |  | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2027-02-15 | 2024-08-29 | 30 | REL | APPR OPND | HB /D /05 | EMERGENCY POWER GENERATION/DISTRIBUTION |  | A |  | MIN | DK50 |  |  | 2024-05-26
2024-W21-22 | 4 | NOSD | WDF | MTN-INST | MTN-MECH | 2100108496 | Findings after Synergi 672065 | Install remote seal | REL MACM PRC SETC | APPR WMAT RDBL | 1.5 | 0 |  | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2027-02-15 | 2024-08-29 | 40 | REL | APPR OPND | HB /D /05 | EMERGENCY POWER GENERATION/DISTRIBUTION |  | A |  | MIN | DK50 |  |  | 2024-05-27
2024-W21-22 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100108496 | Findings after Synergi 672065 | Install drain and vent valves | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2027-02-15 | 2024-08-29 | 50 | REL | APPR OPND | HB /D /05 | EMERGENCY POWER GENERATION/DISTRIBUTION |  | A |  | MIN | DK50 |  |  | 2024-05-28
2024-W21-22 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100108496 | Findings after Synergi 672065 | De-isolate tranmitter / Calibrate | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-08-29 | 2024-08-30 | 2024-08-30 | 2027-02-15 | 2024-08-29 | 60 | REL | APPR OPND | HB /D /05 | EMERGENCY POWER GENERATION/DISTRIBUTION |  | A |  | MIN | DK50 |  |  | 2024-05-29
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100108662 | Hinge on MAC broken. HBCA-MAC-0162002 | Replace MAC-0162002 | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-08-31 | 2024-04-18 | 10 | REL | APPR OPND | HB /C /03/HBCA-MAC-0162002 | MANUAL ALARM CALL POINT |  | A |  | MIN | DK50 |  |  | 2024-05-22
0 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100108664 | EX Callstation HDBR-PA-14007 malfunction | Replkace EX Callstation | REL MACM PRC SETC | APPR WMAT RDBL | 4 | 0 |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-09-03 | 2024-04-21 | 10 | REL | APPR OPND | HD /B /08/HDBR-PA-14007 | EX MICROPHONE STATION # 6 |  | A |  | MIN | DK60
2026-W13-14 | 2 | NE | WDF | MTN-INST | PRODTECH | 2100108782 | High conductivity on Potable water Maker | Isolate | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-04-24 | 2024-03-10 | 10 | REL | APPR OPND | HB /D /85/HBDB-AE-105001 | ANALYZER ELEMENT |  | C |  | MIN | DK50
2026-W13-14 | 2 | NE | WDF | MTN-INST | MTN-INST | 2100108782 | High conductivity on Potable water Maker | Replace Conductivity Sensor | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-04-24 | 2024-03-10 | 30 | REL | APPR OPND | HB /D /85/HBDB-AE-105001 | ANALYZER ELEMENT |  | C |  | MIN | DK50
2026-W13-14 | 2 | NE | WDF | MTN-INST | PRODTECH | 2100108782 | High conductivity on Potable water Maker | De-isolate | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-04-24 | 2024-03-10 | 40 | REL | APPR OPND | HB /D /85/HBDB-AE-105001 | ANALYZER ELEMENT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100110143 | Malfunction HBAA-PI-5912B | Process isolation / de-isolation | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-09-30 | 2024-05-18 | 10 | REL | APPR OPND | HB /A /07/HBAA-PM-5912B | PUMP MOTOR |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100110143 | Malfunction HBAA-PI-5912B | Replace pressure gauge | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-09-30 | 2024-05-18 | 20 | REL | APPR OPND | HB /A /07/HBAA-PM-5912B | PUMP MOTOR |  | A |  | MIN | DK50
2024-W49-50 | 4 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200003155 | Spare Air-comp drawer to be placed in | Recive in new spare drawer for Air com | REL MANC PRC SETC | APPR WMAT RDBL | 2 | 0 | W49-50 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2018-09-05 | 2018-04-08 | 10 | REL | APPR OPND | HB /D /6 | ELECTRIC ENERGY |  | A |  | MEL | DK50
2024-W23-24 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200007697 | Defect door sauna bathroom. | Defect door sauna bathroom | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2021-11-20 | 2021-08-22 | 10 | REL | APPR OPND | HB /C /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK50 |  | PROK | 2024-05-25
2024-W21-22 | 3 | NOSD | WGN | MTN-INST | MTN-INST | 2200016271 | Install lock on MPHM | Install lock on MPHM | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-12-15 | 2024-12-15 | 2024-12-15 | 2024-04-28 | 2023-12-15 | 10 | REL | APPR OPND | HB /B /11/HBBB-A-3745 | MULTIPHASE METER |  | A |  | MIN | DK50 |  |  | 2024-05-23
0 | 3 | NOSD | WGN | MTN-TELE | MTN-TELE | 2200016328 | Additional field works for PA system | Assistance with works | REL MACM PRC SETC | APPR WMAT RDBL | 70 | 0 |  | 2024-06-17 | 2024-08-05 | 2024-06-17 | 2024-05-04 | 2023-12-21 | 10 | REL | APPR OPND | HD /A /08/PA-LSP | PA SPEAKERS |  | A |  | MIN | DK60
0 | 3 | NOSD | WGN | MTN-TELE | VEN-COMM | 2200016328 | Additional field works for PA system | Splicing optical fiber | REL MACM PRC SETC | APPR WMAT RDBL | 168 | 0 |  | 2024-06-17 | 2024-08-05 | 2024-06-30 | 2024-05-04 | 2023-12-21 | 20 | REL | APPR OPND | HD /A /08/PA-LSP | PA SPEAKERS |  | A |  | MIN | DK60
0 | 3 | NOSD | WGN | MTN-TELE | VEN-COMM | 2200016328 | Additional field works for PA system | Checking tapping for loudspekers | REL MACM PRC SETC | APPR WMAT RDBL | 168 | 0 |  | 2024-06-17 | 2024-08-05 | 2024-07-18 | 2024-05-04 | 2023-12-21 | 30 | REL | APPR OPND | HD /A /08/PA-LSP | PA SPEAKERS |  | A |  | MIN | DK60
2024-W23-24 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016852 | Replace filter in VFD doors for Exportp. | Replace filter in VFD doors for Exportp. | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-06-10 | 2024-01-27 | 10 | REL | APPR OPND | HB /D /23/HBDC-XE-3651 | VFD FOR OIL EXPORT PUMP MOTOR |  | A |  | MEL | DK50 |  | PROK | 2024-06-02
2024-W23-24 | 3 | NOSD | WGN | MTN-ELEC | PRODTECH | 2200016852 | Replace filter in VFD doors for Exportp. | Isolate | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-06-10 | 2024-01-27 | 20 | REL | APPR OPND | HB /D /23/HBDC-XE-3651 | VFD FOR OIL EXPORT PUMP MOTOR |  | A |  | MEL | DK50 |  | PROK | 2024-06-03
2024-W23-24 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016852 | Replace filter in VFD doors for Exportp. | Replace Filter | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-06-10 | 2024-01-27 | 30 | REL | APPR OPND | HB /D /23/HBDC-XE-3651 | VFD FOR OIL EXPORT PUMP MOTOR |  | A |  | MEL | DK50 |  | PROK | 2024-06-04
2024-W23-24 | 3 | NOSD | WGN | MTN-ELEC | PRODTECH | 2200016852 | Replace filter in VFD doors for Exportp. | De Isolate | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-06-10 | 2024-01-27 | 40 | REL | APPR OPND | HB /D /23/HBDC-XE-3651 | VFD FOR OIL EXPORT PUMP MOTOR |  | A |  | MEL | DK50 |  | PROK | 2024-06-05
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017364 | Replace vibration dampers on HBCM-A-1235 | Recover refrigerant into receiver | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-25 | 2024-07-28 | 2024-03-15 | 10 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017364 | Replace vibration dampers on HBCM-A-1235 | Isolate compressor breaker | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-26 | 2024-07-28 | 2024-03-15 | 20 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017364 | Replace vibration dampers on HBCM-A-1235 | Cover / scaf / "tent" before weld | REL MACM PRC SETC | APPR WMAT RDBL | 6 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-26 | 2024-07-28 | 2024-03-15 | 30 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017364 | Replace vibration dampers on HBCM-A-1235 | Cut out / weld in flex pipes in system | REL MACM PRC SETC | APPR WMAT RDBL | 24 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-26 | 2024-07-28 | 2024-03-15 | 40 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | CON-NDTI | 2200017364 | Replace vibration dampers on HBCM-A-1235 | X-ray (100%) of 4 welds | REL MACM PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-29 | 2024-07-28 | 2024-03-15 | 50 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017364 | Replace vibration dampers on HBCM-A-1235 | Leak test @10 bar with N2 | REL MACM PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-01 | 2024-07-28 | 2024-03-15 | 60 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017364 | Replace vibration dampers on HBCM-A-1235 | Apply vacuum, recharge refrigerant | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-02 | 2024-07-28 | 2024-03-15 | 70 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017364 | Replace vibration dampers on HBCM-A-1235 | Deisolate / test / top up refrigerant | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-03 | 2024-07-28 | 2024-03-15 | 80 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017364 | Replace vibration dampers on HBCM-A-1235 | Paint | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-05 | 2024-07-28 | 2024-03-15 | 90 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017364 | Replace vibration dampers on HBCM-A-1235 | Insulate | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-05 | 2024-07-28 | 2024-03-15 | 100 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017364 | Replace vibration dampers on HBCM-A-1235 | Purchase of materials | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-06 | 2024-07-28 | 2024-03-15 | 110 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017365 | Replace vibration dampers on HBCM-A-1236 | Recover refrigerant into receiver | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-25 | 2024-07-28 | 2024-03-15 | 10 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017365 | Replace vibration dampers on HBCM-A-1236 | Isolate compressor breaker | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-26 | 2024-07-28 | 2024-03-15 | 20 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017365 | Replace vibration dampers on HBCM-A-1236 | Cover / scaf / "tent" before weld | REL MACM PRC SETC | APPR WMAT RDBL | 6 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-26 | 2024-07-28 | 2024-03-15 | 30 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017365 | Replace vibration dampers on HBCM-A-1236 | Cut out / weld in flex pipes in system | REL MACM PRC SETC | APPR WMAT RDBL | 24 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-26 | 2024-07-28 | 2024-03-15 | 40 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | CON-NDTI | 2200017365 | Replace vibration dampers on HBCM-A-1236 | X-ray (100%) of 4 welds | REL MACM PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-29 | 2024-07-28 | 2024-03-15 | 50 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017365 | Replace vibration dampers on HBCM-A-1236 | Leak test @10 bar with N2 | REL MACM PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-01 | 2024-07-28 | 2024-03-15 | 60 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017365 | Replace vibration dampers on HBCM-A-1236 | Apply vacuum, recharge refrigerant | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-02 | 2024-07-28 | 2024-03-15 | 70 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017365 | Replace vibration dampers on HBCM-A-1236 | Deisolate / test / top up refrigerant | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-03 | 2024-07-28 | 2024-03-15 | 80 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017365 | Replace vibration dampers on HBCM-A-1236 | Paint | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-05 | 2024-07-28 | 2024-03-15 | 90 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017365 | Replace vibration dampers on HBCM-A-1236 | Insulate | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-05 | 2024-07-28 | 2024-03-15 | 100 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017365 | Replace vibration dampers on HBCM-A-1236 | Purchase of materials | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-06 | 2024-07-28 | 2024-03-15 | 110 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017366 | Replace vibration dampers on HBCM-A-1264 | Recover refrigerant into receiver | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-25 | 2024-07-28 | 2024-03-15 | 10 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017366 | Replace vibration dampers on HBCM-A-1264 | Isolate compressor breaker | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-26 | 2024-07-28 | 2024-03-15 | 20 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017366 | Replace vibration dampers on HBCM-A-1264 | Cover / scaf / "tent" before weld | REL MACM PRC SETC | APPR WMAT RDBL | 6 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-26 | 2024-07-28 | 2024-03-15 | 30 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017366 | Replace vibration dampers on HBCM-A-1264 | Cut out / weld in flex pipes in system | REL MACM PRC SETC | APPR WMAT RDBL | 24 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-26 | 2024-07-28 | 2024-03-15 | 40 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | CON-NDTI | 2200017366 | Replace vibration dampers on HBCM-A-1264 | X-ray (100%) of 4 welds | REL MACM PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-04-29 | 2024-07-28 | 2024-03-15 | 50 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017366 | Replace vibration dampers on HBCM-A-1264 | Leak test @10 bar with N2 | REL MACM PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-01 | 2024-07-28 | 2024-03-15 | 60 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017366 | Replace vibration dampers on HBCM-A-1264 | Apply vacuum, recharge refrigerant | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-02 | 2024-07-28 | 2024-03-15 | 70 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017366 | Replace vibration dampers on HBCM-A-1264 | Deisolate / test / top up refrigerant | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-03 | 2024-07-28 | 2024-03-15 | 80 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017366 | Replace vibration dampers on HBCM-A-1264 | Paint | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-05 | 2024-07-28 | 2024-03-15 | 90 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017366 | Replace vibration dampers on HBCM-A-1264 | Insulate | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-05 | 2024-07-28 | 2024-03-15 | 100 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017366 | Replace vibration dampers on HBCM-A-1264 | Purchase of materials | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-04-25 | 2024-05-06 | 2024-05-06 | 2024-07-28 | 2024-03-15 | 110 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017367 | Replace vibration dampers on HBCM-A-1265 | Recover refrigerant into receiver | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-04-10 | 2024-04-21 | 2024-04-10 | 2024-07-28 | 2024-03-15 | 10 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017367 | Replace vibration dampers on HBCM-A-1265 | Isolate compressor breaker | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-10 | 2024-04-21 | 2024-04-11 | 2024-07-28 | 2024-03-15 | 20 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017367 | Replace vibration dampers on HBCM-A-1265 | Cover / scaf / "tent" before weld | REL MACM PRC SETC | APPR WMAT RDBL | 6 | 0 |  | 2024-04-10 | 2024-04-21 | 2024-04-11 | 2024-07-28 | 2024-03-15 | 30 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017367 | Replace vibration dampers on HBCM-A-1265 | Cut out / weld in flex pipes in system | REL MACM PRC SETC | APPR WMAT RDBL | 24 | 0 |  | 2024-04-10 | 2024-04-21 | 2024-04-11 | 2024-07-28 | 2024-03-15 | 40 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | CON-NDTI | 2200017367 | Replace vibration dampers on HBCM-A-1265 | X-ray (100%) of 4 welds | REL MACM PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-04-10 | 2024-04-21 | 2024-04-14 | 2024-07-28 | 2024-03-15 | 50 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017367 | Replace vibration dampers on HBCM-A-1265 | Leak test @10 bar with N2 | REL MACM PRC SETC | APPR WMAT RDBL | 12 | 0 |  | 2024-04-10 | 2024-04-21 | 2024-04-16 | 2024-07-28 | 2024-03-15 | 60 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200017367 | Replace vibration dampers on HBCM-A-1265 | Apply vacuum, recharge refrigerant | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-04-10 | 2024-04-21 | 2024-04-17 | 2024-07-28 | 2024-03-15 | 70 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017367 | Replace vibration dampers on HBCM-A-1265 | Deisolate / test / top up refrigerant | REL MACM PRC SETC | APPR WMAT RDBL | 8 | 0 |  | 2024-04-10 | 2024-04-21 | 2024-04-18 | 2024-07-28 | 2024-03-15 | 80 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017367 | Replace vibration dampers on HBCM-A-1265 | Paint | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-10 | 2024-04-21 | 2024-04-20 | 2024-07-28 | 2024-03-15 | 90 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017367 | Replace vibration dampers on HBCM-A-1265 | Insulate | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-10 | 2024-04-21 | 2024-04-20 | 2024-07-28 | 2024-03-15 | 100 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200017367 | Replace vibration dampers on HBCM-A-1265 | Purchase of materials | REL MACM PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-04-10 | 2024-04-21 | 2024-04-21 | 2024-07-28 | 2024-03-15 | 110 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | E |  | MEL | DK50
2026-W13-14 | 3 | NE | WGN | MTN-MECH | MTN-MECH | 2200017711 | Weekly/daily cleaning of sewage syst. HB | Weekly/daily cleaning of sewage syst. HB | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-12 | 2024-04-13 | 2024-04-12 | 2024-08-25 | 2024-04-12 | 10 | REL | APPR OPND | HB /C /82/HBCM-A-5132 | SEWAGE TREATMENT UNIT |  | C |  | MMS | DK50
2026-W13-14 | 3 | NE | WGN | MTN-MECH | PRODTECH | 2200017711 | Weekly/daily cleaning of sewage syst. HB | De-isolate | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-12 | 2024-04-13 | 2024-04-12 | 2024-08-25 | 2024-04-12 | 15 | REL | APPR OPND | HB /C /82/HBCM-A-5132 | SEWAGE TREATMENT UNIT |  | C |  | MMS | DK50
2026-W13-14 | 3 | NE | WGN | MTN-MECH | MTN-MECH | 2200017711 | Weekly/daily cleaning of sewage syst. HB | Inspection of selected black water pipes | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-12 | 2024-04-13 | 2024-04-12 | 2024-08-25 | 2024-04-12 | 20 | REL | APPR OPND | HB /C /82/HBCM-A-5132 | SEWAGE TREATMENT UNIT |  | C |  | MMS | DK50
2026-W13-14 | 3 | NE | WGN | MTN-MECH | PRODTECH | 2200017711 | Weekly/daily cleaning of sewage syst. HB | Isolate | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-12 | 2024-04-13 | 2024-04-13 | 2024-08-25 | 2024-04-12 | 30 | REL | APPR OPND | HB /C /82/HBCM-A-5132 | SEWAGE TREATMENT UNIT |  | C |  | MMS | DK50
0 | 3 | NE | WGN | MTN-MECH | MTN-MECH | 2200017712 | Weekly/daily cleaning of sewage syst. Ha | Weekly/daily cleaning of sewage syst. HD | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-12 | 2024-04-13 | 2024-04-12 | 2024-08-25 | 2024-04-12 | 10 | REL | APPR OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | C |  | MMS | DK60
0 | 3 | NE | WGN | MTN-MECH | PRODTECH | 2200017712 | Weekly/daily cleaning of sewage syst. Ha | De-isolate | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-12 | 2024-04-13 | 2024-04-12 | 2024-08-25 | 2024-04-12 | 15 | REL | APPR OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | C |  | MMS | DK60
0 | 3 | NE | WGN | MTN-MECH | MTN-MECH | 2200017712 | Weekly/daily cleaning of sewage syst. Ha | Inspection of selected black water pipes | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-12 | 2024-04-13 | 2024-04-12 | 2024-08-25 | 2024-04-12 | 20 | REL | APPR OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | C |  | MMS | DK60
0 | 3 | NE | WGN | MTN-MECH | PRODTECH | 2200017712 | Weekly/daily cleaning of sewage syst. Ha | Isolate | REL MACM PRC SETC | APPR WMAT RDBL | 1 | 0 |  | 2024-04-12 | 2024-04-13 | 2024-04-13 | 2024-08-25 | 2024-04-12 | 30 | REL | APPR OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | C |  | MMS | DK60
0 | 4 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300000799 | GE01 for Sys 018 SWBD/TRANSFORMER/LIGHT | GE01 for Sys 018 SWBD/TRANSFORMER/LIGHT | REL MANC PRC SETC | APPR WMAT RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2019-12-31 | 2019-12-31 | 10 | REL | APPR OPND | HD /A /6 | ELECTRIC ENERGY |  | A |  | MEL | DK60
2024-W21-22 | 3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300006929 | HB Gas detectors to offshore | HB Gas detectors to offshore | REL MANC PRC SETC | APPR WMAT RDBL | 10 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-04-20 | 2023-12-07 | 10 | REL | APPR OPND | HB /D /03/FGS-DETECTORS | FLAME, HEAT, GAS, SMOKE DETECTORS - HBD |  | A |  | MIN | DK50 |  |  | 2024-05-23
2024-W21-22 | D | NOSD | WPM | MTN-INST | MTN-INST | 2400294047 | 2Y GASSONIC 1701 EQUIP CALIBR - HBD | GASSONIC 1701 EQUIP CALIBR - HBD | REL MANC PRC SETC | APPR WMAT RDBL | 6 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-05 | 2023-10-24 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A | DKHB-2052 | MIN | DK50 | IN0074 |  | 2024-05-23
2024-W21-22 | D | NOSD | WPM | MTN-INST | MTN-INST | 2400322713 | 6M PROCESS CALIBR EQUIP MAINT - HBD | PROCESS CALIBR EQUIP MAINT - HBD | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-05-21 | 2024-04-26 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A | DKHB-2045 | MIN | DK50 | IN0114 |  | 2024-05-24
2024-W21-22 | D | NOSD | WPM | MTN-INST | MTN-INST | 2400325804 | 6M PORTABLE INSTRUMENTS CALIBR - HBD | PORTABLE INSTRUMENTS CALIBR - HBD | REL MANC PRC SETC | APPR WMAT RDBL | 6 | 0 |  | 2024-04-15 | 2024-04-16 | 2024-04-15 | 2024-05-28 | 2024-05-03 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A | DKHB-2049 | MIN | DK50 | IN0114 |  | 2024-05-20
2024-W27-28 | D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400329569 | 1Y HV TESTER/EARTHING EQUIP MAINT - HBD | HV TESTER/EARTHING EQUIP MAINT - HBD | REL MACM PRC SETC | APPR WMAT RDBL | 2 | 0 |  | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-06-16 | 2024-04-30 | 10 | REL | APPR OPND | HB /D /84/TEST-EQUIPMENT | TEST EQUIPMENT |  | A | DKHB-2044 | MEL | DK50 | EL0044 | PROK | 2024-05-25
0 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400330061 | 1Y BREATHING AIR COMP INSPEC HDBC-A-5403 | BREATHING AIR COMP INSPEC HDBC-A-5403 | REL MACM PRC SETC | APPR WMAT RDBL | 6 | 0 |  | 2024-05-23 | 2024-05-25 | 2024-05-23 | 2024-06-28 | 2024-05-23 | 10 | REL | APPR OPND | HD /B /07/HDBC-A-5403 | AIR COMPRESSOR |  | E | DKHD-0098 | MMR | DK60 | MR0023
0 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400330061 | 1Y BREATHING AIR COMP INSPEC HDBC-A-5403 | BREATHING AIR COMP INSPEC HDBC-A-5403 | REL MACM PRC SETC | APPR WMAT RDBL | 6 | 0 |  | 2024-05-23 | 2024-05-25 | 2024-05-24 | 2024-06-28 | 2024-05-23 | 20 | REL | APPR OPND | HD /B /07/HDBC-A-5403 | AIR COMPRESSOR |  | E | DKHD-0098 | MMR | DK60 | MR0023
0 | D | NOSD | WPM | MTN-INST | MTN-INST | 2400335697 | 1Y WEIGHT IN HLO REPLACEMENT | WEIGHT IN HLO - REPLACEMENT | REL MACM PRC SETC | APPR WMAT RDBL | 3 | 0 |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2024-07-23 | 2024-06-06 | 10 | REL | APPR OPND | HD /B /84/HDBF-WT-69004 | WEIGHT FOR HLO |  | A | DKHD-2045 | MIN | DK60 | IN0103
2024-W23-24 | 3 | HB-FLARE | WGN | MTN-ELEC | MTN-ELEC | 2200003156 | Test of backfeeding power-POG HB-18-03 | L3 Test of POG HB-18-03, step by step | REL MANC PPRT PRC SETC | APPR WMAT AWSD AWSC RDBL | 9 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-01-30 | 2018-11-01 | 10 | REL | APPR OPND | HB /D /6 | ELECTRIC ENERGY | 99000119 | G |  | MEL | DK50
2024-W23-24 | 3 | HB-FLARE | WGN | MTN-ELEC | MTN-ELEC | 2200003156 | Test of backfeeding power-POG HB-18-03 | Additional parts | REL MANC PPRT PRC SETC | APPR WMAT AWSD AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-01-30 | 2018-11-01 | 20 | REL | APPR OPND | HB /D /6 | ELECTRIC ENERGY | 99000119 | G |  | MEL | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | VEN-MECH | 2100022698 | Exchange XCV-34005 incl. actuator | Score - Midas Meter survey | REL PRT MANC PRC SETC | APPR WMAT AWSC RDBL | 48 | 0 |  | 2024-09-18 | 2024-12-07 | 2024-09-18 | 2019-08-26 | 2019-05-28 | 1 | REL | APPR OPND | HB /A /34/HBAA-XCV-34005 | PRODUCTION MANIFOLD INLET VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-PIPF | 2100022698 | Exchange XCV-34005 incl. actuator | L3 Site visit | REL PRT MANC PRC SETC | APPR WMAT AWSC RDBL | 8.7 | 0 |  | 2024-09-18 | 2024-12-07 | 2024-11-26 | 2019-08-26 | 2019-05-28 | 10 | REL | APPR OPND | HB /A /34/HBAA-XCV-34005 | PRODUCTION MANIFOLD INLET VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-SCAF | 2100022698 | Exchange XCV-34005 incl. actuator | L3 Prepare rigging equipment | REL PRT MANC PRC SETC | APPR WMAT AWSC RDBL | 17.4 | 0 |  | 2024-09-18 | 2024-12-07 | 2024-11-27 | 2019-08-26 | 2019-05-28 | 20 | REL | APPR OPND | HB /A /34/HBAA-XCV-34005 | PRODUCTION MANIFOLD INLET VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100022698 | Exchange XCV-34005 incl. actuator | L3 Isolate equipment | REL PRT MANC PRC SETC | APPR WMAT AWSC RDBL | 12 | 0 |  | 2024-09-18 | 2024-12-07 | 2024-11-29 | 2019-08-26 | 2019-05-28 | 30 | REL | APPR OPND | HB /A /34/HBAA-XCV-34005 | PRODUCTION MANIFOLD INLET VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-PIPF | 2100022698 | Exchange XCV-34005 incl. actuator | L3 Dismantle Hydraulic & hubs | REL PRT MANC PRC SETC | APPR WMAT AWSC RDBL | 13.4 | 0 |  | 2024-09-18 | 2024-12-07 | 2024-11-30 | 2019-08-26 | 2019-05-28 | 40 | REL | APPR OPND | HB /A /34/HBAA-XCV-34005 | PRODUCTION MANIFOLD INLET VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | VEN-ELEC | 2100022698 | Exchange XCV-34005 incl. actuator | L3 Disconnect cables | REL PRT MANC PRC SETC | APPR WMAT AWSC RDBL | 2 | 0 |  | 2024-09-18 | 2024-12-07 | 2024-11-30 | 2019-08-26 | 2019-05-28 | 50 | REL | APPR OPND | HB /A /34/HBAA-XCV-34005 | PRODUCTION MANIFOLD INLET VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-SCAF | 2100022698 | Exchange XCV-34005 incl. actuator | L3 Rig in & out of valve | REL PRT MANC PRC SETC | APPR WMAT AWSC RDBL | 17.4 | 0 |  | 2024-09-18 | 2024-12-07 | 2024-12-01 | 2019-08-26 | 2019-05-28 | 60 | REL | APPR OPND | HB /A /34/HBAA-XCV-34005 | PRODUCTION MANIFOLD INLET VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100022698 | Exchange XCV-34005 incl. actuator | L2 Connect hubs & hydraulic | REL PRT MANC PRC SETC | APPR WMAT AWSC RDBL | 20 | 0 |  | 2024-09-18 | 2024-12-07 | 2024-12-02 | 2019-08-26 | 2019-05-28 | 70 | REL | APPR OPND | HB /A /34/HBAA-XCV-34005 | PRODUCTION MANIFOLD INLET VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-ELEC | 2100022698 | Exchange XCV-34005 incl. actuator | L2 Connect cables | REL PRT MANC PRC SETC | APPR WMAT AWSC RDBL | 3 | 0 |  | 2024-09-18 | 2024-12-07 | 2024-12-02 | 2019-08-26 | 2019-05-28 | 80 | REL | APPR OPND | HB /A /34/HBAA-XCV-34005 | PRODUCTION MANIFOLD INLET VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100022698 | Exchange XCV-34005 incl. actuator | L3 Remove isolation | REL PRT MANC PRC SETC | APPR WMAT AWSC RDBL | 12 | 0 |  | 2024-09-18 | 2024-12-07 | 2024-12-05 | 2019-08-26 | 2019-05-28 | 90 | REL | APPR OPND | HB /A /34/HBAA-XCV-34005 | PRODUCTION MANIFOLD INLET VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-SCAF | 2100022698 | Exchange XCV-34005 incl. actuator | L3 Remove rigging equipment | REL PRT MANC PRC SETC | APPR WMAT AWSC RDBL | 13.4 | 0 |  | 2024-09-18 | 2024-12-07 | 2024-12-06 | 2019-08-26 | 2019-05-28 | 100 | REL | APPR OPND | HB /A /34/HBAA-XCV-34005 | PRODUCTION MANIFOLD INLET VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | MTN-PIPF | 2100026259 | Exchange of valve XCV-300706 | Pre. Permit and linewalk | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 5.4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2018-09-26 | 2018-06-28 | 1 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | MTN-SCAF | 2100026259 | Exchange of valve XCV-300706 | Pre. Permit and linewalk | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 5.4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2018-09-26 | 2018-06-28 | 2 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | VEN-ELEC | 2100026259 | Exchange of valve XCV-300706 | Pre. Permit and linewalk | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 5.4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2018-09-26 | 2018-06-28 | 3 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | MTN-SCAF | 2100026259 | Exchange of valve XCV-300706 | L3 Prepare scaffold & lifting equipment | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 5.4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2018-09-26 | 2018-06-28 | 10 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | PRODTECH | 2100026259 | Exchange of valve XCV-300706 | L3 Isolate equipment | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2018-09-26 | 2018-06-28 | 20 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | VEN-ELEC | 2100026259 | Exchange of valve XCV-300706 | Disconnect tubing and switches | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2018-09-26 | 2018-06-28 | 25 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | MTN-PIPF | 2100026259 | Exchange of valve XCV-300706 | L3 Remove actuator | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2.7 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2018-09-26 | 2018-06-28 | 30 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | MTN-PIPF | 2100026259 | Exchange of valve XCV-300706 | L3 Loosen bolts on hubs | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2.7 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2018-09-26 | 2018-06-28 | 40 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | MTN-SCAF | 2100026259 | Exchange of valve XCV-300706 | L3 Rig out of valve | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 5.4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2018-09-26 | 2018-06-28 | 50 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | MTN-SCAF | 2100026259 | Exchange of valve XCV-300706 | L3 Rig in of valve | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2.7 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2018-09-26 | 2018-06-28 | 60 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | MTN-PIPF | 2100026259 | Exchange of valve XCV-300706 | L2 Install new valve | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2.7 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2018-09-26 | 2018-06-28 | 70 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | MTN-PIPF | 2100026259 | Exchange of valve XCV-300706 | L3 Install actuator | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2018-09-26 | 2018-06-28 | 80 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | VEN-ELEC | 2100026259 | Exchange of valve XCV-300706 | Connect tubing and switches | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2018-09-26 | 2018-06-28 | 85 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | PRODTECH | 2100026259 | Exchange of valve XCV-300706 | L3 Remove isolation | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2018-09-26 | 2018-06-28 | 90 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBB07-GL | WDF | MTN-PIPF | MTN-SCAF | 2100026259 | Exchange of valve XCV-300706 | L3 Remove Scaffolf & Lifting equipment | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2.7 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-07 | 2018-09-26 | 2018-06-28 | 100 | REL | APPR OPND | HB /B /10/HBBB-XCV-300706 | CONTROL VALVE WELL 07 | 99000119 | C |  | MMS | DK50
0 | 4 | HDAPW | WDF | MTN-MECH | PRODTECH | 2100026989 | NO HCV for dræn har intern lækage V-5 | Safing | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2 | 0 | PROD | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-12-29 | 2017-08-01 | 10 | REL | APPR OPND | HD /A /28 | CLOSED DRAINS/OPEN DRAINS | 99000120 | F |  | MMS | DK60
0 | 4 | HDAPW | WDF | MTN-MECH | MTN-MECH | 2100026989 | NO HCV for dræn har intern lækage V-5 | Udskifte 2" ventilen | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 8 | 0 | Se revision code | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-12-29 | 2017-08-01 | 20 | REL | APPR OPND | HD /A /28 | CLOSED DRAINS/OPEN DRAINS | 99000120 | F |  | MMS | DK60
0 | 4 | HDAPW | WDF | MTN-MECH | PRODTECH | 2100026989 | NO HCV for dræn har intern lækage V-5 | Desafing | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2 | 0 | PROD | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2017-12-29 | 2017-08-01 | 30 | REL | APPR OPND | HD /A /28 | CLOSED DRAINS/OPEN DRAINS | 99000120 | F |  | MMS | DK60
0 | 4 | HDAPW | WDF | MTN-MECH | PRODTECH | 2100026989 | NO HCV for dræn har intern lækage V-5 | Leaktest | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 | PROD | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2017-12-29 | 2017-08-01 | 40 | REL | APPR OPND | HD /A /28 | CLOSED DRAINS/OPEN DRAINS | 99000120 | F |  | MMS | DK60
0 | 4 | HDAPW | WDF | MTN-MECH | PRODTECH | 2100027291 | HCV for dræn har int lækage V-5012 | Safing | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2017-12-29 | 2017-08-01 | 10 | REL | APPR OPND | HD /A /28 | CLOSED DRAINS/OPEN DRAINS | 99000120 | F |  | MMS | DK60
0 | 4 | HDAPW | WDF | MTN-MECH | MTN-MECH | 2100027291 | HCV for dræn har int lækage V-5012 | Udskifte ventilen | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2017-12-29 | 2017-08-01 | 20 | REL | APPR OPND | HD /A /28 | CLOSED DRAINS/OPEN DRAINS | 99000120 | F |  | MMS | DK60
0 | 4 | HDAPW | WDF | MTN-MECH | PRODTECH | 2100027291 | HCV for dræn har int lækage V-5012 | Desafing | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2017-12-29 | 2017-08-01 | 30 | REL | APPR OPND | HD /A /28 | CLOSED DRAINS/OPEN DRAINS | 99000120 | F |  | MMS | DK60
0 | 4 | HDAPW | WDF | MTN-MECH | PRODTECH | 2100027291 | HCV for dræn har int lækage V-5012 | Leaktest | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2017-12-29 | 2017-08-01 | 40 | REL | APPR OPND | HD /A /28 | CLOSED DRAINS/OPEN DRAINS | 99000120 | F |  | MMS | DK60
2026-W13-14 | 3 | HBA16-WI | WDF | MTN-INST | PRODTECH | 2100095244 | HBA16 choke external leak hydraulic oil | Well SD state prep. | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2024-01-17 | 2023-09-04 | 10 | REL | APPR OPND | HB /A /55/HBAA-CVA-30166 | CHOKE VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA16-WI | WDF | MTN-INST | MTN-INST | 2100095244 | HBA16 choke external leak hydraulic oil | Isolate valve control panel | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2024-01-17 | 2023-09-04 | 20 | REL | APPR OPND | HB /A /55/HBAA-CVA-30166 | CHOKE VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA16-WI | WDF | MTN-INST | MTN-INST | 2100095244 | HBA16 choke external leak hydraulic oil | Replace valve control panel | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2024-01-17 | 2023-09-04 | 30 | REL | APPR OPND | HB /A /55/HBAA-CVA-30166 | CHOKE VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA16-WI | WDF | MTN-INST | MTN-INST | 2100095244 | HBA16 choke external leak hydraulic oil | De-isolate valve control panel/Test with | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2024-01-17 | 2023-09-04 | 40 | REL | APPR OPND | HB /A /55/HBAA-CVA-30166 | CHOKE VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA16-WI | WDF | MTN-INST | PRODTECH | 2100095244 | HBA16 choke external leak hydraulic oil | Well is back to service | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2024-01-17 | 2023-09-04 | 50 | REL | APPR OPND | HB /A /55/HBAA-CVA-30166 | CHOKE VALVE |  | E |  | MIN | DK50
2024-W23-24 | 3 | HBB04-GL | WDF | MTN-INST | MTN-INST | 2100103039 | ZSO/ZSC signal for HBB04 Choke | Adjust replace position switches | REL MACM PRC SETC | APPR WMAT AWSC RDBL | 3 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2024-01-15 | 2023-12-01 | 10 | REL | APPR OPND | HB /B /10/HBBB-CVA-300407 | CHOKE VALVE - NO VALVE INSATLLED |  | E |  | MIN | DK50
2024-W23-24 | 3 | HBB04-GL | WDF | MTN-INST | MTN-INST | 2100103039 | ZSO/ZSC signal for HBB04 Choke | Replace solenoid valves | REL MACM PRC SETC | APPR WMAT AWSC RDBL | 2 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2024-01-15 | 2023-12-01 | 20 | REL | APPR OPND | HB /B /10/HBBB-CVA-300407 | CHOKE VALVE - NO VALVE INSATLLED |  | E |  | MIN | DK50
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241240 | 6M GALLY MAINTENANCE VENDOR | GALLY MAINTENANCE VENDOR | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 4 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2023-04-01 | 2023-03-13 | 10 | REL | APPR OPND | HD /B /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | A | DKHD-2037 | MEL | DK60 | EL0103 | PROK
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400241240 | 6M GALLY MAINTENANCE VENDOR | Personal Isolation | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2023-04-01 | 2023-03-13 | 20 | REL | APPR OPND | HD /B /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | A | DKHD-2037 | MEL | DK60 | EL0103 | PROK
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241240 | 6M GALLY MAINTENANCE VENDOR | Inspection acc. to desciption | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2023-04-01 | 2023-03-13 | 30 | REL | APPR OPND | HD /B /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | A | DKHD-2037 | MEL | DK60 | EL0103 | PROK
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241240 | 6M GALLY MAINTENANCE VENDOR | Meassure RCD functiontest (L-AUS) | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2023-04-01 | 2023-03-13 | 40 | REL | APPR OPND | HD /B /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | A | DKHD-2037 | MEL | DK60 | EL0103 | PROK
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400241240 | 6M GALLY MAINTENANCE VENDOR | De isolate | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2023-04-01 | 2023-03-13 | 50 | REL | APPR OPND | HD /B /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | A | DKHD-2037 | MEL | DK60 | EL0103 | PROK
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241240 | 6M GALLY MAINTENANCE VENDOR | Test Equipment | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2023-04-01 | 2023-03-13 | 60 | REL | APPR OPND | HD /B /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | A | DKHD-2037 | MEL | DK60 | EL0103 | PROK
0 | C | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400274747 | 6M GALLY MAINTENANCE VENDOR | GALLY MAINTENANCE VENDOR | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 4 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-10-01 | 2023-09-12 | 10 | REL | APPR OPND | HD /B /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | A | DKHD-2037 | MEL | DK60 | EL0103
0 | C | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400302383 | 1Y CRANE HOIST EQUIP, HD | Crane hoist equipment Re-cert | REL MACM PRC SETC | APPR WMAT AWSC RDBL | 3 | 0 |  | 2024-04-20 | 2024-04-20 | 2024-04-20 | 2024-05-01 | 2024-03-26 | 10 | REL | APPR OPND | HD /A /78 | LIFTING EQUIPMENT |  | A | DKHD-2028 | MMS | DK60 | MS0153
2026-W13-14 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400302705 | 1Y HBDC-FE-365111 - METERING | ISOLATION BY PRODUCTION | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-12 | 2024-04-08 | 2024-02-16 | 2024-01-11 | 10 | REL | APPR OPND | HB /D /23/HBDC-FIT-365111 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6004 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400302705 | 1Y HBDC-FE-365111 - METERING | DISASSEMBLY OF METERING | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-12 | 2024-04-08 | 2024-02-16 | 2024-01-11 | 20 | REL | APPR OPND | HB /D /23/HBDC-FIT-365111 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6004 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-RIGG | 2400302705 | 1Y HBDC-FE-365111 - METERING | RIGGING SUPPORT | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-12 | 2024-04-09 | 2024-02-16 | 2024-01-11 | 30 | REL | APPR OPND | HB /D /23/HBDC-FIT-365111 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6004 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-INST | 2400302705 | 1Y HBDC-FE-365111 - METERING | HBDC-FE-365111 - METERING | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 2.8 | 0 | W15-W16 | 2024-04-08 | 2024-04-12 | 2024-04-09 | 2024-02-16 | 2024-01-11 | 40 | REL | APPR OPND | HB /D /23/HBDC-FIT-365111 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6004 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-RIGG | 2400302705 | 1Y HBDC-FE-365111 - METERING | DE-RIGGING SUPPORT | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-12 | 2024-04-10 | 2024-02-16 | 2024-01-11 | 50 | REL | APPR OPND | HB /D /23/HBDC-FIT-365111 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6004 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400302705 | 1Y HBDC-FE-365111 - METERING | ASSEMBLY OF METERING | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-12 | 2024-04-10 | 2024-02-16 | 2024-01-11 | 60 | REL | APPR OPND | HB /D /23/HBDC-FIT-365111 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6004 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400302705 | 1Y HBDC-FE-365111 - METERING | DE-ISOLATION BY PRODUCTION | REL MANC PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-12 | 2024-04-11 | 2024-02-16 | 2024-01-11 | 70 | REL | APPR OPND | HB /D /23/HBDC-FIT-365111 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6004 | MIN | DK50 | IN0014
0 | C | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400314647 | 6M GALLY MAINTENANCE VENDOR | GALLY MAINTENANCE VENDOR | REL MACM PRC SETC | APPR WMAT AWSC RDBL | 4 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-04-01 | 2024-03-13 | 10 | REL | APPR OPND | HD /B /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | A | DKHD-2037 | MEL | DK60 | EL0103
0 | D | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400325807 | 1Y EXERCISE EQUIPMENT VENDOR | TREADMILL | REL MACM PRC SETC | APPR WMAT AWSC RDBL | 2 | 0 |  | 2024-04-12 | 2024-04-12 | 2024-04-12 | 2024-05-29 | 2024-04-12 | 20 | REL | APPR OPND | HD /B /82/GYM-EQUIPMENT | GYM EQUIPMENT |  | A | DKHD-2033 | MEL | DK60 | EL0103
0 | D | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400325807 | 1Y EXERCISE EQUIPMENT VENDOR | EXERCISE AND SPINNING BIKES | REL MACM PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 |  | 2024-04-12 | 2024-04-12 | 2024-04-12 | 2024-05-29 | 2024-04-12 | 40 | REL | APPR OPND | HD /B /82/GYM-EQUIPMENT | GYM EQUIPMENT |  | A | DKHD-2033 | MEL | DK60 | EL0103
0 | D | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400325807 | 1Y EXERCISE EQUIPMENT VENDOR | CROSSTRAINER | REL MACM PRC SETC | APPR WMAT AWSC RDBL | 2 | 0 |  | 2024-04-12 | 2024-04-12 | 2024-04-12 | 2024-05-29 | 2024-04-12 | 50 | REL | APPR OPND | HD /B /82/GYM-EQUIPMENT | GYM EQUIPMENT |  | A | DKHD-2033 | MEL | DK60 | EL0103
0 | D | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400325807 | 1Y EXERCISE EQUIPMENT VENDOR | ROWING MACHINE | REL MACM PRC SETC | APPR WMAT AWSC RDBL | 2 | 0 |  | 2024-04-12 | 2024-04-12 | 2024-04-12 | 2024-05-29 | 2024-04-12 | 70 | REL | APPR OPND | HD /B /82/GYM-EQUIPMENT | GYM EQUIPMENT |  | A | DKHD-2033 | MEL | DK60 | EL0103
0 | D | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400325807 | 1Y EXERCISE EQUIPMENT VENDOR | MULTI MACH. BENCHES, WEIGHTS, & BARBELLS | REL MACM PRC SETC | APPR WMAT AWSC RDBL | 1 | 0 |  | 2024-04-12 | 2024-04-12 | 2024-04-12 | 2024-05-29 | 2024-04-12 | 100 | REL | APPR OPND | HD /B /82/GYM-EQUIPMENT | GYM EQUIPMENT |  | A | DKHD-2033 | MEL | DK60 | EL0103
0 | 4 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100096538 | No light in Subsidiary light on HDC | No light in Subsidiary light on HDC | REL PCNF MANC PRC SETC | APPR WMAT AWDO RFRZ ROUT | 0 | 0 |  | 2024-09-03 | 2024-09-05 | 2024-09-03 | 2026-07-29 | 2024-02-10 | 10 | PCNF REL | APPR OPND | HD /C /64/HDCC-SL-15011 | SUBSIDIARY LANTERN |  | A |  | MEL | DK60
0 | 4 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100096538 | No light in Subsidiary light on HDC | Replace light bulb | REL PCNF MANC PRC SETC | APPR WMAT AWDO RFRZ ROUT | 6 | 24 |  | 2024-09-03 | 2024-09-05 | 2024-09-03 | 2026-07-29 | 2024-02-10 | 20 | PCNF REL | APPR OPND | HD /C /64/HDCC-SL-15011 | SUBSIDIARY LANTERN |  | A |  | MEL | DK60
0 | 4 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100096538 | No light in Subsidiary light on HDC | return from repair | REL PCNF MANC PRC SETC | APPR WMAT AWDO RFRZ ROUT | 0 | 0 |  | 2024-09-03 | 2024-09-05 | 2024-09-03 | 2026-07-29 | 2024-02-10 | 30 | REL | APPR OPND | HD /C /64/HDCC-SL-15011 | SUBSIDIARY LANTERN |  | A |  | MEL | DK60
0 | 4 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100096538 | No light in Subsidiary light on HDC | Additional parts | REL PCNF MANC PRC SETC | APPR WMAT AWDO RFRZ ROUT | 0 | 0 |  | 2024-09-03 | 2024-09-05 | 2024-09-03 | 2026-07-29 | 2024-02-10 | 40 | REL | APPR OPND | HD /C /64/HDCC-SL-15011 | SUBSIDIARY LANTERN |  | A |  | MEL | DK60
0 | 4 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100096538 | No light in Subsidiary light on HDC | Replace lantern | REL PCNF MANC PRC SETC | APPR WMAT AWDO RFRZ ROUT | 6 | 0 |  | 2024-09-03 | 2024-09-05 | 2024-09-03 | 2026-07-29 | 2024-02-10 | 50 | REL | APPR OPND | HD /C /64/HDCC-SL-15011 | SUBSIDIARY LANTERN |  | A |  | MEL | DK60
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100052927 | HBD/78: Replace luffing winch | Pre-survey | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 6 | 0 |  | 2024-05-17 | 2024-09-08 | 2024-05-17 | 2022-03-13 | 2021-10-14 | 28 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100052927 | HBD/78: Replace luffing winch | Pre-survey | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 6 | 0 |  | 2024-05-17 | 2024-09-08 | 2024-05-17 | 2022-03-13 | 2021-10-14 | 29 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100052927 | HBD/78: Replace luffing winch | Dismount luffing wire | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 24 | 0 | W20-23 DK50-M-6990 | 2024-05-17 | 2024-09-08 | 2024-08-10 | 2022-03-13 | 2021-10-14 | 30 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100052927 | HBD/78: Replace luffing winch | Assist dismount luffing wire | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 12 | 0 | W20-23 DK50-M-6990 | 2024-05-17 | 2024-09-08 | 2024-08-10 | 2022-03-13 | 2021-10-14 | 40 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100052927 | HBD/78: Replace luffing winch | Isolate/de-isolate of crane HBDE-A-6150 | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 4 | 0 | W20-23 DK50-M-6990 | 2024-05-17 | 2024-09-08 | 2024-08-11 | 2022-03-13 | 2021-10-14 | 50 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100052927 | HBD/78: Replace luffing winch | Build/demol of scaffold/gallows | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 200 | 0 | W20-23 DK50-M-6990 | 2024-05-17 | 2024-09-08 | 2024-08-12 | 2022-03-13 | 2021-10-14 | 60 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100052927 | HBD/78: Replace luffing winch | Disassembly of luffing winch | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 24 | 0 | W20-23 DK50-M-6990990 | 2024-05-17 | 2024-09-08 | 2024-08-25 | 2022-03-13 | 2021-10-14 | 70 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100052927 | HBD/78: Replace luffing winch | Replace luffing winch | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 100 | 0 | W20-23 DK50-M-6990 | 2024-05-17 | 2024-09-08 | 2024-08-27 | 2022-03-13 | 2021-10-14 | 80 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100052927 | HBD/78: Replace luffing winch | Assembly of new luffing winch | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 30 | 0 | W20-23 DK50-M-6990 | 2024-05-17 | 2024-09-08 | 2024-09-02 | 2022-03-13 | 2021-10-14 | 90 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100052927 | HBD/78: Replace luffing winch | Re-install luffing wire | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 12 | 0 | W20-23 DK50-M-6990 | 2024-05-17 | 2024-09-08 | 2024-09-04 | 2022-03-13 | 2021-10-14 | 100 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100052927 | HBD/78: Replace luffing winch | Adjustment and testing of new winch | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 12 | 0 | W20-23 DK50-M-6990 | 2024-05-17 | 2024-09-08 | 2024-09-04 | 2022-03-13 | 2021-10-14 | 110 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100052927 | HBD/78: Replace luffing winch | Perform proof load test | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 24 | 0 | W20-23 DK50-M-6990 | 2024-05-17 | 2024-09-08 | 2024-09-05 | 2022-03-13 | 2021-10-14 | 120 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100052927 | HBD/78: Replace luffing winch | Operation of crane | REL PCNF MANC PRC SETC | APPR WMAT AWDO RDBL ROUT | 12 | 0 | W20-23 DK50-M-6990 | 2024-05-17 | 2024-09-08 | 2024-09-05 | 2022-03-13 | 2021-10-14 | 130 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 |  | WDF | MTN-MECH | PRODTECH | 2100040211 | HBDB-A-0452 Hoses to be replaced | Isolate HBDB-A-0452 | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-17 | 2024-06-20 | 2024-06-17 | 2021-02-15 | 2020-11-17 | 10 | REL | APPR OPND | HB /D /01/HBDB-A-0452 | WATER MIST CABINET (FOR A-0362) |  | C |  | MMS | DK50
2026-W13-14 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100040211 | HBDB-A-0452 Hoses to be replaced | Replace water fill hose Pos. 1 | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-17 | 2024-06-20 | 2024-06-17 | 2021-02-15 | 2020-11-17 | 20 | REL | APPR OPND | HB /D /01/HBDB-A-0452 | WATER MIST CABINET (FOR A-0362) |  | C |  | MMS | DK50
2026-W13-14 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100040211 | HBDB-A-0452 Hoses to be replaced | Replace H2O discharge hose Pos. 2 | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-17 | 2024-06-20 | 2024-06-18 | 2021-02-15 | 2020-11-17 | 30 | REL | APPR OPND | HB /D /01/HBDB-A-0452 | WATER MIST CABINET (FOR A-0362) |  | C |  | MMS | DK50
2026-W13-14 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100040211 | HBDB-A-0452 Hoses to be replaced | Replace N2 hose SOV to Water bot. Pos. 3 | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-17 | 2024-06-20 | 2024-06-18 | 2021-02-15 | 2020-11-17 | 40 | REL | APPR OPND | HB /D /01/HBDB-A-0452 | WATER MIST CABINET (FOR A-0362) |  | C |  | MMS | DK50
2026-W13-14 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100040211 | HBDB-A-0452 Hoses to be replaced | Replasce N2 hose to PSL Pos. 4 | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-17 | 2024-06-20 | 2024-06-19 | 2021-02-15 | 2020-11-17 | 50 | REL | APPR OPND | HB /D /01/HBDB-A-0452 | WATER MIST CABINET (FOR A-0362) |  | C |  | MMS | DK50
2026-W13-14 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100040211 | HBDB-A-0452 Hoses to be replaced | Replace N2 hose to slave Pos. 5 | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-17 | 2024-06-20 | 2024-06-19 | 2021-02-15 | 2020-11-17 | 60 | REL | APPR OPND | HB /D /01/HBDB-A-0452 | WATER MIST CABINET (FOR A-0362) |  | C |  | MMS | DK50
2026-W13-14 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100040211 | HBDB-A-0452 Hoses to be replaced | De-Isolate/Test HBDB-A-0452 | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-06-17 | 2024-06-20 | 2024-06-19 | 2021-02-15 | 2020-11-17 | 70 | REL | APPR OPND | HB /D /01/HBDB-A-0452 | WATER MIST CABINET (FOR A-0362) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100049127 | actuator is extern leak BDV-34075 | isolate valve | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2022-04-14 | 2021-08-17 | 10 | REL | APPR OPND | HB /A /11/HBAB-BDV-34075 | BLOWDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049127 | actuator is extern leak BDV-34075 | replace act | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 6 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2022-04-14 | 2021-08-17 | 20 | REL | APPR OPND | HB /A /11/HBAB-BDV-34075 | BLOWDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100049127 | actuator is extern leak BDV-34075 | de-isolate, leak test, etc. | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2022-04-14 | 2021-08-17 | 30 | REL | APPR OPND | HB /A /11/HBAB-BDV-34075 | BLOWDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100067249 | HMI freezes when event log is selected | Isolation & safing of HBDC-A-4352 | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-03 | 2024-10-06 | 2024-10-03 | 2022-06-18 | 2022-05-09 | 10 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | VEN-MECH | 2100067249 | HMI freezes when event log is selected | Replace HMI & test | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-03 | 2024-10-06 | 2024-10-04 | 2022-06-18 | 2022-05-09 | 20 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100067249 | HMI freezes when event log is selected | De-isolation & desafing of HBDC-A-4352 | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-03 | 2024-10-06 | 2024-10-05 | 2022-06-18 | 2022-05-09 | 30 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | A |  | MMR | DK50 |  | PROK
2024-W25-26 | 3 | HBAPWELL | WDF | MTN-ROPE | MTN-MECH | 2100070959 | FFSP Flange Face Corrosion HBA-2"-GPS-02 | Flange Face Corrosion HBA-2"-GPS-0294914 | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2022-12-30 | 2022-08-17 | 10 | REL | APPR OPND | HB /A /37/HBA-2-GPS-029-4914-GF-U | 2 PROCESS GAS SOUR LINE |  | A |  | MFM | DK50
2024-W25-26 | 3 | HBAPWELL | WDF | MTN-ROPE | MTN-ROPE | 2100070959 | FFSP Flange Face Corrosion HBA-2"-GPS-02 | New spool | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2022-12-30 | 2022-08-17 | 20 | REL | APPR OPND | HB /A /37/HBA-2-GPS-029-4914-GF-U | 2 PROCESS GAS SOUR LINE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100071063 | Missing insulation HBBB-HRS-03103 | Rectify damaged insulation | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2023-04-24 | 2023-04-25 | 2023-04-24 | 2025-06-16 | 2022-12-29 | 10 | REL | APPR OPND | HB /B /01/HBBB-HRS-03103 | HORSE REEL STATION - PRODUCTION DECK |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100073547 | HBD/78: Replacement of battery switch | Isolation/de-isolation of crane HBDE-A-6 | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2023-02-14 | 2022-10-02 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073547 | HBD/78: Replacement of battery switch | Replacement of battery switch | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2023-02-14 | 2022-10-02 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088075 | HBC/78: Replace handrail+ladder | Isolation/deisolation of crane | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2023-09-23 | 2023-05-11 | 10 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088075 | HBC/78: Replace handrail+ladder | Replace ladder to crane | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2023-09-23 | 2023-05-11 | 20 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100088075 | HBC/78: Replace handrail+ladder | Ass. Replace ladder | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2023-09-23 | 2023-05-11 | 30 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | PRODTECH | 2100089855 | New SLDBB for PIT-29106 | Inhibit PIT-29106 | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-10-21 | 2023-06-08 | 10 | REL | APPR OPND | HB /A /37/HBAA-PIT-29106 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | PRODTECH | 2100089855 | New SLDBB for PIT-29106 | Process isolation | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-10-21 | 2023-06-08 | 20 | REL | APPR OPND | HB /A /37/HBAA-PIT-29106 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-INST | 2100089855 | New SLDBB for PIT-29106 | Isolate transmitter and heat tracing | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-10-21 | 2023-06-08 | 30 | REL | APPR OPND | HB /A /37/HBAA-PIT-29106 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-LAGG | 2100089855 | New SLDBB for PIT-29106 | Remove lagging | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-10-21 | 2023-06-08 | 40 | REL | APPR OPND | HB /A /37/HBAA-PIT-29106 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-INST | 2100089855 | New SLDBB for PIT-29106 | Dismount transmitter and replace SDBB | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-10-21 | 2023-06-08 | 50 | REL | APPR OPND | HB /A /37/HBAA-PIT-29106 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-INST | 2100089855 | New SLDBB for PIT-29106 | Remount transmitter and calibrate | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2023-10-21 | 2023-06-08 | 60 | REL | APPR OPND | HB /A /37/HBAA-PIT-29106 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-LAGG | 2100089855 | New SLDBB for PIT-29106 | Re-install lagging | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2023-10-21 | 2023-06-08 | 70 | REL | APPR OPND | HB /A /37/HBAA-PIT-29106 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-INST | 2100089855 | New SLDBB for PIT-29106 | De-isolate transmitter and heat tracing | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2023-10-21 | 2023-06-08 | 80 | REL | APPR OPND | HB /A /37/HBAA-PIT-29106 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | PRODTECH | 2100089855 | New SLDBB for PIT-29106 | Remove process isolation and inhibition | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2023-10-21 | 2023-06-08 | 90 | REL | APPR OPND | HB /A /37/HBAA-PIT-29106 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100094119 | HBD - Replace Pilots HBDB-X-4060 | Isolate and depressurize system/N2 PURGE | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2024-07-21 | 2024-07-30 | 2024-07-21 | 2024-06-30 | 2023-08-05 | 10 | REL | APPR OPND | HB /D /36/HBDB-X-4060 | LP FLARE TIP (CONT/PEAK) |  | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-RIGG | 2100094119 | HBD - Replace Pilots HBDB-X-4060 | Prepare for rig down old pilot burners | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-07-21 | 2024-07-30 | 2024-07-23 | 2024-06-30 | 2023-08-05 | 20 | REL | APPR OPND | HB /D /36/HBDB-X-4060 | LP FLARE TIP (CONT/PEAK) |  | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100094119 | HBD - Replace Pilots HBDB-X-4060 | Dismantle old pilot burners | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-07-21 | 2024-07-30 | 2024-07-26 | 2024-06-30 | 2023-08-05 | 30 | REL | APPR OPND | HB /D /36/HBDB-X-4060 | LP FLARE TIP (CONT/PEAK) |  | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-RIGG | 2100094119 | HBD - Replace Pilots HBDB-X-4060 | Rig down old pilot burners | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-07-21 | 2024-07-30 | 2024-07-26 | 2024-06-30 | 2023-08-05 | 40 | REL | APPR OPND | HB /D /36/HBDB-X-4060 | LP FLARE TIP (CONT/PEAK) |  | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-RIGG | 2100094119 | HBD - Replace Pilots HBDB-X-4060 | Rig up new pilot burners | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-07-21 | 2024-07-30 | 2024-07-27 | 2024-06-30 | 2023-08-05 | 50 | REL | APPR OPND | HB /D /36/HBDB-X-4060 | LP FLARE TIP (CONT/PEAK) |  | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100094119 | HBD - Replace Pilots HBDB-X-4060 | Install new pilot burners | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-07-21 | 2024-07-30 | 2024-07-29 | 2024-06-30 | 2023-08-05 | 60 | REL | APPR OPND | HB /D /36/HBDB-X-4060 | LP FLARE TIP (CONT/PEAK) |  | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-ELEC | 2100094119 | HBD - Replace Pilots HBDB-X-4060 | Dismantle Igniter Cable | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-07-21 | 2024-07-30 | 2024-07-29 | 2024-06-30 | 2023-08-05 | 70 | REL | APPR OPND | HB /D /36/HBDB-X-4060 | LP FLARE TIP (CONT/PEAK) |  | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-ELEC | 2100094119 | HBD - Replace Pilots HBDB-X-4060 | Install new New Igniter Cable | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-07-21 | 2024-07-30 | 2024-07-30 | 2024-06-30 | 2023-08-05 | 80 | REL | APPR OPND | HB /D /36/HBDB-X-4060 | LP FLARE TIP (CONT/PEAK) |  | A |  | MMS | DK50
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094578 | New glass for XE-1563 | Isolate Circuit for lamp | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2023-12-31 | 2023-08-18 | 20 | REL | APPR OPND | HB /D /64/HBDD-XE-1563 | NAV.AIDS SECONDARY LANTERN (10NM) |  | A |  | MEL | DK50 |  |  | 2024-05-28
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094578 | New glass for XE-1563 | Replace lens | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2023-12-31 | 2023-08-18 | 30 | REL | APPR OPND | HB /D /64/HBDD-XE-1563 | NAV.AIDS SECONDARY LANTERN (10NM) |  | A |  | MEL | DK50 |  |  | 2024-05-29
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094578 | New glass for XE-1563 | De-Isolate Circuit for lamp | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2023-12-31 | 2023-08-18 | 40 | REL | APPR OPND | HB /D /64/HBDD-XE-1563 | NAV.AIDS SECONDARY LANTERN (10NM) |  | A |  | MEL | DK50 |  |  | 2024-05-31
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094578 | New glass for XE-1563 | Function Test. | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2023-12-31 | 2023-08-18 | 50 | REL | APPR OPND | HB /D /64/HBDD-XE-1563 | NAV.AIDS SECONDARY LANTERN (10NM) |  | A |  | MEL | DK50 |  |  | 2024-06-01
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096139 | Replace batteries in emerg. lights HBC | Replace batteries in emerg. lights HBC | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W19-W20 | 2024-05-06 | 2024-05-13 | 2024-05-06 | 2024-01-31 | 2023-09-18 | 10 | REL | APPR OPND | HB /C /62/EMERGENCY-LIGHTS-LEVEL-1 | EMERGENCY LIGHTS LEVEL 1 |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100096139 | Replace batteries in emerg. lights HBC | Isolate Equipment. | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W19-W20 | 2024-05-06 | 2024-05-13 | 2024-05-06 | 2024-01-31 | 2023-09-18 | 20 | REL | APPR OPND | HB /C /62/EMERGENCY-LIGHTS-LEVEL-1 | EMERGENCY LIGHTS LEVEL 1 |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096139 | Replace batteries in emerg. lights HBC | Replace batteries | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 30 | 0 | W19-W20 | 2024-05-06 | 2024-05-13 | 2024-05-06 | 2024-01-31 | 2023-09-18 | 30 | REL | APPR OPND | HB /C /62/EMERGENCY-LIGHTS-LEVEL-1 | EMERGENCY LIGHTS LEVEL 1 |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100096139 | Replace batteries in emerg. lights HBC | De-isolate Equipment | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W19-W20 | 2024-05-06 | 2024-05-13 | 2024-05-12 | 2024-01-31 | 2023-09-18 | 40 | REL | APPR OPND | HB /C /62/EMERGENCY-LIGHTS-LEVEL-1 | EMERGENCY LIGHTS LEVEL 1 |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096139 | Replace batteries in emerg. lights HBC | Test & put back in service | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W19-W20 | 2024-05-06 | 2024-05-13 | 2024-05-13 | 2024-01-31 | 2023-09-18 | 50 | REL | APPR OPND | HB /C /62/EMERGENCY-LIGHTS-LEVEL-1 | EMERGENCY LIGHTS LEVEL 1 |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100100874 | Replace Simul drop cylinder LB1 | Replace Simul drop cylinder LB1 | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-24 | 2024-06-25 | 2024-06-24 | 2026-10-11 | 2024-04-24 | 10 | REL | APPR OPND | HB /C /02/HBCA-X-0701 | LIFEBOAT 1 - 45 PERS. |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100100874 | Replace Simul drop cylinder LB1 | Rigging in/out of simul drop cylinder | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-06-24 | 2024-06-25 | 2024-06-24 | 2026-10-11 | 2024-04-24 | 20 | REL | APPR OPND | HB /C /02/HBCA-X-0701 | LIFEBOAT 1 - 45 PERS. |  | A |  | MMS | DK50
2024-W27-28 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100105450 | Change Filter do to High DP |  | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-07-14 | 2024-03-01 | 10 | REL | APPR OPND | HB /D /30/HBDB-FIL-4172 | CHARCOAL FILTER |  | E |  | MMS | DK50 |  |  | 2024-05-25
2024-W27-28 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100107156 | HBC Heat detectors need to be replaced | Replace HC-0163405 | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-16 | 2024-04-18 | 2024-04-16 | 2024-08-09 | 2024-03-27 | 10 | REL | APPR OPND | HB /C /03/HBCB-HC-0163405 | HEAT DETECTOR |  | A |  | MIN | DK50 |  |  | 2024-05-26
2024-W27-28 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100107156 | HBC Heat detectors need to be replaced | Replace HC-0163101 | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-16 | 2024-04-18 | 2024-04-17 | 2024-08-09 | 2024-03-27 | 20 | REL | APPR OPND | HB /C /03/HBCB-HC-0163405 | HEAT DETECTOR |  | A |  | MIN | DK50 |  |  | 2024-05-28
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | PRODTECH | 2100108181 | New DB for PIT-394411 | Inhibit Pressure transmitter | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2027-02-09 | 2024-08-23 | 10 | REL | APPR OPND | HB /A /75/HBAA-PIT-394411 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100108181 | New DB for PIT-394411 | Isolate pressure transmitter | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2027-02-09 | 2024-08-23 | 20 | REL | APPR OPND | HB /A /75/HBAA-PIT-394411 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100108181 | New DB for PIT-394411 | Install new DBB valve | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2.5 | 0 |  | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2027-02-09 | 2024-08-23 | 30 | REL | APPR OPND | HB /A /75/HBAA-PIT-394411 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100108181 | New DB for PIT-394411 | De-isolate transmitter / Test with CCR | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2027-02-09 | 2024-08-23 | 40 | REL | APPR OPND | HB /A /75/HBAA-PIT-394411 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | PRODTECH | 2100108181 | New DB for PIT-394411 | Remome inhibit / reset the alarm | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2027-02-09 | 2024-08-23 | 50 | REL | APPR OPND | HB /A /75/HBAA-PIT-394411 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100108488 | Findings after synergi 672065 | Inhibit transmitter/Remove Inhibit | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-08-28 | 2024-04-15 | 10 | REL | APPR OPND | HB /A /28/HBAA-LIT-50010 | LEVEL INDICATOR TRANSMITTER (ESD) |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100108488 | Findings after synergi 672065 | Install new drain and vent valves | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 3.5 | 0 |  | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-08-28 | 2024-04-15 | 20 | REL | APPR OPND | HB /A /28/HBAA-LIT-50010 | LEVEL INDICATOR TRANSMITTER (ESD) |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100108490 | Findings after synergi 672065 | Inhibit transmitter/Remove Inhibit | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-08-28 | 2024-04-15 | 10 | REL | APPR OPND | HB /C /28/HBCM-LIT-50001 | OPEN DRAIN TANK HBCM-T-5033 LEVEL (ESD) |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100108490 | Findings after synergi 672065 | Install new drain and vent valves | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 3.5 | 0 |  | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-08-28 | 2024-04-15 | 20 | REL | APPR OPND | HB /C /28/HBCM-LIT-50001 | OPEN DRAIN TANK HBCM-T-5033 LEVEL (ESD) |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | VEN-CRAN | VEN-CRAN | 2100108537 | HBC/78 Upgrade of suction lines pumps | Function test of crane | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-06-15 | 2024-06-17 | 2024-06-15 | 2024-08-28 | 2024-04-15 | 10 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | VEN-CRAN | MTN-ROUS | 2100108537 | HBC/78 Upgrade of suction lines pumps | Ass. test | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-06-15 | 2024-06-17 | 2024-06-15 | 2024-08-28 | 2024-04-15 | 20 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | VEN-CRAN | PRODTECH | 2100108537 | HBC/78 Upgrade of suction lines pumps | Isolation/deisolation of crane | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-15 | 2024-06-17 | 2024-06-15 | 2024-08-28 | 2024-04-15 | 30 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | VEN-CRAN | VEN-CRAN | 2100108537 | HBC/78 Upgrade of suction lines pumps | Drin oil from tank | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-15 | 2024-06-17 | 2024-06-15 | 2024-08-28 | 2024-04-15 | 40 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | VEN-CRAN | VEN-CRAN | 2100108537 | HBC/78 Upgrade of suction lines pumps | Install new fittings and hoses | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-15 | 2024-06-17 | 2024-06-15 | 2024-08-28 | 2024-04-15 | 50 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | VEN-CRAN | VEN-CRAN | 2100108537 | HBC/78 Upgrade of suction lines pumps | Fill up hydraulic oil | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-15 | 2024-06-17 | 2024-06-16 | 2024-08-28 | 2024-04-15 | 60 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | VEN-CRAN | VEN-CRAN | 2100108537 | HBC/78 Upgrade of suction lines pumps | Vent air out from pumps new lines | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-15 | 2024-06-17 | 2024-06-16 | 2024-08-28 | 2024-04-15 | 70 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | VEN-CRAN | VEN-CRAN | 2100108537 | HBC/78 Upgrade of suction lines pumps | Function test of crane | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-06-15 | 2024-06-17 | 2024-06-16 | 2024-08-28 | 2024-04-15 | 80 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | VEN-CRAN | VEN-CRAN | 2100108537 | HBC/78 Upgrade of suction lines pumps | Ass. test | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-06-15 | 2024-06-17 | 2024-06-16 | 2024-08-28 | 2024-04-15 | 90 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2024-W25-26 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100108663 | Diesel filter differential PI ex leak | Replace Pressure Gauge | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-08-02 | 2024-03-20 | 10 | REL | APPR OPND | HB /D /05/HBDE-G-1710 | EMERGENCY DIESEL GENERATOR |  | A |  | MIN | DK50 |  |  | 2024-05-22
0 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100109332 | HDAG-PA-14551B cable damaged | Replace loudsåeaker | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-09-02 | 2024-04-20 | 10 | REL | APPR OPND | HD /B /08/HDBE-PA-14002 | PA "B" MDF |  | A |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100109332 | HDAG-PA-14551B cable damaged | Fix cabling | REL MACM PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-09-02 | 2024-04-20 | 20 | REL | APPR OPND | HD /B /08/HDBE-PA-14002 | PA "B" MDF |  | A |  | MIN | DK60
2024-W21-22 | 2 | NOSD | WDF | MTN-INST | MTN-INST | 2100110128 | Pilot valve not working for RWU | Isolate Interface valve | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-19 | 2024-04-04 | 10 | REL | APPR OPND | HB /A /07/HBAA-A-3111 | WELLHEAD CONTROL PANEL |  | A |  | MIN | DK50 |  |  | 2024-05-20
2024-W21-22 | 2 | NOSD | WDF | MTN-INST | MTN-INST | 2100110128 | Pilot valve not working for RWU | Replace Interface valve | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-19 | 2024-04-04 | 20 | REL | APPR OPND | HB /A /07/HBAA-A-3111 | WELLHEAD CONTROL PANEL |  | A |  | MIN | DK50 |  |  | 2024-05-21
2024-W21-22 | 2 | NOSD | WDF | MTN-INST | MTN-INST | 2100110128 | Pilot valve not working for RWU | De-isolate / Test with CCR | REL MANC PRC SETC | APPR WMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-19 | 2024-04-04 | 30 | REL | APPR OPND | HB /A /07/HBAA-A-3111 | WELLHEAD CONTROL PANEL |  | A |  | MIN | DK50 |  |  | 2024-05-23
2024-W21-22 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079228 | PSV on hot pot water internaly leaking | Install new type of PSV | REL PCNF MANC PRC SETC | APPR WMAT AWDO AWSC RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2023-06-02 | 2023-01-18 | 50 | PCNF REL | APPR OPND | HB /D /72/HBDB-PSV-115001 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50 |  |  | 2024-05-23
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-INST | 2100025863 | LOTI:Change SDBB, new instr pipe and re- | SDBB and inst pipe shall be renewed. | REL PCNF CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2019-05-20 | 2019-04-30 | 10 | PCNF REL | APPR OPND | HB /A /10/HBAA-PIT-38507 | PRESSURE INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100025863 | LOTI:Change SDBB, new instr pipe and re- | isolate for change SDBB - Prod | REL PCNF CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL ROUT | 3 | 0 | LOTI | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2019-05-20 | 2019-04-30 | 20 | PCNF REL | APPR OPND | HB /A /10/HBAA-PIT-38507 | PRESSURE INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-INST | 2100025863 | LOTI:Change SDBB, new instr pipe and re- | Change SDBB / PIT 38507 | REL PCNF CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL ROUT | 6 | 0 | LOTI | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2019-05-20 | 2019-04-30 | 30 | PCNF REL | APPR OPND | HB /A /10/HBAA-PIT-38507 | PRESSURE INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-INST | 2100025863 | LOTI:Change SDBB, new instr pipe and re- | Replace PIT 38506 | REL PCNF CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL ROUT | 6 | 0 | LOTI | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2019-05-20 | 2019-04-30 | 40 | PCNF REL | APPR OPND | HB /A /10/HBAA-PIT-38507 | PRESSURE INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-INST | 2100025863 | LOTI:Change SDBB, new instr pipe and re- | Replace PIT 38507 | REL PCNF CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL ROUT | 6 | 0 | LOTI | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2019-05-20 | 2019-04-30 | 50 | PCNF REL | APPR OPND | HB /A /10/HBAA-PIT-38507 | PRESSURE INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100025863 | LOTI:Change SDBB, new instr pipe and re- | Leak test | REL PCNF CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL ROUT | 2 | 0 | LOTI | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2019-05-20 | 2019-04-30 | 60 | PCNF REL | APPR OPND | HB /A /10/HBAA-PIT-38507 | PRESSURE INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100025863 | LOTI:Change SDBB, new instr pipe and re- | De-isolate - Prod | REL PCNF CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL ROUT | 3 | 0 | LOTI | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2019-05-20 | 2019-04-30 | 70 | PCNF REL | APPR OPND | HB /A /10/HBAA-PIT-38507 | PRESSURE INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-LAGG | 2100025863 | LOTI:Change SDBB, new instr pipe and re- | Re-insulate inst. pipping | REL PCNF CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL ROUT | 17.4 | 0 | LOTI | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2019-05-20 | 2019-04-30 | 71 | PCNF REL | APPR OPND | HB /A /10/HBAA-PIT-38507 | PRESSURE INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-PIPF | 2100024451 | ANOP HC leak in HBB04 flowline | Permit preparation - Weld | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 |  | 2024-03-28 | 2024-04-06 | 2024-03-28 | 2019-06-19 | 2019-03-21 | 20 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | DK0500014781 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-SCAF | 2100024451 | ANOP HC leak in HBB04 flowline | Permit preparation - Scaf | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 |  | 2024-03-28 | 2024-04-06 | 2024-03-28 | 2019-06-19 | 2019-03-21 | 30 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | DK0500014781 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-SCAF | 2100024451 | ANOP HC leak in HBB04 flowline | Prepare the work site, and place riggere | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 |  | 2024-03-28 | 2024-04-06 | 2024-03-30 | 2019-06-19 | 2019-03-21 | 40 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | DK0500014781 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-PIPF | 2100024451 | ANOP HC leak in HBB04 flowline | Control materials -Weld | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4.4 | 0 |  | 2024-03-28 | 2024-04-06 | 2024-03-28 | 2019-06-19 | 2019-03-21 | 50 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | DK0500014781 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-SCAF | 2100024451 | ANOP HC leak in HBB04 flowline | Build scaffold - Scaf | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 |  | 2024-03-28 | 2024-04-06 | 2024-03-29 | 2019-06-19 | 2019-03-21 | 51 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | DK0500014781 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | PRODTECH | 2100024451 | ANOP HC leak in HBB04 flowline | Isolate spool´s - Prod | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | POSS CAMP BK IN | 2024-03-28 | 2024-04-06 | 2024-04-01 | 2019-06-19 | 2019-03-21 | 60 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | DK0500014781 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-PIPF | 2100024451 | ANOP HC leak in HBB04 flowline | Change out gasket - Weld | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 |  | 2024-03-28 | 2024-04-06 | 2024-04-01 | 2019-06-19 | 2019-03-21 | 70 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | DK0500014781 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-SCAF | 2100024451 | ANOP HC leak in HBB04 flowline | Assst Weld whit changing gasket - Scaf | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 |  | 2024-03-28 | 2024-04-06 | 2024-04-01 | 2019-06-19 | 2019-03-21 | 80 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | DK0500014781 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | PRODTECH | 2100024451 | ANOP HC leak in HBB04 flowline | Leak test - Prod | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 6 | 0 | POSS CAMP BK IN | 2024-03-28 | 2024-04-06 | 2024-04-02 | 2019-06-19 | 2019-03-21 | 90 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | DK0500014781 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | PRODTECH | 2100024451 | ANOP HC leak in HBB04 flowline | De-isolate spools. - Prod | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | POSS CAMP BK IN | 2024-03-28 | 2024-04-06 | 2024-04-04 | 2019-06-19 | 2019-03-21 | 100 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | DK0500014781 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-SCAF | 2100024451 | ANOP HC leak in HBB04 flowline | Remove rigger gear Scaf | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 |  | 2024-03-28 | 2024-04-06 | 2024-04-04 | 2019-06-19 | 2019-03-21 | 110 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | DK0500014781 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-SCAF | 2100024451 | ANOP HC leak in HBB04 flowline | remove scaffold - Scaf | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 |  | 2024-03-28 | 2024-04-06 | 2024-04-05 | 2019-06-19 | 2019-03-21 | 120 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | DK0500014781 | C |  | MFM | DK50
2026-W13-14 | 4 | HBDSW | WDF | MTN-MECH | MTN-ROPE | 2100024452 | ANOPR HBD V-5365 DS-2 flange leakage | Check Permit & Line Walk(Scaff) | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 3.4 | 0 | SD Period TBC | 2025-01-01 | 2025-01-22 | 2025-01-01 | 2020-10-30 | 2018-11-10 | 1 | REL | APPR OPND | HB /D /76/HBD-20-WS-053-8246-AM-U | 20 SEA WATER SERVICE LINE | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBDSW | WDF | MTN-MECH | MTN-ROPE | 2100024452 | ANOPR HBD V-5365 DS-2 flange leakage | Check Permit & Line Walk (Weld) | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 3.4 | 0 | SD Period TBC | 2025-01-01 | 2025-01-22 | 2025-01-01 | 2020-10-30 | 2018-11-10 | 2 | REL | APPR OPND | HB /D /76/HBD-20-WS-053-8246-AM-U | 20 SEA WATER SERVICE LINE | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBDSW | WDF | MTN-MECH | MTN-ROPE | 2100024452 | ANOPR HBD V-5365 DS-2 flange leakage | L3 Build scaffolding and hang up waist | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 117.9 | 0 | SD Period TBC/Sbye BT Req | 2025-01-01 | 2025-01-22 | 2025-01-01 | 2020-10-30 | 2018-11-10 | 5 | REL | APPR OPND | HB /D /76/HBD-20-WS-053-8246-AM-U | 20 SEA WATER SERVICE LINE | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBDSW | WDF | MTN-MECH | PRODTECH | 2100024452 | ANOPR HBD V-5365 DS-2 flange leakage | L3 Safing of HBD-V-5365 | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | SD Period TBC | 2025-01-01 | 2025-01-22 | 2025-01-06 | 2020-10-30 | 2018-11-10 | 10 | REL | APPR OPND | HB /D /76/HBD-20-WS-053-8246-AM-U | 20 SEA WATER SERVICE LINE | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBDSW | WDF | MTN-MECH | MTN-ROPE | 2100024452 | ANOPR HBD V-5365 DS-2 flange leakage | L3 Replace Gasket HBD- 20" WS-538246-AM | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 26.1 | 0 | SD Period TBC | 2025-01-01 | 2025-01-22 | 2025-01-06 | 2020-10-30 | 2018-11-10 | 30 | REL | APPR OPND | HB /D /76/HBD-20-WS-053-8246-AM-U | 20 SEA WATER SERVICE LINE | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBDSW | WDF | MTN-MECH | MTN-ROPE | 2100024452 | ANOPR HBD V-5365 DS-2 flange leakage | L3 Desafing of of HBD-V-5365 | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | SD Period TBC | 2025-01-01 | 2025-01-22 | 2025-01-07 | 2020-10-30 | 2018-11-10 | 31 | REL | APPR OPND | HB /D /76/HBD-20-WS-053-8246-AM-U | 20 SEA WATER SERVICE LINE | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBDSW | WDF | MTN-MECH | PRODTECH | 2100024452 | ANOPR HBD V-5365 DS-2 flange leakage | L3 Remove Scaffolding and Clean up | REL MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 175 | 0 | SD Period TBC/Sbye BT Req | 2025-01-01 | 2025-01-22 | 2025-01-08 | 2020-10-30 | 2018-11-10 | 40 | REL | APPR OPND | HB /D /76/HBD-20-WS-053-8246-AM-U | 20 SEA WATER SERVICE LINE | 99000087 | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100096136 | HBA/78 Damage Nylon bushings Luffing cyl | Isolate/Deisolate crane | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-04-21 | 2024-04-27 | 2024-04-21 | 2024-02-03 | 2023-09-21 | 10 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100096136 | HBA/78 Damage Nylon bushings Luffing cyl | Dismantle bearing on cylinders | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 10 | 0 |  | 2024-04-21 | 2024-04-27 | 2024-04-21 | 2024-02-03 | 2023-09-21 | 20 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100096136 | HBA/78 Damage Nylon bushings Luffing cyl | Ass. dismantle bearing | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2024-04-21 | 2024-04-27 | 2024-04-21 | 2024-02-03 | 2023-09-21 | 30 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100096136 | HBA/78 Damage Nylon bushings Luffing cyl | Move cylinder back | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-21 | 2024-04-27 | 2024-04-22 | 2024-02-03 | 2023-09-21 | 40 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100096136 | HBA/78 Damage Nylon bushings Luffing cyl | Ass. moving cylinder back | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-21 | 2024-04-27 | 2024-04-21 | 2024-02-03 | 2023-09-21 | 50 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-PAIN | 2100096136 | HBA/78 Damage Nylon bushings Luffing cyl | Clean off corrosion and paint cylinder | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 20 | 0 |  | 2024-04-21 | 2024-04-27 | 2024-04-22 | 2024-02-03 | 2023-09-21 | 60 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100096136 | HBA/78 Damage Nylon bushings Luffing cyl | Move cylinder to bearing postion | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-21 | 2024-04-27 | 2024-04-24 | 2024-02-03 | 2023-09-21 | 70 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100096136 | HBA/78 Damage Nylon bushings Luffing cyl | Ass. moving cylinder back | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-21 | 2024-04-27 | 2024-04-21 | 2024-02-03 | 2023-09-21 | 80 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100096136 | HBA/78 Damage Nylon bushings Luffing cyl | Install new bearings | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 10 | 0 |  | 2024-04-21 | 2024-04-27 | 2024-04-25 | 2024-02-03 | 2023-09-21 | 90 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100096136 | HBA/78 Damage Nylon bushings Luffing cyl | Ass. Install new bearings | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2024-04-21 | 2024-04-27 | 2024-04-25 | 2024-02-03 | 2023-09-21 | 100 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100096136 | HBA/78 Damage Nylon bushings Luffing cyl | Proof load test | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-04-21 | 2024-04-27 | 2024-04-26 | 2024-02-03 | 2023-09-21 | 110 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100096136 | HBA/78 Damage Nylon bushings Luffing cyl | Ass. proof load test | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-21 | 2024-04-27 | 2024-04-21 | 2024-02-03 | 2023-09-21 | 120 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W23-24 | 2 |  | WDF | MTN-ELEC | MTN-ELEC | 2100110138 | Overheated connection pole on battery. | Overheated connection pole on battery. | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-05-16 | 2024-04-01 | 10 | REL | APPR OPND | HB /D /64/HBDD-AE-1551 | BATTERY PACK |  | A |  | MEL | DK50 |  | PROK
2024-W23-24 | 2 |  | WDF | MTN-ELEC | MTN-ELEC | 2100110138 | Overheated connection pole on battery. | Site Visit - TBT. | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-05-16 | 2024-04-01 | 20 | REL | APPR OPND | HB /D /64/HBDD-AE-1551 | BATTERY PACK |  | A |  | MEL | DK50 |  | PROK
2024-W23-24 | 2 |  | WDF | MTN-ELEC | MTN-ELEC | 2100110138 | Overheated connection pole on battery. | Isolate accordingly. | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-05-16 | 2024-04-01 | 30 | REL | APPR OPND | HB /D /64/HBDD-AE-1551 | BATTERY PACK |  | A |  | MEL | DK50 |  | PROK
2024-W23-24 | 2 |  | WDF | MTN-ELEC | MTN-ELEC | 2100110138 | Overheated connection pole on battery. | Replace and install Faulty Battery Cell | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2024-05-16 | 2024-04-01 | 40 | REL | APPR OPND | HB /D /64/HBDD-AE-1551 | BATTERY PACK |  | A |  | MEL | DK50 |  | PROK
2024-W23-24 | 2 |  | WDF | MTN-ELEC | MTN-ELEC | 2100110138 | Overheated connection pole on battery. | De-isolate for test and Check up. | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-13 | 2024-05-14 | 2024-05-14 | 2024-05-16 | 2024-04-01 | 50 | REL | APPR OPND | HB /D /64/HBDD-AE-1551 | BATTERY PACK |  | A |  | MEL | DK50 |  | PROK
2024-W23-24 | 2 |  | WDF | MTN-ELEC | MTN-ELEC | 2100110138 | Overheated connection pole on battery. | Check up clean up - documentation | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-13 | 2024-05-14 | 2024-05-14 | 2024-05-16 | 2024-04-01 | 60 | REL | APPR OPND | HB /D /64/HBDD-AE-1551 | BATTERY PACK |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284414 | PSV Exchange - HBDC-PSV-596103 | Isolation of PSV | REL CSER MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /07/HBDC-PSV-596103 | PRESSURE SAFETY VALVE PUMP |  | C | DKHB-PSV085 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284414 | PSV Exchange - HBDC-PSV-596103 | Prod Assist (breaking containment) | REL CSER MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /07/HBDC-PSV-596103 | PRESSURE SAFETY VALVE PUMP |  | C | DKHB-PSV085 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284414 | PSV Exchange - HBDC-PSV-596103 | Install re-certified PSV | REL CSER MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /07/HBDC-PSV-596103 | PRESSURE SAFETY VALVE PUMP |  | C | DKHB-PSV085 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284414 | PSV Exchange - HBDC-PSV-596103 | De-isolation and leak test | REL CSER MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /07/HBDC-PSV-596103 | PRESSURE SAFETY VALVE PUMP |  | C | DKHB-PSV085 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284414 | PSV Exchange - HBDC-PSV-596103 | Documentation & CNF WO | REL CSER MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /07/HBDC-PSV-596103 | PRESSURE SAFETY VALVE PUMP |  | C | DKHB-PSV085 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284414 | PSV Exchange - HBDC-PSV-596103 | Check PSV flanges & alignment | REL CSER MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /07/HBDC-PSV-596103 | PRESSURE SAFETY VALVE PUMP |  | C | DKHB-PSV085 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284437 | PSV Exchange - HBDC-PSV-395101A | Isolation of PSV | REL CSER MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /75/HBDC-PSV-395101A | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV187 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284437 | PSV Exchange - HBDC-PSV-395101A | Prod Assist (breaking containment) | REL CSER MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /75/HBDC-PSV-395101A | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV187 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284437 | PSV Exchange - HBDC-PSV-395101A | Install re-certified PSV | REL CSER MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /75/HBDC-PSV-395101A | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV187 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284437 | PSV Exchange - HBDC-PSV-395101A | De-isolation and leak test | REL CSER MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /75/HBDC-PSV-395101A | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV187 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284437 | PSV Exchange - HBDC-PSV-395101A | Documentation & CNF WO | REL CSER MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /75/HBDC-PSV-395101A | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV187 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284437 | PSV Exchange - HBDC-PSV-395101A | Check PSV flanges & alignment | REL CSER MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /75/HBDC-PSV-395101A | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV187 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284440 | PSV Exchange - HBDC-PSV-396601 | Isolation of PSV | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /75/HBDC-PSV-396601 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV200 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284440 | PSV Exchange - HBDC-PSV-396601 | Prod Assist (breaking containment) | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /75/HBDC-PSV-396601 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV200 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284440 | PSV Exchange - HBDC-PSV-396601 | Install re-certified PSV | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /75/HBDC-PSV-396601 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV200 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284440 | PSV Exchange - HBDC-PSV-396601 | De-isolation and leak test | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /75/HBDC-PSV-396601 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV200 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284440 | PSV Exchange - HBDC-PSV-396601 | Documentation & CNF WO | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /75/HBDC-PSV-396601 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV200 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284440 | PSV Exchange - HBDC-PSV-396601 | Check PSV flanges & alignment | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /75/HBDC-PSV-396601 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV200 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284441 | PSV Exchange - HBDC-PSV-396701A | Isolation of PSV | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /75/HBDC-PSV-396701A | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV201 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284441 | PSV Exchange - HBDC-PSV-396701A | Prod Assist (breaking containment) | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /75/HBDC-PSV-396701A | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV201 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284441 | PSV Exchange - HBDC-PSV-396701A | Install re-certified PSV | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /75/HBDC-PSV-396701A | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV201 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284441 | PSV Exchange - HBDC-PSV-396701A | De-isolation and leak test | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /75/HBDC-PSV-396701A | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV201 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284441 | PSV Exchange - HBDC-PSV-396701A | Documentation & CNF WO | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /75/HBDC-PSV-396701A | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV201 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284441 | PSV Exchange - HBDC-PSV-396701A | Check PSV flanges & alignment | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /75/HBDC-PSV-396701A | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV201 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284443 | PSV Exchange - HBDC-PSV-396801A | Isolation of PSV | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /75/HBDC-PSV-396801A | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV203 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284443 | PSV Exchange - HBDC-PSV-396801A | Prod Assist (breaking containment) | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /75/HBDC-PSV-396801A | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV203 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284443 | PSV Exchange - HBDC-PSV-396801A | Install re-certified PSV | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /75/HBDC-PSV-396801A | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV203 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284443 | PSV Exchange - HBDC-PSV-396801A | De-isolation and leak test | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /75/HBDC-PSV-396801A | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV203 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284443 | PSV Exchange - HBDC-PSV-396801A | Documentation & CNF WO | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /75/HBDC-PSV-396801A | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV203 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284443 | PSV Exchange - HBDC-PSV-396801A | Check PSV flanges & alignment | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /75/HBDC-PSV-396801A | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV203 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284444 | PSV Exchange - HBDC-PSV-396801B | Isolation of PSV | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /75/HBDC-PSV-396801B | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV204 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284444 | PSV Exchange - HBDC-PSV-396801B | Prod Assist (breaking containment) | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /75/HBDC-PSV-396801B | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV204 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284444 | PSV Exchange - HBDC-PSV-396801B | Install re-certified PSV | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /75/HBDC-PSV-396801B | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV204 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284444 | PSV Exchange - HBDC-PSV-396801B | De-isolation and leak test | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /75/HBDC-PSV-396801B | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV204 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284444 | PSV Exchange - HBDC-PSV-396801B | Documentation & CNF WO | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /75/HBDC-PSV-396801B | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV204 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284444 | PSV Exchange - HBDC-PSV-396801B | Check PSV flanges & alignment | REL CSER MANC PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /75/HBDC-PSV-396801B | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV204 | MMS | DK50
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400314639 | 1Y PED. CRANE CHECK VENDOR-HBBB-X-6120 | ISOLATION BY PRODUCTION | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-22 | 2024-05-23 | 10 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | C | DKHB-0657 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400314639 | 1Y PED. CRANE CHECK VENDOR-HBBB-X-6120 | PED. CRANE INSP. VENDOR-HBBB-X-6120 | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 92 | 0 |  | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-22 | 2024-05-23 | 20 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | C | DKHB-0657 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400314639 | 1Y PED. CRANE CHECK VENDOR-HBBB-X-6120 | PED. CRANE INSP. VENDOR-HBBB-X-6120 | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-06-20 | 2024-07-01 | 2024-06-25 | 2024-06-22 | 2024-05-23 | 30 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | C | DKHB-0657 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400314639 | 1Y PED. CRANE CHECK VENDOR-HBBB-X-6120 | DE-ISOLATION BY PRODUCTION | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-20 | 2024-07-01 | 2024-06-26 | 2024-06-22 | 2024-05-23 | 40 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | C | DKHB-0657 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400314639 | 1Y PED. CRANE CHECK VENDOR-HBBB-X-6120 | Check of slip ring & electric checks | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-06-20 | 2024-07-01 | 2024-06-27 | 2024-06-22 | 2024-05-23 | 50 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | C | DKHB-0657 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400314639 | 1Y PED. CRANE CHECK VENDOR-HBBB-X-6120 | General assistance | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-06-20 | 2024-07-01 | 2024-06-29 | 2024-06-22 | 2024-05-23 | 60 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | C | DKHB-0657 | MMS | DK50 | MS0154 | PROK
0 | B | NOSD | WPM | MTN-MECH | PRODTECH | 2400321326 | 1Y CRANE, HDBR-A-6102 (VENDOR) | ISOLATION BY PRODUCTION | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-07-18 | 2024-07-29 | 2024-07-18 | 2024-07-27 | 2024-06-27 | 10 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | C | DKHD-0702 | MMS | DK60 | MS0153 | PROK
0 | B | NOSD | WPM | MTN-MECH | MTN-CRAN | 2400321326 | 1Y CRANE, HDBR-A-6102 (VENDOR) | CRANE, MAINTENANCE, HDBR-A-6102 | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 92 | 0 |  | 2024-07-18 | 2024-07-29 | 2024-07-18 | 2024-07-27 | 2024-06-27 | 20 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | C | DKHD-0702 | MMS | DK60 | MS0153 | PROK
0 | B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400321326 | 1Y CRANE, HDBR-A-6102 (VENDOR) | Assistance for vendor | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-07-18 | 2024-07-29 | 2024-07-23 | 2024-07-27 | 2024-06-27 | 30 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | C | DKHD-0702 | MMS | DK60 | MS0153 | PROK
0 | B | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400321326 | 1Y CRANE, HDBR-A-6102 (VENDOR) | CRANE, POWER PACK, HDBR-AM-6102 | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-07-18 | 2024-07-29 | 2024-07-25 | 2024-07-27 | 2024-06-27 | 40 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | C | DKHD-0702 | MMS | DK60 | MS0153 | PROK
0 | B | NOSD | WPM | MTN-MECH | PRODTECH | 2400321326 | 1Y CRANE, HDBR-A-6102 (VENDOR) | DE-ISOLATION BY PRODUCTION | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-07-18 | 2024-07-29 | 2024-07-28 | 2024-07-27 | 2024-06-27 | 50 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | C | DKHD-0702 | MMS | DK60 | MS0153 | PROK
0 | B | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400321326 | 1Y CRANE, HDBR-A-6102 (VENDOR) | Assist with electrical checks | REL MACM PRC SETC | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-07-18 | 2024-07-29 | 2024-07-28 | 2024-07-27 | 2024-06-27 | 60 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | C | DKHD-0702 | MMS | DK60 | MS0153 | PROK
2024-W23-24 | 3 | NE | WDF | MTN-TURB | MTN-TURB | 2100107678 | IP/HP Change out of TDP-799 & Gauges | Replace Magnehelic press indicators | REL MANC PRC SETC | APPR WMAT | 4 | 0 |  | 2024-06-01 | 2024-06-02 | 2024-06-01 | 2024-08-14 | 2024-04-01 | 10 | REL | APPR OPND | HB /D /31/HBDC-PDIT-435415 | TPD 799, DIFFERENTIAL PRESSURE TRANSM. |  | A |  | MMR | DK50 |  |  | 2024-05-22
2024-W23-24 | 3 | NE | WDF | MTN-TURB | MTN-TURB | 2100107678 | IP/HP Change out of TDP-799 & Gauges | Replace DP transmitter | REL MANC PRC SETC | APPR WMAT | 4 | 0 |  | 2024-06-01 | 2024-06-02 | 2024-06-01 | 2024-08-14 | 2024-04-01 | 20 | REL | APPR OPND | HB /D /31/HBDC-PDIT-435415 | TPD 799, DIFFERENTIAL PRESSURE TRANSM. |  | A |  | MMR | DK50 |  |  | 2024-05-24
2024-W21-22 | 3 | NE | WDF | MTN-TURB | MTN-TURB | 2100107679 | A-1660 Change out of TDP-799 and Gauges | Replace Magnehelic press indicators | REL MANC PRC SETC | APPR WMAT | 4 | 0 |  | 2024-06-01 | 2024-06-03 | 2024-06-01 | 2024-08-13 | 2024-03-31 | 10 | REL | APPR OPND | HB /D /60/HBDC-PDT-166325 | TPD799, TURBINE AIR INTAKE PDT |  | A |  | MMR | DK50 |  |  | 2024-05-20
2024-W21-22 | 3 | NE | WDF | MTN-TURB | MTN-TURB | 2100107679 | A-1660 Change out of TDP-799 and Gauges | Replace DP transmitter | REL MANC PRC SETC | APPR WMAT | 4 | 0 |  | 2024-06-01 | 2024-06-03 | 2024-06-02 | 2024-08-13 | 2024-03-31 | 20 | REL | APPR OPND | HB /D /60/HBDC-PDT-166325 | TPD799, TURBINE AIR INTAKE PDT |  | A |  | MMR | DK50 |  |  | 2024-05-22
2024-W23-24 | 3 | NE | WDF | MTN-TURB | MTN-TURB | 2100107681 | A-1650 Change out of TDP-799 and Gauges | Replace Magnehelic press indicators | REL MANC PRC SETC | APPR WMAT | 4 | 0 |  | 2024-06-01 | 2024-06-03 | 2024-06-01 | 2024-08-13 | 2024-03-31 | 10 | REL | APPR OPND | HB /D /60/HBDC-PDT-165325 | TPD799, TURBINE AIR INTAKE PDT |  | A |  | MMR | DK50 |  |  | 2024-05-23
2024-W23-24 | 3 | NE | WDF | MTN-TURB | MTN-TURB | 2100107681 | A-1650 Change out of TDP-799 and Gauges | Replace DP transmitter | REL MANC PRC SETC | APPR WMAT | 4 | 0 |  | 2024-06-01 | 2024-06-03 | 2024-06-02 | 2024-08-13 | 2024-03-31 | 20 | REL | APPR OPND | HB /D /60/HBDC-PDT-165325 | TPD799, TURBINE AIR INTAKE PDT |  | A |  | MMR | DK50 |  |  | 2024-05-24
2026-W13-14 | 2 |  | WSO | WELLSUPV | WELLSUPV | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | HBA04,WL,MFC,Leak detection,19833 | REL PCNF MANC PRC SETC | APPR WMAT | 0 | 0 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 10 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | WELLSUPV | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | Bennet Well Explorer | REL PCNF MANC PRC SETC | APPR WMAT | 0 | 0 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 20 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | WELLSUPV | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | Oilenco tools | REL PCNF MANC PRC SETC | APPR WMAT | 0 | 0 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 30 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | WELLSUPV | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | Ocean Team chemicals | REL PCNF MANC PRC SETC | APPR WMAT | 0 | 0 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 40 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | WELLSUPV | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | Beams | REL PCNF MANC PRC SETC | APPR WMAT | 0 | 0 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 50 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | WELLSUPV | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | Glycol 40/60 | REL PCNF MANC PRC SETC | APPR WMAT | 0 | 0 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 60 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | PRODTECH | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | Safing well/well handover (production) | REL PCNF MANC PRC SETC | APPR WMAT | 12 | 0 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 70 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | MTN-ROUS | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | Crane assist during WL R/U and RD | REL PCNF MANC PRC SETC | APPR WMAT | 48 | 0 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 80 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | MTN-SCAF | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | Scaffolder assistance for RU and RD | REL PCNF MANC PRC SETC | APPR WMAT | 48 | 72 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 90 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | MTN-ELEC | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | Electrician assistance for RU and RD | REL PCNF MANC PRC SETC | APPR WMAT | 12 | 4 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 100 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | MTN-TELE | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | Tele assist during WL RRU and RD | REL PCNF MANC PRC SETC | APPR WMAT | 24 | 12 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 110 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | VEN-CRAN | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | Crane support assitance for days | REL PCNF MANC PRC SETC | APPR WMAT | 168 | 0 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 120 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | WELLSUPV | 2900001394 | HBA04,WL,MFC,Leak detection,19833 | Interwell | REL PCNF MANC PRC SETC | APPR WMAT | 0 | 0 |  | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-04-20 | 2024-03-06 | 130 | REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100079464 | HBB/78: Replace hydr. hoses on luffing c | Isolation/deisolation of crane | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2023-06-12 | 2023-01-28 | 100 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100079464 | HBB/78: Replace hydr. hoses on luffing c | Replace hose 537, 539, 543 | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2023-06-12 | 2023-01-28 | 110 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100079464 | HBB/78: Replace hydr. hoses on luffing c | Leak and function test | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2023-06-12 | 2023-01-28 | 120 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100022929 | HBD/78: Mount JB and replace cabel from | Build scaff around pedestal | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT SCH RDBL | 60 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2019-03-01 | 2018-10-02 | 50 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150-06 | ELECTRICAL SYSTEM |  | C |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100022929 | HBD/78: Mount JB and replace cabel from | QC papers on new junctionbox | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT SCH RDBL | 3 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2019-03-01 | 2018-10-02 | 80 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150-06 | ELECTRICAL SYSTEM |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100030733 | Replacement of Lockout relay HBCA-N-1840 | Isolate switchboard | REL GMPS MANC PPRT PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W49-50 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2020-07-28 | 2020-04-29 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-1-1 | INCOMING GENR. FROM HBCM-G-1731 (52-GB) |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100030733 | Replacement of Lockout relay HBCA-N-1840 | Replace Lock out relay and test | REL GMPS MANC PPRT PRC SETC | APPR SMAT SCH RDBL | 3 | 0 | W49-50 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2020-07-28 | 2020-04-29 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-1-1 | INCOMING GENR. FROM HBCM-G-1731 (52-GB) |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100030733 | Replacement of Lockout relay HBCA-N-1840 | De-isolate | REL GMPS MANC PPRT PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W49-50 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2020-07-28 | 2020-04-29 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-1-1 | INCOMING GENR. FROM HBCM-G-1731 (52-GB) |  | C |  | MEL | DK50
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100038754 | Change motor drive on breaker | Isolate and pull breaker out | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2021-01-16 | 2020-10-18 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-07-01 | HDBE-N18110701, TIE BREAKER TO N-1810 |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100038754 | Change motor drive on breaker | Change motorcharger | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 9 | 0 | W45-46 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2021-01-16 | 2020-10-18 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-07-01 | HDBE-N18110701, TIE BREAKER TO N-1810 |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100038754 | Change motor drive on breaker | Re-install breaker | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2021-01-16 | 2020-10-18 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-07-01 | HDBE-N18110701, TIE BREAKER TO N-1810 |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100038754 | Change motor drive on breaker | Function test breaker | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2021-01-16 | 2020-10-18 | 40 | REL | APPR OPND | HD /B /61/HDBE-N-1811-07-01 | HDBE-N18110701, TIE BREAKER TO N-1810 |  | C |  | MEL | DK60
2026-W1-2 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100066283 | Seawater leak from shaft seal P-5367 | Isolate P-5367 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2022-08-02 | 2022-05-04 | 10 | REL | APPR OPND | HB /D /51/HBDB-P-5367 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100066283 | Seawater leak from shaft seal P-5367 | Mechanical scope of work. | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 24 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2022-08-02 | 2022-05-04 | 20 | REL | APPR OPND | HB /D /51/HBDB-P-5367 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100066283 | Seawater leak from shaft seal P-5367 | De-isolate and test run | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-10 | 2022-08-02 | 2022-05-04 | 30 | REL | APPR OPND | HB /D /51/HBDB-P-5367 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100067257 | Action A-2 from 3y check helifuel system | Isolate heli fuel system | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W41-42 | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2023-04-14 | 2022-08-17 | 20 | REL | APPR OPND | HB /C /81/HBCB-A-5601 | PUMP SKID WITH AVIATION FUEL PUMP |  | A |  | MMR | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100067257 | Action A-2 from 3y check helifuel system | Install visual flow indicator FM and FWS | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 4 | 0 | W41-42 | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2023-04-14 | 2022-08-17 | 30 | REL | APPR OPND | HB /C /81/HBCB-A-5601 | PUMP SKID WITH AVIATION FUEL PUMP |  | A |  | MMR | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100067257 | Action A-2 from 3y check helifuel system | Install visual flow indicator FM and FWS | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 4 | 0 | W41-42 | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2023-04-14 | 2022-08-17 | 40 | REL | APPR OPND | HB /C /81/HBCB-A-5601 | PUMP SKID WITH AVIATION FUEL PUMP |  | A |  | MMR | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100067257 | Action A-2 from 3y check helifuel system | De-isolate heli fuel system | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W41-42 | 2024-03-28 | 2024-03-29 | 2024-03-29 | 2023-04-14 | 2022-08-17 | 50 | REL | APPR OPND | HB /C /81/HBCB-A-5601 | PUMP SKID WITH AVIATION FUEL PUMP |  | A |  | MMR | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100068547 | Change of defect simocode in drawer | Isolate and prove dead | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-09-09 | 2022-06-11 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B10-CB | PH TANK MIXER MOTER HBDB-MM-4183 |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100068547 | Change of defect simocode in drawer | Change of defect simocode in drawer | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 3 | 0 | W45-46 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-09-09 | 2022-06-11 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B10-CB | PH TANK MIXER MOTER HBDB-MM-4183 |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100068547 | Change of defect simocode in drawer | De-Isolate above and test | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2022-09-09 | 2022-06-11 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B10-CB | PH TANK MIXER MOTER HBDB-MM-4183 |  | C |  | MEL | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100076502 | HBB-XCV-300904 intern leak. | Pre/post rigger equip | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 4 | 0 | W07-W08 | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2023-04-15 | 2022-12-01 | 10 | REL | APPR OPND | HB /B /10/HBBB-XCV-300904 | CONTROL VALVE WELL 09 |  | C |  | MMS | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100076502 | HBB-XCV-300904 intern leak. | Production isolation | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W07-W08 | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2023-04-15 | 2022-12-01 | 20 | REL | APPR OPND | HB /B /10/HBBB-XCV-300904 | CONTROL VALVE WELL 09 |  | C |  | MMS | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100076502 | HBB-XCV-300904 intern leak. | Rigger asistance Actuator off/on | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 4 | 0 | W07-W08 | 2024-08-25 | 2024-08-28 | 2024-08-26 | 2023-04-15 | 2022-12-01 | 30 | REL | APPR OPND | HB /B /10/HBBB-XCV-300904 | CONTROL VALVE WELL 09 |  | C |  | MMS | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100076502 | HBB-XCV-300904 intern leak. | Replace Actuator | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 8 | 0 | W07-W08 | 2024-08-25 | 2024-08-28 | 2024-08-27 | 2023-04-15 | 2022-12-01 | 40 | REL | APPR OPND | HB /B /10/HBBB-XCV-300904 | CONTROL VALVE WELL 09 |  | C |  | MMS | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100076502 | HBB-XCV-300904 intern leak. | Production deisolation w leak test | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 3 | 0 | W07-W08 | 2024-08-25 | 2024-08-28 | 2024-08-28 | 2023-04-15 | 2022-12-01 | 50 | REL | APPR OPND | HB /B /10/HBBB-XCV-300904 | CONTROL VALVE WELL 09 |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBA25-GL | WDF | MTN-MECH | MTN-SCAF | 2100076962 | Weep from SDBB valve at CHV-392513 | Mount Platform scaffold | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1.5 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2023-04-25 | 2022-12-11 | 10 | REL | APPR OPND | HB /A /75/HBAA-CHV-392513 | CHECK VALVE UPSTREAM CIP-392513 |  | A |  | MMS | DK50
2026-W1-2 | 3 | HBA25-GL | WDF | MTN-MECH | PRODTECH | 2100076962 | Weep from SDBB valve at CHV-392513 | Isolation Of Valve | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2023-04-25 | 2022-12-11 | 20 | REL | APPR OPND | HB /A /75/HBAA-CHV-392513 | CHECK VALVE UPSTREAM CIP-392513 |  | A |  | MMS | DK50
2026-W1-2 | 3 | HBA25-GL | WDF | MTN-MECH | MTN-MECH | 2100076962 | Weep from SDBB valve at CHV-392513 | Demount Valve | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 0.5 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2023-04-25 | 2022-12-11 | 30 | REL | APPR OPND | HB /A /75/HBAA-CHV-392513 | CHECK VALVE UPSTREAM CIP-392513 |  | A |  | MMS | DK50
2026-W1-2 | 3 | HBA25-GL | WDF | MTN-MECH | MTN-MECH | 2100076962 | Weep from SDBB valve at CHV-392513 | Install New Valve | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 0.5 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2023-04-25 | 2022-12-11 | 40 | REL | APPR OPND | HB /A /75/HBAA-CHV-392513 | CHECK VALVE UPSTREAM CIP-392513 |  | A |  | MMS | DK50
2026-W1-2 | 3 | HBA25-GL | WDF | MTN-MECH | PRODTECH | 2100076962 | Weep from SDBB valve at CHV-392513 | Deisolate & leak test | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2023-04-25 | 2022-12-11 | 50 | REL | APPR OPND | HB /A /75/HBAA-CHV-392513 | CHECK VALVE UPSTREAM CIP-392513 |  | A |  | MMS | DK50
2026-W1-2 | 3 | HBA25-GL | WDF | MTN-MECH | MTN-SCAF | 2100076962 | Weep from SDBB valve at CHV-392513 | Remove Platform Scaffold | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1.5 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2023-04-25 | 2022-12-11 | 60 | REL | APPR OPND | HB /A /75/HBAA-CHV-392513 | CHECK VALVE UPSTREAM CIP-392513 |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080947 | Checkvalve on P-5034 not work | Checkvalve on P-5034 not work | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2023-07-05 | 2023-02-20 | 10 | REL | APPR OPND | HB /C /28/HBCM-P-5034 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100080947 | Checkvalve on P-5034 not work | Isolate P-5034 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2023-07-05 | 2023-02-20 | 20 | REL | APPR OPND | HB /C /28/HBCM-P-5034 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080947 | Checkvalve on P-5034 not work | Isolate Mech P-5034 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 5 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2023-07-05 | 2023-02-20 | 30 | REL | APPR OPND | HB /C /28/HBCM-P-5034 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080947 | Checkvalve on P-5034 not work | Rigging out checkvalve | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2023-07-05 | 2023-02-20 | 40 | REL | APPR OPND | HB /C /28/HBCM-P-5034 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080947 | Checkvalve on P-5034 not work | Rigging new checkvalve | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2023-07-05 | 2023-02-20 | 50 | REL | APPR OPND | HB /C /28/HBCM-P-5034 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100080947 | Checkvalve on P-5034 not work | Deisolate P-5034 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2023-07-05 | 2023-02-20 | 60 | REL | APPR OPND | HB /C /28/HBCM-P-5034 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100089385 | Heat tracing and insulation missing | Install insulation PIT-30016 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 8 | 0 | W07-W08 | 2024-09-16 | 2024-09-17 | 2024-09-16 | 2023-10-12 | 2023-05-30 | 20 | PCNF REL | APPR OPND | HB /A /10/HBAA-PIT-30016 | WELL FLUID FLOWLINE WELL 1 |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100089385 | Heat tracing and insulation missing | Install insulation PIT-30076 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 8 | 0 | W07-W08 | 2024-09-16 | 2024-09-17 | 2024-09-16 | 2023-10-12 | 2023-05-30 | 30 | PCNF REL | APPR OPND | HB /A /10/HBAA-PIT-30016 | WELL FLUID FLOWLINE WELL 1 |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100089385 | Heat tracing and insulation missing | Install insulation PIT-30116 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 8 | 0 | W07-W08 | 2024-09-16 | 2024-09-17 | 2024-09-16 | 2023-10-12 | 2023-05-30 | 40 | PCNF REL | APPR OPND | HB /A /10/HBAA-PIT-30016 | WELL FLUID FLOWLINE WELL 1 |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100089385 | Heat tracing and insulation missing | Deisolate heat tracing | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W07-W08 | 2024-09-16 | 2024-09-17 | 2024-09-17 | 2023-10-12 | 2023-05-30 | 50 | PCNF REL | APPR OPND | HB /A /10/HBAA-PIT-30016 | WELL FLUID FLOWLINE WELL 1 |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096593 | PI Watermaker gauges to be replaced | Replace pressure gauge PI-105031 | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1.5 | 2 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-02-15 | 2023-10-03 | 10 | PCNF REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096593 | PI Watermaker gauges to be replaced | Replace pressure gauge PI-105032 | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1.5 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-02-15 | 2023-10-03 | 20 | PCNF REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096593 | PI Watermaker gauges to be replaced | Replace pressure gauge PI-105033 | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1.5 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-02-15 | 2023-10-03 | 30 | PCNF REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096593 | PI Watermaker gauges to be replaced | Replace pressure gauge PI-105034 | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1.5 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-02-15 | 2023-10-03 | 40 | PCNF REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096593 | PI Watermaker gauges to be replaced | Replace pressure gauge PI-105035 | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1.5 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-02-15 | 2023-10-03 | 50 | PCNF REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096593 | PI Watermaker gauges to be replaced | Replace pressure gauge PI-105036 | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1.5 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-02-15 | 2023-10-03 | 60 | PCNF REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096593 | PI Watermaker gauges to be replaced | Replace pressure gauge PI-105037 | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1.5 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-02-15 | 2023-10-03 | 70 | PCNF REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096593 | PI Watermaker gauges to be replaced | Replace pressure gauge PI-105038 | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1.5 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-02-15 | 2023-10-03 | 80 | PCNF REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096593 | PI Watermaker gauges to be replaced | Replace pressure gauge PI-105039 | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1.5 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-02-15 | 2023-10-03 | 90 | PCNF REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096687 | Defective Transmitter HBCM-FIT-03004 | Investigate HBCM-FIT-03004 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 3 | 6 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-02-19 | 2023-10-07 | 20 | PCNF REL | APPR OPND | HB /C /01/HBCM-FIT-03004 | FIREWATER PUMP TEST |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100096687 | Defective Transmitter HBCM-FIT-03004 | Remove scaffolding | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 8 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-02-19 | 2023-10-07 | 30 | PCNF REL | APPR OPND | HB /C /01/HBCM-FIT-03004 | FIREWATER PUMP TEST |  | A |  | MIN | DK50
2026-W1-2 | 4 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100096939 | Switch/Contactor for P-3653 VFD | Switch/Contactor for P-3653 VFD | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 0 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2026-08-08 | 2024-02-20 | 10 | REL | APPR OPND | HB /D /23/HBDB-PM-3653 | ELEC. PUMP MOTOR |  | A |  | MEL | DK50
2026-W1-2 | 4 | NE | WDF | MTN-ELEC | PRODTECH | 2100096939 | Switch/Contactor for P-3653 VFD | Isolate and prove dead | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2026-08-08 | 2024-02-20 | 20 | REL | APPR OPND | HB /D /23/HBDB-PM-3653 | ELEC. PUMP MOTOR |  | A |  | MEL | DK50
2026-W1-2 | 4 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100096939 | Switch/Contactor for P-3653 VFD | Disconnect switch. | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2026-08-08 | 2024-02-20 | 30 | REL | APPR OPND | HB /D /23/HBDB-PM-3653 | ELEC. PUMP MOTOR |  | A |  | MEL | DK50
2026-W1-2 | 4 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100096939 | Switch/Contactor for P-3653 VFD | Mount new 3 positon switch. | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2026-08-08 | 2024-02-20 | 40 | REL | APPR OPND | HB /D /23/HBDB-PM-3653 | ELEC. PUMP MOTOR |  | A |  | MEL | DK50
2026-W1-2 | 4 | NE | WDF | MTN-ELEC | PRODTECH | 2100096939 | Switch/Contactor for P-3653 VFD | De-Isolate and put back in service | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-26 | 2026-08-08 | 2024-02-20 | 50 | REL | APPR OPND | HB /D /23/HBDB-PM-3653 | ELEC. PUMP MOTOR |  | A |  | MEL | DK50
2026-W1-2 | 4 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100096939 | Switch/Contactor for P-3653 VFD | Test equipment. | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-26 | 2026-08-08 | 2024-02-20 | 60 | REL | APPR OPND | HB /D /23/HBDB-PM-3653 | ELEC. PUMP MOTOR |  | A |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100100018 | Broken sensor and pipe for HBA-TIT-30105 | Isolate HBA-TIT-30105 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-04-12 | 2023-11-29 | 10 | REL | APPR OPND | HB /A /10/HBAA-TIT-30105 | TEMPERATURE INDICATOR TRANSMITTER |  | A |  | MIN | DK50 |  | AW-INFO
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100100018 | Broken sensor and pipe for HBA-TIT-30105 | Replace sensor and gland | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-04-12 | 2023-11-29 | 20 | REL | APPR OPND | HB /A /10/HBAA-TIT-30105 | TEMPERATURE INDICATOR TRANSMITTER |  | A |  | MIN | DK50 |  | AW-INFO
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100100018 | Broken sensor and pipe for HBA-TIT-30105 | De-isolate and check | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-09 | 2024-04-12 | 2023-11-29 | 30 | REL | APPR OPND | HB /A /10/HBAA-TIT-30105 | TEMPERATURE INDICATOR TRANSMITTER |  | A |  | MIN | DK50 |  | AW-INFO
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100102440 | HBD/78: Replace corroded slew bearing bo | Isolate/Deisolate crane | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-03-31 | 2024-01-06 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150-04 | SLEWING SYSTEM |  | D |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100102440 | HBD/78: Replace corroded slew bearing bo | Replace all outer slew bolts | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 40 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-03-31 | 2024-01-06 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150-04 | SLEWING SYSTEM |  | D |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100102440 | HBD/78: Replace corroded slew bearing bo | Ass. replacement of bolts | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 8 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-03-31 | 2024-01-06 | 25 | REL | APPR OPND | HB /D /78/HBDE-A-6150-04 | SLEWING SYSTEM |  | D |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100102440 | HBD/78: Replace corroded slew bearing bo | Proof load test | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 6 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-03-31 | 2024-01-06 | 30 | REL | APPR OPND | HB /D /78/HBDE-A-6150-04 | SLEWING SYSTEM |  | D |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100102440 | HBD/78: Replace corroded slew bearing bo | Ass. load test | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 3 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-03-31 | 2024-01-06 | 40 | REL | APPR OPND | HB /D /78/HBDE-A-6150-04 | SLEWING SYSTEM |  | D |  | MMS | DK50
0 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100108910 | HDB Amp 4 & 5 Not working | Replace Amp 4 & 5 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 4.5 | 1 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-09-06 | 2024-04-24 | 10 | PCNF REL | APPR OPND | HD /B /08/HDBE-PA-14009 | AMPIID FRAME |  | A |  | MIN | DK60
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012735 | Replace HBDC-PSV-575502 - PSV 2023 | Isolation of PSV | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W47-48 | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2025-11-19 | 2023-06-03 | 10 | PCNF REL | APPR OPND | HB /D /70/HBDC-PSV-575502 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012735 | Replace HBDC-PSV-575502 - PSV 2023 | Prod Assist (breaking containment) | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W47-48 | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2025-11-19 | 2023-06-03 | 20 | PCNF REL | APPR OPND | HB /D /70/HBDC-PSV-575502 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012735 | Replace HBDC-PSV-575502 - PSV 2023 | Rigging assist (remove) | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT SCH RDBL | 24 | 0 | W47-48 | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2025-11-19 | 2023-06-03 | 30 | PCNF REL | APPR OPND | HB /D /70/HBDC-PSV-575502 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012735 | Replace HBDC-PSV-575502 - PSV 2023 | Remove PSV and install new PSV | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT SCH RDBL | 5 | 0 | W47-48 | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2025-11-19 | 2023-06-03 | 40 | PCNF REL | APPR OPND | HB /D /70/HBDC-PSV-575502 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012735 | Replace HBDC-PSV-575502 - PSV 2023 | Rigging Assist (Install) | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT SCH RDBL | 12 | 6 | W47-48 | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2025-11-19 | 2023-06-03 | 60 | PCNF REL | APPR OPND | HB /D /70/HBDC-PSV-575502 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012735 | Replace HBDC-PSV-575502 - PSV 2023 | Prod Assist (breaking containment) | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W47-48 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2025-11-19 | 2023-06-03 | 70 | PCNF REL | APPR OPND | HB /D /70/HBDC-PSV-575502 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012735 | Replace HBDC-PSV-575502 - PSV 2023 | De-isolation and leak test | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT SCH RDBL | 4 | 0 | W47-48 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2025-11-19 | 2023-06-03 | 90 | PCNF REL | APPR OPND | HB /D /70/HBDC-PSV-575502 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012740 | Replace HBBB-PSV-38017 - PSV 2023 | Isolation of PSV | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2025-11-19 | 2023-06-03 | 10 | REL | APPR OPND | HB /B /34/HBBB-PSV-38017 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012740 | Replace HBBB-PSV-38017 - PSV 2023 | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2025-11-19 | 2023-06-03 | 20 | REL | APPR OPND | HB /B /34/HBBB-PSV-38017 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012740 | Replace HBBB-PSV-38017 - PSV 2023 | Rigging assist (install) | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 24 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-16 | 2025-11-19 | 2023-06-03 | 30 | REL | APPR OPND | HB /B /34/HBBB-PSV-38017 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012740 | Replace HBBB-PSV-38017 - PSV 2023 | Remove PSV and install new PSV | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 5 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-21 | 2025-11-19 | 2023-06-03 | 40 | REL | APPR OPND | HB /B /34/HBBB-PSV-38017 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012740 | Replace HBBB-PSV-38017 - PSV 2023 | Rigging Assist (remove) | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 12 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-22 | 2025-11-19 | 2023-06-03 | 60 | REL | APPR OPND | HB /B /34/HBBB-PSV-38017 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012740 | Replace HBBB-PSV-38017 - PSV 2023 | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-24 | 2025-11-19 | 2023-06-03 | 70 | REL | APPR OPND | HB /B /34/HBBB-PSV-38017 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012740 | Replace HBBB-PSV-38017 - PSV 2023 | De-isolation and leak test | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 4 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-25 | 2025-11-19 | 2023-06-03 | 90 | REL | APPR OPND | HB /B /34/HBBB-PSV-38017 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012745 | Replace HBAA-PSV-394410 - PSV 2023 | Isolation of PSV | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2025-11-19 | 2023-06-03 | 10 | REL | APPR OPND | HB /A /75/HBAA-PSV-394410 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012745 | Replace HBAA-PSV-394410 - PSV 2023 | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2025-11-19 | 2023-06-03 | 20 | REL | APPR OPND | HB /A /75/HBAA-PSV-394410 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012745 | Replace HBAA-PSV-394410 - PSV 2023 | Install re-certified PSV | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 5 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2025-11-19 | 2023-06-03 | 30 | REL | APPR OPND | HB /A /75/HBAA-PSV-394410 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012745 | Replace HBAA-PSV-394410 - PSV 2023 | De-isolation and leak test | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 4 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2025-11-19 | 2023-06-03 | 40 | REL | APPR OPND | HB /A /75/HBAA-PSV-394410 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015386 | Replace FFLB2 coolant with GlysantinG30 | Isolate lifeboat | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-02-13 | 2023-10-01 | 10 | REL | APPR OPND | HB /C /02/HBCA-X-0702 | LIFEBOAT 2 - 45 PERS. |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015386 | Replace FFLB2 coolant with GlysantinG30 | Flush coolant system with Glysantin G30 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-02-13 | 2023-10-01 | 20 | REL | APPR OPND | HB /C /02/HBCA-X-0702 | LIFEBOAT 2 - 45 PERS. |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015386 | Replace FFLB2 coolant with GlysantinG30 | De-isolate accordingly | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-02-13 | 2023-10-01 | 30 | REL | APPR OPND | HB /C /02/HBCA-X-0702 | LIFEBOAT 2 - 45 PERS. |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015387 | Replace FFLB3 coolant with GlysantinG30 | Isolate lifeboat | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-02-13 | 2023-10-01 | 10 | REL | APPR OPND | HB /D /02/HBDC-X-0750 | LIFEBOAT & DAVIT WITH 45 LIFE JACKETS |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015387 | Replace FFLB3 coolant with GlysantinG30 | Flush coolant system with Glysantin G30 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-02-13 | 2023-10-01 | 20 | REL | APPR OPND | HB /D /02/HBDC-X-0750 | LIFEBOAT & DAVIT WITH 45 LIFE JACKETS |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015387 | Replace FFLB3 coolant with GlysantinG30 | De-isolate accordingly | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-02-13 | 2023-10-01 | 30 | REL | APPR OPND | HB /D /02/HBDC-X-0750 | LIFEBOAT & DAVIT WITH 45 LIFE JACKETS |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015388 | Replace FFLB4 coolant with GlysantinG30 | Isolate lifeboat | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-02-13 | 2023-10-01 | 10 | REL | APPR OPND | HB /D /02/HBDC-X-0751 | LIFEBOAT & DAVIT WITH 45 LIFE JACKETS |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015388 | Replace FFLB4 coolant with GlysantinG30 | Flush coolant system with Glysantin G30 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-02-13 | 2023-10-01 | 20 | REL | APPR OPND | HB /D /02/HBDC-X-0751 | LIFEBOAT & DAVIT WITH 45 LIFE JACKETS |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015388 | Replace FFLB4 coolant with GlysantinG30 | De-isolate accordingly | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-02-13 | 2023-10-01 | 30 | REL | APPR OPND | HB /D /02/HBDC-X-0751 | LIFEBOAT & DAVIT WITH 45 LIFE JACKETS |  | C |  | MMS | DK50
2026-W1-2 | 2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016033 | New socketoutlet for the soup pot | New socketoutlet for the soup pot | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 0 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2023-11-17 | 2023-10-03 | 10 | REL | APPR OPND | HB /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016033 | New socketoutlet for the soup pot | spiral cable | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 0 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2023-11-17 | 2023-10-03 | 20 | REL | APPR OPND | HB /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016033 | New socketoutlet for the soup pot | Isolate and prove dead | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2023-11-17 | 2023-10-03 | 30 | REL | APPR OPND | HB /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016033 | New socketoutlet for the soup pot | Connect spiral cable to JB above sealing | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 4 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2023-11-17 | 2023-10-03 | 40 | REL | APPR OPND | HB /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016033 | New socketoutlet for the soup pot | Connect new plug to spiral cable | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-23 | 2023-11-17 | 2023-10-03 | 50 | REL | APPR OPND | HB /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016033 | New socketoutlet for the soup pot | Deisolate and test. | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-23 | 2023-11-17 | 2023-10-03 | 60 | REL | APPR OPND | HB /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 3 | NE | WGN | MTN-MECH | PRODTECH | 2200016102 | Cooling water replacement HBDE-G-1710 | Isolation & safing of HBDE-G-1710 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2024-04-08 | 2023-11-25 | 10 | REL | APPR OPND | HB /D /05/HBDE-G-1710 | EMERGENCY DIESEL GENERATOR |  | A |  | MMR | DK50 |  | PROK
2026-W1-2 | 3 | NE | WGN | MTN-MECH | MTN-MECH | 2200016102 | Cooling water replacement HBDE-G-1710 | Replace coolant to glysantin G30 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2024-04-08 | 2023-11-25 | 20 | REL | APPR OPND | HB /D /05/HBDE-G-1710 | EMERGENCY DIESEL GENERATOR |  | A |  | MMR | DK50 |  | PROK
2026-W1-2 | 3 | NE | WGN | MTN-MECH | PRODTECH | 2200016102 | Cooling water replacement HBDE-G-1710 | De-isolation & desafing of HBDE-G-1710 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2024-04-08 | 2023-11-25 | 30 | REL | APPR OPND | HB /D /05/HBDE-G-1710 | EMERGENCY DIESEL GENERATOR |  | A |  | MMR | DK50 |  | PROK
2026-W1-2 | 2 | NE | WGN | MTN-INST | MTN-INST | 2200016640 | HBDC - Aware Mapper, Harddisk replacemen | HBDC - Aware Mapper, Harddisk replacemne | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 20 | 12 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-01-15 | 2023-12-01 | 10 | PCNF REL | APPR OPND | HB /C /08 | COMMUNICATION/TELECOM |  | A |  | MIN | DK50
2026-W1-2 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300004799 | Mimic led for LG valve HBA15 Node E01 | Mimic led for LG valve HBA15 Node E01 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 0 | 0 | W11-W12 | 2024-03-13 | 2024-03-17 | 2024-03-13 | 2023-08-16 | 2023-04-03 | 10 | REL | APPR OPND | HB /D /03/HBDC-FP-0250T | ESD & F&G TILE MATRIX PANEL |  | A |  | MIN | DK50
2026-W1-2 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300004799 | Mimic led for LG valve HBA15 Node E01 |  | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 24 | 0 | W11-W12 | 2024-03-13 | 2024-03-17 | 2024-03-13 | 2023-08-16 | 2023-04-03 | 20 | REL | APPR OPND | HB /D /03/HBDC-FP-0250T | ESD & F&G TILE MATRIX PANEL |  | A |  | MIN | DK50
0 | C | NOSD | WPM | MTN-MECH | VEN-MECH | 2400241921 | 6M AIR SYSTEM INSPECTION HDBC-5401/2 | AIR SYSTEM INSPECTION HDBC-5401/2 | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 5 | 0 | W11-W12 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2023-04-23 | 2023-04-04 | 10 | REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | A | DKHD-0054 | MMR | DK60 | MR0033
0 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241921 | 6M AIR SYSTEM INSPECTION HDBC-5401/2 | VENDOR SUPPORT | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 3 | 0 | W11-W12 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2023-04-23 | 2023-04-04 | 20 | REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | A | DKHD-0054 | MMR | DK60 | MR0033
0 | C | NOSD | WPM | MTN-MECH | MTN-INST | 2400241921 | 6M AIR SYSTEM INSPECTION HDBC-5401/2 | VENDOR SUPPORT | REL GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 3 | 0 | W11-W12 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2023-04-23 | 2023-04-04 | 30 | REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | A | DKHD-0054 | MMR | DK60 | MR0033
0 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400298347 | 2Y WCM HDAB-V-3401 - METERING | ISOLATION BY PRODUCTION | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W13-W14 | 2024-03-25 | 2024-03-30 | 2024-03-25 | 2024-01-15 | 2023-11-21 | 10 | PCNF REL | APPR OPND | HD /A /11/METERING | METERING HYDROCARBON EXTRACTION |  | A | DKHD-6018 | MIN | DK60 | IN0013
0 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400298347 | 2Y WCM HDAB-V-3401 - METERING | Assistance for Metering | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 16 | 0 | W13-W14 | 2024-03-25 | 2024-03-30 | 2024-03-25 | 2024-01-15 | 2023-11-21 | 20 | PCNF REL | APPR OPND | HD /A /11/METERING | METERING HYDROCARBON EXTRACTION |  | A | DKHD-6018 | MIN | DK60 | IN0013
0 | C | NOSD | WPM | MTN-INST | MTN-INST | 2400298347 | 2Y WCM HDAB-V-3401 - METERING | WCM METERING HDAB-V-3401 | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 24 | 8 | W13-W14 | 2024-03-25 | 2024-03-30 | 2024-03-27 | 2024-01-15 | 2023-11-21 | 30 | PCNF REL | APPR OPND | HD /A /11/METERING | METERING HYDROCARBON EXTRACTION |  | A | DKHD-6018 | MIN | DK60 | IN0013
0 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400298347 | 2Y WCM HDAB-V-3401 - METERING | DE-ISOLATION BY PRODUCTION | REL PCNF GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 2 | 0 | W13-W14 | 2024-03-25 | 2024-03-30 | 2024-03-29 | 2024-01-15 | 2023-11-21 | 40 | PCNF REL | APPR OPND | HD /A /11/METERING | METERING HYDROCARBON EXTRACTION |  | A | DKHD-6018 | MIN | DK60 | IN0013
0 | D | NOSD | WPM | MTN-INST | MTN-INST | 2400316101 | 1Y SERVICE OF SIMULTAN AEROTEST | SERVICE OF SIMULTAN AEROTEST | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-05-03 | 2024-03-17 | 10 | REL | APPR OPND | HD /A /84/TEST-EQUIPMENT | TEST EQUIPMENT |  | A | DKHD-2022 | MIN | DK60 | IN0113
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100053836 | Replacement of frequency relay | Isolation of CP-1752 | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH | 1 | 0 | W41-42 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2021-10-05 | 2021-08-26 | 10 | REL | APPR OPND | HD /B /05/HDBD-CP-1752 | GENERATOR CONTROL PANEL |  | A |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100053836 | Replacement of frequency relay | Replacement of frequency relay | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH | 4 | 0 | W41-42 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2021-10-05 | 2021-08-26 | 20 | REL | APPR OPND | HD /B /05/HDBD-CP-1752 | GENERATOR CONTROL PANEL |  | A |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100053836 | Replacement of frequency relay | De-Isolation of CP-1752 | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH | 1 | 0 | W41-42 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2021-10-05 | 2021-08-26 | 30 | REL | APPR OPND | HD /B /05/HDBD-CP-1752 | GENERATOR CONTROL PANEL |  | A |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100053836 | Replacement of frequency relay | As-built documentation | REL PRT GMPS MANC PRC SETC | APPR SMAT SCH | 1 | 0 | W41-42 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2021-10-05 | 2021-08-26 | 40 | REL | APPR OPND | HD /B /05/HDBD-CP-1752 | GENERATOR CONTROL PANEL |  | A |  | MEL | DK60
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100033880 | Steen HBB-04 SDBB liftgasmanifold to HBB | Prepare/carry out isolation w N2 purging | REL PRT GMPS MANC PRC SETC | APPR SMAT RFRZ | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2020-08-14 | 2020-07-05 | 10 | REL | APPR OPND | HB /B /37/HBBB-HCV-290403 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100033880 | Steen HBB-04 SDBB liftgasmanifold to HBB | Replace 2" SDBB Vlv | REL PRT GMPS MANC PRC SETC | APPR SMAT RFRZ | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2020-08-14 | 2020-07-05 | 20 | REL | APPR OPND | HB /B /37/HBBB-HCV-290403 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100033880 | Steen HBB-04 SDBB liftgasmanifold to HBB | Production deisolation/leak test | REL PRT GMPS MANC PRC SETC | APPR SMAT RFRZ | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2020-08-14 | 2020-07-05 | 30 | REL | APPR OPND | HB /B /37/HBBB-HCV-290403 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50 |  | PROK
2024-W23-24 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100051818 | HBA17 liftgas hcv external leak | HBA17 liftgas hcv external leak | REL GMPS MANC PRC SETC | APPR SMAT RFRZ | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2021-07-24 | 2021-07-04 | 10 | REL | APPR OPND | HB /A /37/HBAA-HCV-29174 | LIFT GAS MANIFOLD OUTLET VALVE | 99000119 | A |  | MMS | DK50 |  | PROK
2024-W23-24 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100051818 | HBA17 liftgas hcv external leak | Isolate valve | REL GMPS MANC PRC SETC | APPR SMAT RFRZ | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2021-07-24 | 2021-07-04 | 20 | REL | APPR OPND | HB /A /37/HBAA-HCV-29174 | LIFT GAS MANIFOLD OUTLET VALVE | 99000119 | A |  | MMS | DK50 |  | PROK
2024-W23-24 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100051818 | HBA17 liftgas hcv external leak | Installation of new grease-nipple kit | REL GMPS MANC PRC SETC | APPR SMAT RFRZ | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2021-07-24 | 2021-07-04 | 30 | REL | APPR OPND | HB /A /37/HBAA-HCV-29174 | LIFT GAS MANIFOLD OUTLET VALVE | 99000119 | A |  | MMS | DK50 |  | PROK
2024-W23-24 | 3 | HB-DIFF | WDF | MTN-ELEC | MTN-ELEC | 2100022796 | REPL broken breaker Q5 in N-1801 B | Isolate Q5. See attached wiring diagram | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2019-05-25 | 2019-04-15 | 10 | REL | APPR OPND | HB /A /09/HBAA-BM-1220 | MOTOR FOR BLOWER B-1220 |  | C |  | MEL | DK50
2024-W23-24 | 3 | HB-DIFF | WDF | MTN-ELEC | MTN-ELEC | 2100022796 | REPL broken breaker Q5 in N-1801 B | Peplace Q5 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 6 | Kim PTW 200108 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2019-05-25 | 2019-04-15 | 20 | PCNF REL | APPR OPND | HB /A /09/HBAA-BM-1220 | MOTOR FOR BLOWER B-1220 |  | C |  | MEL | DK50
2024-W23-24 | 3 | HB-DIFF | WDF | MTN-ELEC | MTN-ELEC | 2100022796 | REPL broken breaker Q5 in N-1801 B | De-Isolate and test | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2019-05-25 | 2019-04-15 | 30 | REL | APPR OPND | HB /A /09/HBAA-BM-1220 | MOTOR FOR BLOWER B-1220 |  | C |  | MEL | DK50
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100023497 | SMAT:HDB-New uv lights + fault blower mo | L3-Check materials | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 2 | W47-48 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2018-04-14 | 2018-03-25 | 10 | PCNF REL | APPR OPND | HD /B /82/HDBC-X-5151 | UV STERILIZER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100023497 | SMAT:HDB-New uv lights + fault blower mo | L3-replacment of parts | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SMAT RDBL | 40 | 9 | W47-48 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2018-04-14 | 2018-03-25 | 20 | PCNF REL | APPR OPND | HD /B /82/HDBC-X-5151 | UV STERILIZER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100023497 | SMAT:HDB-New uv lights + fault blower mo | L3-test and documentation | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 1 | W47-48 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2018-04-14 | 2018-03-25 | 30 | PCNF REL | APPR OPND | HD /B /82/HDBC-X-5151 | UV STERILIZER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100023497 | SMAT:HDB-New uv lights + fault blower mo | Isolate and prove dead | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2018-04-14 | 2018-03-25 | 60 | REL | APPR OPND | HD /B /82/HDBC-X-5151 | UV STERILIZER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100023497 | SMAT:HDB-New uv lights + fault blower mo | Change cables | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2018-04-14 | 2018-03-25 | 70 | REL | APPR OPND | HD /B /82/HDBC-X-5151 | UV STERILIZER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100023497 | SMAT:HDB-New uv lights + fault blower mo | De-isolate and test | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2018-04-14 | 2018-03-25 | 80 | REL | APPR OPND | HD /B /82/HDBC-X-5151 | UV STERILIZER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | Prep Scaf, Rope & Hard-Soft Barriers | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 12 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2018-02-13 | 2017-11-15 | 10 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | Cut-away Support tray | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 4 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2018-02-13 | 2017-11-15 | 20 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | Erect SB WindNet Cover of area | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 8 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2018-02-13 | 2017-11-15 | 30 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | Pre and Post Clean Beam & Waste | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-25 | 2018-02-13 | 2017-11-15 | 40 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | QC-Log, Surface Primer | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-25 | 2018-02-13 | 2017-11-15 | 50 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | Clean & QC-Test within coating layers | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-25 | 2018-02-13 | 2017-11-15 | 60 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | Paint to Spec, QC-Inspection | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 6 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-25 | 2018-02-13 | 2017-11-15 | 70 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | Clean-up & Remove WindNet+Waste | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-25 | 2018-02-13 | 2017-11-15 | 80 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | Prep Hoists Equipment & Test | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 12 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-25 | 2018-02-13 | 2017-11-15 | 90 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | Rigging Up Spool | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 8 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-26 | 2018-02-13 | 2017-11-15 | 100 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | L3 Montage af ny support | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 4 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-26 | 2018-02-13 | 2017-11-15 | 110 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | L3 Nedtagning af taljer | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 8 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-26 | 2018-02-13 | 2017-11-15 | 120 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | L3 Nedtagning af stillads | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 4 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-27 | 2018-02-13 | 2017-11-15 | 130 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | P-COATING-2100023840-0160 | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-27 | 2018-02-13 | 2017-11-15 | 160 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | P-CONSUMER-GOODS-2100023840-0170 | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-27 | 2018-02-13 | 2017-11-15 | 170 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | P-RENT-MDKW-2100023840-0180 | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-27 | 2018-02-13 | 2017-11-15 | 180 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | Order new pipe support. | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-27 | 2018-02-13 | 2017-11-15 | 200 | REL | APPR OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023840 | ANOP SMAT:Montage support 26" søvandsrør | Add material order shims | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-27 | 2018-02-13 | 2017-11-15 | 210 | REL | INIT OPND | HD /A /76 | COOLING WATER |  | A |  | MFM | DK60
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100024764 | SMAT:Corrosion on switch over pressure | Isolate TN 1856 | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2020-06-08 | 2019-06-14 | 10 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | A |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100024764 | SMAT:Corrosion on switch over pressure | Replace overpressure switch | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2020-06-08 | 2019-06-14 | 20 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | A |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100024764 | SMAT:Corrosion on switch over pressure | De-Isolate and test | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2020-06-08 | 2019-06-14 | 30 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100026071 | Mont. af exhaust bælg på G-1650/60 | Safing af GENERATOR UNIT G-1650/60 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 5 | 0 |  | 2024-03-11 | 2024-04-01 | 2024-03-11 | 2017-11-09 | 2017-08-11 | 10 | REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | F |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100026071 | Mont. af exhaust bælg på G-1650/60 | Rigger assistance | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 34.8 | 0 |  | 2024-03-11 | 2024-04-01 | 2024-03-12 | 2017-11-09 | 2017-08-11 | 20 | REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | F |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100026071 | Mont. af exhaust bælg på G-1650/60 | Bygning af stillads | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 69.7 | 0 |  | 2024-03-11 | 2024-04-01 | 2024-03-19 | 2017-11-09 | 2017-08-11 | 30 | REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | F |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100026071 | Mont. af exhaust bælg på G-1650/60 | Mont. af exhaust bælg G-1650 & 1660 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 52 | 0 |  | 2024-03-11 | 2024-04-01 | 2024-03-22 | 2017-11-09 | 2017-08-11 | 40 | REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | F |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100026071 | Mont. af exhaust bælg på G-1650/60 | Desafing | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 5 | 0 |  | 2024-03-11 | 2024-04-01 | 2024-03-28 | 2017-11-09 | 2017-08-11 | 60 | REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | F |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100026071 | Mont. af exhaust bælg på G-1650/60 | Nedtagning af stillads | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 69.7 | 0 |  | 2024-03-11 | 2024-04-01 | 2024-03-29 | 2017-11-09 | 2017-08-11 | 70 | REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | F |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026071 | Mont. af exhaust bælg på G-1650/60 | Additional protection Relay | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-03-11 | 2024-04-01 | 2024-04-01 | 2017-11-09 | 2017-08-11 | 80 | REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | F |  | MMR | DK50
0 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100026388 | Test circuit unstable (replace Relays) | Isolate drawer | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2021-03-23 | 2020-03-28 | 9 | REL | APPR OPND | HD /B /05/HDBE-N-1841-04-07 | HDBE-FAN-1204 FAN COIL UNIT-EMG SW. RM |  | C |  | MEL | DK60
0 | 4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100026388 | Test circuit unstable (replace Relays) | Replace test relays in drawer | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W45-46 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2021-03-23 | 2020-03-28 | 10 | REL | APPR OPND | HD /B /05/HDBE-N-1841-04-07 | HDBE-FAN-1204 FAN COIL UNIT-EMG SW. RM |  | C |  | MEL | DK60
0 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100026388 | Test circuit unstable (replace Relays) | De-isolate | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2021-03-23 | 2020-03-28 | 20 | REL | APPR OPND | HD /B /05/HDBE-N-1841-04-07 | HDBE-FAN-1204 FAN COIL UNIT-EMG SW. RM |  | C |  | MEL | DK60
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100031950 | PIT-300812 Insulation installation | New iinsolation to be mounted | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2020-07-02 | 2020-05-23 | 60 | PCNF REL | APPR OPND | HB /B /55/HBBB-PIT-300812 | PRESSURE INDIC. TRANSMITTER (SCADA) | 99000119 | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-INST | 2100031950 | PIT-300812 Insulation installation | **************************************** | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2020-07-02 | 2020-05-23 | 70 | REL | APPR OPND | HB /B /55/HBBB-PIT-300812 | PRESSURE INDIC. TRANSMITTER (SCADA) | 99000119 | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100031950 | PIT-300812 Insulation installation | Isolate Heat Tracing | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0.5 | 0 |  | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2020-07-02 | 2020-05-23 | 80 | REL | APPR OPND | HB /B /55/HBBB-PIT-300812 | PRESSURE INDIC. TRANSMITTER (SCADA) | 99000119 | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100031950 | PIT-300812 Insulation installation | Install insulation for the transmitter | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 4.5 | 0 |  | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2020-07-02 | 2020-05-23 | 90 | REL | APPR OPND | HB /B /55/HBBB-PIT-300812 | PRESSURE INDIC. TRANSMITTER (SCADA) | 99000119 | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100031950 | PIT-300812 Insulation installation | Deisolate heat rtracing | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0.5 | 0 |  | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2020-07-02 | 2020-05-23 | 100 | REL | APPR OPND | HB /B /55/HBBB-PIT-300812 | PRESSURE INDIC. TRANSMITTER (SCADA) | 99000119 | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-INST | 2100031950 | PIT-300812 Insulation installation |  | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2020-07-02 | 2020-05-23 | 110 | REL | APPR OPND | HB /B /55/HBBB-PIT-300812 | PRESSURE INDIC. TRANSMITTER (SCADA) | 99000119 | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-INST | 2100031950 | PIT-300812 Insulation installation |  | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2020-07-02 | 2020-05-23 | 120 | REL | APPR OPND | HB /B /55/HBBB-PIT-300812 | PRESSURE INDIC. TRANSMITTER (SCADA) | 99000119 | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-INST | 2100031950 | PIT-300812 Insulation installation |  | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2020-07-02 | 2020-05-23 | 130 | REL | APPR OPND | HB /B /55/HBBB-PIT-300812 | PRESSURE INDIC. TRANSMITTER (SCADA) | 99000119 | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | PRODTECH | 2100031950 | PIT-300812 Insulation installation |  | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2020-07-02 | 2020-05-23 | 140 | REL | APPR OPND | HB /B /55/HBBB-PIT-300812 | PRESSURE INDIC. TRANSMITTER (SCADA) | 99000119 | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-INST | 2100031950 | PIT-300812 Insulation installation |  | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2020-07-02 | 2020-05-23 | 150 | REL | APPR OPND | HB /B /55/HBBB-PIT-300812 | PRESSURE INDIC. TRANSMITTER (SCADA) | 99000119 | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | PRODTECH | PRODTECH | 2100032004 | Level glass on IGF dirty | Isolate heat tracing | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0.5 | 0 |  | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2021-04-26 | 2020-08-29 | 5 | REL | APPR OPND | HB /D /27/HBDB-LG-507501 | LEVEL GLASS |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | PRODTECH | PRODTECH | 2100032004 | Level glass on IGF dirty | Isolate level glass | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2021-04-26 | 2020-08-29 | 10 | REL | APPR OPND | HB /D /27/HBDB-LG-507501 | LEVEL GLASS |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | PRODTECH | PRODTECH | 2100032004 | Level glass on IGF dirty | Clean level glass | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 |  | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2021-04-26 | 2020-08-29 | 20 | REL | APPR OPND | HB /D /27/HBDB-LG-507501 | LEVEL GLASS |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | PRODTECH | PRODTECH | 2100032004 | Level glass on IGF dirty | De-isolate level glass | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2021-04-26 | 2020-08-29 | 30 | REL | APPR OPND | HB /D /27/HBDB-LG-507501 | LEVEL GLASS |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | PRODTECH | PRODTECH | 2100032004 | Level glass on IGF dirty | De-isolate heat tracing | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0.5 | 0 |  | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2021-04-26 | 2020-08-29 | 40 | REL | APPR OPND | HB /D /27/HBDB-LG-507501 | LEVEL GLASS |  | A |  | MIN | DK50
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3901A Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 10 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3901B Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 20 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3902A Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 30 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3902B Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 40 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3903 Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 50 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3904 Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 60 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3905 Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 70 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3906 Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 80 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3907A Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 90 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3907B Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 100 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3907C Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 110 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3907D Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 120 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3908A Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 130 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3908B Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 140 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3908C Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 150 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3908D Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 160 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3909 Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 170 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3910 Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 180 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3911A Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 190 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3911B Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 200 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3911C Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 210 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3912A Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 220 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3912B Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 230 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | HDAE-PD-3912C Additional bracket/resting | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-06-09 | 2020-05-26 | 2020-05-06 | 240 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Assist during survey | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 10 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 260 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Isolate HDAE-P-3707 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 280 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Install support f/4. PD-3907A/B/C/D | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 16 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 290 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | deisolate/test HDAE-P-3707 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-13 | 2020-05-26 | 2020-05-06 | 300 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Isolate HDAE-P-3708 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 310 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Install support f/4. PD-3908A/B/C/D | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 16 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 320 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | deisolate/test HDAE-P-3708 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-13 | 2020-05-26 | 2020-05-06 | 330 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Isolate HDAE-P-3901 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 340 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Install support f/2. PD-3901A/B | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 8 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 350 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | deisolate/test HDAE-P-3901 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-12 | 2020-05-26 | 2020-05-06 | 360 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Isolate HDAE-P-3902 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 370 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Install support f/2. PD-3902A/B | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 8 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 380 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | deisolate/test HDAE-P-3902 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-12 | 2020-05-26 | 2020-05-06 | 390 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Isolate HDAE-P-3911 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 400 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Install support f/2 PD-3911A/B/C | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 410 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | deisolate/test HDAE-P-3911 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-13 | 2020-05-26 | 2020-05-06 | 420 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Isolate HDAE-P-3912 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 430 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100032192 | HDA - No Dampener supports, Synergi 6303 | Install support f/3 PD-3912A/B/C | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 440 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | deisolate/test HDAE-P-3912 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W05-06 | 2024-03-11 | 2024-06-09 | 2024-03-13 | 2020-05-26 | 2020-05-06 | 450 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100032192 | HDA - No Dampener supports, Synergi 6303 | materials | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-03-11 | 2024-06-09 | 2024-03-11 | 2020-05-26 | 2020-05-06 | 460 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MMS | DK60
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100036341 | BM-1210 HVAC HBA Q4 CB fault | Isolate DP-N-1801 | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | 24-W05-06 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2020-10-01 | 2020-08-22 | 10 | REL | APPR OPND | HB /A /61/HBAA-N-1801-Q05 | VENT FAN HBAA-BM-1220 |  | D |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100036341 | BM-1210 HVAC HBA Q4 CB fault | Change circuit breaker Q4 | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 8 | 0 | 24-W05-06 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2020-10-01 | 2020-08-22 | 20 | REL | APPR OPND | HB /A /61/HBAA-N-1801-Q05 | VENT FAN HBAA-BM-1220 |  | D |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100036341 | BM-1210 HVAC HBA Q4 CB fault | De-isolate the above. | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | 24-W05-06 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2020-10-01 | 2020-08-22 | 30 | REL | APPR OPND | HB /A /61/HBAA-N-1801-Q05 | VENT FAN HBAA-BM-1220 |  | D |  | MEL | DK50
2024-W23-24 | 3 | HBA29-GL | WDF | MTN-INST | MTN-MECH | 2100036342 | Intermitted fault from HBA 29 LG ESDV | Intermitted fault from HBA 29 LG ESDV | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2020-09-20 | 2020-08-11 | 10 | REL | APPR OPND | HB /A /75/HBAA-ESDV-392900 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MIN | DK50
2024-W23-24 | 3 | HBA29-GL | WDF | MTN-INST | MTN-MECH | 2100036342 | Intermitted fault from HBA 29 LG ESDV | Change out limit switches, ESDV closes | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2020-09-20 | 2020-08-11 | 20 | REL | APPR OPND | HB /A /75/HBAA-ESDV-392900 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100037768 | HBB/78: Replace corroded slackrope syste | Prepare lifting plan | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-18 | 2024-03-09 | 2021-08-26 | 2020-12-29 | 9 | REL | APPR OPND | HB /B /78/HBBB-X-6120-0201 | MAIN HOIST |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100037768 | HBB/78: Replace corroded slackrope syste | Locate spare parts and conduct TBT | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-18 | 2024-03-09 | 2021-08-26 | 2020-12-29 | 10 | REL | APPR OPND | HB /B /78/HBBB-X-6120-0201 | MAIN HOIST |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100037768 | HBB/78: Replace corroded slackrope syste | Isolate crane HBB/78 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-18 | 2024-03-09 | 2021-08-26 | 2020-12-29 | 20 | REL | APPR OPND | HB /B /78/HBBB-X-6120-0201 | MAIN HOIST |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100037768 | HBB/78: Replace corroded slackrope syste | Prepare tools and spareparts | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-18 | 2024-03-09 | 2021-08-26 | 2020-12-29 | 30 | REL | APPR OPND | HB /B /78/HBBB-X-6120-0201 | MAIN HOIST |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100037768 | HBB/78: Replace corroded slackrope syste | Build scaffolding | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 30 | 0 |  | 2024-03-09 | 2024-03-18 | 2024-03-09 | 2021-08-26 | 2020-12-29 | 40 | REL | APPR OPND | HB /B /78/HBBB-X-6120-0201 | MAIN HOIST |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100037768 | HBB/78: Replace corroded slackrope syste | Replace slackrope system | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 0 |  | 2024-03-09 | 2024-03-18 | 2024-03-12 | 2021-08-26 | 2020-12-29 | 50 | REL | APPR OPND | HB /B /78/HBBB-X-6120-0201 | MAIN HOIST |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100037768 | HBB/78: Replace corroded slackrope syste | Ass. Replaceing slackrope system | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 8 | 0 |  | 2024-03-09 | 2024-03-18 | 2024-03-09 | 2021-08-26 | 2020-12-29 | 51 | REL | APPR OPND | HB /B /78/HBBB-X-6120-0201 | MAIN HOIST |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100037768 | HBB/78: Replace corroded slackrope syste | Rigger support | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 0 |  | 2024-03-09 | 2024-03-18 | 2024-03-12 | 2021-08-26 | 2020-12-29 | 60 | REL | APPR OPND | HB /B /78/HBBB-X-6120-0201 | MAIN HOIST |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100037768 | HBB/78: Replace corroded slackrope syste | Remove scaffolding | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 20 | 0 |  | 2024-03-09 | 2024-03-18 | 2024-03-15 | 2021-08-26 | 2020-12-29 | 70 | REL | APPR OPND | HB /B /78/HBBB-X-6120-0201 | MAIN HOIST |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100037768 | HBB/78: Replace corroded slackrope syste | De-isolate crane HBB/78 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-18 | 2024-03-17 | 2021-08-26 | 2020-12-29 | 80 | REL | APPR OPND | HB /B /78/HBBB-X-6120-0201 | MAIN HOIST |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100037768 | HBB/78: Replace corroded slackrope syste | Function test slackrope system | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-18 | 2024-03-17 | 2021-08-26 | 2020-12-29 | 90 | REL | APPR OPND | HB /B /78/HBBB-X-6120-0201 | MAIN HOIST |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100037768 | HBB/78: Replace corroded slackrope syste | Documentation | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-18 | 2024-03-17 | 2021-08-26 | 2020-12-29 | 100 | REL | APPR OPND | HB /B /78/HBBB-X-6120-0201 | MAIN HOIST |  | C |  | MMS | DK50
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038401 | Installation of mcb on batt bank 17021 | Setup UNISTRUT and box for MCB | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | W43-44 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2021-01-09 | 2020-10-11 | 10 | REL | APPR OPND | HD /B /05/HDBD-BAT-17021 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100038401 | Installation of mcb on batt bank 17021 | Isolate battery chargers | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W43-44 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2021-01-09 | 2020-10-11 | 20 | REL | APPR OPND | HD /B /05/HDBD-BAT-17021 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038401 | Installation of mcb on batt bank 17021 | Install MCB and cables | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | W43-44 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-01-09 | 2020-10-11 | 30 | REL | APPR OPND | HD /B /05/HDBD-BAT-17021 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100038401 | Installation of mcb on batt bank 17021 | De-isolate above | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W43-44 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-01-09 | 2020-10-11 | 40 | REL | APPR OPND | HD /B /05/HDBD-BAT-17021 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038401 | Installation of mcb on batt bank 17021 | AS BUILT update drawings | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W43-44 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-01-09 | 2020-10-11 | 50 | REL | APPR OPND | HD /B /05/HDBD-BAT-17021 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100038451 | LOTI:HDBF-A-1212A/1212B Backup batteries | Upload PLC programme | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W43-44 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-13 | 2020-10-15 | 10 | REL | APPR OPND | HD /B /09/HDBF-A-1212A | AIR COOLED CONDENSER | 99000121 | A |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100038451 | LOTI:HDBF-A-1212A/1212B Backup batteries | Change batteries in PLC | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W43-44 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-13 | 2020-10-15 | 20 | REL | APPR OPND | HD /B /09/HDBF-A-1212A | AIR COOLED CONDENSER | 99000121 | A |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100038451 | LOTI:HDBF-A-1212A/1212B Backup batteries | Start up system & test | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W43-44 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-13 | 2020-10-15 | 30 | REL | APPR OPND | HD /B /09/HDBF-A-1212A | AIR COOLED CONDENSER | 99000121 | A |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100038752 | Replace multifunct. energymeter & Switch | Isolate accordingly | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2021-01-16 | 2020-10-18 | 10 | REL | APPR OPND | HD /B /05/HDBE-N-1841-03-01 | HDBE-N18410301, INCOMER FROM EDG G-1752 |  | C |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038752 | Replace multifunct. energymeter & Switch | Replace switch and energymeter | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2021-01-16 | 2020-10-18 | 20 | REL | APPR OPND | HD /B /05/HDBE-N-1841-03-01 | HDBE-N18410301, INCOMER FROM EDG G-1752 |  | C |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100038752 | Replace multifunct. energymeter & Switch | De-isolate | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-29 | 2021-01-16 | 2020-10-18 | 30 | REL | APPR OPND | HD /B /05/HDBE-N-1841-03-01 | HDBE-N18410301, INCOMER FROM EDG G-1752 |  | C |  | MEL | DK60 |  | PROK
2026-W13-14 | 4 | HBBPWELL | WDF | MTN-MECH | PRODTECH | 2100040113 | HBBA-A-5914 Hydraulic leaks inside WH pa | Isolate leaking parts of hydraulic syste | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | requires SD | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2021-06-15 | 2021-01-16 | 10 | REL | APPR OPND | HB /B /07/HBBA-A-5914 | HYDRAULIC ACCUMULATOR PACKAGE |  | C |  | MMS | DK50
2026-W13-14 | 4 | HBBPWELL | WDF | MTN-MECH | MTN-INST | 2100040113 | HBBA-A-5914 Hydraulic leaks inside WH pa | Replace leaking valve with a new valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2021-06-15 | 2021-01-16 | 20 | REL | APPR OPND | HB /B /07/HBBA-A-5914 | HYDRAULIC ACCUMULATOR PACKAGE |  | C |  | MMS | DK50
2026-W13-14 | 4 | HBBPWELL | WDF | MTN-MECH | MTN-INST | 2100040113 | HBBA-A-5914 Hydraulic leaks inside WH pa | Replace leaking packings | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2021-06-15 | 2021-01-16 | 30 | REL | APPR OPND | HB /B /07/HBBA-A-5914 | HYDRAULIC ACCUMULATOR PACKAGE |  | C |  | MMS | DK50
2026-W13-14 | 4 | HBBPWELL | WDF | MTN-MECH | PRODTECH | 2100040113 | HBBA-A-5914 Hydraulic leaks inside WH pa | De-isolate system, pressurize, test the | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W01-02 | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2021-06-15 | 2021-01-16 | 40 | REL | APPR OPND | HB /B /07/HBBA-A-5914 | HYDRAULIC ACCUMULATOR PACKAGE |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100042575 | Replace Multi inst. LCD HBCA-N-1840B-01 | Isolate accordingly | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2021-08-01 | 2021-03-04 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-01 | SECTION NO.01 |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100042575 | Replace Multi inst. LCD HBCA-N-1840B-01 | Replace Instrument | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2021-08-01 | 2021-03-04 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-01 | SECTION NO.01 |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100042575 | Replace Multi inst. LCD HBCA-N-1840B-01 | De-isolate above | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-29 | 2021-08-01 | 2021-03-04 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-01 | SECTION NO.01 |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048123 | Replace HBAA-LCV-34127A | Prepare Permit/Tools/Matr | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W09-10 | 2024-03-09 | 2024-03-14 | 2024-03-09 | 2021-11-20 | 2021-06-23 | 10 | REL | APPR OPND | HB /A /11/HBAA-LCV-34127A | LEVEL CONTROL VALVE. V-3411 |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100048123 | Replace HBAA-LCV-34127A | Rig up equipment | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W09-10 | 2024-03-09 | 2024-03-14 | 2024-03-09 | 2021-11-20 | 2021-06-23 | 20 | REL | APPR OPND | HB /A /11/HBAA-LCV-34127A | LEVEL CONTROL VALVE. V-3411 |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048123 | Replace HBAA-LCV-34127A | Isolate valve | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W09-10 | 2024-03-09 | 2024-03-14 | 2024-03-10 | 2021-11-20 | 2021-06-23 | 30 | REL | APPR OPND | HB /A /11/HBAA-LCV-34127A | LEVEL CONTROL VALVE. V-3411 |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048123 | Replace HBAA-LCV-34127A | Replace valve | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 0 | W09-10 | 2024-03-09 | 2024-03-14 | 2024-03-10 | 2021-11-20 | 2021-06-23 | 40 | REL | APPR OPND | HB /A /11/HBAA-LCV-34127A | LEVEL CONTROL VALVE. V-3411 |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048123 | Replace HBAA-LCV-34127A | De-isolate leaktest etc. | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W09-10 | 2024-03-09 | 2024-03-14 | 2024-03-13 | 2021-11-20 | 2021-06-23 | 50 | REL | APPR OPND | HB /A /11/HBAA-LCV-34127A | LEVEL CONTROL VALVE. V-3411 |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100048123 | Replace HBAA-LCV-34127A | Rig down equipment | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W09-10 | 2024-03-09 | 2024-03-14 | 2024-03-13 | 2021-11-20 | 2021-06-23 | 60 | REL | APPR OPND | HB /A /11/HBAA-LCV-34127A | LEVEL CONTROL VALVE. V-3411 |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | PRODTECH | 2100050469 | Def. PDI blok and PI at cooling medium | Isolate PDI | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 2 | W09-W10 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-01-12 | 2021-08-15 | 10 | PCNF REL | APPR OPND | HB /D /50 | WTR LIFT (WTR PROD WELLS, TRANS LINES) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100050469 | Def. PDI blok and PI at cooling medium | Replace PDI | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 18 | W09-W10 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-01-12 | 2021-08-15 | 60 | PCNF REL | APPR OPND | HB /D /50 | WTR LIFT (WTR PROD WELLS, TRANS LINES) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100050469 | Def. PDI blok and PI at cooling medium | Replace Block&Bleed valves | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 18 | W09-W10 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-01-12 | 2021-08-15 | 70 | PCNF REL | APPR OPND | HB /D /50 | WTR LIFT (WTR PROD WELLS, TRANS LINES) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | PRODTECH | 2100050469 | Def. PDI blok and PI at cooling medium | Deisolate PDI | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 2 | W09-W10 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-01-12 | 2021-08-15 | 80 | PCNF REL | APPR OPND | HB /D /50 | WTR LIFT (WTR PROD WELLS, TRANS LINES) |  | C |  | MIN | DK50
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100052816 | Level transmitter on Emerg. G-1752 | **************************************** | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2022-10-10 | 2021-09-09 | 2021-07-31 | 60 | PCNF REL | APPR OPND | HD /B /05/HDBD-LT-17053 | LEVEL TRANSMITTER |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100052816 | Level transmitter on Emerg. G-1752 | Build scaffold | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 16 | 21 | W09-10 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-09-09 | 2021-07-31 | 81 | PCNF REL | APPR OPND | HD /B /05/HDBD-LT-17053 | LEVEL TRANSMITTER |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100052816 | Level transmitter on Emerg. G-1752 | Empty diesel tank | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 2 | 0 | W33-34 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-09-09 | 2021-07-31 | 91 | PCNF REL | APPR OPND | HD /B /05/HDBD-LT-17053 | LEVEL TRANSMITTER |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100052816 | Level transmitter on Emerg. G-1752 | Isolate level transmitter | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 0.5 | 0 | W33-34 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-09-09 | 2021-07-31 | 101 | PCNF REL | APPR OPND | HD /B /05/HDBD-LT-17053 | LEVEL TRANSMITTER |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100052816 | Level transmitter on Emerg. G-1752 | Replace level transmitter | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 3 | 0 | W33-34 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-09-09 | 2021-07-31 | 111 | PCNF REL | APPR OPND | HD /B /05/HDBD-LT-17053 | LEVEL TRANSMITTER |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100052816 | Level transmitter on Emerg. G-1752 | Deisolate level transmitter | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 0.5 | 0 | W33-34 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-09-09 | 2021-07-31 | 121 | PCNF REL | APPR OPND | HD /B /05/HDBD-LT-17053 | LEVEL TRANSMITTER |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100052816 | Level transmitter on Emerg. G-1752 | Calibrate level transmitter | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 2 | 4 | W33-34 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-09-09 | 2021-07-31 | 131 | PCNF REL | APPR OPND | HD /B /05/HDBD-LT-17053 | LEVEL TRANSMITTER |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100052816 | Level transmitter on Emerg. G-1752 | Deisolate diesel tanl | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 0.5 | 0 | W33-34 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-09-09 | 2021-07-31 | 141 | PCNF REL | APPR OPND | HD /B /05/HDBD-LT-17053 | LEVEL TRANSMITTER |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100052816 | Level transmitter on Emerg. G-1752 | Remove scaffolding | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 4 | 0 | W33-34 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-09-09 | 2021-07-31 | 151 | PCNF REL | APPR OPND | HD /B /05/HDBD-LT-17053 | LEVEL TRANSMITTER |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100052816 | Level transmitter on Emerg. G-1752 | Exd level transmitter | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-09-09 | 2021-07-31 | 161 | PCNF REL | APPR OPND | HD /B /05/HDBD-LT-17053 | LEVEL TRANSMITTER |  | C |  | MIN | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100054830 | ANOS HDA Grating/Handrail Rep. | HDA -Grating/Handrail Rep. on Jacket-MPM | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 72 | 57 |  | 2023-04-24 | 2023-05-02 | 2023-04-24 | 2022-08-21 | 2021-12-24 | 10 | PCNF REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100054830 | ANOS HDA Grating/Handrail Rep. | Material handling | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-04-24 | 2023-05-02 | 2023-04-24 | 2022-08-21 | 2021-12-24 | 20 | PCNF REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100054830 | ANOS HDA Grating/Handrail Rep. | Temporary repair grating GVI-236 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 36 | 0 |  | 2023-04-24 | 2023-05-02 | 2023-04-24 | 2022-08-21 | 2021-12-24 | 40 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100054830 | ANOS HDA Grating/Handrail Rep. | Renew grating GVI-236 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 200 | 0 |  | 2023-04-24 | 2023-05-02 | 2023-04-25 | 2022-08-21 | 2021-12-24 | 50 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
2026-W13-14 | 3 | HBB05-GL | WDF | MTN-MECH | MTN-MECH | 2100056166 | HBBB-FP-3140 override valves is leaking | Prepare Matr/Tools | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-08 | 2022-01-20 | 2021-10-22 | 10 | REL | APPR OPND | HB /B /07/HBBB-FP-3140 | FIELD PANEL |  | C |  | MMS | DK50
2026-W13-14 | 3 | HBB05-GL | WDF | MTN-MECH | PRODTECH | 2100056166 | HBBB-FP-3140 override valves is leaking | Production isolation | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-08 | 2022-01-20 | 2021-10-22 | 20 | REL | APPR OPND | HB /B /07/HBBB-FP-3140 | FIELD PANEL |  | C |  | MMS | DK50
2026-W13-14 | 3 | HBB05-GL | WDF | MTN-MECH | MTN-MECH | 2100056166 | HBBB-FP-3140 override valves is leaking | Replace MCV 3way Vlv | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-09 | 2022-01-20 | 2021-10-22 | 30 | REL | APPR OPND | HB /B /07/HBBB-FP-3140 | FIELD PANEL |  | C |  | MMS | DK50
2026-W13-14 | 3 | HBB05-GL | WDF | MTN-MECH | MTN-MECH | 2100056166 | HBBB-FP-3140 override valves is leaking | Replace WCV 3way Vlv | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-10 | 2022-01-20 | 2021-10-22 | 40 | REL | APPR OPND | HB /B /07/HBBB-FP-3140 | FIELD PANEL |  | C |  | MMS | DK50
2026-W13-14 | 3 | HBB05-GL | WDF | MTN-MECH | PRODTECH | 2100056166 | HBBB-FP-3140 override valves is leaking | Production de-isolation w func. Test | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-10 | 2022-01-20 | 2021-10-22 | 50 | REL | APPR OPND | HB /B /07/HBBB-FP-3140 | FIELD PANEL |  | C |  | MMS | DK50
2026-W13-14 | 3 | HBB05-GL | WDF | MTN-MECH | MTN-MECH | 2100056166 | HBBB-FP-3140 override valves is leaking | extra valves/minimum buy | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-11 | 2022-01-20 | 2021-10-22 | 60 | REL | APPR OPND | HB /B /07/HBBB-FP-3140 | FIELD PANEL |  | C |  | MMS | DK50
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100057883 | LOTI:Breaker Q1 is periodic defective | Isolate accordingly | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W25-26 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-02-21 | 2021-11-23 | 10 | REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR | 99000121 | C |  | MEL | DK50
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057883 | LOTI:Breaker Q1 is periodic defective | Redraw breaker from HBDC-XE-3651 | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W25-26 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-02-21 | 2021-11-23 | 20 | REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR | 99000121 | C |  | MEL | DK50
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057883 | LOTI:Breaker Q1 is periodic defective | Check settings HBDC-XE-3651 | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W25-26 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-02-21 | 2021-11-23 | 21 | REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR | 99000121 | C |  | MEL | DK50
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057883 | LOTI:Breaker Q1 is periodic defective | Install repaired breaker in HBDC-XE-3651 | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W25-26 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-02-21 | 2021-11-23 | 30 | REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR | 99000121 | C |  | MEL | DK50
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057883 | LOTI:Breaker Q1 is periodic defective | Install redrawn breaker in HBDC-XE-3653 | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W25-26 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2022-02-21 | 2021-11-23 | 40 | REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR | 99000121 | C |  | MEL | DK50
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057883 | LOTI:Breaker Q1 is periodic defective | De-isolate accordingly | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W25-26 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2022-02-21 | 2021-11-23 | 50 | REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR | 99000121 | C |  | MEL | DK50
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100057883 | LOTI:Breaker Q1 is periodic defective | Function test breakers | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W25-26 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2022-02-21 | 2021-11-23 | 60 | REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR | 99000121 | C |  | MEL | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100058047 | HBDC-HCV-415202-U is internally leaking | Isolate and depressurize system | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2022-06-25 | 2022-01-26 | 10 | REL | APPR OPND | HB /D /30/HBDC-HCV-415202-U | HCV UPSTREAM PSV-415202 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-LAGG | 2100058047 | HBDC-HCV-415202-U is internally leaking | Remove insulation | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2022-06-25 | 2022-01-26 | 20 | REL | APPR OPND | HB /D /30/HBDC-HCV-415202-U | HCV UPSTREAM PSV-415202 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058047 | HBDC-HCV-415202-U is internally leaking | Prepare for rigging out the valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2022-06-25 | 2022-01-26 | 25 | REL | APPR OPND | HB /D /30/HBDC-HCV-415202-U | HCV UPSTREAM PSV-415202 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100058047 | HBDC-HCV-415202-U is internally leaking | Disconnect passing valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2022-06-25 | 2022-01-26 | 27 | REL | APPR OPND | HB /D /30/HBDC-HCV-415202-U | HCV UPSTREAM PSV-415202 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058047 | HBDC-HCV-415202-U is internally leaking | Rig-out passing valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2022-06-25 | 2022-01-26 | 30 | REL | APPR OPND | HB /D /30/HBDC-HCV-415202-U | HCV UPSTREAM PSV-415202 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058047 | HBDC-HCV-415202-U is internally leaking | Rig-in new valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2022-06-25 | 2022-01-26 | 33 | REL | APPR OPND | HB /D /30/HBDC-HCV-415202-U | HCV UPSTREAM PSV-415202 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100058047 | HBDC-HCV-415202-U is internally leaking | Mount new valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2022-06-25 | 2022-01-26 | 40 | REL | APPR OPND | HB /D /30/HBDC-HCV-415202-U | HCV UPSTREAM PSV-415202 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-LAGG | 2100058047 | HBDC-HCV-415202-U is internally leaking | Re-install insulation | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2022-06-25 | 2022-01-26 | 50 | REL | APPR OPND | HB /D /30/HBDC-HCV-415202-U | HCV UPSTREAM PSV-415202 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100058047 | HBDC-HCV-415202-U is internally leaking | Pressurize system and test for leakages | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2022-06-25 | 2022-01-26 | 60 | REL | APPR OPND | HB /D /30/HBDC-HCV-415202-U | HCV UPSTREAM PSV-415202 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100058256 | PCV-394103 cant regulate. Change of trim | Scaf for access valve preparation | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2022-03-01 | 2021-12-01 | 10 | REL | APPR OPND | HB /A /75/HBAA-PCV-394103 | PRESSURE CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100058256 | PCV-394103 cant regulate. Change of trim | Isolate + inhibit PCV-394103 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2022-03-01 | 2021-12-01 | 20 | REL | APPR OPND | HB /A /75/HBAA-PCV-394103 | PRESSURE CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100058256 | PCV-394103 cant regulate. Change of trim | Disconnect pneumatic and controls | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2022-03-01 | 2021-12-01 | 30 | REL | APPR OPND | HB /A /75/HBAA-PCV-394103 | PRESSURE CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100058256 | PCV-394103 cant regulate. Change of trim | Removal of PCV | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-27 | 2022-03-01 | 2021-12-01 | 40 | REL | APPR OPND | HB /A /75/HBAA-PCV-394103 | PRESSURE CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100058256 | PCV-394103 cant regulate. Change of trim | Change New Trim | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-27 | 2022-03-01 | 2021-12-01 | 50 | REL | APPR OPND | HB /A /75/HBAA-PCV-394103 | PRESSURE CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100058256 | PCV-394103 cant regulate. Change of trim | Mount New PCV | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-27 | 2022-03-01 | 2021-12-01 | 60 | REL | APPR OPND | HB /A /75/HBAA-PCV-394103 | PRESSURE CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100058256 | PCV-394103 cant regulate. Change of trim | Re-connect pneu & positioner | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-28 | 2022-03-01 | 2021-12-01 | 70 | REL | APPR OPND | HB /A /75/HBAA-PCV-394103 | PRESSURE CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100058256 | PCV-394103 cant regulate. Change of trim | Deisolation PCV | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-28 | 2022-03-01 | 2021-12-01 | 80 | REL | APPR OPND | HB /A /75/HBAA-PCV-394103 | PRESSURE CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100058256 | PCV-394103 cant regulate. Change of trim | Calibrate New PCV | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-28 | 2022-03-01 | 2021-12-01 | 90 | REL | APPR OPND | HB /A /75/HBAA-PCV-394103 | PRESSURE CONTROL VALVE |  | A |  | MMS | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100058257 | Isolation for cable is damaged. | Erect scaffold | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 8 | 0 | W45-46 MPM | 2023-01-30 | 2023-01-31 | 2023-01-30 | 2022-06-26 | 2022-01-27 | 10 | REL | APPR OPND | HB /A /37/HBAA-FCV-29053 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MIN | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100058257 | Isolation for cable is damaged. | Isolate Control Valve / Inhibit | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 1 | 0 | W45-46 MPM | 2023-01-30 | 2023-01-31 | 2023-01-30 | 2022-06-26 | 2022-01-27 | 20 | REL | APPR OPND | HB /A /37/HBAA-FCV-29053 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MIN | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100058257 | Isolation for cable is damaged. | Remove Cable | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 1 | 0 | W45-46 MPM | 2023-01-30 | 2023-01-31 | 2023-01-30 | 2022-06-26 | 2022-01-27 | 30 | REL | APPR OPND | HB /A /37/HBAA-FCV-29053 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MIN | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100058257 | Isolation for cable is damaged. | Install Support | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 3 | 0 | W45-46 MPM | 2023-01-30 | 2023-01-31 | 2023-01-30 | 2022-06-26 | 2022-01-27 | 40 | REL | APPR OPND | HB /A /37/HBAA-FCV-29053 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MIN | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100058257 | Isolation for cable is damaged. | Install Cablie splicing | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 1 | 0 | W45-46 MPM | 2023-01-30 | 2023-01-31 | 2023-01-30 | 2022-06-26 | 2022-01-27 | 50 | REL | APPR OPND | HB /A /37/HBAA-FCV-29053 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MIN | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100058257 | Isolation for cable is damaged. | Deisolate and test Control Valve / Re-in | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 1 | 0 | W45-46 MPM | 2023-01-30 | 2023-01-31 | 2023-01-30 | 2022-06-26 | 2022-01-27 | 70 | REL | APPR OPND | HB /A /37/HBAA-FCV-29053 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MIN | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100058257 | Isolation for cable is damaged. | Dismantle scaffold | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 4 | 0 | W45-46 MPM | 2023-01-30 | 2023-01-31 | 2023-01-30 | 2022-06-26 | 2022-01-27 | 80 | REL | APPR OPND | HB /A /37/HBAA-FCV-29053 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MIN | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100058257 | Isolation for cable is damaged. | Additional materials | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-01-30 | 2023-01-31 | 2023-01-30 | 2022-06-26 | 2022-01-27 | 90 | REL | APPR OPND | HB /A /37/HBAA-FCV-29053 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MIN | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100059471 | Replace temperature switch on HBDC-TN-18 | Isolate HBDC-TN-1856 | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W37-38 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2022-11-21 | 2022-03-26 | 10 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059471 | Replace temperature switch on HBDC-TN-18 | De-mount silica gel vessel for paint | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W37-38 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2022-11-21 | 2022-03-26 | 20 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100059471 | Replace temperature switch on HBDC-TN-18 | Bristle blast + paint vessel in workshop | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 5 | 0 | W37-38 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2022-11-21 | 2022-03-26 | 30 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059471 | Replace temperature switch on HBDC-TN-18 | Replace Temperature switch | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | W37-38 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2022-11-21 | 2022-03-26 | 40 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059471 | Replace temperature switch on HBDC-TN-18 | Install painted silica gel vessel | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W37-38 | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2022-11-21 | 2022-03-26 | 50 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100059471 | Replace temperature switch on HBDC-TN-18 | De-Isolate above | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W37-38 | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2022-11-21 | 2022-03-26 | 60 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100059472 | Replace temperature switch on HBDC-TN-18 | Isolate HBDC-TN-1857 | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 3 | 0 | W37-38 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2022-11-21 | 2022-03-26 | 10 | REL | APPR OPND | HB /D /61/HBDC-TN-1857 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100059472 | Replace temperature switch on HBDC-TN-18 | De-mount silica gel vessel for paint | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 2 | 0 | W37-38 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2022-11-21 | 2022-03-26 | 20 | REL | APPR OPND | HB /D /61/HBDC-TN-1857 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100059472 | Replace temperature switch on HBDC-TN-18 | Bristle blast + paint vessel in workshop | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 5 | 0 | W37-38 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2022-11-21 | 2022-03-26 | 30 | REL | APPR OPND | HB /D /61/HBDC-TN-1857 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100059472 | Replace temperature switch on HBDC-TN-18 | Replace Temperature switch | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 6 | 0 | W37-38 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2022-11-21 | 2022-03-26 | 40 | REL | APPR OPND | HB /D /61/HBDC-TN-1857 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100059472 | Replace temperature switch on HBDC-TN-18 | Replace pressure relief switch | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 4 | 0 | W37-38 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2022-11-21 | 2022-03-26 | 50 | REL | APPR OPND | HB /D /61/HBDC-TN-1857 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100059472 | Replace temperature switch on HBDC-TN-18 | Install painted silica gel vessel | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 2 | 0 | W37-38 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2022-11-21 | 2022-03-26 | 60 | REL | APPR OPND | HB /D /61/HBDC-TN-1857 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2024-W37-38 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100059472 | Replace temperature switch on HBDC-TN-18 | De-Isolate above | REL GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 2 | 0 | W37-38 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2022-11-21 | 2022-03-26 | 70 | REL | APPR OPND | HB /D /61/HBDC-TN-1857 | 11/3KV POWER TRANSFORMER |  | E |  | MEL | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | PRODTECH | 2100059577 | HBDB-HCV-535517 Intern leak on cooler ou | Isolate and depressurize system | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | Opertunity | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2022-03-28 | 2021-12-28 | 10 | REL | APPR OPND | HB /D /76/HBDB-HCV-535517 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-RIGG | 2100059577 | HBDB-HCV-535517 Intern leak on cooler ou | Prepare for rigging out the valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | Opertunity | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-03-28 | 2021-12-28 | 20 | REL | APPR OPND | HB /D /76/HBDB-HCV-535517 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-MECH | 2100059577 | HBDB-HCV-535517 Intern leak on cooler ou | Dismantle passing butterfly valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | Opertunity | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-03-28 | 2021-12-28 | 30 | REL | APPR OPND | HB /D /76/HBDB-HCV-535517 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-RIGG | 2100059577 | HBDB-HCV-535517 Intern leak on cooler ou | Rig-out passing valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1.5 | 0 | Opertunity | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-03-28 | 2021-12-28 | 40 | REL | APPR OPND | HB /D /76/HBDB-HCV-535517 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-RIGG | 2100059577 | HBDB-HCV-535517 Intern leak on cooler ou | Rig-in new valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1.5 | 0 | Opertunity | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-03-28 | 2021-12-28 | 50 | REL | APPR OPND | HB /D /76/HBDB-HCV-535517 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-MECH | 2100059577 | HBDB-HCV-535517 Intern leak on cooler ou | Mount new valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | Opertunity | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2022-03-28 | 2021-12-28 | 60 | REL | APPR OPND | HB /D /76/HBDB-HCV-535517 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | PRODTECH | 2100059577 | HBDB-HCV-535517 Intern leak on cooler ou | De-isolate, pressurize system and test f | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | Opertunity | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2022-03-28 | 2021-12-28 | 70 | REL | APPR OPND | HB /D /76/HBDB-HCV-535517 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2024-W21-22 | 3 | HB-FLARE | WDF | MTN-ROPE | MTN-ROPE | 2100059932 | Dripping gasket HCV-038068 | prep rigging equipment - MPM | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | MPM Team W21-22 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-04-06 | 2022-01-06 | 10 | REL | APPR OPND | HB /D /01/HBDB-HCV-038068 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50 |  |  | 2024-06-02
2024-W21-22 | 3 | HB-FLARE | WDF | MTN-ROPE | PRODTECH | 2100059932 | Dripping gasket HCV-038068 | ICC | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | MPM Team W21-22 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-04-06 | 2022-01-06 | 20 | REL | APPR OPND | HB /D /01/HBDB-HCV-038068 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50 |  |  | 2024-06-04
2024-W21-22 | 3 | HB-FLARE | WDF | MTN-ROPE | MTN-ROPE | 2100059932 | Dripping gasket HCV-038068 | Replace gasktes- MPM | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | MPM Team W21-22 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-04-06 | 2022-01-06 | 30 | REL | APPR OPND | HB /D /01/HBDB-HCV-038068 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50 |  |  | 2024-06-06
2024-W21-22 | 3 | HB-FLARE | WDF | MTN-ROPE | MTN-ROPE | 2100059932 | Dripping gasket HCV-038068 | assist - MPM | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | MPM Team W21-22 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-04-06 | 2022-01-06 | 40 | REL | APPR OPND | HB /D /01/HBDB-HCV-038068 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50 |  |  | 2024-06-08
2024-W21-22 | 3 | HB-FLARE | WDF | MTN-ROPE | PRODTECH | 2100059932 | Dripping gasket HCV-038068 | De-isolate, leak test | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | MPM Team W21-22 | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2022-04-06 | 2022-01-06 | 50 | REL | APPR OPND | HB /D /01/HBDB-HCV-038068 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50 |  |  | 2024-06-10
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100062303 | HBDC-HCV-445101-U Internal leaking | Prepare for rigging out the valve | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-09-21 | 2022-04-24 | 10 | REL | APPR OPND | HB /D /32/HBDC-HCV-445101-U | HCV UPSTREAM ESDV-445101 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100062303 | HBDC-HCV-445101-U Internal leaking | Isolate and depressurize system | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-09-21 | 2022-04-24 | 20 | REL | APPR OPND | HB /D /32/HBDC-HCV-445101-U | HCV UPSTREAM ESDV-445101 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100062303 | HBDC-HCV-445101-U Internal leaking | Dismantle passing ball valve | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-09-21 | 2022-04-24 | 30 | REL | APPR OPND | HB /D /32/HBDC-HCV-445101-U | HCV UPSTREAM ESDV-445101 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100062303 | HBDC-HCV-445101-U Internal leaking | Rigging out old valve - approx. 80 kg | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-09-21 | 2022-04-24 | 40 | REL | APPR OPND | HB /D /32/HBDC-HCV-445101-U | HCV UPSTREAM ESDV-445101 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100062303 | HBDC-HCV-445101-U Internal leaking | Rigging in new valve | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-09-21 | 2022-04-24 | 50 | REL | APPR OPND | HB /D /32/HBDC-HCV-445101-U | HCV UPSTREAM ESDV-445101 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100062303 | HBDC-HCV-445101-U Internal leaking | Install new valve | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-09-21 | 2022-04-24 | 60 | REL | APPR OPND | HB /D /32/HBDC-HCV-445101-U | HCV UPSTREAM ESDV-445101 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100062303 | HBDC-HCV-445101-U Internal leaking | Pressurize system and test for leakages | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2022-09-21 | 2022-04-24 | 70 | REL | APPR OPND | HB /D /32/HBDC-HCV-445101-U | HCV UPSTREAM ESDV-445101 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100062303 | HBDC-HCV-445101-U Internal leaking | Remove rigging gear | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2022-09-21 | 2022-04-24 | 80 | REL | APPR OPND | HB /D /32/HBDC-HCV-445101-U | HCV UPSTREAM ESDV-445101 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100064482 | Replace DGPT2 relay on TN-1859 | Isolate transformer TN-1859 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-11-06 | 2022-03-11 | 10 | REL | APPR OPND | HB /D /61/HBDC-TN-1859 | 11/0.71 KV POWER TRANSFORMER |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064482 | Replace DGPT2 relay on TN-1859 | Replace DGPT2 according to attached VDM | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 9 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-11-06 | 2022-03-11 | 20 | REL | APPR OPND | HB /D /61/HBDC-TN-1859 | 11/0.71 KV POWER TRANSFORMER |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064482 | Replace DGPT2 relay on TN-1859 | Assist to Vendor | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 9 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-11-06 | 2022-03-11 | 30 | REL | APPR OPND | HB /D /61/HBDC-TN-1859 | 11/0.71 KV POWER TRANSFORMER |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100064482 | Replace DGPT2 relay on TN-1859 | De-Isolate above | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2022-11-06 | 2022-03-11 | 40 | REL | APPR OPND | HB /D /61/HBDC-TN-1859 | 11/0.71 KV POWER TRANSFORMER |  | C |  | MEL | DK50
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100065605 | Defect protection relay BUS-TIE BREAKER | Isolate accordingly | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W37-38 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2022-07-15 | 2022-04-16 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A09-BA | BUS-TIE BREAKER ACB-82 |  | C |  | MEL | DK50
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100065605 | Defect protection relay BUS-TIE BREAKER | Change of defect protection relay | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W37-38 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2022-07-15 | 2022-04-16 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A09-BA | BUS-TIE BREAKER ACB-82 |  | C |  | MEL | DK50
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100065605 | Defect protection relay BUS-TIE BREAKER | De-isolate accordingly and test | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W37-38 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2022-07-15 | 2022-04-16 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A09-BA | BUS-TIE BREAKER ACB-82 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100065606 | Change def. pos. indicator HBDD-DP-1960- | Isolate accordingly | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2022-07-15 | 2022-04-16 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A04-01 | BUS-COUPLER A-C |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100065606 | Change def. pos. indicator HBDD-DP-1960- | Change of defect position indicator | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2022-07-15 | 2022-04-16 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A04-01 | BUS-COUPLER A-C |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100065606 | Change def. pos. indicator HBDD-DP-1960- | De-isolate accordingly and test | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2022-07-15 | 2022-04-16 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A04-01 | BUS-COUPLER A-C |  | C |  | MEL | DK50 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100065794 | Change lightfixtures CCR. | Isolate accordingly and prove dead | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-05-23 | 2022-04-13 | 10 | REL | APPR OPND | HD /B /06/HDBE-DP-1924-12 | LIGHTING MONITOR RM (3-06) LEVEL 3 |  | C |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100065794 | Change lightfixtures CCR. | Change light fixtures | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 5 | 0 | W45-46 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-05-23 | 2022-04-13 | 20 | REL | APPR OPND | HD /B /06/HDBE-DP-1924-12 | LIGHTING MONITOR RM (3-06) LEVEL 3 |  | C |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100065794 | Change lightfixtures CCR. | De-isolate accordingly and test | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2022-05-23 | 2022-04-13 | 30 | REL | APPR OPND | HD /B /06/HDBE-DP-1924-12 | LIGHTING MONITOR RM (3-06) LEVEL 3 |  | C |  | MEL | DK60 |  | PROK
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100067584 | Replace DGPT2 relay on TN-1858. | Isolate transformer TN-1858 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2023-04-20 | 2022-08-23 | 10 | REL | APPR OPND | HB /D /61/HBDC-TN-1858 | 11/3KV POWER TRANSFORMER |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067584 | Replace DGPT2 relay on TN-1858. | Replace DGPT2 according to attached VDM | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 9 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2023-04-20 | 2022-08-23 | 20 | REL | APPR OPND | HB /D /61/HBDC-TN-1858 | 11/3KV POWER TRANSFORMER |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067584 | Replace DGPT2 relay on TN-1858. | Assist to Vendor | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 9 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2023-04-20 | 2022-08-23 | 30 | REL | APPR OPND | HB /D /61/HBDC-TN-1858 | 11/3KV POWER TRANSFORMER |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100067584 | Replace DGPT2 relay on TN-1858. | De-Isolate above | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2023-04-20 | 2022-08-23 | 40 | REL | APPR OPND | HB /D /61/HBDC-TN-1858 | 11/3KV POWER TRANSFORMER |  | C |  | MEL | DK50
2024-W19-20 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100069199 | Flange Face Corrosion HBCM-A-1235/ 1264 | Isolate Electrical 1235 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-06-30 | 2022-09-26 | 20 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50 |  |  | 2024-05-06
2024-W19-20 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100069199 | Flange Face Corrosion HBCM-A-1235/ 1264 | Isolate Mechanically 1235 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-06-30 | 2022-09-26 | 30 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50 |  |  | 2024-05-07
2024-W19-20 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100069199 | Flange Face Corrosion HBCM-A-1235/ 1264 | Drain water 1235 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-06-30 | 2022-09-26 | 40 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50 |  |  | 2024-05-08
2024-W19-20 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100069199 | Flange Face Corrosion HBCM-A-1235/ 1264 | Demount ends 1235 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-06-30 | 2022-09-26 | 50 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50 |  |  | 2024-05-09
2024-W19-20 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100069199 | Flange Face Corrosion HBCM-A-1235/ 1264 | Clean condenser 1235 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-06-30 | 2022-09-26 | 60 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50 |  |  | 2024-05-10
2024-W19-20 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100069199 | Flange Face Corrosion HBCM-A-1235/ 1264 | Mount end caps with new blind end 1235 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-06-30 | 2022-09-26 | 70 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50 |  |  | 2024-05-11
2024-W19-20 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100069199 | Flange Face Corrosion HBCM-A-1235/ 1264 | De-isolate mechanically 1235 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-06-30 | 2022-09-26 | 80 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50 |  |  | 2024-05-12
2024-W19-20 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100069199 | Flange Face Corrosion HBCM-A-1235/ 1264 | De-isolate Electrical 1235 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-06-30 | 2022-09-26 | 90 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50 |  |  | 2024-05-13
2024-W19-20 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100069199 | Flange Face Corrosion HBCM-A-1235/ 1264 | Test 1235 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-06-30 | 2022-09-26 | 100 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50 |  |  | 2024-05-14
2024-W51-52 | 3 | HBA23-GL | WDF | MTN-MECH | PRODTECH | 2100071676 | Weep from HBA23 choke tell hole | Isolation by Production | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W51-52 | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2023-01-12 | 2022-08-30 | 10 | REL | APPR OPND | HB /A /10/HBAA-CVA-30236 | CHOKE VALVE |  | A |  | MMS | DK50
2024-W51-52 | 3 | HBA23-GL | WDF | MTN-MECH | MTN-MECH | 2100071676 | Weep from HBA23 choke tell hole | Remove Sealing Rings | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W51-52 | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2023-01-12 | 2022-08-30 | 20 | REL | APPR OPND | HB /A /10/HBAA-CVA-30236 | CHOKE VALVE |  | A |  | MMS | DK50
2024-W51-52 | 3 | HBA23-GL | WDF | MTN-MECH | MTN-MECH | 2100071676 | Weep from HBA23 choke tell hole | Mount New Sealing Rings | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W51-52 | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2023-01-12 | 2022-08-30 | 30 | REL | APPR OPND | HB /A /10/HBAA-CVA-30236 | CHOKE VALVE |  | A |  | MMS | DK50
2024-W51-52 | 3 | HBA23-GL | WDF | MTN-MECH | PRODTECH | 2100071676 | Weep from HBA23 choke tell hole | Deisolate and test Run | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W51-52 | 2024-03-28 | 2024-03-29 | 2024-03-29 | 2023-01-12 | 2022-08-30 | 40 | REL | APPR OPND | HB /A /10/HBAA-CVA-30236 | CHOKE VALVE |  | A |  | MMS | DK50
2024-W45-46 | 2 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100072052 | Cable and light is blocking for the WTW | Pull new cables | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 36 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2022-09-10 | 2022-07-27 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-09 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50
2024-W45-46 | 2 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100072052 | Cable and light is blocking for the WTW | Pull new cables - overboard work | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 36 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2022-09-10 | 2022-07-27 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-09 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50
2024-W45-46 | 2 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100072052 | Cable and light is blocking for the WTW | Tie wrap cables | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 36 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-17 | 2022-09-10 | 2022-07-27 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-09 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50
2024-W45-46 | 2 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100072052 | Cable and light is blocking for the WTW | Isolate and prove dead | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2022-09-10 | 2022-07-27 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-09 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50
2024-W45-46 | 2 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100072052 | Cable and light is blocking for the WTW | Change over of cables in lights | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 24 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2022-09-10 | 2022-07-27 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-09 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50
2024-W45-46 | 2 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100072052 | Cable and light is blocking for the WTW | De-Isolate above and test | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2022-09-10 | 2022-07-27 | 60 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-09 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50
2024-W45-46 | 2 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100072052 | Cable and light is blocking for the WTW | Remove old cables | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 36 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2022-09-10 | 2022-07-27 | 70 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-09 | EMERG. LIGHTING ESCAPE ROUTE LEVEL 1 |  | C |  | MEL | DK50
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072443 | Change Transduces N-1852 | Program transducers | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 5 | 0 | W49-50 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2023-01-31 | 2022-09-18 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | A |  | MEL | DK50
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072443 | Change Transduces N-1852 | open signals for transducer signals | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2023-01-31 | 2022-09-18 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | A |  | MEL | DK50
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072443 | Change Transduces N-1852 | Change transducers | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 0 | W49-50 | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2023-01-31 | 2022-09-18 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | A |  | MEL | DK50
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072443 | Change Transduces N-1852 | Remove inhibit for transducer signals | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2023-01-31 | 2022-09-18 | 40 | REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | A |  | MEL | DK50
2024-W33-34 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072444 | Defect Semaphore N-1852-M15 | Isolate and prove dead | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W33-34 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2023-01-31 | 2022-09-18 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M15 | SPARE MOTOR FEEDER |  | C |  | MEL | DK50
2024-W33-34 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100072444 | Defect Semaphore N-1852-M15 | Change earth indicator lamp | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W33-34 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2023-01-31 | 2022-09-18 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M15 | SPARE MOTOR FEEDER |  | C |  | MEL | DK50
2024-W33-34 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072444 | Defect Semaphore N-1852-M15 | De-Isolate above and test | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W33-34 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2023-01-31 | 2022-09-18 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M15 | SPARE MOTOR FEEDER |  | C |  | MEL | DK50
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100074146 | DEIF display module out of order | Add. spares | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-03 | 2022-10-19 | 50 | PCNF REL | APPR OPND | HB /D /61/HBDC-CP-1890 | POWER MANAGEMENT SYSTEM CONTROL PANEL |  | A |  | MEL | DK50 |  |  | 2024-04-20
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100074436 | HCV-435101-U is internally leaking | Isolation of valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-03-10 | 2022-10-26 | 10 | REL | APPR OPND | HB /D /32/HBDC-HCV-435101-U | HCV UPSTREAM PSV-435101 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100074436 | HCV-435101-U is internally leaking | Rigging assist removal of valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2023-03-10 | 2022-10-26 | 20 | REL | APPR OPND | HB /D /32/HBDC-HCV-435101-U | HCV UPSTREAM PSV-435101 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100074436 | HCV-435101-U is internally leaking | Dismantle of valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-03-10 | 2022-10-26 | 30 | REL | APPR OPND | HB /D /32/HBDC-HCV-435101-U | HCV UPSTREAM PSV-435101 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100074436 | HCV-435101-U is internally leaking | Rigging assist install new valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2023-03-10 | 2022-10-26 | 40 | REL | APPR OPND | HB /D /32/HBDC-HCV-435101-U | HCV UPSTREAM PSV-435101 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100074436 | HCV-435101-U is internally leaking | Install new valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-03-10 | 2022-10-26 | 50 | REL | APPR OPND | HB /D /32/HBDC-HCV-435101-U | HCV UPSTREAM PSV-435101 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100074436 | HCV-435101-U is internally leaking | de-isolation and leak test | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2023-03-10 | 2022-10-26 | 60 | REL | APPR OPND | HB /D /32/HBDC-HCV-435101-U | HCV UPSTREAM PSV-435101 |  | A |  | MMS | DK50
2024-W35-36 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075205 | Breaker Manual device broken N-1851-K14 | Isolate and prove dead | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0.5 | 0 | W35-36 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2025-09-07 | 2023-03-22 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K14 | SPARE VCB FEEDER |  | A |  | MEL | DK50 |  | PROK
2024-W35-36 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075205 | Breaker Manual device broken N-1851-K14 | Change charging lever | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W35-36 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2025-09-07 | 2023-03-22 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K14 | SPARE VCB FEEDER |  | A |  | MEL | DK50 |  | PROK
2024-W35-36 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075205 | Breaker Manual device broken N-1851-K14 | De-Isolate above and test | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0.5 | 0 | W35-36 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2025-09-07 | 2023-03-22 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K14 | SPARE VCB FEEDER |  | A |  | MEL | DK50 |  | PROK
2024-W35-36 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100075351 | Defect earth fault relay N-1854 | Isolate and prove dead | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W35-36 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2025-09-12 | 2023-03-27 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B12-LB | SPARE |  | C |  | MEL | DK50
2024-W35-36 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075351 | Defect earth fault relay N-1854 | Change earth fault relay | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W35-36 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2025-09-12 | 2023-03-27 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B12-LB | SPARE |  | C |  | MEL | DK50
2024-W35-36 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100075351 | Defect earth fault relay N-1854 | De-Isolate above and test | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W35-36 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2025-09-12 | 2023-03-27 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B12-LB | SPARE |  | C |  | MEL | DK50
2026-W13-14 | 3 | HB-DIFF | WDF | MTN-ELEC | MTN-ELEC | 2100076140 | No power for BM HBAA-BM-1210 Q4 | Isolate Q4. See attached wiring diagram | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | 24-W05-06 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2023-04-06 | 2022-11-22 | 10 | REL | APPR OPND | HB /A /61/HBAA-N-1801-Q04 | VENT FAN BM-1210 |  | C |  | MEL | DK50
2026-W13-14 | 3 | HB-DIFF | WDF | MTN-ELEC | MTN-ELEC | 2100076140 | No power for BM HBAA-BM-1210 Q4 | Replace Q4 | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | 24-W05-06 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2023-04-06 | 2022-11-22 | 20 | REL | APPR OPND | HB /A /61/HBAA-N-1801-Q04 | VENT FAN BM-1210 |  | C |  | MEL | DK50
2026-W13-14 | 3 | HB-DIFF | WDF | MTN-ELEC | MTN-ELEC | 2100076140 | No power for BM HBAA-BM-1210 Q4 | De-Isolate and test | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | 24-W05-06 | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2023-04-06 | 2022-11-22 | 30 | REL | APPR OPND | HB /A /61/HBAA-N-1801-Q04 | VENT FAN BM-1210 |  | C |  | MEL | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100076241 | HCV upstream PSV-445101 internal leak | Isolation of valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-09-27 | 2023-04-11 | 10 | REL | APPR OPND | HB /D /32/HBDC-HCV-445101-V1 | V-4451 TO HP FLARE U/S PSV-445101 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100076241 | HCV upstream PSV-445101 internal leak | Dismantle of valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-09-27 | 2023-04-11 | 20 | REL | APPR OPND | HB /D /32/HBDC-HCV-445101-V1 | V-4451 TO HP FLARE U/S PSV-445101 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100076241 | HCV upstream PSV-445101 internal leak | Install new valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-09-27 | 2023-04-11 | 30 | REL | APPR OPND | HB /D /32/HBDC-HCV-445101-V1 | V-4451 TO HP FLARE U/S PSV-445101 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100076241 | HCV upstream PSV-445101 internal leak | de-isolation and leak test | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-09-27 | 2023-04-11 | 40 | REL | APPR OPND | HB /D /32/HBDC-HCV-445101-V1 | V-4451 TO HP FLARE U/S PSV-445101 |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076870 | Change of defect undervoltage relay N-18 | Isolate and prove dead | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0.5 | 0 | W04 Caverion | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-04-23 | 2022-12-09 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B02-CA | SAND BLAST.WS SUPP.THY.CP HBDE-UCP-12422 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100076870 | Change of defect undervoltage relay N-18 | Change of defect undervoltage relay | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W04 Caverion | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-04-23 | 2022-12-09 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B02-CA | SAND BLAST.WS SUPP.THY.CP HBDE-UCP-12422 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076870 | Change of defect undervoltage relay N-18 | De-Isolate and test | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0.5 | 0 | W04 Caverion | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2023-04-23 | 2022-12-09 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B02-CA | SAND BLAST.WS SUPP.THY.CP HBDE-UCP-12422 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100077668 | Change of defect contactor HBCA-N-1810-4 | Isolate and prove dead | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0.5 | 0 | W03 Caverion | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-05-07 | 2022-12-23 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-4-1A | SPARE |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100077668 | Change of defect contactor HBCA-N-1810-4 | Change of defect contactor | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W03 Caverion | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-05-07 | 2022-12-23 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-4-1A | SPARE |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100077668 | Change of defect contactor HBCA-N-1810-4 | De-Isolate and test | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0.5 | 0 | W03 Caverion | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2023-05-07 | 2022-12-23 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-4-1A | SPARE |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100078304 | XCV-536553 doesn't close | Rigging Prework | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 8 | 0 | W07-W08 | 2024-09-18 | 2024-09-23 | 2024-09-18 | 2023-05-19 | 2023-01-04 | 10 | REL | APPR OPND | HB /D /51/HBDB-XCV-536553 | ON OFF VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078304 | XCV-536553 doesn't close | Production isolation | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W07-W08 | 2024-09-18 | 2024-09-23 | 2024-09-19 | 2023-05-19 | 2023-01-04 | 20 | REL | APPR OPND | HB /D /51/HBDB-XCV-536553 | ON OFF VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100078304 | XCV-536553 doesn't close | Rigger assistance | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W07-W08 | 2024-09-18 | 2024-09-23 | 2024-09-19 | 2023-05-19 | 2023-01-04 | 30 | REL | APPR OPND | HB /D /51/HBDB-XCV-536553 | ON OFF VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078304 | XCV-536553 doesn't close | Replace XCV valve/reuse Actuator | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 10 | 0 | W07-W08 | 2024-09-18 | 2024-09-23 | 2024-09-20 | 2023-05-19 | 2023-01-04 | 40 | REL | APPR OPND | HB /D /51/HBDB-XCV-536553 | ON OFF VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078304 | XCV-536553 doesn't close | Production deisolation | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W07-W08 | 2024-09-18 | 2024-09-23 | 2024-09-21 | 2023-05-19 | 2023-01-04 | 50 | REL | APPR OPND | HB /D /51/HBDB-XCV-536553 | ON OFF VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100078304 | XCV-536553 doesn't close | Rigging Postwork | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 8 | 0 | W07-W08 | 2024-09-18 | 2024-09-23 | 2024-09-22 | 2023-05-19 | 2023-01-04 | 60 | REL | APPR OPND | HB /D /51/HBDB-XCV-536553 | ON OFF VALVE |  | C |  | MMS | DK50
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078492 | HDB Bunkerhose for potwater | Install bunker hose | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W39-40 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2023-05-14 | 2022-12-30 | 10 | PCNF REL | APPR OPND | HD /B /85 | SOFT WATER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100078492 | HDB Bunkerhose for potwater | Ass. Installation | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W39-40 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2023-05-14 | 2022-12-30 | 20 | PCNF REL | APPR OPND | HD /B /85 | SOFT WATER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078492 | HDB Bunkerhose for potwater | Deisolate bunker hose | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W39-40 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2023-05-14 | 2022-12-30 | 30 | PCNF REL | APPR OPND | HD /B /85 | SOFT WATER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078492 | HDB Bunkerhose for potwater | Report back to SR | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W39-40 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2023-05-14 | 2022-12-30 | 40 | PCNF REL | APPR OPND | HD /B /85 | SOFT WATER |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078495 | Panel handel is broken HDBD-BCP-1751 | open panel door | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W19-W20 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2025-11-09 | 2023-05-24 | 10 | REL | APPR OPND | HD /B /05/HDBD-BCP-1751 | BATTERY CONTROL PANEL |  | A |  | MEL | DK60
0 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078495 | Panel handel is broken HDBD-BCP-1751 | change door handle | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W19-W20 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2025-11-09 | 2023-05-24 | 20 | REL | APPR OPND | HD /B /05/HDBD-BCP-1751 | BATTERY CONTROL PANEL |  | A |  | MEL | DK60
2024-W15-16 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100079926 | Small seeps on inst. pipes in HPU 5929 | Isolate hydraulic line | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-07-30 | 2024-08-03 | 2024-07-30 | 2025-12-06 | 2023-06-20 | 10 | REL | APPR OPND | HB /B /07/HBBA-A-5929 | HYDRAULIC POWER PACKAGE |  | C |  | MIN | DK50 |  |  | 2024-04-08
2024-W15-16 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100079926 | Small seeps on inst. pipes in HPU 5929 | Remove Pipe element | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 5 | 0 |  | 2024-07-30 | 2024-08-03 | 2024-07-30 | 2025-12-06 | 2023-06-20 | 20 | REL | APPR OPND | HB /B /07/HBBA-A-5929 | HYDRAULIC POWER PACKAGE |  | C |  | MIN | DK50 |  |  | 2024-04-09
2024-W15-16 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100079926 | Small seeps on inst. pipes in HPU 5929 | Re-install Pipe element | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 5 | 0 |  | 2024-07-30 | 2024-08-03 | 2024-08-02 | 2025-12-06 | 2023-06-20 | 30 | REL | APPR OPND | HB /B /07/HBBA-A-5929 | HYDRAULIC POWER PACKAGE |  | C |  | MIN | DK50 |  |  | 2024-04-10
2024-W15-16 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100079926 | Small seeps on inst. pipes in HPU 5929 | De-isolate Pipe element | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1.5 | 0 |  | 2024-07-30 | 2024-08-03 | 2024-08-03 | 2025-12-06 | 2023-06-20 | 40 | REL | APPR OPND | HB /B /07/HBBA-A-5929 | HYDRAULIC POWER PACKAGE |  | C |  | MIN | DK50 |  |  | 2024-04-11
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080528 | XCV on seawater filter will not close | Troubleshooting Valve/Actuator | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 6 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-17 | 2023-07-04 | 2023-02-19 | 10 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536455 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100080528 | XCV on seawater filter will not close | Troubleshooting Valve indication | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-17 | 2023-07-04 | 2023-02-19 | 20 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536455 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100080528 | XCV on seawater filter will not close | Production assistance | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-17 | 2023-07-04 | 2023-02-19 | 30 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536455 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100080528 | XCV on seawater filter will not close | Production assistance safing hydraulic | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-17 | 2023-07-04 | 2023-02-19 | 40 | REL | APPR OPND | HB /D /51/HBDB-XCV-536455 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080528 | XCV on seawater filter will not close | Replace actuator | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 8 | 0 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-17 | 2023-07-04 | 2023-02-19 | 50 | REL | APPR OPND | HB /D /51/HBDB-XCV-536455 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100080528 | XCV on seawater filter will not close | De-safe and function test | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-19 | 2023-07-04 | 2023-02-19 | 60 | REL | APPR OPND | HB /D /51/HBDB-XCV-536455 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080805 | XCV-536454 can't close | Troubleshooting Valve/Actuator | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 6 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-17 | 2023-07-05 | 2023-02-20 | 10 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536454 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080805 | XCV-536454 can't close | Troubleshooting Valve indication | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-17 | 2023-07-05 | 2023-02-20 | 20 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536454 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080805 | XCV-536454 can't close | Production assistance | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-17 | 2023-07-05 | 2023-02-20 | 30 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536454 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100080805 | XCV-536454 can't close | Production assistance safing hydraulic | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-17 | 2023-07-05 | 2023-02-20 | 40 | REL | APPR OPND | HB /D /51/HBDB-XCV-536454 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080805 | XCV-536454 can't close | Replace actuator | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-17 | 2023-07-05 | 2023-02-20 | 50 | REL | APPR OPND | HB /D /51/HBDB-XCV-536454 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100080805 | XCV-536454 can't close | De-safe and function test | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-18 | 2023-07-05 | 2023-02-20 | 60 | REL | APPR OPND | HB /D /51/HBDB-XCV-536454 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100086078 | HBA-27 flowline 3/4" drain valve blocked | HBA-27 flowline 3/4" drain valve blocked | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W09-W10 | 2024-09-03 | 2024-09-05 | 2024-09-03 | 2023-08-17 | 2023-04-04 | 10 | REL | APPR OPND | HB /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL-VALVES |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100086078 | HBA-27 flowline 3/4" drain valve blocked | ISOLATE XCV-30278 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W09-W10 | 2024-09-03 | 2024-09-05 | 2024-09-03 | 2023-08-17 | 2023-04-04 | 20 | REL | APPR OPND | HB /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL-VALVES |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100086078 | HBA-27 flowline 3/4" drain valve blocked | Dismantle valve 3/4"DRAIN VALVE | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W09-W10 | 2024-09-03 | 2024-09-05 | 2024-09-03 | 2023-08-17 | 2023-04-04 | 30 | REL | APPR OPND | HB /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL-VALVES |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100086078 | HBA-27 flowline 3/4" drain valve blocked | INSTALL 3/4" DRAIN VALVE | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W09-W10 | 2024-09-03 | 2024-09-05 | 2024-09-04 | 2023-08-17 | 2023-04-04 | 40 | REL | APPR OPND | HB /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL-VALVES |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100086078 | HBA-27 flowline 3/4" drain valve blocked | De-isolate | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W09-W10 | 2024-09-03 | 2024-09-05 | 2024-09-04 | 2023-08-17 | 2023-04-04 | 50 | REL | APPR OPND | HB /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL-VALVES |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100086078 | HBA-27 flowline 3/4" drain valve blocked | Materials | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W09-W10 | 2024-09-03 | 2024-09-05 | 2024-09-05 | 2023-08-17 | 2023-04-04 | 60 | REL | APPR OPND | HB /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL-VALVES |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-INST | PRODTECH | 2100086360 | Seep from SDBB on HCV-445302B-I | Process Isolation | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2023-08-23 | 2023-04-10 | 10 | REL | APPR OPND | HB /D /31/HBDC-HCV-445302B-I | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-INST | MTN-INST | 2100086360 | Seep from SDBB on HCV-445302B-I | Isolate Pressure transmitter | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0.5 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2023-08-23 | 2023-04-10 | 20 | REL | APPR OPND | HB /D /31/HBDC-HCV-445302B-I | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-INST | MTN-INST | 2100086360 | Seep from SDBB on HCV-445302B-I | Replace SDBB valve for Pressure transmit | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2023-08-23 | 2023-04-10 | 40 | REL | APPR OPND | HB /D /31/HBDC-HCV-445302B-I | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-INST | MTN-INST | 2100086360 | Seep from SDBB on HCV-445302B-I | Deisolate and test Pressure transmitter | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2023-08-23 | 2023-04-10 | 50 | REL | APPR OPND | HB /D /31/HBDC-HCV-445302B-I | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-INST | MTN-RIGG | 2100086360 | Seep from SDBB on HCV-445302B-I | ERECT SCALFOLD | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2023-08-23 | 2023-04-10 | 70 | REL | APPR OPND | HB /D /31/HBDC-HCV-445302B-I | HAND CONTROL VALVE |  | A |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | PRODTECH | 2100088927 | Debris removal in HBA04 choke | Isolate system | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 20 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | MTN-MECH | 2100088927 | Debris removal in HBA04 choke | remove choke for cleaning | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 8 | 0 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 40 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | PRODTECH | 2100088927 | Debris removal in HBA04 choke | deisolate system | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 70 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | MTN-MECH | 2100088927 | Debris removal in HBA04 choke | Test and clean after completed work | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 80 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | MTN-RIGG | 2100088927 | Debris removal in HBA04 choke | Prepare Lifting equipment | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 6 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 100 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | MTN-MECH | 2100088927 | Debris removal in HBA04 choke | Prepare permit/tools/matr | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 8 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 110 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | PRODTECH | 2100088927 | Debris removal in HBA04 choke | Prod prepare permit/isolation | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 120 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | MTN-RIGG | 2100088927 | Debris removal in HBA04 choke | Rigger assistance | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 8 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 130 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | MTN-MECH | 2100088927 | Debris removal in HBA04 choke | Check valve removal | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 140 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | MTN-MECH | 2100088927 | Debris removal in HBA04 choke | New check valve installation | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 150 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | PRODTECH | 2100088927 | Debris removal in HBA04 choke | Prod deisolate w function/leak test | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 160 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | MTN-RIGG | 2100088927 | Debris removal in HBA04 choke | Rigging equipment removal | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 170 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2024-W47-48 | 3 | HBA04-WI | WDF | MTN-MECH | MTN-MECH | 2100088927 | Debris removal in HBA04 choke | Housekeeping | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W47-48 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2023-10-01 | 2023-05-19 | 180 | PCNF REL | APPR OPND | HB /A /55/HBAA-CVA-30046 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100091591 | Gas seep from grease nippel | Isolate and depressurize system. | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2023-11-24 | 2023-07-12 | 10 | REL | APPR OPND | HB /A /37/HBAA-HCV-29034 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100091591 | Gas seep from grease nippel | Demount HCV 3/4"Nipple | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2023-11-24 | 2023-07-12 | 20 | REL | APPR OPND | HB /A /37/HBAA-HCV-29034 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100091591 | Gas seep from grease nippel | Mount New HCV 3/4"Nipple | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2023-11-24 | 2023-07-12 | 30 | REL | APPR OPND | HB /A /37/HBAA-HCV-29034 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100091591 | Gas seep from grease nippel | Demount HCV Valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-09 | 2023-11-24 | 2023-07-12 | 40 | REL | APPR OPND | HB /A /37/HBAA-HCV-29034 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100095366 | HBA29 LG FCV stempacking to be replaced | Isolate and depressurize system. | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2023-09-13 | 2023-07-30 | 10 | REL | APPR OPND | HB /A /37/HBAA-FCV-29293 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100095366 | HBA29 LG FCV stempacking to be replaced | Replace Stem Packing | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2023-09-13 | 2023-07-30 | 20 | REL | APPR OPND | HB /A /37/HBAA-FCV-29293 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100095366 | HBA29 LG FCV stempacking to be replaced | Replace ZT O-ring | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2023-09-13 | 2023-07-30 | 30 | REL | APPR OPND | HB /A /37/HBAA-FCV-29293 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | HBALIFTG | WDF | MTN-MECH | MTN-INST | 2100095366 | HBA29 LG FCV stempacking to be replaced | Production deisolation w. function test | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2023-09-13 | 2023-07-30 | 40 | REL | APPR OPND | HB /A /37/HBAA-FCV-29293 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MMS | DK50 |  | PROK
2024-W49-50 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100100223 | Replace pump - heavy corroded | Prepare lifting Equipment | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-03-06 | 2023-10-23 | 10 | REL | APPR OPND | HB /D /85/HBDB-PM-1057 | POTABLE WATER PUMP MOTOR |  | A |  | MMS | DK50
2024-W49-50 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100100223 | Replace pump - heavy corroded | Isolation Of Valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-03-06 | 2023-10-23 | 20 | REL | APPR OPND | HB /D /85/HBDB-PM-1057 | POTABLE WATER PUMP MOTOR |  | A |  | MMS | DK50
2024-W49-50 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100100223 | Replace pump - heavy corroded | Dismantle pump and Accesories | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-03-06 | 2023-10-23 | 30 | REL | APPR OPND | HB /D /85/HBDB-PM-1057 | POTABLE WATER PUMP MOTOR |  | A |  | MMS | DK50
2024-W49-50 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100100223 | Replace pump - heavy corroded | Riggout pump | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-03-06 | 2023-10-23 | 40 | REL | APPR OPND | HB /D /85/HBDB-PM-1057 | POTABLE WATER PUMP MOTOR |  | A |  | MMS | DK50
2024-W49-50 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100100223 | Replace pump - heavy corroded | Rigg in New Pump | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-03-06 | 2023-10-23 | 50 | REL | APPR OPND | HB /D /85/HBDB-PM-1057 | POTABLE WATER PUMP MOTOR |  | A |  | MMS | DK50
2024-W49-50 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100100223 | Replace pump - heavy corroded | Mount New Pump | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-03-06 | 2023-10-23 | 60 | REL | APPR OPND | HB /D /85/HBDB-PM-1057 | POTABLE WATER PUMP MOTOR |  | A |  | MMS | DK50
2024-W49-50 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100100223 | Replace pump - heavy corroded | Deisolation | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-03-06 | 2023-10-23 | 70 | REL | APPR OPND | HB /D /85/HBDB-PM-1057 | POTABLE WATER PUMP MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100100871 | Air Valve for FD in CCR/Office | Air Valve for FD in CCR/Office | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-22 | 2024-02-09 | 2023-09-27 | 10 | REL | APPR OPND | HB /D /07 | INSTRUMENT AIR/GAS - HYDRAULIC POWER |  | A |  | MEL | DK50
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-SCAF | 2100100871 | Air Valve for FD in CCR/Office | Erect small scaffold | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-22 | 2024-02-09 | 2023-09-27 | 20 | REL | APPR OPND | HB /D /07 | INSTRUMENT AIR/GAS - HYDRAULIC POWER |  | A |  | MEL | DK50
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100100871 | Air Valve for FD in CCR/Office | Isolate | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-22 | 2024-02-09 | 2023-09-27 | 30 | REL | APPR OPND | HB /D /07 | INSTRUMENT AIR/GAS - HYDRAULIC POWER |  | A |  | MEL | DK50
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-MECH | 2100100871 | Air Valve for FD in CCR/Office | Replace valve | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-23 | 2024-02-09 | 2023-09-27 | 40 | REL | APPR OPND | HB /D /07 | INSTRUMENT AIR/GAS - HYDRAULIC POWER |  | A |  | MEL | DK50
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100100871 | Air Valve for FD in CCR/Office | De - Isolate | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-23 | 2024-02-09 | 2023-09-27 | 50 | REL | APPR OPND | HB /D /07 | INSTRUMENT AIR/GAS - HYDRAULIC POWER |  | A |  | MEL | DK50
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-MECH | 2100100871 | Air Valve for FD in CCR/Office | Test | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-24 | 2024-02-09 | 2023-09-27 | 60 | REL | APPR OPND | HB /D /07 | INSTRUMENT AIR/GAS - HYDRAULIC POWER |  | A |  | MEL | DK50
2026-W13-14 | 3 | NE | WDF | MTN-ELEC | MTN-SCAF | 2100100871 | Air Valve for FD in CCR/Office | Dismantle scaffold | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-24 | 2024-02-09 | 2023-09-27 | 70 | REL | APPR OPND | HB /D /07 | INSTRUMENT AIR/GAS - HYDRAULIC POWER |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100101432 | Replace FIL-1202 on HBC | Replace FIL-1202 on HBC | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-22 | 2024-04-29 | 2023-12-16 | 10 | REL | APPR OPND | HB /C /09/HBCM-FIL-1202 | ACCOMMODATION / UTILITY AIR INLET FILTER |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100101432 | Replace FIL-1202 on HBC | Build scaffold | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-22 | 2024-04-29 | 2023-12-16 | 20 | REL | APPR OPND | HB /C /09/HBCM-FIL-1202 | ACCOMMODATION / UTILITY AIR INLET FILTER |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100101432 | Replace FIL-1202 on HBC | Dismantling scaffolding | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-23 | 2024-04-29 | 2023-12-16 | 30 | REL | APPR OPND | HB /C /09/HBCM-FIL-1202 | ACCOMMODATION / UTILITY AIR INLET FILTER |  | A |  | MEL | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100104969 | Incorrect gaskets in anti fouling system | Incorrect gaskets in anti fouling system | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-22 | 2024-07-06 | 2024-02-22 | 10 | REL | APPR OPND | HB /C /52/HBCM-A-5233 | SEAWATER ANTI-FOULING UNIT |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100104969 | Incorrect gaskets in anti fouling system | Isolate | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-23 | 2024-07-06 | 2024-02-22 | 20 | REL | APPR OPND | HB /C /52/HBCM-A-5233 | SEAWATER ANTI-FOULING UNIT |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100104969 | Incorrect gaskets in anti fouling system | replace gaskets | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 8 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-23 | 2024-07-06 | 2024-02-22 | 30 | REL | APPR OPND | HB /C /52/HBCM-A-5233 | SEAWATER ANTI-FOULING UNIT |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100104969 | Incorrect gaskets in anti fouling system | deisolate | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-25 | 2024-04-24 | 2024-07-06 | 2024-02-22 | 40 | REL | APPR OPND | HB /C /52/HBCM-A-5233 | SEAWATER ANTI-FOULING UNIT |  | A |  | MMS | DK50
0 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105043 | HDB/78: Flush slew bearing w. grease. | Flush slew bearing w. grease 3xtupe | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W11-W12 | 2024-03-13 | 2024-05-31 | 2024-03-13 | 2024-02-24 | 2024-01-10 | 10 | PCNF REL | APPR OPND | HD /B /78/HDBR-A-6102-04 | SLEWING SYSTEM |  | A |  |  | DK60 |  | PROK
0 | 2 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100105043 | HDB/78: Flush slew bearing w. grease. | Ass. Flush slew bearing | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 2 | W11-W12 | 2024-03-13 | 2024-05-31 | 2024-03-13 | 2024-02-24 | 2024-01-10 | 20 | PCNF REL | APPR OPND | HD /B /78/HDBR-A-6102-04 | SLEWING SYSTEM |  | A |  |  | DK60 |  | PROK
0 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105043 | HDB/78: Flush slew bearing w. grease. | Grease sample | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W11-W12 | 2024-03-13 | 2024-05-31 | 2024-05-31 | 2024-02-24 | 2024-01-10 | 30 | REL | APPR OPND | HD /B /78/HDBR-A-6102-04 | SLEWING SYSTEM |  | A |  |  | DK60 |  | PROK
2024-W15-16 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100106317 | Replace FCV-29173 | Replace FCV-29173 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-03-14 | 2024-01-29 | 10 | REL | APPR OPND | HB /A /37/HBAA-FCV-29173 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50 |  |  | 2024-04-08
2026-W13-14 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100109093 | Dump valve 35004 Stuck Open | Dump valve 35004 Stuck Open | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 6 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-05-01 | 2024-03-17 | 10 | PCNF REL | APPR OPND | HB /A /50/HBAA-CVA-35004 | CHOKE |  | C |  | MMS | DK50
2026-W13-14 | 2 | NE | WDF | MTN-MECH | PRODTECH | 2100109093 | Dump valve 35004 Stuck Open | solate choke mech | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 1 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-05-01 | 2024-03-17 | 20 | PCNF REL | APPR OPND | HB /A /50/HBAA-CVA-35004 | CHOKE |  | C |  | MMS | DK50
2026-W13-14 | 2 | NE | WDF | MTN-MECH | MTN-ELEC | 2100109093 | Dump valve 35004 Stuck Open | Isolate - deisolate choke elec. | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 1 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-05-01 | 2024-03-17 | 30 | PCNF REL | APPR OPND | HB /A /50/HBAA-CVA-35004 | CHOKE |  | C |  | MMS | DK50
2026-W13-14 | 2 | NE | WDF | MTN-MECH | MTN-RIGG | 2100109093 | Dump valve 35004 Stuck Open | Assist on Rigging Choke Out & back In | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 2 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-05-01 | 2024-03-17 | 40 | PCNF REL | APPR OPND | HB /A /50/HBAA-CVA-35004 | CHOKE |  | C |  | MMS | DK50
2026-W13-14 | 2 | NE | WDF | MTN-MECH | MTN-MECH | 2100109093 | Dump valve 35004 Stuck Open | Dismantle Blind hubs and install Choke | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-05-01 | 2024-03-17 | 70 | PCNF REL | APPR OPND | HB /A /50/HBAA-CVA-35004 | CHOKE |  | C |  | MMS | DK50
2026-W13-14 | 2 | NE | WDF | MTN-MECH | MTN-INST | 2100109093 | Dump valve 35004 Stuck Open | Connect Wires, Hydraulic & test ZT | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-05-01 | 2024-03-17 | 80 | REL | APPR OPND | HB /A /50/HBAA-CVA-35004 | CHOKE |  | C |  | MMS | DK50
2024-W21-22 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003392 | Request for seal to hydrocyclone | Request for seal to hydrocyclone | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2020-03-28 | 2020-03-08 | 10 | REL | APPR OPND | HB /D /27/HBDB-V-5071 | HYDROCYCLONE VESSEL |  | C |  | MMS | DK50 |  |  | 2024-05-22
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200006842 | 9Y overhaul VFD exp. pmp.PM-3653 No PID | ID Magnetization of motor | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2021-05-24 | 2021-04-14 | 60 | PCNF REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200006842 | 9Y overhaul VFD exp. pmp.PM-3653 No PID | Test of VFD after overhaul | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2021-05-24 | 2021-04-14 | 70 | PCNF REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200006842 | 9Y overhaul VFD exp. pmp.PM-3653 No PID | Test of VFD after overhaul | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2021-05-24 | 2021-04-14 | 80 | PCNF REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200006842 | 9Y overhaul VFD exp. pmp.PM-3653 No PID | Isolate accordingly | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2021-05-24 | 2021-04-14 | 90 | REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200006842 | 9Y overhaul VFD exp. pmp.PM-3653 No PID | Change battery, 3651,3652,3653 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2021-05-24 | 2021-04-14 | 100 | REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR |  | E |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200006842 | 9Y overhaul VFD exp. pmp.PM-3653 No PID | De-isolate accordingly and test | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2021-05-24 | 2021-04-14 | 110 | REL | APPR OPND | HB /D /23/HBDC-XE-3653 | VFD FOR OIL EXPORT PUMP MOTOR |  | E |  | MEL | DK50
2024-W29-30 | 3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009867 | 2022 Halfdan B PVI materiels | 2022 Halfdan B PVI materiels | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2022-03-12 | 2022-03-12 | 2022-03-12 | 2022-06-10 | 2022-03-12 | 10 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR |  | A |  | INP | DK50 |  |  | 2024-05-19
2024-W29-30 | 3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009867 | 2022 Halfdan B PVI materiels | Scholz Gasket EP-3823 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2022-03-12 | 2022-03-12 | 2022-03-12 | 2022-06-10 | 2022-03-12 | 220 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR |  | A |  | INP | DK50 |  |  | 2024-05-20
2024-W29-30 | 3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009867 | 2022 Halfdan B PVI materiels | Spools & Internals | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2022-03-12 | 2022-03-12 | 2022-03-12 | 2022-06-10 | 2022-03-12 | 230 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR |  | A |  | INP | DK50 |  |  | 2024-05-21
2024-W29-30 | 3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009867 | 2022 Halfdan B PVI materiels | 2" Blindflange | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2022-03-12 | 2022-03-12 | 2022-03-12 | 2022-06-10 | 2022-03-12 | 270 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR |  | A |  | INP | DK50 |  |  | 2024-05-22
2024-W29-30 | 3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009867 | 2022 Halfdan B PVI materiels | PVI materiaels V-3411 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2022-03-12 | 2022-03-12 | 2022-03-12 | 2022-06-10 | 2022-03-12 | 280 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR |  | A |  | INP | DK50 |  |  | 2024-05-23
0 | 3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200010858 | Replace Winch LB1, HDBM-X-0701 | Isolate lifeboat/HPU | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-27 | 2024-04-22 | 2022-09-15 | 2022-06-17 | 10 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | MTN-SCAF | 2200010858 | Replace Winch LB1, HDBM-X-0701 | Scaffolding for access to winch up/down | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 24 | 0 | W17-W18 | 2024-04-22 | 2024-04-27 | 2024-04-22 | 2022-09-15 | 2022-06-17 | 20 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010858 | Replace Winch LB1, HDBM-X-0701 | Replace winch | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 8 | 0 | W17-W18 | 2024-04-22 | 2024-04-27 | 2024-04-24 | 2022-09-15 | 2022-06-17 | 30 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200010858 | Replace Winch LB1, HDBM-X-0701 | Replace winch | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 0 | W17-W18 | 2024-04-22 | 2024-04-27 | 2024-04-26 | 2022-09-15 | 2022-06-17 | 40 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200010858 | Replace Winch LB1, HDBM-X-0701 | De-isolate Lifeboat/HPU | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-27 | 2024-04-27 | 2022-09-15 | 2022-06-17 | 50 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200010858 | Replace Winch LB1, HDBM-X-0701 | Loadtest (later by Verhoef) | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-27 | 2024-04-27 | 2022-09-15 | 2022-06-17 | 60 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A |  | MMS | DK60
2024-W35-36 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200011586 | Reverse check valve acc. to HAZOP | Reverse check valve acc. to HAZOP | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 0 | W35-36 | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2023-02-06 | 2022-09-24 | 10 | REL | APPR OPND | HB /B /34/HBBA-HCV-380012 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2024-W35-36 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200011586 | Reverse check valve acc. to HAZOP | Additional materials | REL PRT GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-29 | 2023-02-06 | 2022-09-24 | 20 | REL | APPR OPND | HB /B /34/HBBA-HCV-380012 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2024-W15-16 | 3 | NOSD | WGN | MTN-INST | MTN-TELE | 2200011736 | Upgrade OIW-monitor on produced water (V | Replace IT Switch, and installe new PC | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 12 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-02-27 | 2022-10-15 | 120 | PCNF REL | APPR OPND | HB /D /27/HBDB-AT-507501 | ANALYZ.TRANSM.-OIL IN WATER (METERING) |  | A |  | MIN | DK50 |  |  | 2024-04-17
2024-W15-16 | 3 | NOSD | WGN | MTN-INST | MTN-TELE | 2200011736 | Upgrade OIW-monitor on produced water (V | Check/Calibrate OIW | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 3 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-02-27 | 2022-10-15 | 150 | PCNF REL | APPR OPND | HB /D /27/HBDB-AT-507501 | ANALYZ.TRANSM.-OIL IN WATER (METERING) |  | A |  | MIN | DK50 |  |  | 2024-04-18
2024-W17-18 | 3 | NOSD | WGN | MTN-INST | MTN-INST | 2200012418 | Purchase of HBC LTE Equipment | HBC LTE Installation | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-05-14 | 2022-12-30 | 10 | REL | APPR OPND | HB /C /08 | COMMUNICATION/TELECOM |  | A |  | MIN | DK50 |  |  | 2024-04-22
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | PRODTECH | 2200012729 | Replace HBAA-PSV-35000A - PSV 2023 | Isolation of PSV | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-09 | 2025-11-19 | 2023-06-03 | 10 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000A | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | PRODTECH | 2200012729 | Replace HBAA-PSV-35000A - PSV 2023 | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-09 | 2025-11-19 | 2023-06-03 | 20 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000A | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | MTN-RIGG | 2200012729 | Replace HBAA-PSV-35000A - PSV 2023 | Rigging assist (install) | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 24 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-09 | 2025-11-19 | 2023-06-03 | 30 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000A | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | MTN-MECH | 2200012729 | Replace HBAA-PSV-35000A - PSV 2023 | Remove PSV and install new PSV | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 5 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-14 | 2025-11-19 | 2023-06-03 | 40 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000A | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | MTN-RIGG | 2200012729 | Replace HBAA-PSV-35000A - PSV 2023 | Rigging Assist (remove) | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-15 | 2025-11-19 | 2023-06-03 | 60 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000A | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | PRODTECH | 2200012729 | Replace HBAA-PSV-35000A - PSV 2023 | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 2 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-18 | 2025-11-19 | 2023-06-03 | 70 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000A | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | PRODTECH | 2200012729 | Replace HBAA-PSV-35000A - PSV 2023 | De-isolation and leak test | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 4 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-18 | 2025-11-19 | 2023-06-03 | 90 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000A | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2024-W17-18 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000584 | DK48 NDT/FORCE MATERIAL ORDER 2020 | DK48 NDT/FORCE MATERIAL ORDER 2020 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-11-27 | 2020-11-27 | 2020-11-27 | 2020-12-31 | 2020-01-01 | 10 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-05-05
2024-W17-18 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000584 | DK48 NDT/FORCE MATERIAL ORDER 2020 | MATERIAL MØRKEKAMMER HBC 22.09.2020 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-11-27 | 2020-11-27 | 2020-11-27 | 2020-12-31 | 2020-01-01 | 20 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-05-06
2024-W17-18 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000584 | DK48 NDT/FORCE MATERIAL ORDER 2020 | 2300000584 26.11.20 MAT FILM,PASTA MM | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-11-27 | 2020-11-27 | 2020-11-27 | 2020-12-31 | 2020-01-01 | 30 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-05-07
0 | 4 | NE | WRO | MTN-CRAN | MTN-CRAN | 2300000686 | HALFDAN A DECK SYSTEM 61 | HALFDAN A DECK SYSTEM 61 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W07-W08 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-12-31 | 2019-10-31 | 10 | REL | APPR OPND | HD /A /78 | LIFTING EQUIPMENT |  | A |  | MMS | DK60
2024-W39-40 | 4 | NE | WRO | MTN-INST | MTN-INST | 2300000687 | General for sys 80 Halfdan B | General for sys 80 Halfdan B | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2020-12-31 | 2019-10-24 | 10 | REL | APPR OPND | HB /C /84 | WORKSHOP/WAREHOUSE |  | A |  | MIN | DK50 |  |  | 2024-04-22
2024-W25-26 | 4 | NE | WRO | MTN-MECH | MTN-MECH | 2300000692 | Sys-31 Matbestilling/backload HB 2020 | S-31 Matbestilling/backload HB 2020 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2020-12-31 | 2019-12-03 | 10 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MMS | DK50 |  |  | 2024-05-22
0 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000772 | DK49 SMEDE MATERIAL ORDER 2019 | DK49 SMEDE MATERIAL ORDER 2019 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | CON | DK60
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000773 | DK48 "BURET" PRO MATERIAL ORDER 2019 | DK48 "BURET" PRO MATERIAL ORDER 2019 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-04-21
2024-W33-34 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000775 | DK48 BACKLOAD OC MATERIAL 2019 | DK48 BACKLOAD OC MATERIAL 2019 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | CON | DK50 |  |  | 2024-05-05
0 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000786 | DK49 BACKLOAD OC EQ. MATERIAL 2019 | DK49 BACKLOAD OC EQ. MATERIAL 2019 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | CON | DK60
0 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000787 | KONTOR HALFDAN A 2019 | KONTOR HALFDAN A 2019 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  |  | DK60
0 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000788 | ARBEJDSTØJ HALFDAN A 2019 | ARBEJDSTØJ HALFDAN A 2019 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  |  | DK60
0 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000789 | DECK HALFDAN A 2019 | DECK HALFDAN A 2019 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  |  | DK60
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000790 | SIKKERHEDSUDSTYR PPE HALFDAN B 2019 | SIKKERHEDSUDSTYR PPE HALFDAN B 2019 | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-13 | 2020-02-13 | 2020-02-13 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HB /A | HALFDAN BA |  | A |  |  | DK50 |  |  | 2024-04-21
2024-W33-34 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000791 | PROD OLIE/N2 HALFDAN B 2019 | PROD OLIE/N2 HALFDAN B 2019 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HB /A | HALFDAN BA |  | A |  |  | DK50 |  |  | 2024-05-19
2024-W17-18 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000793 | SIKKERHEDSUDSTYR HALFDAN B 2019 | SIKKERHEDSUDSTYR HALFDAAN B 2019 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HB /A | HALFDAN BA |  | A |  |  | DK50 |  |  | 2024-05-05
2024-W31-32 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000795 | ARBEJDSTØJ HALFDAN B 2019 | ARBEJDSTØJ HALFDAN B 2019 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HB /A | HALFDAN BA |  | A |  |  | DK50 |  |  | 2024-05-05
2024-W37-38 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000796 | DECK HALFDAN B 2019 | DECK HALFDAN B 2019 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HB /A | HALFDAN BA |  | A |  |  | DK50 |  |  | 2024-04-21
0 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000798 | SIKKERHED HALFDAN A 2019 | SIKKERHED HALFDAN A 2019 | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  |  | DK60
2024-W33-34 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001406 | DK50 - Replace by 2300002491 PROD - WORK | DK50 - CONSUMABLE PROD - WORKSHOP | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2020-09-09 | 2020-09-09 | 2020-09-09 | 2021-07-06 | 2020-09-09 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK50
0 | 4 |  | WRO | MTN-PAIN | MTN-PAIN | 2300002011 | HD; Standard leak sealing items | HD; Standard leak sealing items | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-09-30 | 2021-02-02 | 10 | REL | APPR OPND | HD | Halfdan D |  | A |  | MFM | DK60
2024-W33-34 | 4 |  | WRO | MTN-PAIN | MTN-PAIN | 2300002012 | HB; Standard leak sealing items | HB; Standard leak sealing items | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-09-30 | 2021-02-02 | 10 | REL | APPR OPND | HB | Halfdan B |  | A |  | MFM | DK50
0 | 3 | NOSD | WRO | PRODTECH | PRODTECH | 2300003338 | Purchase of new Safemaster Ladders | Purchase of new Safemaster Ladders | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-12-13 | 2021-11-03 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
2024-W27-28 | 3 | NOSD | WRO | PRODTECH | PRODTECH | 2300003628 | HBC - TIM - Total Industrial Mobility | HBC - TIM – Total Industrial Mobility | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2022-02-05 | 2022-02-05 | 2022-02-05 | 2022-05-06 | 2022-02-05 | 10 | REL | APPR OPND | HB | Halfdan B |  | A |  | PRD | DK50 |  |  | 2024-06-02
2024-W49-50 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300006735 | Survey WO for Siemens system replacement | Survey WO for Siemens system replacement | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W49-50 | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-03-23 | 2023-11-09 | 10 | REL | APPR OPND | HB /A /03/HBAA-FP-0201A | REMOTE I/O UNIT FOR ESD PANEL |  | A |  | MIN | DK50
2024-W49-50 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300006735 | Survey WO for Siemens system replacement | add. materials | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 | W49-50 | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-03-23 | 2023-11-09 | 20 | REL | APPR OPND | HB /A /03/HBAA-FP-0201A | REMOTE I/O UNIT FOR ESD PANEL |  | A |  | MIN | DK50
2024-W49-50 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300006735 | Survey WO for Siemens system replacement | Telecom support during survey | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 30 | 0 | W49-50 | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-03-23 | 2023-11-09 | 30 | REL | APPR OPND | HB /A /03/HBAA-FP-0201A | REMOTE I/O UNIT FOR ESD PANEL |  | A |  | MIN | DK50
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308631 | 1Y HVAC FAN COILS HDBE-A-1203/4 | PERSONAL ISOLATION | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-03-17 | 2024-02-10 | 10 | REL | APPR OPND | HD /B /09/HDBE-E-1203 | DX COOLING COIL |  | A | DKHD-2016 | MEL | DK60 | EL0013
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308631 | 1Y HVAC FAN COILS HDBE-A-1203/4 | HVAC CHECK FAN COIL BELT DRIVEN | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 7 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-03-17 | 2024-02-10 | 20 | REL | APPR OPND | HD /B /09/HDBE-E-1203 | DX COOLING COIL |  | A | DKHD-2016 | MEL | DK60 | EL0013
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308631 | 1Y HVAC FAN COILS HDBE-A-1203/4 | PERSONAL DE-ISOLATION | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-09 | 2024-03-17 | 2024-02-10 | 30 | REL | APPR OPND | HD /B /09/HDBE-E-1203 | DX COOLING COIL |  | A | DKHD-2016 | MEL | DK60 | EL0013
2026-W13-14 | C | HBDIGF2 | WPM | MTN-INST | PRODTECH | 2400315179 | 1Y HBDB-FIT-507601 - PW METERING | ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 1 | 0 | W09-W10 | 2024-03-05 | 2024-03-10 | 2024-03-05 | 2024-04-10 | 2024-03-05 | 10 | REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
2026-W13-14 | C | HBDIGF2 | WPM | MTN-INST | MTN-MECH | 2400315179 | 1Y HBDB-FIT-507601 - PW METERING | DISASSEMBLY OF METERING | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 4 | 0 | W09-W10 | 2024-03-05 | 2024-03-10 | 2024-03-05 | 2024-04-10 | 2024-03-05 | 20 | REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
2026-W13-14 | C | HBDIGF2 | WPM | MTN-INST | MTN-RIGG | 2400315179 | 1Y HBDB-FIT-507601 - PW METERING | RIGGING SUPPORT | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 4 | 0 | W09-W10 | 2024-03-05 | 2024-03-10 | 2024-03-06 | 2024-04-10 | 2024-03-05 | 30 | REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
2026-W13-14 | C | HBDIGF2 | WPM | MTN-INST | MTN-INST | 2400315179 | 1Y HBDB-FIT-507601 - PW METERING | HBDB-FIT-507601 - PW METERING | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 9 | 0 | W09-W10 | 2024-03-05 | 2024-03-10 | 2024-03-06 | 2024-04-10 | 2024-03-05 | 40 | REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
2026-W13-14 | C | HBDIGF2 | WPM | MTN-INST | MTN-RIGG | 2400315179 | 1Y HBDB-FIT-507601 - PW METERING | DE-RIGGING SUPPORT | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 4 | 0 | W09-W10 | 2024-03-05 | 2024-03-10 | 2024-03-08 | 2024-04-10 | 2024-03-05 | 50 | REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
2026-W13-14 | C | HBDIGF2 | WPM | MTN-INST | MTN-MECH | 2400315179 | 1Y HBDB-FIT-507601 - PW METERING | ASSEMBLY OF METERING | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 4 | 0 | W09-W10 | 2024-03-05 | 2024-03-10 | 2024-03-09 | 2024-04-10 | 2024-03-05 | 60 | REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
2026-W13-14 | C | HBDIGF2 | WPM | MTN-INST | PRODTECH | 2400315179 | 1Y HBDB-FIT-507601 - PW METERING | DE-ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 1 | 0 | W09-W10 | 2024-03-05 | 2024-03-10 | 2024-03-10 | 2024-04-10 | 2024-03-05 | 70 | REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315193 | 1Y HVAC EXT. FAN-1215 & EXH. FAN-1211A/B | PERSONAL ISOLATION | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-25 | 2024-04-14 | 2024-03-09 | 10 | REL | APPR OPND | HD /B /09/GENERAL-EXHAUST | FANS 1211A/B |  | A | DKHD-2008 | MEL | DK60 | EL0013
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315193 | 1Y HVAC EXT. FAN-1215 & EXH. FAN-1211A/B | EXHAUST CHECK, DUTY & STBY, BELT DRIVEN | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 5 | 0 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-25 | 2024-04-14 | 2024-03-09 | 20 | REL | APPR OPND | HD /B /09/GENERAL-EXHAUST | FANS 1211A/B |  | A | DKHD-2008 | MEL | DK60 | EL0013
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315193 | 1Y HVAC EXT. FAN-1215 & EXH. FAN-1211A/B | EXHAUST CHECK (SINGLE, BELT DRIVEN) | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 3 | 0 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-26 | 2024-04-14 | 2024-03-09 | 30 | REL | APPR OPND | HD /B /09/GENERAL-EXHAUST | FANS 1211A/B |  | A | DKHD-2008 | MEL | DK60 | EL0013
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315193 | 1Y HVAC EXT. FAN-1215 & EXH. FAN-1211A/B | PERSONAL DE-ISOLATION | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-27 | 2024-04-14 | 2024-03-09 | 40 | REL | APPR OPND | HD /B /09/GENERAL-EXHAUST | FANS 1211A/B |  | A | DKHD-2008 | MEL | DK60 | EL0013
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315195 | 1Y HVAC EXTRACT GALLEY HDB | PERSONAL ISOLATION | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-04-14 | 2024-03-09 | 10 | REL | APPR OPND | HD /B /09/HVAC-GALLEY | HVAC GALLEY |  | A | DKHD-2020 | MEL | DK60 | EL0103
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315195 | 1Y HVAC EXTRACT GALLEY HDB | EXHAUST CHECK, DUTY & STBY, BELT DRIVEN | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 5 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-04-14 | 2024-03-09 | 20 | REL | APPR OPND | HD /B /09/HVAC-GALLEY | HVAC GALLEY |  | A | DKHD-2020 | MEL | DK60 | EL0103
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315195 | 1Y HVAC EXTRACT GALLEY HDB | PERSONAL DE-ISOLATION | REL GMPS MANC PRC SETC | APPR SMAT RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-26 | 2024-04-14 | 2024-03-09 | 30 | REL | APPR OPND | HD /B /09/HVAC-GALLEY | HVAC GALLEY |  | A | DKHD-2020 | MEL | DK60 | EL0103
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325386 | 1Y HVAC EXT. HDBD-FAN-1210A/B - 1217A/B | PERSONAL ISOLATION | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 1 | 0 | W17-W18 | 2024-04-17 | 2024-04-18 | 2024-04-17 | 2024-05-23 | 2024-04-17 | 10 | REL | APPR OPND | HD /B /09/TOILET-EXTRACT | FANS 1210A/B |  | A | DKHD-2015 | MEL | DK60 | EL0013
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325386 | 1Y HVAC EXT. HDBD-FAN-1210A/B - 1217A/B | EXHAUST CHECK, DUTY & STBY, BELT DRIVEN | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 6 | 0 | W17-W18 | 2024-04-17 | 2024-04-18 | 2024-04-17 | 2024-05-23 | 2024-04-17 | 20 | REL | APPR OPND | HD /B /09/TOILET-EXTRACT | FANS 1210A/B |  | A | DKHD-2015 | MEL | DK60 | EL0013
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325386 | 1Y HVAC EXT. HDBD-FAN-1210A/B - 1217A/B | PERSONAL DE-ISOLATION | REL GMPS MACM PRC SETC | APPR SMAT RDBL | 1 | 0 | W17-W18 | 2024-04-17 | 2024-04-18 | 2024-04-18 | 2024-05-23 | 2024-04-17 | 30 | REL | APPR OPND | HD /B /09/TOILET-EXTRACT | FANS 1210A/B |  | A | DKHD-2015 | MEL | DK60 | EL0013
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | HBA16, WL, SSSV reactivation, SV19706 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 10 | PCNF REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | PRODTECH | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | Safing well/well handover (production) | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 20 | PCNF REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | MTN-ROUS | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | Crane assist during WL R/U and RD | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 48 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 30 | PCNF REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | MTN-SCAF | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | Scaffolder assistance for RU and RD | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 48 | 49 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 40 | PCNF REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | MTN-ELEC | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | Electrician assistance for RU and RD | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 12 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 50 | PCNF REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | MTN-TELE | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | Tele assist during WL RRU and RD | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 24 | 13 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 60 | PCNF REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | VEN-CRAN | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | Crane support assitance for days | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 168 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 70 | PCNF REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | Oilenco tools | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 80 | PCNF REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | WRSSSV | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 90 | PCNF REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | Ocean Team chemicals | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 100 | PCNF REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | H2S Equipment 50 days | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 110 | PCNF REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | Glycol 40/60 | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 120 | PCNF REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001042 | HBA16, WL, SSSV reactivation, SV19706 | Additionel cost Schlumberger Wireline | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 130 | REL | APPR OPND | HB /A /55/HBA16-WATER-INJECTION-WELLHEAD | HBA16 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | WELLMAIN | 2900001214 | Scheduled WHM 2024 HBA | Scheduled WHM 2024 HBA | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-01-15 | 2024-05-29 | 2024-01-15 | 10 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | MTN-RIGG | 2900001214 | Scheduled WHM 2024 HBA | Rigger Assistance for WHM | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 50 | 52 |  | 2024-01-15 | 2024-02-24 | 2024-01-15 | 2024-05-29 | 2024-01-15 | 20 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | MTN-SCAF | 2900001214 | Scheduled WHM 2024 HBA | Scaff assistance for WHM | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 50 | 61 |  | 2024-01-15 | 2024-02-24 | 2024-01-25 | 2024-05-29 | 2024-01-15 | 30 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | MTN-INST | 2900001214 | Scheduled WHM 2024 HBA | Instrument assistance for WHM | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 50 | 50 |  | 2024-01-15 | 2024-02-24 | 2024-02-04 | 2024-05-29 | 2024-01-15 | 40 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | MTN-MECH | 2900001214 | Scheduled WHM 2024 HBA | Mechanical assistance for WHM | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 50 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-02-14 | 2024-05-29 | 2024-01-15 | 50 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | WELLMAIN | 2900001214 | Scheduled WHM 2024 HBA | Major spares | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-02-24 | 2024-05-29 | 2024-01-15 | 60 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | WELLMAIN | 2900001214 | Scheduled WHM 2024 HBA | VR tool | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-02-24 | 2024-05-29 | 2024-01-15 | 70 | PCNF REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | WELLMAIN | 2900001215 | Scheduled WHM 2024 HBB | Scheduled WHM 2024 HBB | REL PCNF GMPS MACM PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-01-15 | 2024-05-29 | 2024-01-15 | 10 | PCNF REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | MTN-RIGG | 2900001215 | Scheduled WHM 2024 HBB | Rigger Assistance for WHM | REL PCNF GMPS MACM PRC SETC | APPR SMAT RDBL | 50 | 24 |  | 2024-01-15 | 2024-02-24 | 2024-01-15 | 2024-05-29 | 2024-01-15 | 20 | PCNF REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | MTN-SCAF | 2900001215 | Scheduled WHM 2024 HBB | Scaff assistance for WHM | REL PCNF GMPS MACM PRC SETC | APPR SMAT RDBL | 50 | 18 |  | 2024-01-15 | 2024-02-24 | 2024-01-25 | 2024-05-29 | 2024-01-15 | 30 | PCNF REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | MTN-ELEC | 2900001215 | Scheduled WHM 2024 HBB | Electrician assistance for WHM | REL PCNF GMPS MACM PRC SETC | APPR SMAT RDBL | 50 | 4 |  | 2024-01-15 | 2024-02-24 | 2024-02-04 | 2024-05-29 | 2024-01-15 | 40 | PCNF REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | MTN-MECH | 2900001215 | Scheduled WHM 2024 HBB | Mechanical assistance for WHM | REL PCNF GMPS MACM PRC SETC | APPR SMAT RDBL | 50 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-02-14 | 2024-05-29 | 2024-01-15 | 50 | PCNF REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | WELLMAIN | 2900001215 | Scheduled WHM 2024 HBB | WHM Toolhouse | REL PCNF GMPS MACM PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-02-24 | 2024-05-29 | 2024-01-15 | 60 | PCNF REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
0 | 3 |  | WSO | WELLMAIN | WELLMAIN | 2900001216 | Scheduled WHM 2024 HDA | Scheduled WHM 2024 HDA | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-01-15 | 2024-05-29 | 2024-01-15 | 10 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLMAIN | MTN-RIGG | 2900001216 | Scheduled WHM 2024 HDA | Rigger Assistance for WHM | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 50 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-01-15 | 2024-05-29 | 2024-01-15 | 20 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLMAIN | MTN-SCAF | 2900001216 | Scheduled WHM 2024 HDA | Scaff assistance for WHM | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 50 | 57 |  | 2024-01-15 | 2024-02-24 | 2024-01-25 | 2024-05-29 | 2024-01-15 | 30 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLMAIN | MTN-ELEC | 2900001216 | Scheduled WHM 2024 HDA | Electrician assistance for WHM | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 50 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-02-04 | 2024-05-29 | 2024-01-15 | 40 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLMAIN | MTN-MECH | 2900001216 | Scheduled WHM 2024 HDA | Mechanical assistance for WHM | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 50 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-02-14 | 2024-05-29 | 2024-01-15 | 50 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLMAIN | WELLMAIN | 2900001216 | Scheduled WHM 2024 HDA | Major spares | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-02-24 | 2024-05-29 | 2024-01-15 | 60 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLMAIN | WELLMAIN | 2900001216 | Scheduled WHM 2024 HDA | VR tool | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-02-24 | 2024-05-29 | 2024-01-15 | 70 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLMAIN | WELLMAIN | 2900001216 | Scheduled WHM 2024 HDA | WHM Toolhouse | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-02-24 | 2024-05-29 | 2024-01-15 | 80 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLMAIN | WELLMAIN | 2900001216 | Scheduled WHM 2024 HDA | MEG | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-02-24 | 2024-05-29 | 2024-01-15 | 90 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLMAIN | WELLMAIN | 2900001216 | Scheduled WHM 2024 HDA | Additional Major spares | REL PCNF GMPS MANC PRC SETC | APPR SMAT RDBL | 0 | 0 |  | 2024-01-15 | 2024-02-24 | 2024-02-24 | 2024-05-29 | 2024-01-15 | 100 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
2024-W33-34 | 4 | HB-GORM | WDF | MTN-INST | MTN-INST | 2100079927 | Small seeps on inst. pipes in HPU 5934 | Isolate hydraulic line | REL GMPS MANC PRC SETC | APPR SMAT AWSD AWSC RDBL | 1 | 0 | W33-34 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-12-06 | 2023-06-20 | 10 | REL | APPR OPND | HB /B /07/HBBA-FP-5934 | VALVE CONTROL PANEL |  | H |  | MIN | DK50
2024-W33-34 | 4 | HB-GORM | WDF | MTN-INST | MTN-INST | 2100079927 | Small seeps on inst. pipes in HPU 5934 | Remove Pipe element | REL GMPS MANC PRC SETC | APPR SMAT AWSD AWSC RDBL | 5 | 0 | W33-34 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-12-06 | 2023-06-20 | 20 | REL | APPR OPND | HB /B /07/HBBA-FP-5934 | VALVE CONTROL PANEL |  | H |  | MIN | DK50
2024-W33-34 | 4 | HB-GORM | WDF | MTN-INST | MTN-INST | 2100079927 | Small seeps on inst. pipes in HPU 5934 | Re-install Pipe element | REL GMPS MANC PRC SETC | APPR SMAT AWSD AWSC RDBL | 5 | 0 | W33-34 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-12-06 | 2023-06-20 | 30 | REL | APPR OPND | HB /B /07/HBBA-FP-5934 | VALVE CONTROL PANEL |  | H |  | MIN | DK50
2024-W33-34 | 4 | HB-GORM | WDF | MTN-INST | MTN-INST | 2100079927 | Small seeps on inst. pipes in HPU 5934 | De-isolate Pipe element | REL GMPS MANC PRC SETC | APPR SMAT AWSD AWSC RDBL | 1 | 0 | W33-34 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-12-06 | 2023-06-20 | 40 | REL | APPR OPND | HB /B /07/HBBA-FP-5934 | VALVE CONTROL PANEL |  | H |  | MIN | DK50
2024-W23-24 | 3 | HD-HBOIL | WGN | MTN-TELE | MTN-TELE | 2200005984 | HBC HIPPS AI Replacement | HBC HIPPS AI Replacement | REL GMPS MANC PRC SETC | APPR SMAT AWSD AWSC | 12 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2021-04-07 | 2021-01-07 | 10 | REL | APPR OPND | HB /C /03/HBCA-CP-0201 | ESD | 99000119 | G |  | MIN | DK50
2024-W23-24 | 3 | HD-HBOIL | WGN | MTN-TELE | MTN-TELE | 2200005984 | HBC HIPPS AI Replacement | additional materials | REL GMPS MANC PRC SETC | APPR SMAT AWSD AWSC | 0 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2021-04-07 | 2021-01-07 | 20 | REL | APPR OPND | HB /C /03/HBCA-CP-0201 | ESD | 99000119 | G |  | MIN | DK50
2024-W23-24 | 3 | HBOIL-SD | WGN | MTN-ELEC | MTN-ELEC | 2200005985 | HBA HIPPS AI replacement | HBA HIPPS AI replacement | REL GMPS MANC PRC SETC | APPR SMAT AWSD AWSC | 12 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2021-04-07 | 2021-01-07 | 10 | REL | APPR OPND | HB /A /03/HBAA-CP-0202 | ESD HIPPS PANEL | 99000119 | G |  | MIN | DK50
2024-W23-24 | 3 | HBOIL-SD | WGN | MTN-ELEC | MTN-ELEC | 2200005985 | HBA HIPPS AI replacement | additional materials | REL GMPS MANC PRC SETC | APPR SMAT AWSD AWSC | 0 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2021-04-07 | 2021-01-07 | 20 | REL | APPR OPND | HB /A /03/HBAA-CP-0202 | ESD HIPPS PANEL | 99000119 | G |  | MIN | DK50
2026-W13-14 | 4 | HBB04-GL | WDF | MTN-INST | MTN-SCAF | 2100050152 | Corrodet Junctionbox HBBB-DIJB-300407 | Erect scaffold | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL SREQ | 8 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-11-27 | 2021-06-30 | 10 | REL | APPR OPND | HB /B /10/HBBB-CVA-300407 | CHOKE VALVE - NO VALVE INSATLLED | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBB04-GL | WDF | MTN-INST | MTN-INST | 2100050152 | Corrodet Junctionbox HBBB-DIJB-300407 | Isolate + Inhibit Choke Valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-11-27 | 2021-06-30 | 20 | REL | APPR OPND | HB /B /10/HBBB-CVA-300407 | CHOKE VALVE - NO VALVE INSATLLED | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBB04-GL | WDF | MTN-INST | MTN-INST | 2100050152 | Corrodet Junctionbox HBBB-DIJB-300407 | Replace Junction Box | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL SREQ | 4 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-11-27 | 2021-06-30 | 30 | REL | APPR OPND | HB /B /10/HBBB-CVA-300407 | CHOKE VALVE - NO VALVE INSATLLED | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBB04-GL | WDF | MTN-INST | MTN-INST | 2100050152 | Corrodet Junctionbox HBBB-DIJB-300407 | Deisolate & Leaktest Choke Valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-11-27 | 2021-06-30 | 40 | REL | APPR OPND | HB /B /10/HBBB-CVA-300407 | CHOKE VALVE - NO VALVE INSATLLED | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBB04-GL | WDF | MTN-INST | MTN-SCAF | 2100050152 | Corrodet Junctionbox HBBB-DIJB-300407 | Dismantle scaffold | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL SREQ | 4 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-11-27 | 2021-06-30 | 50 | REL | APPR OPND | HB /B /10/HBBB-CVA-300407 | CHOKE VALVE - NO VALVE INSATLLED | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HBBPWELL | WDF | MTN-MECH | PRODTECH | 2100025865 | CMAT:Exchange HCV-03300-D & HCV-03300-U | L3 Isolate equipment | REL GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 | + 2400151231 | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2019-06-07 | 2019-05-18 | 10 | REL | APPR OPND | HB /B /01/HBBA-HCV-03300-D | LO - HCV DOWNSTREAM XCV-03300 | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-MECH | 2100025865 | CMAT:Exchange HCV-03300-D & HCV-03300-U | L2 Exchange HCV-03300-D | REL GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 | + 2400151231 | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2019-06-07 | 2019-05-18 | 20 | REL | APPR OPND | HB /B /01/HBBA-HCV-03300-D | LO - HCV DOWNSTREAM XCV-03300 | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-MECH | 2100025865 | CMAT:Exchange HCV-03300-D & HCV-03300-U | L2 Exchange HCV-03300-U | REL GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 | + 2400151231 | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2019-06-07 | 2019-05-18 | 30 | REL | APPR OPND | HB /B /01/HBBA-HCV-03300-D | LO - HCV DOWNSTREAM XCV-03300 | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBBPWELL | WDF | MTN-MECH | PRODTECH | 2100025865 | CMAT:Exchange HCV-03300-D & HCV-03300-U | L3 Remove isolation | REL GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 | + 2400151231 | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2019-06-07 | 2019-05-18 | 40 | REL | APPR OPND | HB /B /01/HBBA-HCV-03300-D | LO - HCV DOWNSTREAM XCV-03300 | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-MECH | 2100025865 | CMAT:Exchange HCV-03300-D & HCV-03300-U | New mats | REL GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2019-06-07 | 2019-05-18 | 50 | REL | APPR OPND | HB /B /01/HBBA-HCV-03300-D | LO - HCV DOWNSTREAM XCV-03300 | 99000119 | D |  | MMS | DK50
2024-W43-44 | 3 | HBD-IPHP | WDF | MTN-ELEC | PRODTECH | 2100026004 | Faulty differential trafo LP-1803 | Isolate drawer | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0.5 | 0 | W43-44 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2020-01-05 | 2019-10-07 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A04-KA | LIGHTING & SMALL POWER HBDD-LP-1803 | 99000119 | C |  | MEL | DK50
2024-W43-44 | 3 | HBD-IPHP | WDF | MTN-ELEC | VEN-ELEC | 2100026004 | Faulty differential trafo LP-1803 | Test drawer and current transformer | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 | W43-44 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2020-01-05 | 2019-10-07 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A04-KA | LIGHTING & SMALL POWER HBDD-LP-1803 | 99000119 | C |  | MEL | DK50
2024-W43-44 | 3 | HBD-IPHP | WDF | MTN-ELEC | VEN-ELEC | 2100026004 | Faulty differential trafo LP-1803 | If broken, replace current transformer | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 20 | 0 | W43-44 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2020-01-05 | 2019-10-07 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A04-KA | LIGHTING & SMALL POWER HBDD-LP-1803 | 99000119 | C |  | MEL | DK50
2024-W43-44 | 3 | HBD-IPHP | WDF | MTN-ELEC | PRODTECH | 2100026004 | Faulty differential trafo LP-1803 | De-isolate | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0.5 | 0 | W43-44 | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2020-01-05 | 2019-10-07 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A04-KA | LIGHTING & SMALL POWER HBDD-LP-1803 | 99000119 | C |  | MEL | DK50
2024-W23-24 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100026021 | Exchange 1" ball valve for air supply EM | Isolate equipment | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-07-12 | 2020-02-13 | 10 | REL | APPR OPND | HB /D /02/HBDC-EMS-062001 | SAFETY SHOWER WITH EYEWASH | 99000119 | F |  | MMS | DK50
2024-W23-24 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100026021 | Exchange 1" ball valve for air supply EM | Exchange valve | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-07-12 | 2020-02-13 | 20 | REL | APPR OPND | HB /D /02/HBDC-EMS-062001 | SAFETY SHOWER WITH EYEWASH | 99000119 | F |  | MMS | DK50
2024-W23-24 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100026021 | Exchange 1" ball valve for air supply EM | Remove isolation | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-07-12 | 2020-02-13 | 30 | REL | APPR OPND | HB /D /02/HBDC-EMS-062001 | SAFETY SHOWER WITH EYEWASH | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100026248 | LOTI:Replace HBBB-FCV-290902 + Actuator | L3 Isolation of HBBB-FCV-290902 | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 | LOTI | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2019-03-06 | 2018-12-06 | 10 | REL | APPR OPND | HB /B /37/HBBB-FCV-290902 | GAS LIFT CONTROL VALVE, HBB-09 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-RIGG | 2100026248 | LOTI:Replace HBBB-FCV-290902 + Actuator | L3 Help removing old valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 | LOTI | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2019-03-06 | 2018-12-06 | 15 | REL | APPR OPND | HB /B /37/HBBB-FCV-290902 | GAS LIFT CONTROL VALVE, HBB-09 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-ELEC | 2100026248 | LOTI:Replace HBBB-FCV-290902 + Actuator | L3 Help disconnect old valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2019-03-06 | 2018-12-06 | 17 | REL | APPR OPND | HB /B /37/HBBB-FCV-290902 | GAS LIFT CONTROL VALVE, HBB-09 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100026248 | LOTI:Replace HBBB-FCV-290902 + Actuator | L2 Replace HBBB-FCV-290902 | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2019-03-06 | 2018-12-06 | 20 | REL | APPR OPND | HB /B /37/HBBB-FCV-290902 | GAS LIFT CONTROL VALVE, HBB-09 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-ELEC | 2100026248 | LOTI:Replace HBBB-FCV-290902 + Actuator | L3 Conenct new valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2019-03-06 | 2018-12-06 | 22 | REL | APPR OPND | HB /B /37/HBBB-FCV-290902 | GAS LIFT CONTROL VALVE, HBB-09 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-RIGG | 2100026248 | LOTI:Replace HBBB-FCV-290902 + Actuator | L3 Help putting in new valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2019-03-06 | 2018-12-06 | 25 | REL | APPR OPND | HB /B /37/HBBB-FCV-290902 | GAS LIFT CONTROL VALVE, HBB-09 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100026248 | LOTI:Replace HBBB-FCV-290902 + Actuator | L3 De-Isoaltion / Test HBBB-FCV-290902 | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2019-03-06 | 2018-12-06 | 30 | REL | APPR OPND | HB /B /37/HBBB-FCV-290902 | GAS LIFT CONTROL VALVE, HBB-09 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-ELEC | PRODTECH | 2100030861 | Breaker N-1802 Q18 broken | Set isolation | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-07-30 | 2020-05-01 | 10 | REL | APPR OPND | HB /A /06/HBAA-N-1802-Q18 | ASUX UNIT HBAA-FP-3040 | 99000119 | E |  | MEL | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-ELEC | VEN-ELEC | 2100030861 | Breaker N-1802 Q18 broken | Replace breaker | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-07-30 | 2020-05-01 | 20 | REL | APPR OPND | HB /A /06/HBAA-N-1802-Q18 | ASUX UNIT HBAA-FP-3040 | 99000119 | E |  | MEL | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-ELEC | PRODTECH | 2100030861 | Breaker N-1802 Q18 broken | De-isolate | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-07-30 | 2020-05-01 | 30 | REL | APPR OPND | HB /A /06/HBAA-N-1802-Q18 | ASUX UNIT HBAA-FP-3040 | 99000119 | E |  | MEL | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-TURB | MTN-TURB | 2100049868 | HBDC-GEA-4352 Lube oil leak from gearbox | Lube oil leak from gearbox for IP/HP | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-12-27 | 2021-07-30 | 10 | PCNF REL | APPR OPND | HB /D /31/HBDC-GEA-4352 | MAIN GEARBOX | 99000119 | D |  | MMR | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-TURB | MTN-TURB | 2100049868 | HBDC-GEA-4352 Lube oil leak from gearbox | SO Muehlhan For refit lagging on gearbox | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-12-27 | 2021-07-30 | 11 | PCNF REL | APPR OPND | HB /D /31/HBDC-GEA-4352 | MAIN GEARBOX | 99000119 | D |  | MMR | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-TURB | PRODTECH | 2100049868 | HBDC-GEA-4352 Lube oil leak from gearbox | Isolation of HBDC-GEA-4352 gearbox | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-12-27 | 2021-07-30 | 20 | PCNF REL | APPR OPND | HB /D /31/HBDC-GEA-4352 | MAIN GEARBOX | 99000119 | D |  | MMR | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-TURB | VEN-MECH | 2100049868 | HBDC-GEA-4352 Lube oil leak from gearbox | Change seals acc. to att. Lube oil leaks | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 12 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-12-27 | 2021-07-30 | 35 | PCNF REL | APPR OPND | HB /D /31/HBDC-GEA-4352 | MAIN GEARBOX | 99000119 | D |  | MMR | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-TURB | PRODTECH | 2100049868 | HBDC-GEA-4352 Lube oil leak from gearbox | Deisolation/test HBDC-GEA-4352 gearbox | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-12-27 | 2021-07-30 | 40 | PCNF REL | APPR OPND | HB /D /31/HBDC-GEA-4352 | MAIN GEARBOX | 99000119 | D |  | MMR | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-TURB | CON-LAGG | 2100049868 | HBDC-GEA-4352 Lube oil leak from gearbox | Re-insulate gearbox, left from overhaul | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-12-27 | 2021-07-30 | 50 | PCNF REL | APPR OPND | HB /D /31/HBDC-GEA-4352 | MAIN GEARBOX | 99000119 | D |  | MMR | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-TURB | MTN-TURB | 2100049868 | HBDC-GEA-4352 Lube oil leak from gearbox | Remove inspection covers and re-seal | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 20 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-12-27 | 2021-07-30 | 60 | PCNF REL | APPR OPND | HB /D /31/HBDC-GEA-4352 | MAIN GEARBOX | 99000119 | D |  | MMR | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-TURB | MTN-TURB | 2100049868 | HBDC-GEA-4352 Lube oil leak from gearbox | Removal and re-fit of coupling covers | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 72 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-12-27 | 2021-07-30 | 70 | PCNF REL | APPR OPND | HB /D /31/HBDC-GEA-4352 | MAIN GEARBOX | 99000119 | D |  | MMR | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | PRODTECH | 2100050876 | Hydralic leak on CVA-30206 | Isolate choke and hydraulic | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-15 | 2024-04-08 | 2021-09-28 | 2021-06-30 | 10 | REL | APPR OPND | HB /A /10/HBAA-CVA-30206 | CHOKE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-RIGG | 2100050876 | Hydralic leak on CVA-30206 | Rig up hoist and sacffolding | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 12 | 0 | W15-W16 | 2024-04-08 | 2024-04-15 | 2024-04-08 | 2021-09-28 | 2021-06-30 | 15 | REL | APPR OPND | HB /A /10/HBAA-CVA-30206 | CHOKE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-MECH | 2100050876 | Hydralic leak on CVA-30206 | Demount actuator | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-15 | 2024-04-11 | 2021-09-28 | 2021-06-30 | 20 | REL | APPR OPND | HB /A /10/HBAA-CVA-30206 | CHOKE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-MECH | 2100050876 | Hydralic leak on CVA-30206 | Mount new actautor | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-15 | 2024-04-11 | 2021-09-28 | 2021-06-30 | 40 | REL | APPR OPND | HB /A /10/HBAA-CVA-30206 | CHOKE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | PRODTECH | 2100050876 | Hydralic leak on CVA-30206 | De-Isolate choke and hydraulic | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-15 | 2024-04-12 | 2021-09-28 | 2021-06-30 | 50 | REL | APPR OPND | HB /A /10/HBAA-CVA-30206 | CHOKE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-RIGG | 2100050876 | Hydralic leak on CVA-30206 | Rig down hoist and sacffolding | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 9 | 0 | W15-W16 | 2024-04-08 | 2024-04-15 | 2024-04-13 | 2021-09-28 | 2021-06-30 | 60 | REL | APPR OPND | HB /A /10/HBAA-CVA-30206 | CHOKE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100051376 | Missing insulation on WI inst. tubing | Missing insulation on WI inst. tubing | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-28 | 2023-04-24 | 2021-10-10 | 2021-07-12 | 10 | REL | APPR OPND | HB /A /55 | INJECTION WELLS/FLOW-LINES/MANIFOLDS |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100051376 | Missing insulation on WI inst. tubing | Replace insulation | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 24 | 0 | W17-18 | 2023-04-24 | 2023-04-28 | 2023-04-24 | 2021-10-10 | 2021-07-12 | 20 | REL | APPR OPND | HB /A /55 | INJECTION WELLS/FLOW-LINES/MANIFOLDS |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-INST | 2100051376 | Missing insulation on WI inst. tubing | 12 Roll, acc. mail Else marie brandt | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-28 | 2023-04-26 | 2021-10-10 | 2021-07-12 | 30 | REL | APPR OPND | HB /A /55 | INJECTION WELLS/FLOW-LINES/MANIFOLDS |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100051376 | Missing insulation on WI inst. tubing | Isolate/deisolate heat tracing | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 |  | 2023-04-24 | 2023-04-28 | 2023-04-26 | 2021-10-10 | 2021-07-12 | 40 | REL | APPR OPND | HB /A /55 | INJECTION WELLS/FLOW-LINES/MANIFOLDS |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-INST | 2100051376 | Missing insulation on WI inst. tubing | Check flow meters | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2023-04-24 | 2023-04-28 | 2023-04-28 | 2021-10-10 | 2021-07-12 | 50 | REL | APPR OPND | HB /A /55 | INJECTION WELLS/FLOW-LINES/MANIFOLDS |  | A |  | MIN | DK50
2024-W35-36 | 4 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100058725 | HBDC-HCV-415201-U internal leak in close | Isolate and depressurize system | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 | W35-36 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-11-06 | 2022-03-11 | 10 | REL | APPR OPND | HB /D /30/HBDC-HCV-415201-U | HCV UPSTREAM PSV-415201 | 99000119 | A |  | MMS | DK50
2024-W35-36 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058725 | HBDC-HCV-415201-U internal leak in close | Prepare for rigging out the valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1.5 | 0 | W35-36 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-11-06 | 2022-03-11 | 20 | REL | APPR OPND | HB /D /30/HBDC-HCV-415201-U | HCV UPSTREAM PSV-415201 | 99000119 | A |  | MMS | DK50
2024-W35-36 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100058725 | HBDC-HCV-415201-U internal leak in close | Dismantle passing ball valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1.5 | 0 | W35-36 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-11-06 | 2022-03-11 | 30 | REL | APPR OPND | HB /D /30/HBDC-HCV-415201-U | HCV UPSTREAM PSV-415201 | 99000119 | A |  | MMS | DK50
2024-W35-36 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058725 | HBDC-HCV-415201-U internal leak in close | Rig-out passing valve and drip ring | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 | W35-36 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-11-06 | 2022-03-11 | 40 | REL | APPR OPND | HB /D /30/HBDC-HCV-415201-U | HCV UPSTREAM PSV-415201 | 99000119 | A |  | MMS | DK50
2024-W35-36 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058725 | HBDC-HCV-415201-U internal leak in close | Rig-in new valve and drip ring | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 | W35-36 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-11-06 | 2022-03-11 | 50 | REL | APPR OPND | HB /D /30/HBDC-HCV-415201-U | HCV UPSTREAM PSV-415201 | 99000119 | A |  | MMS | DK50
2024-W35-36 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100058725 | HBDC-HCV-415201-U internal leak in close | Install new valve and drip ring | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1.5 | 0 | W35-36 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-11-06 | 2022-03-11 | 60 | REL | APPR OPND | HB /D /30/HBDC-HCV-415201-U | HCV UPSTREAM PSV-415201 | 99000119 | A |  | MMS | DK50
2024-W35-36 | 4 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100058725 | HBDC-HCV-415201-U internal leak in close | De-isolate, pressurize system and test f | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 | W35-36 | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2022-11-06 | 2022-03-11 | 70 | REL | APPR OPND | HB /D /30/HBDC-HCV-415201-U | HCV UPSTREAM PSV-415201 | 99000119 | A |  | MMS | DK50
2024-W35-36 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058725 | HBDC-HCV-415201-U internal leak in close | Remove rigging gear | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 | W35-36 | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2022-11-06 | 2022-03-11 | 80 | REL | APPR OPND | HB /D /30/HBDC-HCV-415201-U | HCV UPSTREAM PSV-415201 | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100058811 | HBDC-HCV-415103-U is intern leak. | Isolate and depressurize system | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-11-06 | 2022-03-11 | 10 | REL | APPR OPND | HB /D /32/HBDC-HCV-415103-U | BALL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058811 | HBDC-HCV-415103-U is intern leak. | Prepare for rigging out the valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-11-06 | 2022-03-11 | 20 | REL | APPR OPND | HB /D /32/HBDC-HCV-415103-U | BALL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100058811 | HBDC-HCV-415103-U is intern leak. | Dismantle passing ball valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-11-06 | 2022-03-11 | 30 | REL | APPR OPND | HB /D /32/HBDC-HCV-415103-U | BALL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058811 | HBDC-HCV-415103-U is intern leak. | Rig-out passing valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-11-06 | 2022-03-11 | 40 | REL | APPR OPND | HB /D /32/HBDC-HCV-415103-U | BALL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058811 | HBDC-HCV-415103-U is intern leak. | Rig-in new valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-11-06 | 2022-03-11 | 50 | REL | APPR OPND | HB /D /32/HBDC-HCV-415103-U | BALL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100058811 | HBDC-HCV-415103-U is intern leak. | Mount new valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-11-06 | 2022-03-11 | 60 | REL | APPR OPND | HB /D /32/HBDC-HCV-415103-U | BALL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100058811 | HBDC-HCV-415103-U is intern leak. | Pressurize system and test for leakages | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2022-11-06 | 2022-03-11 | 70 | REL | APPR OPND | HB /D /32/HBDC-HCV-415103-U | BALL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058811 | HBDC-HCV-415103-U is intern leak. | Remove rigging gear | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2022-11-06 | 2022-03-11 | 80 | REL | APPR OPND | HB /D /32/HBDC-HCV-415103-U | BALL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061047 | Leak from seawater filter motor 5369 | Leak from seawater filter motor 5369 | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-23 | 2024-03-11 | 2022-04-29 | 2022-01-29 | 10 | REL | APPR OPND | HB /D /51/HBDB-XM-5369 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100061047 | Leak from seawater filter motor 5369 | Prepare rigging equipment | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 | W27-28 | 2024-03-11 | 2024-03-23 | 2024-03-11 | 2022-04-29 | 2022-01-29 | 20 | REL | APPR OPND | HB /D /51/HBDB-XM-5369 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061047 | Leak from seawater filter motor 5369 | Prepare matr/tool | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 | W27-28 | 2024-03-11 | 2024-03-23 | 2024-03-12 | 2022-04-29 | 2022-01-29 | 30 | REL | APPR OPND | HB /D /51/HBDB-XM-5369 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100061047 | Leak from seawater filter motor 5369 | Production isolation | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 | W27-28 | 2024-03-11 | 2024-03-23 | 2024-03-13 | 2022-04-29 | 2022-01-29 | 40 | REL | APPR OPND | HB /D /51/HBDB-XM-5369 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100061047 | Leak from seawater filter motor 5369 | Rigger assistance Rig up/down | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 | W27-28 | 2024-03-11 | 2024-03-23 | 2024-03-14 | 2022-04-29 | 2022-01-29 | 50 | REL | APPR OPND | HB /D /51/HBDB-XM-5369 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100061047 | Leak from seawater filter motor 5369 | Electrical assistance on cable | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 8 | 0 | W27-28 | 2024-03-11 | 2024-03-23 | 2024-03-15 | 2022-04-29 | 2022-01-29 | 60 | REL | APPR OPND | HB /D /51/HBDB-XM-5369 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061047 | Leak from seawater filter motor 5369 | Backwash Gear/motor removal | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 8 | 0 | W27-28 | 2024-03-11 | 2024-03-23 | 2024-03-17 | 2022-04-29 | 2022-01-29 | 70 | REL | APPR OPND | HB /D /51/HBDB-XM-5369 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061047 | Leak from seawater filter motor 5369 | Rectify worn out parts | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 8 | 0 | W27-28 | 2024-03-11 | 2024-03-23 | 2024-03-18 | 2022-04-29 | 2022-01-29 | 80 | REL | APPR OPND | HB /D /51/HBDB-XM-5369 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061047 | Leak from seawater filter motor 5369 | Backwash Gear/motor install | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 8 | 0 | W27-28 | 2024-03-11 | 2024-03-23 | 2024-03-20 | 2022-04-29 | 2022-01-29 | 90 | REL | APPR OPND | HB /D /51/HBDB-XM-5369 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100061047 | Leak from seawater filter motor 5369 | Production de-isolation w leaktest | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 | W27-28 | 2024-03-11 | 2024-03-23 | 2024-03-22 | 2022-04-29 | 2022-01-29 | 100 | REL | APPR OPND | HB /D /51/HBDB-XM-5369 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061047 | Leak from seawater filter motor 5369 | Function test | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 | W27-28 | 2024-03-11 | 2024-03-23 | 2024-03-22 | 2022-04-29 | 2022-01-29 | 110 | REL | APPR OPND | HB /D /51/HBDB-XM-5369 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100063774 | Seep from FCV-445205 upstream hub | prep rigging equipment | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2023-06-11 | 2022-08-15 | 10 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100063774 | Seep from FCV-445205 upstream hub | Prepare tools | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2023-06-11 | 2022-08-15 | 20 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100063774 | Seep from FCV-445205 upstream hub | ICC | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2023-06-11 | 2022-08-15 | 30 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-INST | 2100063774 | Seep from FCV-445205 upstream hub | Remove supply and power cables | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2023-06-11 | 2022-08-15 | 40 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100063774 | Seep from FCV-445205 upstream hub | Remove valve from line | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2023-06-11 | 2022-08-15 | 50 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100063774 | Seep from FCV-445205 upstream hub | Assist | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 12 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2023-06-11 | 2022-08-15 | 60 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100063774 | Seep from FCV-445205 upstream hub | Inspect sealing surface | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2023-06-11 | 2022-08-15 | 70 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100063774 | Seep from FCV-445205 upstream hub | install valve | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2023-06-11 | 2022-08-15 | 80 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100063774 | Seep from FCV-445205 upstream hub | Assist | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 12 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2023-06-11 | 2022-08-15 | 90 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-INST | 2100063774 | Seep from FCV-445205 upstream hub | Connect supply and power cables | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2023-06-11 | 2022-08-15 | 100 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100063774 | Seep from FCV-445205 upstream hub | De-isolate, leak test | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2023-06-11 | 2022-08-15 | 110 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100063774 | Seep from FCV-445205 upstream hub | lifting plan and permit prep | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 20 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2023-06-11 | 2022-08-15 | 120 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100063774 | Seep from FCV-445205 upstream hub | add mat. | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2023-06-11 | 2022-08-15 | 130 | REL | APPR OPND | HB /D /31/HBDC-FCV-445205 | FLOW CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100079874 | Ringmain valve HCV 030175. Loss of integ | Rigging prework | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 12 | 0 |  | 2024-03-11 | 2024-03-16 | 2024-03-11 | 2023-06-17 | 2023-02-02 | 10 | REL | APPR OPND | HB /D /01/HBDB-HCV-030175 | BUTTERFLY VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100079874 | Ringmain valve HCV 030175. Loss of integ | Isolate valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-16 | 2024-03-12 | 2023-06-17 | 2023-02-02 | 20 | REL | APPR OPND | HB /D /01/HBDB-HCV-030175 | BUTTERFLY VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079874 | Ringmain valve HCV 030175. Loss of integ | changeout valve | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 |  | 2024-03-11 | 2024-03-16 | 2024-03-13 | 2023-06-17 | 2023-02-02 | 30 | REL | APPR OPND | HB /D /01/HBDB-HCV-030175 | BUTTERFLY VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100079874 | Ringmain valve HCV 030175. Loss of integ | rigging assistance | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 12 | 0 |  | 2024-03-11 | 2024-03-16 | 2024-03-13 | 2023-06-17 | 2023-02-02 | 40 | REL | APPR OPND | HB /D /01/HBDB-HCV-030175 | BUTTERFLY VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100079874 | Ringmain valve HCV 030175. Loss of integ | deisolate | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-16 | 2024-03-14 | 2023-06-17 | 2023-02-02 | 50 | REL | APPR OPND | HB /D /01/HBDB-HCV-030175 | BUTTERFLY VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100079874 | Ringmain valve HCV 030175. Loss of integ | Rigging postwork | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 12 | 0 |  | 2024-03-11 | 2024-03-16 | 2024-03-15 | 2023-06-17 | 2023-02-02 | 60 | REL | APPR OPND | HB /D /01/HBDB-HCV-030175 | BUTTERFLY VALVE |  | F |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100087435 | Thread on 1" HCV Leaking. Instr. air | Isolate accordingly | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2026-02-11 | 2023-08-26 | 10 | REL | APPR OPND | HB /D /02/HBDB-EMS-061001 | SAFETY SHOWER WITH EYEWASH |  | D |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087435 | Thread on 1" HCV Leaking. Instr. air | Replace leaking 1" HCV Instr. air | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2026-02-11 | 2023-08-26 | 20 | REL | APPR OPND | HB /D /02/HBDB-EMS-061001 | SAFETY SHOWER WITH EYEWASH |  | D |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100087435 | Thread on 1" HCV Leaking. Instr. air | De-isolate | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2026-02-11 | 2023-08-26 | 30 | REL | APPR OPND | HB /D /02/HBDB-EMS-061001 | SAFETY SHOWER WITH EYEWASH |  | D |  | MMS | DK50
0 | 3 | HDAHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100087439 | S/D tie-in valve internpassing HCV-30398 | Installation of rigging gear | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-09-04 | 2023-04-22 | 10 | PCNF REL | APPR OPND | HD /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL VALVES |  | F |  | MMS | DK60
0 | 3 | HDAHPSEP | WDF | MTN-MECH | PRODTECH | 2100087439 | S/D tie-in valve internpassing HCV-30398 | Safing of HCV | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-09-04 | 2023-04-22 | 20 | PCNF REL | APPR OPND | HD /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL VALVES |  | F |  | MMS | DK60
0 | 3 | HDAHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100087439 | S/D tie-in valve internpassing HCV-30398 | Riggerassist | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 16 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-09-04 | 2023-04-22 | 30 | PCNF REL | APPR OPND | HD /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL VALVES |  | F |  | MMS | DK60
0 | 3 | HDAHPSEP | WDF | MTN-MECH | MTN-MECH | 2100087439 | S/D tie-in valve internpassing HCV-30398 | Replacement of HCV | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 20 | 6 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-09-04 | 2023-04-22 | 40 | PCNF REL | APPR OPND | HD /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL VALVES |  | F |  | MMS | DK60
0 | 3 | HDAHPSEP | WDF | MTN-MECH | PRODTECH | 2100087439 | S/D tie-in valve internpassing HCV-30398 | Desafing and leak test | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-09-04 | 2023-04-22 | 50 | PCNF REL | APPR OPND | HD /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL VALVES |  | F |  | MMS | DK60
0 | 3 | HDAHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100087439 | S/D tie-in valve internpassing HCV-30398 | Demolish rigging gear | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-09-04 | 2023-04-22 | 60 | PCNF REL | APPR OPND | HD /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL VALVES |  | F |  | MMS | DK60
0 | 3 | HDAHPSEP | WDF | MTN-MECH | MTN-MECH | 2100087439 | S/D tie-in valve internpassing HCV-30398 | Drivning plates | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 0 | 15 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-09-04 | 2023-04-22 | 70 | PCNF REL | APPR OPND | HD /A /10/SYSTEM-10-MANUAL-VALVES | SYSTEM 10 MANUAL VALVES |  | F |  | MMS | DK60
2024-W33-34 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100090883 | Fault on VFC MOXA-1 port 9 | Isolation of the converter | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0.5 | 0 | W33-34 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-07-01 | 2023-05-17 | 20 | PCNF REL | APPR OPND | HB /D /35/HBDC-FP-3750 | FLOW COMPUTER UCP |  | C |  | MIN | DK50
2024-W33-34 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100090883 | Fault on VFC MOXA-1 port 9 | Install new convereter | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1.5 | 0 | W33-34 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-07-01 | 2023-05-17 | 30 | PCNF REL | APPR OPND | HB /D /35/HBDC-FP-3750 | FLOW COMPUTER UCP |  | C |  | MIN | DK50
2024-W33-34 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100090883 | Fault on VFC MOXA-1 port 9 | Deisolate new converter | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0.5 | 0 | W33-34 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-07-01 | 2023-05-17 | 40 | PCNF REL | APPR OPND | HB /D /35/HBDC-FP-3750 | FLOW COMPUTER UCP |  | C |  | MIN | DK50
2024-W33-34 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100090883 | Fault on VFC MOXA-1 port 9 | Test new converter | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1.5 | 0 | W33-34 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-07-01 | 2023-05-17 | 50 | PCNF REL | APPR OPND | HB /D /35/HBDC-FP-3750 | FLOW COMPUTER UCP |  | C |  | MIN | DK50
2024-W15-16 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100094510 | 11 kV busbar malfunction alarm | 11 kV busbar malfunction alarm | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2023-08-24 | 2023-07-10 | 10 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851-K07 | BUS TIE BREAKER |  | A |  | MEL | DK50 |  | PROK | 2024-04-10
2024-W15-16 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100094510 | 11 kV busbar malfunction alarm | Troubleshoot Scada alarm | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 5 | 4 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2023-08-24 | 2023-07-10 | 20 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851-K07 | BUS TIE BREAKER |  | A |  | MEL | DK50 |  | PROK | 2024-04-11
2024-W15-16 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100094510 | 11 kV busbar malfunction alarm | Additional parts | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2023-08-24 | 2023-07-10 | 30 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851-K07 | BUS TIE BREAKER |  | A |  | MEL | DK50 |  | PROK | 2024-04-12
2024-W15-16 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094576 | Defekt HPFI relay in HBDD-DP-1960A | Defekt HPFI relay in HBDD-DP-1960A | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-01-05 | 2023-08-23 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A | SECTION A |  | A |  | MEL | DK50 |  | PROK | 2024-04-16
2024-W15-16 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094576 | Defekt HPFI relay in HBDD-DP-1960A | Isolate Equipment. | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-01-05 | 2023-08-23 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A | SECTION A |  | A |  | MEL | DK50 |  | PROK | 2024-04-17
2024-W15-16 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094576 | Defekt HPFI relay in HBDD-DP-1960A | Replace defective relay | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-01-05 | 2023-08-23 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A | SECTION A |  | A |  | MEL | DK50 |  | PROK | 2024-04-18
2024-W15-16 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094576 | Defekt HPFI relay in HBDD-DP-1960A | De-isolate Equipment | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-01-05 | 2023-08-23 | 40 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A | SECTION A |  | A |  | MEL | DK50 |  | PROK | 2024-04-19
2024-W15-16 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094576 | Defekt HPFI relay in HBDD-DP-1960A | Test & put back in service | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0.5 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-01-05 | 2023-08-23 | 50 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A | SECTION A |  | A |  | MEL | DK50 |  | PROK | 2024-04-20
2026-W13-14 | 3 | HBB04-GL | WGN | MTN-ROPE | MTN-MECH | 2200005625 | SYNPR Replacement of dog bone spool lift | Replacement of dog bone spool lift gas | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2021-02-13 | 2020-11-15 | 10 | REL | APPR OPND | HB /B /70/P-G | PIPING GROUP | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WGN | MTN-ROPE | PRODTECH | 2200005625 | SYNPR Replacement of dog bone spool lift | Safing and shut down of lift gas | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2021-02-13 | 2020-11-15 | 20 | REL | APPR OPND | HB /B /70/P-G | PIPING GROUP | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WGN | MTN-ROPE | MTN-ROPE | 2200005625 | SYNPR Replacement of dog bone spool lift | Build scaffold for acces to manifold | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2021-02-13 | 2020-11-15 | 40 | REL | APPR OPND | HB /B /70/P-G | PIPING GROUP | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WGN | MTN-ROPE | MTN-ROPE | 2200005625 | SYNPR Replacement of dog bone spool lift | Rig up gear for lifting manifold | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2021-02-13 | 2020-11-15 | 41 | REL | APPR OPND | HB /B /70/P-G | PIPING GROUP | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WGN | MTN-ROPE | MTN-ROPE | 2200005625 | SYNPR Replacement of dog bone spool lift | Loosen u-bolts on manifold and clamps | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 12 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2021-02-13 | 2020-11-15 | 50 | REL | APPR OPND | HB /B /70/P-G | PIPING GROUP | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WGN | MTN-ROPE | MTN-ROPE | 2200005625 | SYNPR Replacement of dog bone spool lift | lift up mainfold for change out spool | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2021-02-13 | 2020-11-15 | 60 | REL | APPR OPND | HB /B /70/P-G | PIPING GROUP | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WGN | MTN-ROPE | MTN-ROPE | 2200005625 | SYNPR Replacement of dog bone spool lift | Change spool PTW 2026781 | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 18 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2021-02-13 | 2020-11-15 | 70 | REL | APPR OPND | HB /B /70/P-G | PIPING GROUP | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WGN | MTN-ROPE | MTN-ROPE | 2200005625 | SYNPR Replacement of dog bone spool lift | lower down manifold | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2021-02-13 | 2020-11-15 | 80 | REL | APPR OPND | HB /B /70/P-G | PIPING GROUP | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WGN | MTN-ROPE | MTN-ROPE | 2200005625 | SYNPR Replacement of dog bone spool lift | check and tighten spool | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 12 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2021-02-13 | 2020-11-15 | 90 | REL | APPR OPND | HB /B /70/P-G | PIPING GROUP | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WGN | MTN-ROPE | MTN-ROPE | 2200005625 | SYNPR Replacement of dog bone spool lift | Dismantle rigging gear - scaffold | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2021-02-13 | 2020-11-15 | 100 | REL | APPR OPND | HB /B /70/P-G | PIPING GROUP | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WGN | MTN-ROPE | MTN-MECH | 2200005625 | SYNPR Replacement of dog bone spool lift | Additional materials 2 " Blinds | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2021-02-13 | 2020-11-15 | 110 | REL | APPR OPND | HB /B /70/P-G | PIPING GROUP | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WGN | MTN-ROPE | VEN-MECH | 2200005625 | SYNPR Replacement of dog bone spool lift | Genbestilling af: HBB-2-GPS-290501-GF | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2021-02-13 | 2020-11-15 | 120 | REL | INIT OPND | HB /B /70/P-G | PIPING GROUP | 99000119 | C |  | MFM | DK50
2024-W43-44 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012727 | Replace HBDB-PSV-345501 - PSV 2023 | Isolation of PSV | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 | W43-44 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2025-11-19 | 2023-06-03 | 10 | REL | APPR OPND | HB /D /27/HBDB-PSV-345501 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W43-44 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012727 | Replace HBDB-PSV-345501 - PSV 2023 | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 | W43-44 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2025-11-19 | 2023-06-03 | 20 | REL | APPR OPND | HB /D /27/HBDB-PSV-345501 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W43-44 | 4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012727 | Replace HBDB-PSV-345501 - PSV 2023 | Remove PSV and install new PSV | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 5 | 0 | W43-44 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2025-11-19 | 2023-06-03 | 30 | REL | APPR OPND | HB /D /27/HBDB-PSV-345501 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W43-44 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012727 | Replace HBDB-PSV-345501 - PSV 2023 | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 | W43-44 | 2024-03-11 | 2024-03-14 | 2024-03-13 | 2025-11-19 | 2023-06-03 | 50 | REL | APPR OPND | HB /D /27/HBDB-PSV-345501 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W43-44 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012727 | Replace HBDB-PSV-345501 - PSV 2023 | De-isolation and leak test | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 | W43-44 | 2024-03-11 | 2024-03-14 | 2024-03-13 | 2025-11-19 | 2023-06-03 | 70 | REL | APPR OPND | HB /D /27/HBDB-PSV-345501 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211406 | 4Y 400V E-SWB INSP HBDD-N-1855-A06 | ISOLATION BY PRODUCTION | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-09-01 | 2022-06-20 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A06 | SECTION A06 |  | C | DKHB-0421 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211406 | 4Y 400V E-SWB INSP HBDD-N-1855-A06 | 400V E-SWB INSP HBDD-N-1855-A06 | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 18 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-09-01 | 2022-06-20 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A06 | SECTION A06 |  | C | DKHB-0421 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211406 | 4Y 400V E-SWB INSP HBDD-N-1855-A06 | 400V E-SWB INSP HBDD-N-1855-A06 | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-09-01 | 2022-06-20 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A06 | SECTION A06 |  | C | DKHB-0421 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211406 | 4Y 400V E-SWB INSP HBDD-N-1855-A06 | DE-ISOLATION BY PRODUCTION | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-09-01 | 2022-06-20 | 40 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A06 | SECTION A06 |  | C | DKHB-0421 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400211406 | 4Y 400V E-SWB INSP HBDD-N-1855-A06 | Additional parts | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-09-01 | 2022-06-20 | 50 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A06 | SECTION A06 |  | C | DKHB-0421 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211462 | 4Y 400V N-SWB MAINT HBDD-N-1854 | ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2024-07-05 | 2024-07-06 | 2024-07-05 | 2022-11-01 | 2022-08-05 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854 | 400V PROCESS/UTILITY SWITCHBOARD |  | C | DKHB-0580 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211462 | 4Y 400V N-SWB MAINT HBDD-N-1854 | 400V N-SWB MAINT HBDD-N-1854 | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2024-07-05 | 2024-07-06 | 2024-07-05 | 2022-11-01 | 2022-08-05 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854 | 400V PROCESS/UTILITY SWITCHBOARD |  | C | DKHB-0580 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211462 | 4Y 400V N-SWB MAINT HBDD-N-1854 | DE-ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2024-07-05 | 2024-07-06 | 2024-07-05 | 2022-11-01 | 2022-08-05 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854 | 400V PROCESS/UTILITY SWITCHBOARD |  | C | DKHB-0580 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400211462 | 4Y 400V N-SWB MAINT HBDD-N-1854 | Materials | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 |  | 2024-07-05 | 2024-07-06 | 2024-07-06 | 2022-11-01 | 2022-08-05 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1854 | 400V PROCESS/UTILITY SWITCHBOARD |  | C | DKHB-0580 | MEL | DK50 | EL0024
0 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400219476 | 3Y HDA GAS EXP. TO DFF - METER. (VENDOR) | ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 | 24-W07-08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2022-12-21 | 2022-10-08 | 10 | REL | APPR OPND | HD /A /34/METERING | METERING PRODUCED GAS, TRANSFER |  | A | DKHD-6016 | MIN | DK60 | IN0013
0 | C | NOSD | WPM | MTN-INST | MTN-INST | 2400219476 | 3Y HDA GAS EXP. TO DFF - METER. (VENDOR) | Vendor Assistance for metering maint | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 | 24-W07-08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2022-12-21 | 2022-10-08 | 20 | REL | APPR OPND | HD /A /34/METERING | METERING PRODUCED GAS, TRANSFER |  | A | DKHD-6016 | MIN | DK60 | IN0013
0 | C | NOSD | WPM | MTN-INST | VEN-INST | 2400219476 | 3Y HDA GAS EXP. TO DFF - METER. (VENDOR) | HDA GAS EXP. TO DFF - METER. (VENDOR) | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 12 | 0 | 24-W07-08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2022-12-21 | 2022-10-08 | 30 | REL | APPR OPND | HD /A /34/METERING | METERING PRODUCED GAS, TRANSFER |  | A | DKHD-6016 | MIN | DK60 | IN0013
0 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400219476 | 3Y HDA GAS EXP. TO DFF - METER. (VENDOR) | DE-ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 | 24-W07-08 | 2024-09-18 | 2024-09-20 | 2024-09-20 | 2022-12-21 | 2022-10-08 | 40 | REL | APPR OPND | HD /A /34/METERING | METERING PRODUCED GAS, TRANSFER |  | A | DKHD-6016 | MIN | DK60 | IN0013
2024-W31-32 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400241224 | 5Y HBDB-FIT-507601 - PW METERING | ISOLATION BY PRODUCTION | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 | W31-32 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-04-10 | 2023-01-04 | 10 | PCNF REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
2024-W31-32 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400241224 | 5Y HBDB-FIT-507601 - PW METERING | DISASSEMBLY OF METERING | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 | W31-32 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-04-10 | 2023-01-04 | 20 | PCNF REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
2024-W31-32 | C | NOSD | WPM | MTN-INST | MTN-RIGG | 2400241224 | 5Y HBDB-FIT-507601 - PW METERING | RIGGING SUPPORT | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 | W31-32 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-04-10 | 2023-01-04 | 30 | PCNF REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
2024-W31-32 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400241224 | 5Y HBDB-FIT-507601 - PW METERING | ASSEMBLY OF METERING | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 | W31-32 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-04-10 | 2023-01-04 | 50 | PCNF REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
2024-W31-32 | C | NOSD | WPM | MTN-INST | MTN-RIGG | 2400241224 | 5Y HBDB-FIT-507601 - PW METERING | DE-RIGGING SUPPORT | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 | W31-32 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-04-10 | 2023-01-04 | 60 | PCNF REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
2024-W31-32 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400241224 | 5Y HBDB-FIT-507601 - PW METERING | DE-ISOLATION BY PRODUCTION | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 | W31-32 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-04-10 | 2023-01-04 | 70 | PCNF REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A | DKHB-6008 | MIN | DK50 | IN0014
0 | D | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400241571 | 1Y HVAC REFRIG PROVISIONS HDBF-A-1212A/B | 1Y HVAC REFRIG PROVISIONS CHECK | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 24 | 0 | W17-W18 | 2024-04-25 | 2024-04-28 | 2024-04-25 | 2023-04-16 | 2023-02-28 | 10 | REL | APPR OPND | HD /B /09/HDBF-A-1212A | AIR COOLED CONDENSER |  | A | DKHD-2017 | MEL | DK60 | EL0013
0 | D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241571 | 1Y HVAC REFRIG PROVISIONS HDBF-A-1212A/B | SUPPORT TO VENDOR | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 6 | 0 | W17-W18 | 2024-04-25 | 2024-04-28 | 2024-04-27 | 2023-04-16 | 2023-02-28 | 20 | REL | APPR OPND | HD /B /09/HDBF-A-1212A | AIR COOLED CONDENSER |  | A | DKHD-2017 | MEL | DK60 | EL0013
0 | D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241571 | 1Y HVAC REFRIG PROVISIONS HDBF-A-1212A/B | Shipping of R513A Refrigiant | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 0 | 0 | W17-W18 | 2024-04-25 | 2024-04-28 | 2024-04-28 | 2023-04-16 | 2023-02-28 | 30 | REL | APPR OPND | HD /B /09/HDBF-A-1212A | AIR COOLED CONDENSER |  | A | DKHD-2017 | MEL | DK60 | EL0013
0 | D | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400258833 | 1Y EXERCISE EQUIPMENT VENDOR | TREADMILL | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-05-29 | 2023-04-12 | 20 | REL | APPR OPND | HD /B /82/GYM-EQUIPMENT | GYM EQUIPMENT |  | A | DKHD-2033 | MEL | DK60 | EL0103
0 | D | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400258833 | 1Y EXERCISE EQUIPMENT VENDOR | EXERCISE AND SPINNING BIKES | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-05-29 | 2023-04-12 | 40 | REL | APPR OPND | HD /B /82/GYM-EQUIPMENT | GYM EQUIPMENT |  | A | DKHD-2033 | MEL | DK60 | EL0103
0 | D | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400258833 | 1Y EXERCISE EQUIPMENT VENDOR | CROSSTRAINER | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-05-29 | 2023-04-12 | 50 | REL | APPR OPND | HD /B /82/GYM-EQUIPMENT | GYM EQUIPMENT |  | A | DKHD-2033 | MEL | DK60 | EL0103
0 | D | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400258833 | 1Y EXERCISE EQUIPMENT VENDOR | ROWING MACHINE | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-05-29 | 2023-04-12 | 70 | REL | APPR OPND | HD /B /82/GYM-EQUIPMENT | GYM EQUIPMENT |  | A | DKHD-2033 | MEL | DK60 | EL0103
0 | D | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400258833 | 1Y EXERCISE EQUIPMENT VENDOR | MULTI MACH. BENCHES, WEIGHTS, & BARBELLS | REL PRT GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-05-29 | 2023-04-12 | 100 | REL | APPR OPND | HD /B /82/GYM-EQUIPMENT | GYM EQUIPMENT |  | A | DKHD-2033 | MEL | DK60 | EL0103
2026-W13-14 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400281946 | 1Y HBDC-FE-365112 - METERING. | ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2023-10-19 | 2023-09-13 | 10 | REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6005 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400281946 | 1Y HBDC-FE-365112 - METERING. | DISASSEMBLY OF METERING | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 |  | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2023-10-19 | 2023-09-13 | 20 | REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6005 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-RIGG | 2400281946 | 1Y HBDC-FE-365112 - METERING. | RIGGING SUPPORT | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-15 | 2024-03-12 | 2023-10-19 | 2023-09-13 | 30 | REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6005 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-INST | 2400281946 | 1Y HBDC-FE-365112 - METERING. | HBDC-FE-365112 - METERING | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 2.8 | 0 |  | 2024-03-11 | 2024-03-15 | 2024-03-12 | 2023-10-19 | 2023-09-13 | 40 | REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6005 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-RIGG | 2400281946 | 1Y HBDC-FE-365112 - METERING. | DE-RIGGING SUPPORT | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-15 | 2024-03-13 | 2023-10-19 | 2023-09-13 | 50 | REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6005 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400281946 | 1Y HBDC-FE-365112 - METERING. | ASSEMBLY OF METERING | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 4 | 0 |  | 2024-03-11 | 2024-03-15 | 2024-03-13 | 2023-10-19 | 2023-09-13 | 60 | REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6005 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400281946 | 1Y HBDC-FE-365112 - METERING. | DE-ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-15 | 2024-03-14 | 2023-10-19 | 2023-09-13 | 70 | REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6005 | MIN | DK50 | IN0014
0 | C | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400330065 | 1Y WASHING AND DRYING MACHINES VENDOR | WASHING AND DRYING MACHINES VENDOR | REL GMPS MACM PRC SETC | APPR SMAT AWSC RDBL | 12 | 0 |  | 2024-05-23 | 2024-05-24 | 2024-05-23 | 2024-06-28 | 2024-05-23 | 10 | REL | APPR OPND | HD /B /82/LAUNDRY-EQUIPMENT | LAUNDRY EQUIPMENT |  | A | DKHD-2039 | MEL | DK60 | EL0103
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400333192 | 1Y WASHING AND DRYING MACHINES VENDOR | WASHING AND DRYING MACHINES | REL GMPS MACM PRC SETC | APPR SMAT AWSC RDBL | 12 | 0 |  | 2024-05-29 | 2024-05-30 | 2024-05-29 | 2024-07-04 | 2024-05-29 | 10 | REL | APPR OPND | HB /C /82/LAUNDRY-EQUIPMENT | LAUNDRY EQUIPMENT |  | A | DKHB-2071 | MEL | DK50 | EL0104
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100025871 | HBA Flanges on Deluge XCV heavily corr | Flanges on Deluge XCV heavily corr. | REL GMPS MANC PRC SETC | APPR SMAT AWSC | 0 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2019-03-09 | 2018-12-09 | 10 | REL | APPR OPND | HB /A /01/HBAA-XCV-03710 | 8" DELUGE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100025871 | HBA Flanges on Deluge XCV heavily corr | Prepare the work site, and place riggere | REL GMPS MANC PRC SETC | APPR SMAT AWSC | 3 | 0 | 2100025901+ 25900 + 25903 | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2019-03-09 | 2018-12-09 | 20 | REL | APPR OPND | HB /A /01/HBAA-XCV-03710 | 8" DELUGE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100025871 | HBA Flanges on Deluge XCV heavily corr | Isolate XCV-03710 - Prod | REL GMPS MANC PRC SETC | APPR SMAT AWSC | 2 | 0 | 2100025901+ 25900 + 25903 | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2019-03-09 | 2018-12-09 | 30 | REL | APPR OPND | HB /A /01/HBAA-XCV-03710 | 8" DELUGE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100025871 | HBA Flanges on Deluge XCV heavily corr | Replace XCV-03710 - Mech | REL GMPS MANC PRC SETC | APPR SMAT AWSC | 8 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2019-03-09 | 2018-12-09 | 40 | REL | APPR OPND | HB /A /01/HBAA-XCV-03710 | 8" DELUGE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100025871 | HBA Flanges on Deluge XCV heavily corr | Ass - replace XCV-03710 - Scaf | REL GMPS MANC PRC SETC | APPR SMAT AWSC | 8 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2019-03-09 | 2018-12-09 | 50 | REL | APPR OPND | HB /A /01/HBAA-XCV-03710 | 8" DELUGE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100025871 | HBA Flanges on Deluge XCV heavily corr | Replace pilot-valve - Mech | REL GMPS MANC PRC SETC | APPR SMAT AWSC | 3 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2019-03-09 | 2018-12-09 | 60 | REL | APPR OPND | HB /A /01/HBAA-XCV-03710 | 8" DELUGE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100025871 | HBA Flanges on Deluge XCV heavily corr | de-Isolate XCV-03710 - Prod | REL GMPS MANC PRC SETC | APPR SMAT AWSC | 2 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-06 | 2019-03-09 | 2018-12-09 | 70 | REL | APPR OPND | HB /A /01/HBAA-XCV-03710 | 8" DELUGE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100025871 | HBA Flanges on Deluge XCV heavily corr | cleaning work site - Scaf | REL GMPS MANC PRC SETC | APPR SMAT AWSC | 3 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-06 | 2019-03-09 | 2018-12-09 | 80 | REL | APPR OPND | HB /A /01/HBAA-XCV-03710 | 8" DELUGE VALVE | 99000119 | C |  | MMS | DK50
2024-W23-24 | 4 | HBA11-GL | WDF | MTN-INST | MTN-INST | 2100026226 | Pressure test of PI under Gorm SD | L3 Isolate PI-30112 | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC | 1 | 0 | PTW 254747 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-01-19 | 2019-01-24 | 10 | PCNF REL | APPR OPND | HB /A /10/HBA11-WELLHEAD | HBA11 WELLHEAD | 99000119 | C |  | MIN | DK50
2024-W23-24 | 4 | HBA11-GL | WDF | MTN-INST | MTN-INST | 2100026226 | Pressure test of PI under Gorm SD | L3 Change out PI-30112 | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-01-19 | 2019-01-24 | 20 | PCNF REL | APPR OPND | HB /A /10/HBA11-WELLHEAD | HBA11 WELLHEAD | 99000119 | C |  | MIN | DK50
2024-W23-24 | 4 | HBA11-GL | WDF | MTN-INST | MTN-INST | 2100026226 | Pressure test of PI under Gorm SD | L3 De-isolate PI-30112 | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC | 1 | 0 | Gorm SD ( material outsta | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-01-19 | 2019-01-24 | 30 | PCNF REL | APPR OPND | HB /A /10/HBA11-WELLHEAD | HBA11 WELLHEAD | 99000119 | C |  | MIN | DK50
2024-W23-24 | 4 | HBA11-GL | WDF | MTN-INST | MTN-INST | 2100026226 | Pressure test of PI under Gorm SD | L3 Test new PI-30112 | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWSC | 0.5 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-01-19 | 2019-01-24 | 40 | PCNF REL | APPR OPND | HB /A /10/HBA11-WELLHEAD | HBA11 WELLHEAD | 99000119 | C |  | MIN | DK50
0 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400274222 | 6M FLARE SYSTEM LUBRICATION HDA | FLARE SYSTEM LUBRICATION HDA | REL GMPS MANC PRC SETC | APPR SMAT AWSC | 2 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-09-21 | 2023-09-05 | 10 | REL | APPR OPND | HD /A /36/HP-FLARE-SYSTEM | HP FLARE SYSTEM |  | A | DKHD-0056 | MMR | DK60 | MR0143 | PROK
0 | C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400274222 | 6M FLARE SYSTEM LUBRICATION HDA | FLARE SYSTEM LUBRICATION HDA | REL GMPS MANC PRC SETC | APPR SMAT AWSC | 1 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-09-21 | 2023-09-05 | 20 | REL | APPR OPND | HD /A /36/HP-FLARE-SYSTEM | HP FLARE SYSTEM |  | A | DKHD-0056 | MMR | DK60 | MR0143 | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100044168 | HBA/78: faultfind on Oil leak on emerg. | Isolate | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2021-05-04 | 2021-02-03 | 20 | PCNF REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100044168 | HBA/78: faultfind on Oil leak on emerg. | Replace new O-rings | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL ROUT | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2021-05-04 | 2021-02-03 | 30 | PCNF REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100044168 | HBA/78: faultfind on Oil leak on emerg. | De-isolate | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2021-05-04 | 2021-02-03 | 40 | PCNF REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100044168 | HBA/78: faultfind on Oil leak on emerg. | QC, functioncheck, Clean-up | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2021-05-04 | 2021-02-03 | 50 | PCNF REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100049947 | HBD/78: Leaks from hydraulic hose | Isolation/deisolation of crane | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL ROUT | 4 | 0 | W05-W06 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2021-09-03 | 2021-06-05 | 100 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100049947 | HBD/78: Leaks from hydraulic hose | Build/remove scaffold | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL ROUT | 24 | 6 | W05-W06 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2021-09-03 | 2021-06-05 | 110 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100049947 | HBD/78: Leaks from hydraulic hose | Replace 18 hydraulic hoses | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL ROUT | 24 | 0 | W05-W06 | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2021-09-03 | 2021-06-05 | 120 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100049947 | HBD/78: Leaks from hydraulic hose | Operating crane and assist VEN-CRAN | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL ROUT | 6 | 0 | W05-W06 | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2021-09-03 | 2021-06-05 | 130 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100052322 | HBA/78: Replace oil on add. brake Aux.ho | Locate spare parts and conduct TBT | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2021-10-29 | 2021-07-31 | 10 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100052322 | HBA/78: Replace oil on add. brake Aux.ho | Isolate Crane | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2021-10-29 | 2021-07-31 | 20 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100052322 | HBA/78: Replace oil on add. brake Aux.ho | Replace oil, breather and plugs | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 3 | 0 | W15-W16 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2021-10-29 | 2021-07-31 | 30 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100052322 | HBA/78: Replace oil on add. brake Aux.ho | De-isolate crane | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2021-10-29 | 2021-07-31 | 40 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100052322 | HBA/78: Replace oil on add. brake Aux.ho | Ass. function test | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2021-10-29 | 2021-07-31 | 50 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100052322 | HBA/78: Replace oil on add. brake Aux.ho | Function and leak test of crane | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2021-10-29 | 2021-07-31 | 60 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100052322 | HBA/78: Replace oil on add. brake Aux.ho | Documentation | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2021-10-29 | 2021-07-31 | 70 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100073538 | HBA/78: Replace worn fuel hoses | Isolation/deisolation of crane | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 4 | 0 | W15-W16 | 2024-03-13 | 2024-03-19 | 2024-03-13 | 2023-02-21 | 2022-10-09 | 10 | PCNF REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100073538 | HBA/78: Replace worn fuel hoses | Build/remove scaffolding | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 50 | 0 | W15-W16 | 2024-03-13 | 2024-03-19 | 2024-03-13 | 2023-02-21 | 2022-10-09 | 20 | PCNF REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100073538 | HBA/78: Replace worn fuel hoses | Assist and operating crane at leaktest | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 6 | 0 | W15-W16 | 2024-03-13 | 2024-03-19 | 2024-03-13 | 2023-02-21 | 2022-10-09 | 40 | PCNF REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100073538 | HBA/78: Replace worn fuel hoses |  | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 0 | 0 | W15-W16 | 2024-03-13 | 2024-03-19 | 2024-03-13 | 2023-02-21 | 2022-10-09 | 60 | PCNF REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100073748 | HBD/78: Replace incremental sensor Aux. | Isolation/deisolation of crane | REL GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 4 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2023-02-26 | 2022-10-14 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100073748 | HBD/78: Replace incremental sensor Aux. | Replace incremental sensor Aux | REL GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 12 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2023-02-26 | 2022-10-14 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100073748 | HBD/78: Replace incremental sensor Aux. | Assist and operating crane at testing | REL GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 6 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-02 | 2024-08-01 | 2023-02-26 | 2022-10-14 | 30 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100076010 | HBA/78: Replace worn hydr. hoses | Isolate/de-isolate of crane HBAB-X-6130 | REL GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 4 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2023-03-30 | 2022-11-15 | 10 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100076010 | HBA/78: Replace worn hydr. hoses | Replace hydraulic hoses, 13pcs | REL GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 35 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2023-03-30 | 2022-11-15 | 20 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100076010 | HBA/78: Replace worn hydr. hoses | Test and inspect for leaks | REL GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2023-03-30 | 2022-11-15 | 30 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100076010 | HBA/78: Replace worn hydr. hoses | Operation of crane | REL GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2023-03-30 | 2022-11-15 | 40 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100078741 | HBD/78: Investigate machine house for ho | Assist vendor | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 12 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2023-05-27 | 2023-01-12 | 30 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
0 | 3 | NOSD | WDF | MTN-ROUS | VEN-MECH | 2100098695 | Lifeboat 2 - Hydraulic hoses for release | Replace - Hydraulic hoses for release | REL GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-03-17 | 2023-11-03 | 10 | REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | C |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ROUS | VEN-MECH | 2100098696 | Lifeboat 1 - Hydraulic hoses for release | Replace - Hydraulic hoses for release | REL GMPS MANC PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-03-17 | 2023-11-03 | 10 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | C |  | MMS | DK60
2026-W1-2 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100107147 | Defective Fan no1 HBDC-CP-0250 Cabinet | Isolate and replace fan | REL GMPS MACM PRC SETC | APPR SMAT AWDO SCH RDBL RFRZ ROUT | 3 | 0 | W15-W16 | 2024-04-10 | 2024-04-11 | 2024-04-10 | 2024-08-03 | 2024-03-21 | 10 | REL | APPR OPND | HB /A /03/ESD-CONTROL-PANELS | ESD CONTROL PANELS |  | A |  | MIN | DK50
2024-W27-28 | 3 | NOSD | WDF | MTN-INST | MTN-LAGG | 2100067873 | Syn. 650656 - Bolts in wrong mat. HBB | Insulate after repair on PDIT. | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO ROUT | 6 | 0 | W27-28 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-07-04 | 2022-05-25 | 46 | PCNF REL | APPR OPND | HB /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100099537 | HBA/78 Monitor is defect (flickers) | Isolate/Deisolate crane | REL GMPS MANC PRC SETC | APPR SMAT AWDO RFRZ ROUT | 1 | 0 | 24-W03-04 | 2024-04-05 | 2024-04-07 | 2024-04-05 | 2024-04-07 | 2023-11-24 | 10 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-ELEC | 2100099537 | HBA/78 Monitor is defect (flickers) | Install and test new monitor | REL GMPS MANC PRC SETC | APPR SMAT AWDO RFRZ ROUT | 12 | 0 | 24-W03-04 | 2024-04-05 | 2024-04-07 | 2024-04-05 | 2024-04-07 | 2023-11-24 | 20 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100099537 | HBA/78 Monitor is defect (flickers) | Function test | REL GMPS MANC PRC SETC | APPR SMAT AWDO RFRZ ROUT | 1 | 0 | 24-W03-04 | 2024-04-05 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2023-11-24 | 30 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100099537 | HBA/78 Monitor is defect (flickers) | Pending startup settings issue | REL GMPS MANC PRC SETC | APPR SMAT AWDO RFRZ ROUT | 3 | 0 | 24-W03-04 | 2024-04-05 | 2024-04-07 | 2024-04-05 | 2024-04-07 | 2023-11-24 | 50 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W45-46 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100055733 | HBD/78: Replacement of whip wire sheave | Check new materials | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL ROUT | 1 | 0 | W45-46 | 2024-09-15 | 2024-10-07 | 2024-09-15 | 2021-10-26 | 2021-09-16 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W45-46 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100055733 | HBD/78: Replacement of whip wire sheave | Isolate crane HBDE-A-6150 | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL ROUT | 1 | 0 | W45-46 | 2024-09-15 | 2024-10-07 | 2024-09-15 | 2021-10-26 | 2021-09-16 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W45-46 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100055733 | HBD/78: Replacement of whip wire sheave | Build scaffolding platform | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL ROUT | 100 | 0 | W45-46 | 2024-09-15 | 2024-10-07 | 2024-09-15 | 2021-10-26 | 2021-09-16 | 40 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W45-46 | 3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100055733 | HBD/78: Replacement of whip wire sheave | Secure whip hook and lift wire from shea | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL ROUT | 50 | 0 | W45-46 | 2024-09-15 | 2024-10-07 | 2024-09-22 | 2021-10-26 | 2021-09-16 | 50 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W45-46 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100055733 | HBD/78: Replacement of whip wire sheave | Replace wiresheave and pin | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL ROUT | 24 | 0 | W45-46 | 2024-09-15 | 2024-10-07 | 2024-09-27 | 2021-10-26 | 2021-09-16 | 60 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W45-46 | 3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100055733 | HBD/78: Replacement of whip wire sheave | Assist with replacing wire sheave and re | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL ROUT | 50 | 0 | W45-46 | 2024-09-15 | 2024-10-07 | 2024-09-27 | 2021-10-26 | 2021-09-16 | 70 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W45-46 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100055733 | HBD/78: Replacement of whip wire sheave | Remove scaffolding platform | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL ROUT | 100 | 0 | W45-46 | 2024-09-15 | 2024-10-07 | 2024-09-27 | 2021-10-26 | 2021-09-16 | 90 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W45-46 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100055733 | HBD/78: Replacement of whip wire sheave | Deisolate crane HBDE-A-6150 | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL ROUT | 1 | 0 | W45-46 | 2024-09-15 | 2024-10-07 | 2024-10-04 | 2021-10-26 | 2021-09-16 | 100 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W45-46 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100055733 | HBD/78: Replacement of whip wire sheave | Make proff loadtest of whipline | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL ROUT | 12 | 0 | W45-46 | 2024-09-15 | 2024-10-07 | 2024-10-04 | 2021-10-26 | 2021-09-16 | 120 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W45-46 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100055733 | HBD/78: Replacement of whip wire sheave | Operating crane under proff loadtest | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL ROUT | 12 | 0 | W45-46 | 2024-09-15 | 2024-10-07 | 2024-10-04 | 2021-10-26 | 2021-09-16 | 130 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W45-46 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100055733 | HBD/78: Replacement of whip wire sheave | Documentation, QC, create loadtest cert | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL ROUT | 2 | 0 | W45-46 | 2024-09-15 | 2024-10-07 | 2024-10-07 | 2021-10-26 | 2021-09-16 | 140 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | HB-HDAWI | WDF | MTN-MECH | MTN-LAGG | 2100024076 | CHNG out 1" ball vlv(bleed vlv) HB | L3 Permit for conslagg | REL GMPS MANC PPRT PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1.3 | 0 | Need Mat. (Time delay) | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-06-28 | 2019-01-29 | 5 | REL | APPR OPND | HB /A /50/HBAA-EP-3813 | WTR INJECTION PIG RECEIVER/PROD GAS LAU |  | D |  | MMS | DK50
2026-W13-14 | 4 | HB-HDAWI | WDF | MTN-MECH | MTN-LAGG | 2100024076 | CHNG out 1" ball vlv(bleed vlv) HB | L3 Strip of insulation | REL GMPS MANC PPRT PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 0.7 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-06-28 | 2019-01-29 | 10 | REL | APPR OPND | HB /A /50/HBAA-EP-3813 | WTR INJECTION PIG RECEIVER/PROD GAS LAU |  | D |  | MMS | DK50
2026-W13-14 | 4 | HB-HDAWI | WDF | MTN-MECH | PRODTECH | 2100024076 | CHNG out 1" ball vlv(bleed vlv) HB | L3 Isolate HBA-EP-3813 | REL GMPS MANC PPRT PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-06-28 | 2019-01-29 | 20 | REL | APPR OPND | HB /A /50/HBAA-EP-3813 | WTR INJECTION PIG RECEIVER/PROD GAS LAU |  | D |  | MMS | DK50
2026-W13-14 | 4 | HB-HDAWI | WDF | MTN-MECH | MTN-MECH | 2100024076 | CHNG out 1" ball vlv(bleed vlv) HB | L1Disassemble 1" valve & mount new one | REL GMPS MANC PPRT PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-06-28 | 2019-01-29 | 30 | REL | APPR OPND | HB /A /50/HBAA-EP-3813 | WTR INJECTION PIG RECEIVER/PROD GAS LAU |  | D |  | MMS | DK50
2026-W13-14 | 4 | HB-HDAWI | WDF | MTN-MECH | PRODTECH | 2100024076 | CHNG out 1" ball vlv(bleed vlv) HB | L3 De-isolate HBA-EP-3813 | REL GMPS MANC PPRT PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2019-06-28 | 2019-01-29 | 40 | REL | APPR OPND | HB /A /50/HBAA-EP-3813 | WTR INJECTION PIG RECEIVER/PROD GAS LAU |  | D |  | MMS | DK50
2026-W13-14 | 4 | HB-HDAWI | WDF | MTN-MECH | MTN-MECH | 2100024076 | CHNG out 1" ball vlv(bleed vlv) HB | L3 Test new 1" valve & doc | REL GMPS MANC PPRT PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2019-06-28 | 2019-01-29 | 50 | REL | APPR OPND | HB /A /50/HBAA-EP-3813 | WTR INJECTION PIG RECEIVER/PROD GAS LAU |  | D |  | MMS | DK50
2026-W13-14 | 4 | HB-HDAWI | WDF | MTN-MECH | MTN-LAGG | 2100024076 | CHNG out 1" ball vlv(bleed vlv) HB | L3 Insulate the stripped of area | REL GMPS MANC PPRT PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1.3 | 0 | Need time delay | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2019-06-28 | 2019-01-29 | 60 | REL | APPR OPND | HB /A /50/HBAA-EP-3813 | WTR INJECTION PIG RECEIVER/PROD GAS LAU |  | D |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-PIPF | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Permit Preparation - Weld | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 10 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-LAGG | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Permit Preparation - Lagg | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 30 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | VEN-ELEC | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Permit Preparation - Elec | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 33 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-SCAF | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Building of scaffold | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 156 | 72 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 35 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-LAGG | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Remove insulation - Lagg | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 52 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 36 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | VEN-MECH | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | 3D measure of spool - Vendor | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 41 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 37 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-PIPF | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Tjek/Measuring of new spool | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 42 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Isolate for changing flowline - Prod | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 60 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | VEN-ELEC | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | El - demol PIT, tubing og heat tracing | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 13 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 81 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | VEN-ELEC | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Mount PIT, tubing/flow element - tracing | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 13 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 102 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Leak test of flowline - Prod | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 110 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | De-Isolate flowline - Prod | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 120 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-LAGG | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Insulate flowline - Lagg | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 130 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 140 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-SCAF | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Remove scaffolding | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 117 | 43 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 150 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Production task | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 13 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 180 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-PIPF | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Welder Task - clean up - Tools | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 12 | 0 | NOT ON ORIGINAL WEEK PLAN | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 190 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100024654 | FFSPR Replace HBB-02 water inj. slot no | Spools + Erections | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-02 | 2019-04-23 | 200 | PCNF REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | PRODTECH | 2100031730 | Leakage on a hydraulic connection | Isolate 3way valve DV181 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1.5 | 0 | W09-10 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-08-26 | 2020-05-28 | 10 | PCNF REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-INST | 2100031730 | Leakage on a hydraulic connection | Replace Nipple QC501 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W09-10 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-08-26 | 2020-05-28 | 20 | PCNF REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | PRODTECH | 2100031730 | Leakage on a hydraulic connection | De-isolate 3way valve DV181 | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1.5 | 0 | W09-10 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-08-26 | 2020-05-28 | 30 | PCNF REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-INST | 2100031730 | Leakage on a hydraulic connection | Test the installation | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W09-10 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-08-26 | 2020-05-28 | 40 | PCNF REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-INST | 2100031730 | Leakage on a hydraulic connection | Doc preparation for Q | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1.5 | 0 | W09-10 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-08-26 | 2020-05-28 | 50 | PCNF REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-INST | MTN-INST | 2100031730 | Leakage on a hydraulic connection | Finish job and cleanup work area | REL PCNF PRT GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W09-10 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-08-26 | 2020-05-28 | 60 | PCNF REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL |  | E |  | MIN | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059345 | HBDB-PSV-105004 - Flange Face Corrosion | Recalibrate - HBDB-PSV-105004 | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2022-07-04 | 2022-02-04 | 10 | REL | APPR OPND | HB /D /51/HBDB-PSV-105004 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-MECH | CON-WELD | 2100059345 | HBDB-PSV-105004 - Flange Face Corrosion | Permit and linewalk | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2022-07-04 | 2022-02-04 | 20 | REL | APPR OPND | HB /D /51/HBDB-PSV-105004 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059345 | HBDB-PSV-105004 - Flange Face Corrosion | Isolation plan & ICC | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2022-07-04 | 2022-02-04 | 30 | REL | APPR OPND | HB /D /51/HBDB-PSV-105004 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059345 | HBDB-PSV-105004 - Flange Face Corrosion | Isolation of PSV | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2022-07-04 | 2022-02-04 | 40 | REL | APPR OPND | HB /D /51/HBDB-PSV-105004 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059345 | HBDB-PSV-105004 - Flange Face Corrosion | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2022-07-04 | 2022-02-04 | 50 | REL | APPR OPND | HB /D /51/HBDB-PSV-105004 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-MECH | CON-WELD | 2100059345 | HBDB-PSV-105004 - Flange Face Corrosion | Remove PSV and install blinds | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2022-07-04 | 2022-02-04 | 60 | REL | APPR OPND | HB /D /51/HBDB-PSV-105004 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059345 | HBDB-PSV-105004 - Flange Face Corrosion | Leak test blinds | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2022-07-04 | 2022-02-04 | 70 | REL | APPR OPND | HB /D /51/HBDB-PSV-105004 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059345 | HBDB-PSV-105004 - Flange Face Corrosion | Re-certify PSV | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2022-07-04 | 2022-02-04 | 80 | REL | APPR OPND | HB /D /51/HBDB-PSV-105004 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059345 | HBDB-PSV-105004 - Flange Face Corrosion | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2022-07-04 | 2022-02-04 | 90 | REL | APPR OPND | HB /D /51/HBDB-PSV-105004 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-MECH | CON-WELD | 2100059345 | HBDB-PSV-105004 - Flange Face Corrosion | Install re-certified PSV | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2022-07-04 | 2022-02-04 | 100 | REL | APPR OPND | HB /D /51/HBDB-PSV-105004 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059345 | HBDB-PSV-105004 - Flange Face Corrosion | De-isolation and leak test | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2022-07-04 | 2022-02-04 | 110 | REL | APPR OPND | HB /D /51/HBDB-PSV-105004 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W45-46 | 4 | NOSD | WDF | MTN-MECH | CON-WELD | 2100059345 | HBDB-PSV-105004 - Flange Face Corrosion | Documentation & Close out WO | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2022-07-04 | 2022-02-04 | 120 | REL | APPR OPND | HB /D /51/HBDB-PSV-105004 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100059461 | HBD/78: Replace hoses in engine room | Isolate crane HBDE-A-6150 | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W21-22 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-12-25 | 2021-12-05 | 60 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50 |  |  | 2024-06-02
2024-W21-22 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100059461 | HBD/78: Replace hoses in engine room | Replace hyd hoses in engine room | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 12 | 48 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-12-25 | 2021-12-05 | 70 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50 |  |  | 2024-06-04
2024-W21-22 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100059461 | HBD/78: Replace hoses in engine room | Deisolate crane HBDE-A-6150 | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W21-22 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-12-25 | 2021-12-05 | 80 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50 |  |  | 2024-06-07
2024-W21-22 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100059461 | HBD/78: Replace hoses in engine room | Test and inspect for leaks | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W21-22 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-12-25 | 2021-12-05 | 90 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50 |  |  | 2024-06-09
2024-W21-22 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100059461 | HBD/78: Replace hoses in engine room | Cleanup, upload hose certs on job | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W21-22 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-12-25 | 2021-12-05 | 100 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50 |  |  | 2024-06-11
2024-W21-22 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100059461 | HBD/78: Replace hoses in engine room | Mobilization of vendor | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-12-25 | 2021-12-05 | 110 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50 |  |  | 2024-06-13
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100065845 | HBD/78: Replacement of windshield wiper | Find and check spareparts/tools | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W09-W10 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2022-07-21 | 2022-04-22 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100065845 | HBD/78: Replacement of windshield wiper | Isolate crane HBDE-A-6150 | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W09-W10 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2022-07-21 | 2022-04-22 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065845 | HBD/78: Replacement of windshield wiper | Replace windshield wiper on top window | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 12 | 0 | W09-W10 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2022-07-21 | 2022-04-22 | 30 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100065845 | HBD/78: Replacement of windshield wiper | Assist rope team with replacement | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 6 | 0 | W09-W10 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2022-07-21 | 2022-04-22 | 40 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100065845 | HBD/78: Replacement of windshield wiper | Deisolate crane HBDE-A-6150 | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W09-W10 | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2022-07-21 | 2022-04-22 | 50 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100065845 | HBD/78: Replacement of windshield wiper | Test and inspect for leaks | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W09-W10 | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2022-07-21 | 2022-04-22 | 60 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100065845 | HBD/78: Replacement of windshield wiper | Clean up, documents and QC. | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W09-W10 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2022-07-21 | 2022-04-22 | 70 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-MECH | PRODTECH | 2100069880 | DB Block internal leak for LIT-415202 | Isolate and Inhibit Contact Level transm | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-05-28 | 2022-12-10 | 10 | REL | APPR OPND | HB /D /30/HBDB-LIT-415202 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-MECH | MTN-ELEC | 2100069880 | DB Block internal leak for LIT-415202 | Isolate heat tracing | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-05-28 | 2022-12-10 | 15 | REL | APPR OPND | HB /D /30/HBDB-LIT-415202 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-MECH | MTN-MECH | 2100069880 | DB Block internal leak for LIT-415202 | Remove insulation | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-05-28 | 2022-12-10 | 16 | REL | APPR OPND | HB /D /30/HBDB-LIT-415202 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-MECH | MTN-MECH | 2100069880 | DB Block internal leak for LIT-415202 | Remove Valve f, proces isolation | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-05-28 | 2022-12-10 | 20 | REL | APPR OPND | HB /D /30/HBDB-LIT-415202 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-MECH | MTN-MECH | 2100069880 | DB Block internal leak for LIT-415202 | Reinstall Valve f, proces isolation | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-05-28 | 2022-12-10 | 25 | REL | APPR OPND | HB /D /30/HBDB-LIT-415202 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-MECH | MTN-INST | 2100069880 | DB Block internal leak for LIT-415202 | Calibrate Contact Level transmitter (flo | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-05-28 | 2022-12-10 | 30 | REL | APPR OPND | HB /D /30/HBDB-LIT-415202 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-MECH | PRODTECH | 2100069880 | DB Block internal leak for LIT-415202 | Deisolate and repeal inhibits Contact Le | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-05-28 | 2022-12-10 | 50 | REL | APPR OPND | HB /D /30/HBDB-LIT-415202 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-MECH | MTN-MECH | 2100069880 | DB Block internal leak for LIT-415202 | Restore insulation | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-05-28 | 2022-12-10 | 55 | REL | APPR OPND | HB /D /30/HBDB-LIT-415202 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-MECH | MTN-ELEC | 2100069880 | DB Block internal leak for LIT-415202 | Remove isolation from heat tracing | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-05-28 | 2022-12-10 | 60 | REL | APPR OPND | HB /D /30/HBDB-LIT-415202 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-MECH | MTN-RIGG | 2100069880 | DB Block internal leak for LIT-415202 | Rigger Services | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-05-28 | 2022-12-10 | 70 | REL | APPR OPND | HB /D /30/HBDB-LIT-415202 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100072248 | HBB/78 Worn hydr. hoses inside pedestal | Scaffold inside pedestal | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 18 | 12 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-01-23 | 2022-09-10 | 60 | PCNF REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100073421 | HBB/78: remote Connection/Sealing JB | Repair the lid | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2023-02-14 | 2022-10-02 | 5 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50 |  |  | 2024-05-14
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073421 | HBB/78: remote Connection/Sealing JB | Replace remote connection | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2023-02-14 | 2022-10-02 | 10 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50 |  |  | 2024-05-15
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073421 | HBB/78: remote Connection/Sealing JB | Install new seal in the lid / remove old | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2023-02-14 | 2022-10-02 | 20 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50 |  |  | 2024-05-16
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073421 | HBB/78: remote Connection/Sealing JB | Drill holes in bottom of junction box | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-26 | 2023-02-14 | 2022-10-02 | 30 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50 |  |  | 2024-05-17
0 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100074277 | HDB/78: Replace worn hydraulic hoses pla | Isolate/de-isolate of crane HDBR-A-6102 | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W13-14 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2023-02-28 | 2022-10-16 | 10 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100074277 | HDB/78: Replace worn hydraulic hoses pla | Replace worn hydraulic hoses, 10 pcs | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 12 | 0 | W13-14 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2023-02-28 | 2022-10-16 | 20 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100074277 | HDB/78: Replace worn hydraulic hoses pla | Function/leakage test | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W13-14 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2023-02-28 | 2022-10-16 | 30 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100074277 | HDB/78: Replace worn hydraulic hoses pla | Operation of crane | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W13-14 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2023-02-28 | 2022-10-16 | 40 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | PRODTECH | 2100075204 | PIT-29256 insulation missing | Inhibit pressure transmitter | REL GMPS MACM PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2023-06-22 | 2023-06-23 | 2023-06-22 | 2025-09-07 | 2023-03-22 | 10 | REL | APPR OPND | HB /A /37/HBAA-PIT-29256 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100075204 | PIT-29256 insulation missing | Isolate Heat trace | REL GMPS MACM PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2023-06-22 | 2023-06-23 | 2023-06-22 | 2025-09-07 | 2023-03-22 | 20 | REL | APPR OPND | HB /A /37/HBAA-PIT-29256 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100075204 | PIT-29256 insulation missing | Install insulation for pressure transmit | REL GMPS MACM PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4.5 | 0 |  | 2023-06-22 | 2023-06-23 | 2023-06-22 | 2025-09-07 | 2023-03-22 | 30 | REL | APPR OPND | HB /A /37/HBAA-PIT-29256 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100075204 | PIT-29256 insulation missing | Deisolate Heat tracing | REL GMPS MACM PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2023-06-22 | 2023-06-23 | 2023-06-23 | 2025-09-07 | 2023-03-22 | 40 | REL | APPR OPND | HB /A /37/HBAA-PIT-29256 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | PRODTECH | 2100075204 | PIT-29256 insulation missing | Remove inhibit | REL GMPS MACM PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2023-06-22 | 2023-06-23 | 2023-06-23 | 2025-09-07 | 2023-03-22 | 50 | REL | APPR OPND | HB /A /37/HBAA-PIT-29256 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077670 | HBD/78: Replace rubber feet diesel engin | Isolate/de-isolate of crane HBDE-A-6150 | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W07-W08 | 2024-09-16 | 2024-09-21 | 2024-09-17 | 2025-10-18 | 2023-05-02 | 10 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077670 | HBD/78: Replace rubber feet diesel engin | Replace Diesel engine rubber feet | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 12 | 4 | W07-W08 | 2024-09-16 | 2024-09-21 | 2024-09-17 | 2025-10-18 | 2023-05-02 | 20 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077670 | HBD/78: Replace rubber feet diesel engin | Isolate/de-isolate of crane HBDE-A-6150 | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W07-W08 | 2024-09-16 | 2024-09-21 | 2024-09-17 | 2025-10-18 | 2023-05-02 | 30 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100077670 | HBD/78: Replace rubber feet diesel engin | Dismantle/assemble gear | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 18 | 0 | W07-W08 | 2024-09-16 | 2024-09-21 | 2024-09-16 | 2025-10-18 | 2023-05-02 | 40 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100077670 | HBD/78: Replace rubber feet diesel engin | Replace missing engine rubber feet | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 6 | 0 | W07-W08 | 2024-09-16 | 2024-09-21 | 2024-09-16 | 2025-10-18 | 2023-05-02 | 50 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077670 | HBD/78: Replace rubber feet diesel engin | Assist vendor | REL PCNF GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 24 | 0 | W07-W08 | 2024-09-16 | 2024-09-21 | 2024-09-17 | 2025-10-18 | 2023-05-02 | 60 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
0 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100077671 | HDB/78: Replace hoist winch personale br | Isolate/de-isolate of crane HDBR-A-6102 | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-07-11 | 2024-07-17 | 2024-07-11 | 2023-05-03 | 2022-12-19 | 10 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100077671 | HDB/78: Replace hoist winch personale br | Build/demol of scaffold and gallows | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 30 | 0 |  | 2024-07-11 | 2024-07-17 | 2024-07-11 | 2023-05-03 | 2022-12-19 | 20 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100077671 | HDB/78: Replace hoist winch personale br | Replace secondary brake from hoist winch | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2024-07-11 | 2024-07-17 | 2024-07-14 | 2023-05-03 | 2022-12-19 | 30 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100077671 | HDB/78: Replace hoist winch personale br | Handling/lift of brake | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-07-11 | 2024-07-17 | 2024-07-14 | 2023-05-03 | 2022-12-19 | 40 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100077671 | HDB/78: Replace hoist winch personale br | Function/leakage test of brake | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-07-11 | 2024-07-17 | 2024-07-15 | 2023-05-03 | 2022-12-19 | 50 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100077671 | HDB/78: Replace hoist winch personale br | Perform proof load test of secondary bra | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-07-11 | 2024-07-17 | 2024-07-16 | 2023-05-03 | 2022-12-19 | 60 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100077671 | HDB/78: Replace hoist winch personale br | Operation of crane | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-07-11 | 2024-07-17 | 2024-07-16 | 2023-05-03 | 2022-12-19 | 70 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
2026-W13-14 | 3 | NE | WDF | MTN-LAGG | PRODTECH | 2100092679 | Insulation for G-1710 is worn out | Isolation & safing of HBDE-G-1710 | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2026-05-27 | 2023-12-09 | 10 | REL | APPR OPND | HB /D /05/HBDE-G-1710 | EMERGENCY DIESEL GENERATOR |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-LAGG | MTN-MECH | 2100092679 | Insulation for G-1710 is worn out | Replace worn insulation | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2026-05-27 | 2023-12-09 | 20 | REL | APPR OPND | HB /D /05/HBDE-G-1710 | EMERGENCY DIESEL GENERATOR |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-LAGG | PRODTECH | 2100092679 | Insulation for G-1710 is worn out | De-isolation & desafing of HBDE-G-1710 | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2026-05-27 | 2023-12-09 | 30 | REL | APPR OPND | HB /D /05/HBDE-G-1710 | EMERGENCY DIESEL GENERATOR |  | A |  | MMR | DK50 |  | PROK
2024-W45-46 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096589 | PI Wellhead panel broken pressure gauge | Replace pressure gauge PI-29131 | REL GMPS MANC PRC SETC | APPR SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-02-14 | 2023-10-02 | 10 | REL | APPR OPND | HB /A /07/HBAA-A-3111 | WELLHEAD CONTROL PANEL |  | A |  | MIN | DK50
2026-W13-14 | 4 | HBFUELG | WDF | MTN-INST | MTN-MECH | 2100049278 | HCV is internal leaking | Insulate DBB HCV for LIT | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWDO AWSC RDBL ROUT RREQ | 12 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-12-18 | 2021-07-21 | 150 | PCNF REL | APPR OPND | HB /D /70/HBDC-LIT-575102 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | E |  | MIN | DK50 |  | PROK
2026-W13-14 | 4 | HBFUELG | WDF | MTN-INST | MTN-LAGG | 2100049278 | HCV is internal leaking | Restore insulation | REL PCNF GMPS MANC PPRT PRC SETC | APPR SMAT AWDO AWSC RDBL ROUT RREQ | 8 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-12-18 | 2021-07-21 | 160 | REL | APPR OPND | HB /D /70/HBDC-LIT-575102 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | E |  | MIN | DK50 |  | PROK
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-PIPF | 2100024557 | FFSPR Replace HBB-04 well flowline. | Prepare of Permit (Weld) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-09-15 | 2019-05-25 | 2019-04-15 | 10 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-SCAF | 2100024557 | FFSPR Replace HBB-04 well flowline. | Prepare of Permit (Scaff) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 20 | SWL HBB04 - FM | 2024-09-15 | 2024-10-10 | 2024-09-15 | 2019-05-25 | 2019-04-15 | 20 | PCNF REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | VEN-ELEC | 2100024557 | FFSPR Replace HBB-04 well flowline. | Prepare of Permit (EL) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-09-20 | 2019-05-25 | 2019-04-15 | 30 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-SCAF | 2100024557 | FFSPR Replace HBB-04 well flowline. | Building of scaffold for control mesurin | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 156 | 0 | SWL HBB04 - FM | 2024-09-15 | 2024-10-10 | 2024-09-20 | 2019-05-25 | 2019-04-15 | 40 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | VEN-MECH | 2100024557 | FFSPR Replace HBB-04 well flowline. | 3D measure of spool (Vendor) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 41 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-09-15 | 2019-05-25 | 2019-04-15 | 50 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-PIPF | 2100024557 | FFSPR Replace HBB-04 well flowline. | Tjek/Measuring of new spool (Welder) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-09-19 | 2019-05-25 | 2019-04-15 | 52 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-SCAF | 2100024557 | FFSPR Replace HBB-04 well flowline. | Install liftning equipment (Scaff) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 26 | 0 | SWL HBB04 - FM | 2024-09-15 | 2024-10-10 | 2024-09-19 | 2019-05-25 | 2019-04-15 | 53 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | PRODTECH | 2100024557 | FFSPR Replace HBB-04 well flowline. | Isolate (Prod) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-09-20 | 2019-05-25 | 2019-04-15 | 60 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | VEN-ELEC | 2100024557 | FFSPR Replace HBB-04 well flowline. | El - demol PIT, tubing og heat tracing | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 13 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-09-21 | 2019-05-25 | 2019-04-15 | 61 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-PIPF | 2100024557 | FFSPR Replace HBB-04 well flowline. | Demol existing flowline (Weld) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 52 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-09-22 | 2019-05-25 | 2019-04-15 | 70 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-SCAF | 2100024557 | FFSPR Replace HBB-04 well flowline. | Ass. demol existing flowline (Scaff) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 117 | 0 | SWL HBB04 - FM | 2024-09-15 | 2024-10-10 | 2024-09-30 | 2019-05-25 | 2019-04-15 | 80 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-PIPF | 2100024557 | FFSPR Replace HBB-04 well flowline. | Install new flowline (Weld) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 60 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-09-22 | 2019-05-25 | 2019-04-15 | 90 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-SCAF | 2100024557 | FFSPR Replace HBB-04 well flowline. | Assist install new flowline (Scaff) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 156 | 0 | SWL HBB04 - FM | 2024-09-15 | 2024-10-10 | 2024-09-25 | 2019-05-25 | 2019-04-15 | 100 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | VEN-ELEC | 2100024557 | FFSPR Replace HBB-04 well flowline. | Mount PIT, tubing/flow element - tracing | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 13 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-09-25 | 2019-05-25 | 2019-04-15 | 110 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | PRODTECH | 2100024557 | FFSPR Replace HBB-04 well flowline. | Leak test of flowline (Prod) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-09-27 | 2019-05-25 | 2019-04-15 | 120 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | PRODTECH | 2100024557 | FFSPR Replace HBB-04 well flowline. | De-Isolate flowline (Prod) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-09-28 | 2019-05-25 | 2019-04-15 | 130 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-SCAF | 2100024557 | FFSPR Replace HBB-04 well flowline. | Demol scaff and cleaning (Scaff) | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 104 | 0 | SWL HBB04 - FM | 2024-09-15 | 2024-10-10 | 2024-09-29 | 2019-05-25 | 2019-04-15 | 140 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-PIPF | 2100024557 | FFSPR Replace HBB-04 well flowline. | Welder Task - clean up - Tools | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 14 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-10-09 | 2019-05-25 | 2019-04-15 | 150 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | CON-WELD | 2100024557 | FFSPR Replace HBB-04 well flowline. |  | REL PCNF CSER GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-09-15 | 2024-10-10 | 2024-10-09 | 2019-05-25 | 2019-04-15 | 170 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0401-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026204 | Replace 2 corroded HCV's on HBAA-V-5011 | L3 Rig-up scaffold | REL GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 14 | 0 | BL Team | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2020-02-26 | 2019-09-29 | 10 | REL | APPR OPND | HB /A /28/HBAA-V-5011 | DRAIN VESSEL | 99000119 | D |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100026204 | Replace 2 corroded HCV's on HBAA-V-5011 | L3 Rig-up hoist | REL GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 8 | 0 | BL Team | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2020-02-26 | 2019-09-29 | 20 | REL | APPR OPND | HB /A /28/HBAA-V-5011 | DRAIN VESSEL | 99000119 | D |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100026204 | Replace 2 corroded HCV's on HBAA-V-5011 | L2 Isolate HCV-500036 & 500037 | REL GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | BL Team | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2020-02-26 | 2019-09-29 | 30 | REL | APPR OPND | HB /A /28/HBAA-V-5011 | DRAIN VESSEL | 99000119 | D |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100026204 | Replace 2 corroded HCV's on HBAA-V-5011 | L2 Replace old HCV's - ensure careful fa | REL GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 16 | 0 | BL Team | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2020-02-26 | 2019-09-29 | 40 | REL | APPR OPND | HB /A /28/HBAA-V-5011 | DRAIN VESSEL | 99000119 | D |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100026204 | Replace 2 corroded HCV's on HBAA-V-5011 | L2 Leak Test | REL GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | BL Team | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2020-02-26 | 2019-09-29 | 50 | REL | APPR OPND | HB /A /28/HBAA-V-5011 | DRAIN VESSEL | 99000119 | D |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100026204 | Replace 2 corroded HCV's on HBAA-V-5011 | L2 De-isolate HCV-500036 & 500037 | REL GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | BL Team | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2020-02-26 | 2019-09-29 | 60 | REL | APPR OPND | HB /A /28/HBAA-V-5011 | DRAIN VESSEL | 99000119 | D |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100026204 | Replace 2 corroded HCV's on HBAA-V-5011 | L3 Rig-down hoist | REL GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 6 | 0 | BL Team | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2020-02-26 | 2019-09-29 | 70 | REL | APPR OPND | HB /A /28/HBAA-V-5011 | DRAIN VESSEL | 99000119 | D |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026204 | Replace 2 corroded HCV's on HBAA-V-5011 | L3 Rig-dwn scaffold | REL GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 10 | 0 | BL Team | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2020-02-26 | 2019-09-29 | 80 | REL | APPR OPND | HB /A /28/HBAA-V-5011 | DRAIN VESSEL | 99000119 | D |  | MMS | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-ELEC | PRODTECH | 2100035893 | 1" HCV inst. air supply to fire damper | Isolate and inhibit | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2021-03-21 | 2020-10-22 | 10 | REL | APPR OPND | HB /D /09/HBDD-FD-12331 | FIRE DAMPER | 99000119 | A |  | MEL | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-ELEC | MTN-MECH | 2100035893 | 1" HCV inst. air supply to fire damper | Replace HCV | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2021-03-21 | 2020-10-22 | 20 | REL | APPR OPND | HB /D /09/HBDD-FD-12331 | FIRE DAMPER | 99000119 | A |  | MEL | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-ELEC | PRODTECH | 2100035893 | 1" HCV inst. air supply to fire damper | De-isolate | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2021-03-21 | 2020-10-22 | 30 | REL | APPR OPND | HB /D /09/HBDD-FD-12331 | FIRE DAMPER | 99000119 | A |  | MEL | DK50
0 | B | NOSD | WPM | MTN-MECH | VEN-CRAN | 2400221644 | 6M CRANE, HDBR-A-6102 (VENDOR) | CRANE, HDBR-A-6102 INSPECTION | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 0 | W09-W10 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-01-27 | 2023-01-11 | 10 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | C | DKHD-0702 | MMS | DK60 | MS0153
0 | B | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400221644 | 6M CRANE, HDBR-A-6102 (VENDOR) | CRANE, POWER PACK, HDBR-AM-6102 | REL PRT GMPS MANC PRC SETC | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W09-W10 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2023-01-27 | 2023-01-11 | 20 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | C | DKHD-0702 | MMS | DK60 | MS0153
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100024766 | Change IT-SWITCH HBDC-N-1851-K06 B | Isolate switch. See attached description | REL GMPS MANC PPRT PRC SETC | APPR SMAT | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2019-08-16 | 2019-07-07 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K06-B | IT-SWITCH |  | C |  | MEL | DK50 |  | PROK
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100024766 | Change IT-SWITCH HBDC-N-1851-K06 B | Assist PRODTECH with Isolating | REL GMPS MANC PPRT PRC SETC | APPR SMAT | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2019-08-16 | 2019-07-07 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K06-B | IT-SWITCH |  | C |  | MEL | DK50 |  | PROK
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100024766 | Change IT-SWITCH HBDC-N-1851-K06 B | Replace broken switch, test | REL GMPS MANC PPRT PRC SETC | APPR SMAT | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2019-08-16 | 2019-07-07 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K06-B | IT-SWITCH |  | C |  | MEL | DK50 |  | PROK
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100024766 | Change IT-SWITCH HBDC-N-1851-K06 B | De-Isolate above | REL GMPS MANC PPRT PRC SETC | APPR SMAT | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2019-08-16 | 2019-07-07 | 40 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K06-B | IT-SWITCH |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001428 | HBA12,WL, TRSSSV React, SV19838 | HBA12,WL, TRSSSV React, SV19838 | REL GMPS MANC PRC SETC | APPR SMAT | 0 | 0 |  | 2024-04-28 | 2024-06-05 | 2024-04-28 | 2024-09-10 | 2024-04-28 | 10 | REL | APPR OPND | HB /A /55/HBA12-WATER-INJECTION | HBA12 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | PRODTECH | 2900001428 | HBA12,WL, TRSSSV React, SV19838 | Safing well/well handover (production) | REL GMPS MANC PRC SETC | APPR SMAT | 12 | 0 |  | 2024-04-28 | 2024-06-05 | 2024-04-28 | 2024-09-10 | 2024-04-28 | 20 | REL | APPR OPND | HB /A /55/HBA12-WATER-INJECTION | HBA12 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | MTN-ROUS | 2900001428 | HBA12,WL, TRSSSV React, SV19838 | Crane assist during WL R/U and RD | REL GMPS MANC PRC SETC | APPR SMAT | 48 | 0 |  | 2024-04-28 | 2024-06-05 | 2024-05-01 | 2024-09-10 | 2024-04-28 | 30 | REL | APPR OPND | HB /A /55/HBA12-WATER-INJECTION | HBA12 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | MTN-SCAF | 2900001428 | HBA12,WL, TRSSSV React, SV19838 | Scaffolder assistance for RU and RD | REL GMPS MANC PRC SETC | APPR SMAT | 48 | 0 |  | 2024-04-28 | 2024-06-05 | 2024-05-07 | 2024-09-10 | 2024-04-28 | 40 | REL | APPR OPND | HB /A /55/HBA12-WATER-INJECTION | HBA12 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | MTN-ELEC | 2900001428 | HBA12,WL, TRSSSV React, SV19838 | Electrician assistance for RU and RD | REL GMPS MANC PRC SETC | APPR SMAT | 12 | 0 |  | 2024-04-28 | 2024-06-05 | 2024-05-11 | 2024-09-10 | 2024-04-28 | 50 | REL | APPR OPND | HB /A /55/HBA12-WATER-INJECTION | HBA12 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | MTN-TELE | 2900001428 | HBA12,WL, TRSSSV React, SV19838 | Tele assist during WL RRU and RD | REL GMPS MANC PRC SETC | APPR SMAT | 24 | 0 |  | 2024-04-28 | 2024-06-05 | 2024-05-14 | 2024-09-10 | 2024-04-28 | 60 | REL | APPR OPND | HB /A /55/HBA12-WATER-INJECTION | HBA12 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | VEN-CRAN | 2900001428 | HBA12,WL, TRSSSV React, SV19838 | Crane support assitance for days | REL GMPS MANC PRC SETC | APPR SMAT | 168 | 0 |  | 2024-04-28 | 2024-06-05 | 2024-05-19 | 2024-09-10 | 2024-04-28 | 70 | REL | APPR OPND | HB /A /55/HBA12-WATER-INJECTION | HBA12 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001428 | HBA12,WL, TRSSSV React, SV19838 | Oilenco tools | REL GMPS MANC PRC SETC | APPR SMAT | 0 | 0 |  | 2024-04-28 | 2024-06-05 | 2024-06-05 | 2024-09-10 | 2024-04-28 | 80 | REL | APPR OPND | HB /A /55/HBA12-WATER-INJECTION | HBA12 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001428 | HBA12,WL, TRSSSV React, SV19838 | WRSSSV | REL GMPS MANC PRC SETC | APPR SMAT | 0 | 0 |  | 2024-04-28 | 2024-06-05 | 2024-06-05 | 2024-09-10 | 2024-04-28 | 90 | REL | APPR OPND | HB /A /55/HBA12-WATER-INJECTION | HBA12 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001428 | HBA12,WL, TRSSSV React, SV19838 | Ocean Team chemicals | REL GMPS MANC PRC SETC | APPR SMAT | 0 | 0 |  | 2024-04-28 | 2024-06-05 | 2024-06-05 | 2024-09-10 | 2024-04-28 | 100 | REL | APPR OPND | HB /A /55/HBA12-WATER-INJECTION | HBA12 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001428 | HBA12,WL, TRSSSV React, SV19838 | FTET spareparts | REL GMPS MANC PRC SETC | APPR SMAT | 0 | 0 |  | 2024-04-28 | 2024-06-05 | 2024-06-05 | 2024-09-10 | 2024-04-28 | 110 | REL | APPR OPND | HB /A /55/HBA12-WATER-INJECTION | HBA12 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-RIGG | 2100038681 | HBDC-ESDV-290001 internal leakage | prep. for permit, site visit, job - Rigg | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2021-01-15 | 2020-10-17 | 10 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-PIPF | 2100038681 | HBDC-ESDV-290001 internal leakage | prep. for permit, site visit, job - Weld | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2021-01-15 | 2020-10-17 | 20 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-INST | 2100038681 | HBDC-ESDV-290001 internal leakage | prep. for permit, site visit, job - Inst | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2021-01-15 | 2020-10-17 | 30 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-RIGG | 2100038681 | HBDC-ESDV-290001 internal leakage | rig up lifting equipment - Rigg | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2021-01-15 | 2020-10-17 | 40 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | PRODTECH | 2100038681 | HBDC-ESDV-290001 internal leakage | isolate vavle & ACT - prod | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2021-01-15 | 2020-10-17 | 50 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-INST | 2100038681 | HBDC-ESDV-290001 internal leakage | Dismount hydra. & EL from ACT - INST | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2021-01-15 | 2020-10-17 | 60 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-PIPF | 2100038681 | HBDC-ESDV-290001 internal leakage | Remove valve and Act - Weld | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 10 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2021-01-15 | 2020-10-17 | 70 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-PIPF | 2100038681 | HBDC-ESDV-290001 internal leakage | Install new valve & act. - Weld | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 10 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2021-01-15 | 2020-10-17 | 80 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-INST | 2100038681 | HBDC-ESDV-290001 internal leakage | Hook up Hydra. & EL - Inst | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 8 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2021-01-15 | 2020-10-17 | 90 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | PRODTECH | 2100038681 | HBDC-ESDV-290001 internal leakage | De-isolate, leak test etc - Prod | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2021-01-15 | 2020-10-17 | 100 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-RIGG | 2100038681 | HBDC-ESDV-290001 internal leakage | remove lifting equipment - Rigg | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2021-01-15 | 2020-10-17 | 110 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-PIPF | 2100038681 | HBDC-ESDV-290001 internal leakage | Backload old valve & Act | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2021-01-15 | 2020-10-17 | 120 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-PIPF | 2100038681 | HBDC-ESDV-290001 internal leakage | house keeping - Weld | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2021-01-15 | 2020-10-17 | 130 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-MECH | 2100038681 | HBDC-ESDV-290001 internal leakage | house keeping - Inst | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2021-01-15 | 2020-10-17 | 140 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBHPGAS | WDF | MTN-MECH | MTN-MECH | 2100038681 | HBDC-ESDV-290001 internal leakage | house keeping - Rigg | REL PRT GMPS MANC PRC SETC | APPR SECE WMAT AWDO RDBL ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2021-01-15 | 2020-10-17 | 150 | REL | APPR OPND | HB /D /34/HBDC-ESDV-290001 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094950 | Helideck status light not working SL-151 | Isolate FP-15140 Power and Signal | REL PCNF MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-01-11 | 2023-08-29 | 30 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15144 | LOCAL STATUS LIGHT |  | A |  | MEL | DK50 |  | AWINFO | 2024-05-25
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094950 | Helideck status light not working SL-151 | Install new beacon. | REL PCNF MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-01-11 | 2023-08-29 | 40 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15144 | LOCAL STATUS LIGHT |  | A |  | MEL | DK50 |  | AWINFO | 2024-05-26
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094950 | Helideck status light not working SL-151 | De isolate Power and signal. | REL PCNF MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-01-11 | 2023-08-29 | 50 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15144 | LOCAL STATUS LIGHT |  | A |  | MEL | DK50 |  | AWINFO | 2024-05-27
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094950 | Helideck status light not working SL-151 | test Beacon | REL PCNF MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-01-11 | 2023-08-29 | 60 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15144 | LOCAL STATUS LIGHT |  | A |  | MEL | DK50 |  | AWINFO | 2024-05-29
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094950 | Helideck status light not working SL-151 | Materials | REL PCNF MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-01-11 | 2023-08-29 | 80 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15144 | LOCAL STATUS LIGHT |  | A |  | MEL | DK50 |  | AWINFO | 2024-05-30
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094950 | Helideck status light not working SL-151 | Additional parts | REL PCNF MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-01-11 | 2023-08-29 | 90 | REL | APPR OPND | HB /C /62/HBCH-SL-15144 | LOCAL STATUS LIGHT |  | A |  | MEL | DK50 |  | AWINFO | 2024-05-31
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100101433 | Gas det. GD-0181006 with XF fault | Inhibit and replace GD-0181006 | REL MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-14 | 2023-12-01 | 10 | REL | APPR OPND | HB /D /03/HBDB-GD-0181006 | IR GAS DETECTOR |  | A |  | MIN | DK50 |  |  | 2024-05-20
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100101435 | Gas det. GD-0182111 XF fault | Inhibit and replace GD-0182111 | REL MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-19 | 2023-12-06 | 10 | REL | APPR OPND | HB /D /03/HBDC-GD-0182111 | IR GAS DETECTOR |  | A |  | MIN | DK50 |  |  | 2024-05-21
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100101436 | Gas dect. in ext. fault | Inhibit and replace GD-0183602 | REL MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-03-25 | 2023-11-11 | 10 | REL | APPR OPND | HB /D /03/HBDD-GD-0183602 | IR GAS DETECTOR |  | A |  | MIN | DK50 |  |  | 2024-05-25
2026-W13-14 | 3 | NOSD | WDF | MTN-TELE | MTN-SCAF | 2100101437 | Gas det. GD-0184601 with XF fault | Erect and remove scaffolding | REL MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 12 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-04-14 | 2023-12-01 | 10 | REL | APPR OPND | HB /D /03/HBDE-GD-0184601 | IR GAS DETECTOR |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100101437 | Gas det. GD-0184601 with XF fault | Inhibit and replace GD-0184601 | REL MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-28 | 2024-04-14 | 2023-12-01 | 20 | REL | APPR OPND | HB /D /03/HBDE-GD-0184601 | IR GAS DETECTOR |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100107885 | Corroded solenoid for firemonitor 0410 | Isolate Fire Monitor | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-08-19 | 2024-04-06 | 20 | REL | APPR OPND | HB /A /01/HBAZ-A-0410 | PACKAGE |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100107885 | Corroded solenoid for firemonitor 0410 | Replace Solenoid valve | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2.5 | 0 |  | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-08-19 | 2024-04-06 | 30 | REL | APPR OPND | HB /A /01/HBAZ-A-0410 | PACKAGE |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100107885 | Corroded solenoid for firemonitor 0410 | De-isolate / Test | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-08-19 | 2024-04-06 | 40 | REL | APPR OPND | HB /A /01/HBAZ-A-0410 | PACKAGE |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100108177 | Replace solenoid for firemonitor 0450 | Isolate Fire Monitor | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2024-08-19 | 2024-04-06 | 10 | REL | APPR OPND | HB /A /01/HBAZ-A-0450 | FIRE MONITOR |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100108177 | Replace solenoid for firemonitor 0450 | Replace solenoid valve | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2.5 | 0 |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2024-08-19 | 2024-04-06 | 20 | REL | APPR OPND | HB /A /01/HBAZ-A-0450 | FIRE MONITOR |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100108177 | Replace solenoid for firemonitor 0450 | De-isolate / Test | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2024-08-19 | 2024-04-06 | 30 | REL | APPR OPND | HB /A /01/HBAZ-A-0450 | FIRE MONITOR |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100108178 | MOB boat leaking air. | Replace MOB boat with spare boat | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-08 | 2024-11-25 | 2024-05-08 | 2024-08-21 | 2024-04-08 | 10 | REL | APPR OPND | HB /D /02/HBDE-X-0703 | MOB BOAT |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100108178 | MOB boat leaking air. | Pack and backload HBD MOB boat | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-08 | 2024-11-25 | 2024-05-08 | 2024-08-21 | 2024-04-08 | 20 | REL | APPR OPND | HB /D /02/HBDE-X-0703 | MOB BOAT |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100108178 | MOB boat leaking air. | Replace spare MOB boat with HBD boat | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-08 | 2024-11-25 | 2024-11-24 | 2024-08-21 | 2024-04-08 | 30 | REL | APPR OPND | HB /D /02/HBDE-X-0703 | MOB BOAT |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100108178 | MOB boat leaking air. | Pack and backload spare MOB boat | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-08 | 2024-11-25 | 2024-11-25 | 2024-08-21 | 2024-04-08 | 40 | REL | APPR OPND | HB /D /02/HBDE-X-0703 | MOB BOAT |  | A |  | MMS | DK50
2024-W21-22 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100108781 | Replace HBDB-GD-0181001 | Replace HBDB-GD-0181001 | REL MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 5 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-24 | 2024-03-10 | 10 | REL | APPR OPND | HB /D /03/HBDB-GD-0181001 | IR GAS DETECTOR |  | A |  | MIN | DK50 |  |  | 2024-05-20
0 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100110203 | Fire monitor leaking | Fire monitor leaking | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-10-02 | 2024-05-20 | 10 | REL | APPR OPND | HD /B /01/HDBH-MF-0302 | FOAM MONITOR |  | A |  | MMS | DK60
0 | 3 |  | WDF | MTN-MECH | PRODTECH | 2100110203 | Fire monitor leaking | Isolate/de-isiloate | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-10-02 | 2024-05-20 | 20 | REL | APPR OPND | HD /B /01/HDBH-MF-0302 | FOAM MONITOR |  | A |  | MMS | DK60
0 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100110203 | Fire monitor leaking | Replace monitor | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-10-02 | 2024-05-20 | 30 | REL | APPR OPND | HD /B /01/HDBH-MF-0302 | FOAM MONITOR |  | A |  | MMS | DK60
0 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100110203 | Fire monitor leaking | Test monitor | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-10-02 | 2024-05-20 | 50 | REL | APPR OPND | HD /B /01/HDBH-MF-0302 | FOAM MONITOR |  | A |  | MMS | DK60
0 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100110204 | Foam Monitor on helideck leaking | Foam Monitor on helideck leaking | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-10-20 | 2024-10-22 | 2024-10-20 | 2024-10-02 | 2024-05-20 | 10 | REL | APPR OPND | HD /B /01/HDBH-MF-0330 | FOAM MONITOR |  | A |  | MMS | DK60
0 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100110204 | Foam Monitor on helideck leaking | Isolate/de-isiloate | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-10-20 | 2024-10-22 | 2024-10-20 | 2024-10-02 | 2024-05-20 | 20 | REL | APPR OPND | HD /B /01/HDBH-MF-0330 | FOAM MONITOR |  | A |  | MMS | DK60
0 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100110204 | Foam Monitor on helideck leaking | Replace monitor | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-20 | 2024-10-22 | 2024-10-20 | 2024-10-02 | 2024-05-20 | 30 | REL | APPR OPND | HD /B /01/HDBH-MF-0330 | FOAM MONITOR |  | A |  | MMS | DK60
0 | 3 |  | WDF | MTN-MECH | MTN-ELEC | 2100110204 | Foam Monitor on helideck leaking | Replace monitor | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-20 | 2024-10-22 | 2024-10-21 | 2024-10-02 | 2024-05-20 | 40 | REL | APPR OPND | HD /B /01/HDBH-MF-0330 | FOAM MONITOR |  | A |  | MMS | DK60
0 | 3 |  | WDF | MTN-MECH | MTN-MECH | 2100110204 | Foam Monitor on helideck leaking | Test monitor | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-10-20 | 2024-10-22 | 2024-10-21 | 2024-10-02 | 2024-05-20 | 50 | REL | APPR OPND | HD /B /01/HDBH-MF-0330 | FOAM MONITOR |  | A |  | MMS | DK60
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110436 | HBAB-BDV-34056 failed to close on demand | HBAB-BDV-34056 failed to close on demand | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-04-10 | 2024-04-11 | 2024-04-10 | 2024-05-25 | 2024-04-10 | 10 | REL | APPR OPND | HB /A /10/HBAB-BDV-34056 | BLOWDOWN VALVE |  | A |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100110436 | HBAB-BDV-34056 failed to close on demand | Isolate and verifification by production | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-04-10 | 2024-04-11 | 2024-04-10 | 2024-05-25 | 2024-04-10 | 20 | REL | APPR OPND | HB /A /10/HBAB-BDV-34056 | BLOWDOWN VALVE |  | A |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100110436 | HBAB-BDV-34056 failed to close on demand | Rig up hoist | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-04-10 | 2024-04-11 | 2024-04-10 | 2024-05-25 | 2024-04-10 | 30 | REL | APPR OPND | HB /A /10/HBAB-BDV-34056 | BLOWDOWN VALVE |  | A |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110436 | HBAB-BDV-34056 failed to close on demand | Replace actuator | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-10 | 2024-04-11 | 2024-04-10 | 2024-05-25 | 2024-04-10 | 40 | REL | APPR OPND | HB /A /10/HBAB-BDV-34056 | BLOWDOWN VALVE |  | A |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100110436 | HBAB-BDV-34056 failed to close on demand | De-isolate and test for leaks | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-04-10 | 2024-04-11 | 2024-04-11 | 2024-05-25 | 2024-04-10 | 50 | REL | APPR OPND | HB /A /10/HBAB-BDV-34056 | BLOWDOWN VALVE |  | A |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100110436 | HBAB-BDV-34056 failed to close on demand | Rig down hoist | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-04-10 | 2024-04-11 | 2024-04-11 | 2024-05-25 | 2024-04-10 | 60 | REL | APPR OPND | HB /A /10/HBAB-BDV-34056 | BLOWDOWN VALVE |  | A |  | MMR | DK50
2026-W13-14 | A | NOSD | WPM | MTN-TELE | MTN-RIGG | 2400274221 | 3M HBD FZ-812 AMMONIA-ANALYSERS | RIGGING SUPPORT | REL MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2023-09-23 | 2023-09-13 | 10 | REL | APPR OPND | HB /D /03/AMMONIA-ANALYSERS | AMMONIA ANALYSERS |  | C | DKHB-2035 | MIN | DK50 | IN0074
2026-W13-14 | A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400274221 | 3M HBD FZ-812 AMMONIA-ANALYSERS | HBD FZ-812 AMMONIA-ANALYSERS MAINT | REL MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2023-09-23 | 2023-09-13 | 20 | REL | APPR OPND | HB /D /03/AMMONIA-ANALYSERS | AMMONIA ANALYSERS |  | C | DKHB-2035 | MIN | DK50 | IN0074
2026-W13-14 | A | NOSD | WPM | MTN-TELE | MTN-RIGG | 2400274221 | 3M HBD FZ-812 AMMONIA-ANALYSERS | DE-RIGGING SUPPORT | REL MANC PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-10 | 2023-09-23 | 2023-09-13 | 30 | REL | APPR OPND | HB /D /03/AMMONIA-ANALYSERS | AMMONIA ANALYSERS |  | C | DKHB-2035 | MIN | DK50 | IN0074
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400309030 | 3Y EVACUATION SUIT RECERT - HBC | EVACUATION SUIT RECERT - HBC | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-03-16 | 2024-03-17 | 2024-03-16 | 2024-03-18 | 2024-01-16 | 10 | REL | APPR OPND | HB /C /02/EVACUATION-SUITS | EVACUATION SUITS |  | A | DKHB-0031 | MMS | DK50 | MS0044 |  | 2024-05-26
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400309030 | 3Y EVACUATION SUIT RECERT - HBC | PERSONAL ISOLATION | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2024-03-16 | 2024-03-17 | 2024-03-17 | 2024-03-18 | 2024-01-16 | 20 | REL | APPR OPND | HB /C /02/EVACUATION-SUITS | EVACUATION SUITS |  | A | DKHB-0031 | MMS | DK50 | MS0044 |  | 2024-05-28
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400309030 | 3Y EVACUATION SUIT RECERT - HBC | EVACUATION SUIT HEAT CHECK - HBC | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-16 | 2024-03-17 | 2024-03-17 | 2024-03-18 | 2024-01-16 | 30 | REL | APPR OPND | HB /C /02/EVACUATION-SUITS | EVACUATION SUITS |  | A | DKHB-0031 | MMS | DK50 | MS0044 |  | 2024-05-29
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400309030 | 3Y EVACUATION SUIT RECERT - HBC | PERSONAL DE-ISOLATION | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2024-03-16 | 2024-03-17 | 2024-03-17 | 2024-03-18 | 2024-01-16 | 40 | REL | APPR OPND | HB /C /02/EVACUATION-SUITS | EVACUATION SUITS |  | A | DKHB-0031 | MMS | DK50 | MS0044 |  | 2024-05-30
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325790 | 2Y LIFERAFT RECERTIFICATE - HBD | LIFERAFT RECERTIFICATE - HBD | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-05-31 | 2024-05-30 | 2024-06-01 | 2024-04-16 | 10 | REL | APPR OPND | HB /D /02/LIFE-RAFT | LIFE RAFT |  | A | DKHB-0036 | MMS | DK50 | MS0044 |  | 2024-05-21
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400325790 | 2Y LIFERAFT RECERTIFICATE - HBD | LIFERAFT RECERTIFICATE SUPPORT - HBD | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-05-31 | 2024-05-30 | 2024-06-01 | 2024-04-16 | 20 | REL | APPR OPND | HB /D /02/LIFE-RAFT | LIFE RAFT |  | A | DKHB-0036 | MMS | DK50 | MS0044 |  | 2024-05-22
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325800 | 1Y BREATHING AIR UNIT INSPECTION - HBD | BREATHING AIR UNIT INSPECTION - HBD | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-04-28 | 2024-04-30 | 2024-04-28 | 2024-05-28 | 2024-04-28 | 10 | REL | APPR OPND | HB /D /02/LIFE-SAVING-EQUIPMENT | LIFE SAVING EQUIPMENT |  | C | DKHB-0450 | MMR | DK50 | MR0024 |  | 2024-05-20
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400325800 | 1Y BREATHING AIR UNIT INSPECTION - HBD | BREATHING AIR UNIT INSPECTION - HBD | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-28 | 2024-04-30 | 2024-04-30 | 2024-05-28 | 2024-04-28 | 20 | REL | APPR OPND | HB /D /02/LIFE-SAVING-EQUIPMENT | LIFE SAVING EQUIPMENT |  | C | DKHB-0450 | MMR | DK50 | MR0024 |  | 2024-05-22
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400330050 | 1Y BREATHING AIR UNIT INSPECTION - HBC | BREATHING AIR UNIT INSPECTION - HBC | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-05-29 | 2024-05-30 | 2024-05-29 | 2024-06-28 | 2024-05-29 | 10 | REL | APPR OPND | HB /C /02/LIFE-SAVING-EQUIPMENT | LIFE SAVING EQUIPMENT |  | C | DKHB-0028 | MMR | DK50 | MR0024 |  | 2024-05-20
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400330050 | 1Y BREATHING AIR UNIT INSPECTION - HBC | BREATHING AIR UNIT INSPECTION - HBC | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-29 | 2024-05-30 | 2024-05-30 | 2024-06-28 | 2024-05-29 | 20 | REL | APPR OPND | HB /C /02/LIFE-SAVING-EQUIPMENT | LIFE SAVING EQUIPMENT |  | C | DKHB-0028 | MMR | DK50 | MR0024 |  | 2024-05-22
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400330052 | 3Y HAZARDOUS OPEN DRAIN MAINT-HBA | ISOLATION BY PRODUCTION | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-23 | 2024-05-27 | 2024-05-23 | 2024-06-24 | 2024-04-23 | 10 | REL | APPR OPND | HB /A /28/HAZARDOUS-OPEN-DRAIN | HBA HAZARDOUS OPEN DRAIN |  | C | DKHB-0046 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400330052 | 3Y HAZARDOUS OPEN DRAIN MAINT-HBA | HAZARDOUS OPEN DRAIN MAINT-HBA | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 7 | 0 |  | 2024-05-23 | 2024-05-27 | 2024-05-23 | 2024-06-24 | 2024-04-23 | 20 | REL | APPR OPND | HB /A /28/HAZARDOUS-OPEN-DRAIN | HBA HAZARDOUS OPEN DRAIN |  | C | DKHB-0046 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400330052 | 3Y HAZARDOUS OPEN DRAIN MAINT-HBA | HAZARDOUS OPEN DRAIN MAINT-HBA | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 5 | 0 |  | 2024-05-23 | 2024-05-27 | 2024-05-24 | 2024-06-24 | 2024-04-23 | 30 | REL | APPR OPND | HB /A /28/HAZARDOUS-OPEN-DRAIN | HBA HAZARDOUS OPEN DRAIN |  | C | DKHB-0046 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400330052 | 3Y HAZARDOUS OPEN DRAIN MAINT-HBA | HAZARDOUS OPEN DRAIN MAINT-HBA | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2024-05-23 | 2024-05-27 | 2024-05-25 | 2024-06-24 | 2024-04-23 | 40 | REL | APPR OPND | HB /A /28/HAZARDOUS-OPEN-DRAIN | HBA HAZARDOUS OPEN DRAIN |  | C | DKHB-0046 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400330052 | 3Y HAZARDOUS OPEN DRAIN MAINT-HBA | DE-ISOLATION BY PRODUCTION | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-23 | 2024-05-27 | 2024-05-27 | 2024-06-24 | 2024-04-23 | 50 | REL | APPR OPND | HB /A /28/HAZARDOUS-OPEN-DRAIN | HBA HAZARDOUS OPEN DRAIN |  | C | DKHB-0046 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334359 | 1Y POTABLE WATER MAKER - HBDB-A-1050Y | ISOLATION BY PRODUCTION | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-09 | 2024-06-11 | 2024-06-09 | 2024-07-09 | 2024-06-09 | 10 | REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | C | DKHB-0107 | MMS | DK50 | MS0024
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334359 | 1Y POTABLE WATER MAKER - HBDB-A-1050Y | POTABLE WATER MAKER INSP - HBDB-A-1050 | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 5 | 0 |  | 2024-06-09 | 2024-06-11 | 2024-06-09 | 2024-07-09 | 2024-06-09 | 20 | REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | C | DKHB-0107 | MMS | DK50 | MS0024
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334359 | 1Y POTABLE WATER MAKER - HBDB-A-1050Y | POTABLE WATER MAKER INSP - HBDB-A-1050 | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 5 | 0 |  | 2024-06-09 | 2024-06-11 | 2024-06-10 | 2024-07-09 | 2024-06-09 | 30 | REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | C | DKHB-0107 | MMS | DK50 | MS0024
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334359 | 1Y POTABLE WATER MAKER - HBDB-A-1050Y | POTABLE WATER MAKER INSP - HBDB-A-1050 | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-09 | 2024-06-11 | 2024-06-11 | 2024-07-09 | 2024-06-09 | 40 | REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | C | DKHB-0107 | MMS | DK50 | MS0024
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334359 | 1Y POTABLE WATER MAKER - HBDB-A-1050Y | DE-ISOLATION BY PRODUCTION | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-09 | 2024-06-11 | 2024-06-11 | 2024-07-09 | 2024-06-09 | 50 | REL | APPR OPND | HB /D /85/HBDB-A-1050 | POTABLE WATER MAKER UNIT |  | C | DKHB-0107 | MMS | DK50 | MS0024
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334582 | 1Y IGF RECIRC PUMPS MAINT-HBDB-P-5075/6 | ISOLATION BY PRODUCTION | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-20 | 2024-06-28 | 2024-06-20 | 2024-07-20 | 2024-06-20 | 10 | REL | APPR OPND | HB /D /27/HBDB-P-5075 | IGF RECIRCULATION PUMP |  | C | DKHB-0055 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334582 | 1Y IGF RECIRC PUMPS MAINT-HBDB-P-5075/6 | IGF RECIRC PUMPS MAINT-HBDB-P-5075/6 | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 18 | 0 |  | 2024-06-20 | 2024-06-28 | 2024-06-20 | 2024-07-20 | 2024-06-20 | 20 | REL | APPR OPND | HB /D /27/HBDB-P-5075 | IGF RECIRCULATION PUMP |  | C | DKHB-0055 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334582 | 1Y IGF RECIRC PUMPS MAINT-HBDB-P-5075/6 | IGF RECIRC PUMPS MAINT-HBDB-P-5075/6 | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 18 | 0 |  | 2024-06-20 | 2024-06-28 | 2024-06-24 | 2024-07-20 | 2024-06-20 | 30 | REL | APPR OPND | HB /D /27/HBDB-P-5075 | IGF RECIRCULATION PUMP |  | C | DKHB-0055 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334582 | 1Y IGF RECIRC PUMPS MAINT-HBDB-P-5075/6 | IGF RECIRC PUMPS MAINT-HBDB-P-5075/6 | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-20 | 2024-06-28 | 2024-06-27 | 2024-07-20 | 2024-06-20 | 40 | REL | APPR OPND | HB /D /27/HBDB-P-5075 | IGF RECIRCULATION PUMP |  | C | DKHB-0055 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334582 | 1Y IGF RECIRC PUMPS MAINT-HBDB-P-5075/6 | DE-ISOLATION BY PRODUCTION | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-20 | 2024-06-28 | 2024-06-28 | 2024-07-20 | 2024-06-20 | 50 | REL | APPR OPND | HB /D /27/HBDB-P-5075 | IGF RECIRCULATION PUMP |  | C | DKHB-0055 | MMR | DK50 | MR0054
0 | A | NOSD | WPM | MTN-INST | MTN-INST | 2400335693 | 1Y WEATHER MONITORING WDT'S HDA/B | WEATHER MONITORING WIND HDA/B | REL MACM PRC SETC | APPR SECE WMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-23 | 2024-06-23 | 2024-06-23 | 2024-07-23 | 2024-06-23 | 10 | REL | APPR OPND | HD /A /08/WEATHER-MONITORING | WEATHER MONITORING |  | A | DKHD-0122 | MIN | DK60 | IN0123
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100089860 | HBAB-PSV-29191 are seeping from pilot va | Pre. Isolation plan & ICC | REL CSER MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-26 | 2023-09-13 | 2023-05-01 | 20 | REL | APPR OPND | HB /A /37/HBAB-PSV-29191 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | CON-SCAF | 2100089860 | HBAB-PSV-29191 are seeping from pilot va | Pre. Install rigging gear | REL CSER MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-04-26 | 2024-05-01 | 2024-04-26 | 2023-09-13 | 2023-05-01 | 30 | REL | APPR OPND | HB /A /37/HBAB-PSV-29191 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100089860 | HBAB-PSV-29191 are seeping from pilot va | Isolation of HBAB-PSV-29191 | REL CSER MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-27 | 2023-09-13 | 2023-05-01 | 40 | REL | APPR OPND | HB /A /37/HBAB-PSV-29191 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100089860 | HBAB-PSV-29191 are seeping from pilot va | Prod Assist (breaking containment) | REL CSER MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-28 | 2023-09-13 | 2023-05-01 | 50 | REL | APPR OPND | HB /A /37/HBAB-PSV-29191 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | CON-WELD | 2100089860 | HBAB-PSV-29191 are seeping from pilot va | Remove PSV and install new PSV | REL CSER MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-04-26 | 2024-05-01 | 2024-04-28 | 2023-09-13 | 2023-05-01 | 60 | REL | APPR OPND | HB /A /37/HBAB-PSV-29191 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100089860 | HBAB-PSV-29191 are seeping from pilot va | Rigging assist (Remove/Install) | REL CSER MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-26 | 2024-05-01 | 2024-04-29 | 2023-09-13 | 2023-05-01 | 70 | REL | APPR OPND | HB /A /37/HBAB-PSV-29191 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100089860 | HBAB-PSV-29191 are seeping from pilot va | De-isolation & leak test HBAB-PSV-29191 | REL CSER MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-30 | 2023-09-13 | 2023-05-01 | 110 | REL | APPR OPND | HB /A /37/HBAB-PSV-29191 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100089860 | HBAB-PSV-29191 are seeping from pilot va | Documentation & Close out WO | REL CSER MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-30 | 2023-09-13 | 2023-05-01 | 120 | REL | APPR OPND | HB /A /37/HBAB-PSV-29191 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100089860 | HBAB-PSV-29191 are seeping from pilot va | Post. Remove Rigging gear | REL CSER MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 6 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-30 | 2023-09-13 | 2023-05-01 | 130 | REL | APPR OPND | HB /A /37/HBAB-PSV-29191 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
0 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100109566 | Battery cell defect/swollen | Battery cell defect/swollen | REL MACM PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-05-09 | 2024-05-11 | 2024-05-09 | 2024-05-09 | 2024-03-25 | 10 | REL | APPR OPND | HD /B /06/HDBE-AE-1922B | BATTERY BANK B |  | A |  | MEL | DK60
0 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100109566 | Battery cell defect/swollen | Site Visit - TBT. Coordinate with CCR | REL MACM PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-09 | 2024-05-11 | 2024-05-09 | 2024-05-09 | 2024-03-25 | 20 | REL | APPR OPND | HD /B /06/HDBE-AE-1922B | BATTERY BANK B |  | A |  | MEL | DK60
0 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100109566 | Battery cell defect/swollen | Isolate accordingly ICC. | REL MACM PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-05-09 | 2024-05-11 | 2024-05-09 | 2024-05-09 | 2024-03-25 | 30 | REL | APPR OPND | HD /B /06/HDBE-AE-1922B | BATTERY BANK B |  | A |  | MEL | DK60
0 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100109566 | Battery cell defect/swollen | Replace Faulty Batteries | REL MACM PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 10 | 0 |  | 2024-05-09 | 2024-05-11 | 2024-05-09 | 2024-05-09 | 2024-03-25 | 40 | REL | APPR OPND | HD /B /06/HDBE-AE-1922B | BATTERY BANK B |  | A |  | MEL | DK60
0 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100109566 | Battery cell defect/swollen | De-isolate for test and Check up. | REL MACM PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-05-09 | 2024-05-11 | 2024-05-11 | 2024-05-09 | 2024-03-25 | 50 | REL | APPR OPND | HD /B /06/HDBE-AE-1922B | BATTERY BANK B |  | A |  | MEL | DK60
0 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100109566 | Battery cell defect/swollen | clean up site / documentation | REL MACM PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-09 | 2024-05-11 | 2024-05-11 | 2024-05-09 | 2024-03-25 | 60 | REL | APPR OPND | HD /B /06/HDBE-AE-1922B | BATTERY BANK B |  | A |  | MEL | DK60
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400307663 | 2Y EMERGENCY GEN. INSPECT-HBCM-A-1732 | ISOLATION BY PRODUCTION | REL PCNF PRT MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 | W15-W16 | 2024-04-11 | 2024-04-18 | 2024-04-11 | 2024-02-28 | 2024-01-13 | 10 | PCNF REL | APPR OPND | HB /C /05/HBCM-A-1732 | EMERGENCY GENERATOR |  | D | DKHB-0492 | MMR | DK50 | MR0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400307663 | 2Y EMERGENCY GEN. INSPECT-HBCM-A-1732 | EMERGENCY GEN. INSPECT-HBCM-A-1732 | REL PCNF PRT MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 20 | 0 | W15-W16 | 2024-04-11 | 2024-04-18 | 2024-04-12 | 2024-02-28 | 2024-01-13 | 20 | PCNF REL | APPR OPND | HB /C /05/HBCM-A-1732 | EMERGENCY GENERATOR |  | D | DKHB-0492 | MMR | DK50 | MR0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400307663 | 2Y EMERGENCY GEN. INSPECT-HBCM-A-1732 | EMERGENCY GEN. INSPECT-HBCM-A-1732 | REL PCNF PRT MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 6 | 0 | W15-W16 | 2024-04-11 | 2024-04-18 | 2024-04-14 | 2024-02-28 | 2024-01-13 | 30 | PCNF REL | APPR OPND | HB /C /05/HBCM-A-1732 | EMERGENCY GENERATOR |  | D | DKHB-0492 | MMR | DK50 | MR0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400307663 | 2Y EMERGENCY GEN. INSPECT-HBCM-A-1732 | EMERGENCY GEN. INSPECT-HBCM-A-1732 | REL PCNF PRT MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | W15-W16 | 2024-04-11 | 2024-04-18 | 2024-04-15 | 2024-02-28 | 2024-01-13 | 40 | PCNF REL | APPR OPND | HB /C /05/HBCM-A-1732 | EMERGENCY GENERATOR |  | D | DKHB-0492 | MMR | DK50 | MR0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400307663 | 2Y EMERGENCY GEN. INSPECT-HBCM-A-1732 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 | W15-W16 | 2024-04-11 | 2024-04-18 | 2024-04-16 | 2024-02-28 | 2024-01-13 | 60 | PCNF REL | APPR OPND | HB /C /05/HBCM-A-1732 | EMERGENCY GENERATOR |  | D | DKHB-0492 | MMR | DK50 | MR0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400309080 | 1Y HVAC COOL NH3 VENDOR-HBDB-A-1280/85 | PERSONAL ISOLATION | REL MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2024-03-23 | 2024-02-22 | 10 | REL | APPR OPND | HB /D /51/HBDB-A-1280 | NH3 CHILLER PACKAGE (DUTY) |  | C | DKHB-2003 | MEL | DK50 | EL0014
2026-W13-14 | A | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400309080 | 1Y HVAC COOL NH3 VENDOR-HBDB-A-1280/85 | HVAC COOL NH3 VENDOR-HBDB-A-1280/85 | REL MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 15 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2024-03-23 | 2024-02-22 | 20 | REL | APPR OPND | HB /D /51/HBDB-A-1280 | NH3 CHILLER PACKAGE (DUTY) |  | C | DKHB-2003 | MEL | DK50 | EL0014
2026-W13-14 | A | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400309080 | 1Y HVAC COOL NH3 VENDOR-HBDB-A-1280/85 | PERSONAL DE-ISOLATION | REL MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-02 | 2024-03-23 | 2024-02-22 | 30 | REL | APPR OPND | HB /D /51/HBDB-A-1280 | NH3 CHILLER PACKAGE (DUTY) |  | C | DKHB-2003 | MEL | DK50 | EL0014
2026-W13-14 | A | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400309080 | 1Y HVAC COOL NH3 VENDOR-HBDB-A-1280/85 | RETURN TO OPERATION | REL MANC PRC SETC | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-02 | 2024-03-23 | 2024-02-22 | 40 | REL | APPR OPND | HB /D /51/HBDB-A-1280 | NH3 CHILLER PACKAGE (DUTY) |  | C | DKHB-2003 | MEL | DK50 | EL0014
2024-W23-24 | 3 | HBAPWELL | WGN | MTN-TELE | MTN-TELE | 2200008002 | F<(>&<)>G AI card replacement HBB | F&G AI card replacement HBB | REL PCNF GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 20 | 6 | + Siemens scope | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-12-11 | 2021-09-12 | 10 | PCNF REL | APPR OPND | HB /B /03/HBBB-FP-0101E | FIELD PANEL |  | A |  | MIN | DK50
2024-W47-48 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012769 | Replace HBDC-PSV-575001 - PSV 2023 | Isolation of PSV | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 2 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2025-11-26 | 2023-06-10 | 10 | REL | APPR OPND | HB /D /70/HBDC-PSV-575001 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012769 | Replace HBDC-PSV-575001 - PSV 2023 | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 2 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2025-11-26 | 2023-06-10 | 20 | REL | APPR OPND | HB /D /70/HBDC-PSV-575001 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012769 | Replace HBDC-PSV-575001 - PSV 2023 | Rigging assist (remove) | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 24 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-16 | 2025-11-26 | 2023-06-10 | 30 | REL | APPR OPND | HB /D /70/HBDC-PSV-575001 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012769 | Replace HBDC-PSV-575001 - PSV 2023 | Remove PSV and install blinds | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 5 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-21 | 2025-11-26 | 2023-06-10 | 40 | REL | APPR OPND | HB /D /70/HBDC-PSV-575001 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012769 | Replace HBDC-PSV-575001 - PSV 2023 | Re-certify PSV | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 0 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-22 | 2025-11-26 | 2023-06-10 | 50 | REL | APPR OPND | HB /D /70/HBDC-PSV-575001 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012769 | Replace HBDC-PSV-575001 - PSV 2023 | Rigging Assist (Install) | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 12 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-22 | 2025-11-26 | 2023-06-10 | 60 | REL | APPR OPND | HB /D /70/HBDC-PSV-575001 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012769 | Replace HBDC-PSV-575001 - PSV 2023 | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 2 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-24 | 2025-11-26 | 2023-06-10 | 70 | REL | APPR OPND | HB /D /70/HBDC-PSV-575001 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2024-W47-48 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012769 | Replace HBDC-PSV-575001 - PSV 2023 | De-isolation and leak test | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 4 | 0 | W47-48 | 2024-09-15 | 2024-09-26 | 2024-09-25 | 2025-11-26 | 2023-06-10 | 90 | REL | APPR OPND | HB /D /70/HBDC-PSV-575001 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ROUS | VEN-MECH | 2200015385 | Replace FFLB1 coolant with GlysantinG30 | Isolate lifeboat | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-02-13 | 2023-10-01 | 10 | REL | APPR OPND | HB /C /02/HBCA-X-0701 | LIFEBOAT 1 - 45 PERS. |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ROUS | VEN-MECH | 2200015385 | Replace FFLB1 coolant with GlysantinG30 | Flush coolant system with Glysantin G30 | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 3 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-02-13 | 2023-10-01 | 20 | REL | APPR OPND | HB /C /02/HBCA-X-0701 | LIFEBOAT 1 - 45 PERS. |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ROUS | VEN-MECH | 2200015385 | Replace FFLB1 coolant with GlysantinG30 | Add 20litres of Glysantin G30 | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 3 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-02-13 | 2023-10-01 | 30 | REL | APPR OPND | HB /C /02/HBCA-X-0701 | LIFEBOAT 1 - 45 PERS. |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ROUS | VEN-MECH | 2200015385 | Replace FFLB1 coolant with GlysantinG30 | De-isolate accordingly | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-02-13 | 2023-10-01 | 40 | REL | APPR OPND | HB /C /02/HBCA-X-0701 | LIFEBOAT 1 - 45 PERS. |  | C |  | MMS | DK50
2024-W15-16 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200016100 | Cooling water replacement HBCM-A-1731 | Isolation & safing of HBCM-A-1731 | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-04-08 | 2023-11-25 | 10 | REL | APPR OPND | HB /C /05/HBCM-A-1731 | EMERGENCY GENERATOR |  | A |  | MMR | DK50 |  | PROK | 2024-04-08
2024-W15-16 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200016100 | Cooling water replacement HBCM-A-1731 | Replacement of cooling water | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 6 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-04-08 | 2023-11-25 | 20 | REL | APPR OPND | HB /C /05/HBCM-A-1731 | EMERGENCY GENERATOR |  | A |  | MMR | DK50 |  | PROK | 2024-04-09
2024-W15-16 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200016100 | Cooling water replacement HBCM-A-1731 | De-isolation & de-safing of HBCM-A-1731 | REL GMPS MANC PRC SETC | APPR SECE SMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2024-04-08 | 2023-11-25 | 30 | REL | APPR OPND | HB /C /05/HBCM-A-1731 | EMERGENCY GENERATOR |  | A |  | MMR | DK50 |  | PROK | 2024-04-10
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100090651 | HBBB-ESDV-29003 is internally leaking | Isolation of ESDV-29003 | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO RFRZ ROUT | 8 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-25 | 2023-11-04 | 2023-06-22 | 10 | REL | APPR OPND | HB /B /37/HBBB-ESDV-29003 | EMERGENCY SHUTDOWN VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-ELEC | 2100090651 | HBBB-ESDV-29003 is internally leaking | Electrical disconnect and connect | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO RFRZ ROUT | 1 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-27 | 2023-11-04 | 2023-06-22 | 18 | REL | APPR OPND | HB /B /37/HBBB-ESDV-29003 | EMERGENCY SHUTDOWN VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-RIGG | 2100090651 | HBBB-ESDV-29003 is internally leaking | Prepare rigging gear | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO RFRZ ROUT | 3 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-25 | 2023-11-04 | 2023-06-22 | 19 | REL | APPR OPND | HB /B /37/HBBB-ESDV-29003 | EMERGENCY SHUTDOWN VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100090651 | HBBB-ESDV-29003 is internally leaking | Demount valve | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO RFRZ ROUT | 6 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-27 | 2023-11-04 | 2023-06-22 | 20 | REL | APPR OPND | HB /B /37/HBBB-ESDV-29003 | EMERGENCY SHUTDOWN VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-RIGG | 2100090651 | HBBB-ESDV-29003 is internally leaking | Rigging of old valve | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO RFRZ ROUT | 11 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-26 | 2023-11-04 | 2023-06-22 | 21 | REL | APPR OPND | HB /B /37/HBBB-ESDV-29003 | EMERGENCY SHUTDOWN VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100090651 | HBBB-ESDV-29003 is internally leaking | Rebuild actuator to new valve | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO RFRZ ROUT | 6 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-28 | 2023-11-04 | 2023-06-22 | 30 | REL | APPR OPND | HB /B /37/HBBB-ESDV-29003 | EMERGENCY SHUTDOWN VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-RIGG | 2100090651 | HBBB-ESDV-29003 is internally leaking | Rigging of new valve | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO RFRZ ROUT | 11 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-29 | 2023-11-04 | 2023-06-22 | 39 | REL | APPR OPND | HB /B /37/HBBB-ESDV-29003 | EMERGENCY SHUTDOWN VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100090651 | HBBB-ESDV-29003 is internally leaking | Install new valve | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO RFRZ ROUT | 8 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-30 | 2023-11-04 | 2023-06-22 | 40 | REL | APPR OPND | HB /B /37/HBBB-ESDV-29003 | EMERGENCY SHUTDOWN VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100090651 | HBBB-ESDV-29003 is internally leaking | De-isolate and test of ESDV-29003 | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO RFRZ ROUT | 8 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-04-01 | 2023-11-04 | 2023-06-22 | 70 | REL | APPR OPND | HB /B /37/HBBB-ESDV-29003 | EMERGENCY SHUTDOWN VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100050656 | On standby, cracked Actuator Housing ESD | Pre/post Rigging/Lifting Equipment | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-22 | 2021-07-13 | 2021-06-03 | 10 | REL | APPR OPND | HB /A /34/HBAA-ESDV-38049 | EMERGENCY SHUTDOWN VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-SCAF | 2100050656 | On standby, cracked Actuator Housing ESD | Pre/post Scaffold Erection | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-22 | 2021-07-13 | 2021-06-03 | 20 | REL | APPR OPND | HB /A /34/HBAA-ESDV-38049 | EMERGENCY SHUTDOWN VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100050656 | On standby, cracked Actuator Housing ESD | Isolate valve & act | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-23 | 2021-07-13 | 2021-06-03 | 30 | REL | APPR OPND | HB /A /34/HBAA-ESDV-38049 | EMERGENCY SHUTDOWN VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-INST | 2100050656 | On standby, cracked Actuator Housing ESD | Remove/install ACT's supply/Switchbox | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-24 | 2021-07-13 | 2021-06-03 | 40 | REL | APPR OPND | HB /A /34/HBAA-ESDV-38049 | EMERGENCY SHUTDOWN VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100050656 | On standby, cracked Actuator Housing ESD | replace with new act | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-24 | 2021-07-13 | 2021-06-03 | 50 | REL | APPR OPND | HB /A /34/HBAA-ESDV-38049 | EMERGENCY SHUTDOWN VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100050656 | On standby, cracked Actuator Housing ESD | Replace Actuator | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-24 | 2021-07-13 | 2021-06-03 | 60 | REL | APPR OPND | HB /A /34/HBAA-ESDV-38049 | EMERGENCY SHUTDOWN VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100050656 | On standby, cracked Actuator Housing ESD | de-isolate, leak test, etc. | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-08-22 | 2024-08-26 | 2024-08-25 | 2021-07-13 | 2021-06-03 | 70 | REL | APPR OPND | HB /A /34/HBAA-ESDV-38049 | EMERGENCY SHUTDOWN VALVE |  | C |  | MMS | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100076866 | LIT-345103 HP-SEP. ESD Oil - Worn out | Inhibit Contact Level transmitter (float | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W21-22 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-04-20 | 2022-12-06 | 10 | REL | APPR OPND | HB /D /20/HBDC-LIT-345103 | LEVEL INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50 |  |  | 2024-06-02
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100076866 | LIT-345103 HP-SEP. ESD Oil - Worn out | Isolate Contact Level transmitter (float | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 3 | 0 | W21-22 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-04-20 | 2022-12-06 | 20 | REL | APPR OPND | HB /D /20/HBDC-LIT-345103 | LEVEL INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50 |  |  | 2024-06-04
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100076866 | LIT-345103 HP-SEP. ESD Oil - Worn out | Replace Contact Level transmitter (float | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 10 | 0 | W21-22 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-04-20 | 2022-12-06 | 30 | REL | APPR OPND | HB /D /20/HBDC-LIT-345103 | LEVEL INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50 |  |  | 2024-06-05
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100076866 | LIT-345103 HP-SEP. ESD Oil - Worn out | Calibrate Contact Level transmitter (flo | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 10 | 0 | W21-22 | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2023-04-20 | 2022-12-06 | 40 | REL | APPR OPND | HB /D /20/HBDC-LIT-345103 | LEVEL INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50 |  |  | 2024-06-07
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100076866 | LIT-345103 HP-SEP. ESD Oil - Worn out | Deisolate Contact Level transmitter (flo | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 3 | 0 | W21-22 | 2024-03-09 | 2024-03-11 | 2024-03-11 | 2023-04-20 | 2022-12-06 | 50 | REL | APPR OPND | HB /D /20/HBDC-LIT-345103 | LEVEL INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50 |  |  | 2024-06-09
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100076866 | LIT-345103 HP-SEP. ESD Oil - Worn out | Repeal inhibit Contact Level transmitter | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W21-22 | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2023-04-20 | 2022-12-06 | 60 | REL | APPR OPND | HB /D /20/HBDC-LIT-345103 | LEVEL INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50 |  |  | 2024-06-10
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100076866 | LIT-345103 HP-SEP. ESD Oil - Worn out | BL the old trasmitters to J0515957 Prote | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W21-22 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-04-20 | 2022-12-06 | 70 | REL | APPR OPND | HB /D /20/HBDC-LIT-345103 | LEVEL INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50 |  |  | 2024-06-12
2024-W41-42 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400206934 | 1Y HVAC SKID CHECK HBAA-A-1210 | PERSONAL ISOLATION | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W41-42 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-16 | 2022-08-17 | 10 | PCNF REL | APPR OPND | HB /A /09/HBAA-A-1210 | PACKAGE |  | A | DKHB-2018 | MEL | DK50 | EL0014
2024-W41-42 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400206934 | 1Y HVAC SKID CHECK HBAA-A-1210 | HVAC SKID CHECK HBAA-A-1210 | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 12 | 5 | W41-42 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-16 | 2022-08-17 | 20 | PCNF REL | APPR OPND | HB /A /09/HBAA-A-1210 | PACKAGE |  | A | DKHB-2018 | MEL | DK50 | EL0014
2024-W41-42 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400206934 | 1Y HVAC SKID CHECK HBAA-A-1210 | PERSONAL DE-ISOLATION | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W41-42 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-16 | 2022-08-17 | 30 | PCNF REL | APPR OPND | HB /A /09/HBAA-A-1210 | PACKAGE |  | A | DKHB-2018 | MEL | DK50 | EL0014
2024-W41-42 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400206934 | 1Y HVAC SKID CHECK HBAA-A-1210 | RETURN TO OPERATION | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W41-42 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-16 | 2022-08-17 | 40 | PCNF REL | APPR OPND | HB /A /09/HBAA-A-1210 | PACKAGE |  | A | DKHB-2018 | MEL | DK50 | EL0014
2024-W15-16 | A | NOSD | WPM | MTN-INST | MTN-INST | 2400322711 | 6M PORTABLE GAS DETECTORS HBD | HBA PORTABLE-GAS-DETECTORS MAINT | REL GMPS MACM PRC SETC | APPR SECE SMAT AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-05-15 | 2024-04-29 | 10 | REL | APPR OPND | HB /D /03/PORTABLE-GAS-DETECTORS | PORTABLE GAS DETECTORS |  | A | DKHB-2039 | MIN | DK50 | IN0074 |  | 2024-04-08
2026-W13-14 | A | HBD-IPHP | WPM | MTN-MECH | PRODTECH | 2400281933 | 1Y IG SKID SERVICE HBDB-A-0850 | ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-28 | 2024-04-02 | 2024-03-28 | 2023-10-20 | 2023-09-20 | 10 | REL | APPR OPND | HB /D /74/HBDB-A-0850 | INERT GAS PACKAGE |  | F | DKHB-0022 | MMS | DK50 | MR0034
2026-W13-14 | A | HBD-IPHP | WPM | MTN-MECH | MTN-INST | 2400281933 | 1Y IG SKID SERVICE HBDB-A-0850 | IG SKID SERVICE HBDB-A-0850 | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-03-28 | 2024-04-02 | 2024-03-28 | 2023-10-20 | 2023-09-20 | 20 | REL | APPR OPND | HB /D /74/HBDB-A-0850 | INERT GAS PACKAGE |  | F | DKHB-0022 | MMS | DK50 | MR0034
2026-W13-14 | A | HBD-IPHP | WPM | MTN-MECH | MTN-MECH | 2400281933 | 1Y IG SKID SERVICE HBDB-A-0850 | IG SKID SERVICE HBDB-A-0850 | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 19 | 0 |  | 2024-03-28 | 2024-04-02 | 2024-03-29 | 2023-10-20 | 2023-09-20 | 30 | REL | APPR OPND | HB /D /74/HBDB-A-0850 | INERT GAS PACKAGE |  | F | DKHB-0022 | MMS | DK50 | MR0034
2026-W13-14 | A | HBD-IPHP | WPM | MTN-MECH | MTN-ELEC | 2400281933 | 1Y IG SKID SERVICE HBDB-A-0850 | IG SKID SERVICE HBDB-A-0850 | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-28 | 2024-04-02 | 2024-04-02 | 2023-10-20 | 2023-09-20 | 40 | REL | APPR OPND | HB /D /74/HBDB-A-0850 | INERT GAS PACKAGE |  | F | DKHB-0022 | MMS | DK50 | MR0034
2026-W13-14 | A | HBD-IPHP | WPM | MTN-MECH | PRODTECH | 2400281933 | 1Y IG SKID SERVICE HBDB-A-0850 | DE-ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-28 | 2024-04-02 | 2024-04-02 | 2023-10-20 | 2023-09-20 | 50 | REL | APPR OPND | HB /D /74/HBDB-A-0850 | INERT GAS PACKAGE |  | F | DKHB-0022 | MMS | DK50 | MR0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284407 | PSV Calibration - HBAB-PSV-34038 | Isolation of PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2025-01-07 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 10 | PCNF REL | APPR OPND | HB /A /10/HBAB-PSV-34038 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV013 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284407 | PSV Calibration - HBAB-PSV-34038 | Prod Assist (breaking containment) | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2025-01-07 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 20 | PCNF REL | APPR OPND | HB /A /10/HBAB-PSV-34038 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV013 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284407 | PSV Calibration - HBAB-PSV-34038 | Rigging assist (remove) | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 12 |  | 2024-10-30 | 2025-01-07 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 30 | PCNF REL | APPR OPND | HB /A /10/HBAB-PSV-34038 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV013 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284407 | PSV Calibration - HBAB-PSV-34038 | Re-certify PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-30 | 2025-01-07 | 2025-01-02 | 2024-12-31 | 2024-10-30 | 60 | PCNF REL | APPR OPND | HB /A /10/HBAB-PSV-34038 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV013 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284407 | PSV Calibration - HBAB-PSV-34038 | Rigging Assist (Install) | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-30 | 2025-01-07 | 2025-01-03 | 2024-12-31 | 2024-10-30 | 70 | PCNF REL | APPR OPND | HB /A /10/HBAB-PSV-34038 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV013 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284407 | PSV Calibration - HBAB-PSV-34038 | Prod Assist (breaking containment) | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2025-01-07 | 2025-01-04 | 2024-12-31 | 2024-10-30 | 80 | PCNF REL | APPR OPND | HB /A /10/HBAB-PSV-34038 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV013 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284407 | PSV Calibration - HBAB-PSV-34038 | Install re-certified PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-30 | 2025-01-07 | 2025-01-05 | 2024-12-31 | 2024-10-30 | 90 | PCNF REL | APPR OPND | HB /A /10/HBAB-PSV-34038 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV013 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284407 | PSV Calibration - HBAB-PSV-34038 | De-isolation and leak test | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-30 | 2025-01-07 | 2025-01-06 | 2024-12-31 | 2024-10-30 | 100 | PCNF REL | APPR OPND | HB /A /10/HBAB-PSV-34038 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV013 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284407 | PSV Calibration - HBAB-PSV-34038 | Documentation & CNF WO | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2025-01-07 | 2025-01-06 | 2024-12-31 | 2024-10-30 | 110 | PCNF REL | APPR OPND | HB /A /10/HBAB-PSV-34038 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV013 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284407 | PSV Calibration - HBAB-PSV-34038 | Check PSV flanges & alignment | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W09-W10 | 2024-10-30 | 2025-01-07 | 2025-01-07 | 2024-12-31 | 2024-10-30 | 120 | PCNF REL | APPR OPND | HB /A /10/HBAB-PSV-34038 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV013 | MMS | DK50
0 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400290488 | 1Y LIFEBOAT INSPECTION HDBM-X-0701 | LIFEBOAT INSPECTION HDBM-X-0701 | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 38 | 0 | W15-W16 | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2023-11-01 | 2023-10-02 | 10 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | B | DKHD-0132 | MMS | DK60 | MS0043
0 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400290491 | 1Y LIFEBOAT INSPECTION HDBM-X-0702 | LIFEBOAT INSPECTION HDBM-X-0702 | REL GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 38 | 0 | W15-W16 | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2023-11-01 | 2023-10-02 | 10 | REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | B | DKHD-0133 | MMS | DK60 | MS0043
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400309087 | 4Y FIREWATER PUMP PACKAGE HDBD-A-0301 | ISOLATION BY PRODUCTION | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-05-11 | 2024-04-26 | 2024-03-24 | 2024-01-11 | 10 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | D | DKHD-0177 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400309087 | 4Y FIREWATER PUMP PACKAGE HDBD-A-0301 | FIREWATER PUMP PACKAGE HDBD-A-0301 | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 30 | 0 | W17-W18 | 2024-04-26 | 2024-05-11 | 2024-04-26 | 2024-03-24 | 2024-01-11 | 20 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | D | DKHD-0177 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400309087 | 4Y FIREWATER PUMP PACKAGE HDBD-A-0301 | VENDOR ASSISTANCE | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 48 | 0 | W17-W18 | 2024-04-26 | 2024-05-11 | 2024-05-02 | 2024-03-24 | 2024-01-11 | 30 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | D | DKHD-0177 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400309087 | 4Y FIREWATER PUMP PACKAGE HDBD-A-0301 | FIREWATER PUMP PACKAGE HDBD-A-0301 | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 | W17-W18 | 2024-04-26 | 2024-05-11 | 2024-05-07 | 2024-03-24 | 2024-01-11 | 40 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | D | DKHD-0177 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400309087 | 4Y FIREWATER PUMP PACKAGE HDBD-A-0301 | FIREWATER PUMP PACKAGE HDBD-A-0301 | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 6 | 0 | W17-W18 | 2024-04-26 | 2024-05-11 | 2024-05-09 | 2024-03-24 | 2024-01-11 | 50 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | D | DKHD-0177 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400309087 | 4Y FIREWATER PUMP PACKAGE HDBD-A-0301 | DE-ISOLATION BY PRODUCTION | REL PRT GMPS MANC PRC SETC | APPR SECE SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-05-11 | 2024-05-11 | 2024-03-24 | 2024-01-11 | 60 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | D | DKHD-0177 | MMS | DK60 | MS0013
2024-W41-42 | A | HBDIGF1 | WPM | MTN-MECH | MTN-MECH | 2400205766 | 3Y IGF RECIRC PUMPS MAINT-HBDB-P-5075/6 | MATERIAL | REL PCNF MANC PPRT PRC SETC | APPR SECE RDBL RFRZ ROUT | 0 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2022-07-20 | 2022-05-19 | 60 | REL | APPR OPND | HB /D /27/HBDB-P-5075 | IGF RECIRCULATION PUMP |  | D | DKHB-0055 | MMR | DK50 | MR0044
2024-W31-32 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400272938 | 1Y MP PIG LAUNCHR MAINT-HBAA-EP-3811 | ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE RDBL RFRZ ROUT | 1 | 0 | W31-32 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-09-01 | 2023-08-02 | 10 | PCNF REL | APPR OPND | HB /A /12/HBAA-EP-3811 | MULTIPHASE PIG LAUNCHER |  | C | DKHB-0010 | MMS | DK50 | MS0094
2024-W31-32 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400272938 | 1Y MP PIG LAUNCHR MAINT-HBAA-EP-3811 | MP PIG LAUNCHR MAINT-HBAA-EP-3811 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE RDBL RFRZ ROUT | 2 | 0 | W31-32 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-09-01 | 2023-08-02 | 20 | PCNF REL | APPR OPND | HB /A /12/HBAA-EP-3811 | MULTIPHASE PIG LAUNCHER |  | C | DKHB-0010 | MMS | DK50 | MS0094
2024-W31-32 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400272938 | 1Y MP PIG LAUNCHR MAINT-HBAA-EP-3811 | MP PIG LAUNCHR MAINT-HBAA-EP-3811 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE RDBL RFRZ ROUT | 2 | 2 | W31-32 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-09-01 | 2023-08-02 | 30 | PCNF REL | APPR OPND | HB /A /12/HBAA-EP-3811 | MULTIPHASE PIG LAUNCHER |  | C | DKHB-0010 | MMS | DK50 | MS0094
2024-W31-32 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400272938 | 1Y MP PIG LAUNCHR MAINT-HBAA-EP-3811 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE RDBL RFRZ ROUT | 1 | 0 | W31-32 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-09-01 | 2023-08-02 | 40 | PCNF REL | APPR OPND | HB /A /12/HBAA-EP-3811 | MULTIPHASE PIG LAUNCHER |  | C | DKHB-0010 | MMS | DK50 | MS0094
2026-W13-14 | 3 | NOSD | WGN | MTN-LAGG | CON-LAGG | 2200005868 | Insulation assist Bilfinger 18164 | Insulation assist FORCE 18164 | REL MANC NMAT PRC SETC | APPR SECE RDBL | 0 | 0 |  | 2023-04-24 | 2023-05-16 | 2023-04-24 | 2020-10-22 | 2020-07-24 | 10 | REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | COW | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200005868 | Insulation assist Bilfinger 18164 | Erect Scaffold | REL MANC NMAT PRC SETC | APPR SECE RDBL | 78 | 0 |  | 2023-04-24 | 2023-05-16 | 2023-04-24 | 2020-10-22 | 2020-07-24 | 20 | REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | COW | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200005868 | Insulation assist Bilfinger 18164 | Remove Insulation | REL MANC NMAT PRC SETC | APPR SECE RDBL | 27 | 0 |  | 2023-04-24 | 2023-05-16 | 2023-05-02 | 2020-10-22 | 2020-07-24 | 30 | REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | COW | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-LAGG | VEN-MECH | 2200005868 | Insulation assist Bilfinger 18164 | Bilfinger - Scan | REL MANC NMAT PRC SETC | APPR SECE RDBL | 2 | 0 |  | 2023-04-24 | 2023-05-16 | 2023-05-04 | 2020-10-22 | 2020-07-24 | 40 | REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | COW | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200005868 | Insulation assist Bilfinger 18164 | Refit Insulation | REL MANC NMAT PRC SETC | APPR SECE RDBL | 54 | 0 |  | 2023-04-24 | 2023-05-16 | 2023-05-05 | 2020-10-22 | 2020-07-24 | 50 | REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | COW | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200005868 | Insulation assist Bilfinger 18164 | Dismantle Scaffold | REL MANC NMAT PRC SETC | APPR SECE RDBL | 52 | 0 |  | 2023-04-24 | 2023-05-16 | 2023-05-10 | 2020-10-22 | 2020-07-24 | 60 | REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0201-GFW-A | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | COW | DK50
2024-W41-42 | 3 | HBD-IPHP | WGN | MTN-TURB | MTN-TURB | 2200016780 | Survey prior to exh comp replac on 4352 | Survey prior to exh comp replac on 4352 | REL MANC PRC SETC | APPR SECE RDBL | 0 | 0 | W07-W08 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-06-11 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | E |  | MMR | DK50
2026-W13-14 | 3 | NE | WRO | MTN-TELE | CON-VEN | 2300005324 | E51 DK220365 Bypass of V-3451 for PVI | E51 DK220365 Bypass of V-3451 for PVI | REL MANC NMAT PRC SETC | APPR SECE RDBL | 6 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2023-10-01 | 2023-05-19 | 10 | REL | APPR OPND | HB /B /03/HBBA-CP-0230A | ESD PANEL A / NODE E51 |  | A |  | CON | DK50
2026-W13-14 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300005324 | E51 DK220365 Bypass of V-3451 for PVI | Telecom Assistance | REL MANC NMAT PRC SETC | APPR SECE RDBL | 4 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2023-10-01 | 2023-05-19 | 20 | REL | APPR OPND | HB /B /03/HBBA-CP-0230A | ESD PANEL A / NODE E51 |  | A |  | CON | DK50
0 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300006371 | E31 Enable temp. oil exp. to DFG | E31 Enable temp. oil exp. to DFG | REL MANC NMAT PRC SETC | APPR SECE RDBL | 6 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2024-02-10 | 2023-09-28 | 10 | REL | APPR OPND | HD /B /03/HDBE-CPF-0201 | ESD CONTROLLER PANEL |  | A |  | MIN | DK60
0 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300006371 | E31 Enable temp. oil exp. to DFG |  | REL MANC NMAT PRC SETC | APPR SECE RDBL | 0 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-10 | 2024-02-10 | 2023-09-28 | 20 | REL | APPR OPND | HD /B /03/HDBE-CPF-0201 | ESD CONTROLLER PANEL |  | A |  | MIN | DK60
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012733 | Replace HBDB-PSV-416102 - PSV 2023 | Isolation of PSV | REL GMPS MANC PRC SETC | APPR SECE PMAT SCH RDBL | 2 | 0 | W17-W18 | 2024-04-22 | 2024-05-02 | 2024-04-22 | 2025-11-19 | 2023-06-03 | 10 | REL | APPR OPND | HB /D /30/HBDB-PSV-416102 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012733 | Replace HBDB-PSV-416102 - PSV 2023 | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SECE PMAT SCH RDBL | 2 | 0 | W17-W18 | 2024-04-22 | 2024-05-02 | 2024-04-22 | 2025-11-19 | 2023-06-03 | 20 | REL | APPR OPND | HB /D /30/HBDB-PSV-416102 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012733 | Replace HBDB-PSV-416102 - PSV 2023 | Rigging assist (remove) | REL GMPS MANC PRC SETC | APPR SECE PMAT SCH RDBL | 24 | 0 | W17-W18 | 2024-04-22 | 2024-05-02 | 2024-04-22 | 2025-11-19 | 2023-06-03 | 30 | REL | APPR OPND | HB /D /30/HBDB-PSV-416102 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012733 | Replace HBDB-PSV-416102 - PSV 2023 | Remove PSV and install new PSV | REL GMPS MANC PRC SETC | APPR SECE PMAT SCH RDBL | 5 | 0 | W17-W18 | 2024-04-22 | 2024-05-02 | 2024-04-27 | 2025-11-19 | 2023-06-03 | 40 | REL | APPR OPND | HB /D /30/HBDB-PSV-416102 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012733 | Replace HBDB-PSV-416102 - PSV 2023 | Rigging Assist (Install) | REL GMPS MANC PRC SETC | APPR SECE PMAT SCH RDBL | 12 | 0 | W17-W18 | 2024-04-22 | 2024-05-02 | 2024-04-28 | 2025-11-19 | 2023-06-03 | 60 | REL | APPR OPND | HB /D /30/HBDB-PSV-416102 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012733 | Replace HBDB-PSV-416102 - PSV 2023 | Prod Assist (breaking containment) | REL GMPS MANC PRC SETC | APPR SECE PMAT SCH RDBL | 2 | 0 | W17-W18 | 2024-04-22 | 2024-05-02 | 2024-05-01 | 2025-11-19 | 2023-06-03 | 70 | REL | APPR OPND | HB /D /30/HBDB-PSV-416102 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012733 | Replace HBDB-PSV-416102 - PSV 2023 | De-isolation and leak test | REL GMPS MANC PRC SETC | APPR SECE PMAT SCH RDBL | 4 | 0 | W17-W18 | 2024-04-22 | 2024-05-02 | 2024-05-01 | 2025-11-19 | 2023-06-03 | 90 | REL | APPR OPND | HB /D /30/HBDB-PSV-416102 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300004477 | Node lifetime extension - SIS Systems | Node lifetime extension - SIS Systems | REL GMPS MANC PRC SETC | APPR SECE PMAT RDBL | 450 | 0 |  | 2024-07-01 | 2024-09-28 | 2024-07-01 | 2023-07-09 | 2023-02-24 | 10 | REL | APPR OPND | HB /B /03/HBBA-CP-0230A | ESD PANEL A / NODE E51 |  | A |  | MEL | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | QAQCMECH | 2400054898 | PVI HBDC-V-3451 | Matt. bestilling 8/7 SMEDE | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 0 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 11 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-WELD | 2400054898 | PVI HBDC-V-3451 | WELD Preparation PTW | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 8 | 48.5 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 20 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | QAQCMECH | 2400054898 | PVI HBDC-V-3451 | Matt bestilling 27/8-2020 | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 0 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 22 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | SCAF Preparation PTW | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 8 | 8 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 30 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-PAIN | 2400054898 | PVI HBDC-V-3451 | PAIN Preparation PTW | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 8 | 8 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 40 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-ELEC | 2400054898 | PVI HBDC-V-3451 | ELEC Preparation PTW | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 8 | 79.5 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 50 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-LAGG | 2400054898 | PVI HBDC-V-3451 | LAGG preparatio PTW | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 8 | 21 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 60 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Install Scaffolding, drip tray | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 585 | 1745.5 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 90 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Check Liftning Proc & Line Walk (Scaff) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 10 | 36.5 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 110 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Install liftning equipment | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 130 | 722 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 115 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-WELD | 2400054898 | PVI HBDC-V-3451 | Preparing of PVI (Weld) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 52 | 188 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 120 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-WELD | 2400054898 | PVI HBDC-V-3451 | Layout of tools (Weld) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 52 | 33 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 130 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-WELD | 2400054898 | PVI HBDC-V-3451 | Check materials (Weld) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 104 | 17.5 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 160 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-LAGG | 2400054898 | PVI HBDC-V-3451 | Remove insulation (Lagger) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 39 | 31.5 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 175 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-ELEC | 2400054898 | PVI HBDC-V-3451 | Remove Heat Tracing (El) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 26 | 18 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 180 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | PRODTECH | 2400054898 | PVI HBDC-V-3451 | Safing (Prod) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 10 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 200 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-WELD | 2400054898 | PVI HBDC-V-3451 | Install blind Flg and spades (Weld) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 156 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 210 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Scaff ass blind and spades (Scaff) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 156 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 220 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-WELD | 2400054898 | PVI HBDC-V-3451 | Inspektion of Flg and lumen (Weld) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 52 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 240 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-ELEC | 2400054898 | PVI HBDC-V-3451 | Demol instrument (El) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 52 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 270 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-WELD | 2400054898 | PVI HBDC-V-3451 | Open vessel mannhold (Weld) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 52 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 280 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-ELEC | 2400054898 | PVI HBDC-V-3451 | Install light in vessel(EL) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 26 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-19 | 2023-12-31 | 2020-11-23 | 340 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-PAIN | 2400054898 | PVI HBDC-V-3451 | Lugemand (Paint) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 780 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-19 | 2023-12-31 | 2020-11-23 | 350 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-PAIN | 2400054898 | PVI HBDC-V-3451 | Cleaning of indside equipment (Paint) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 520 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-20 | 2023-12-31 | 2020-11-23 | 360 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-PAIN | 2400054898 | PVI HBDC-V-3451 | Cleaning of Levelglas (Paint) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 78 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-01 | 2023-12-31 | 2020-11-23 | 370 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-WELD | 2400054898 | PVI HBDC-V-3451 | Epuipment removed indside (Weld) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 312 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-01 | 2023-12-31 | 2020-11-23 | 420 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Epuipment removed indside (Scaff | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 234 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-01 | 2023-12-31 | 2020-11-23 | 430 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Rigging out internals for onshore scaf | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 78 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-11 | 2023-12-31 | 2020-11-23 | 431 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Pack internals for shipping to onshore | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 39 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-13 | 2023-12-31 | 2020-11-23 | 432 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-ELEC | 2400054898 | PVI HBDC-V-3451 | Cleaning of remote seals (EL) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 26 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-02 | 2023-12-31 | 2020-11-23 | 440 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-PAIN | 2400054898 | PVI HBDC-V-3451 | Cleaning of equipment (Paint) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 156 | 98 |  | 2021-07-23 | 2024-05-06 | 2024-04-02 | 2023-12-31 | 2020-11-23 | 450 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | QAQCMECH | 2400054898 | PVI HBDC-V-3451 | Inspection of Equipment / Nozzles (QC) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 13 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-14 | 2023-12-31 | 2020-11-23 | 500 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Rigging in internals from onshore scaf | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 78 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-14 | 2023-12-31 | 2020-11-23 | 510 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | QAQCMECH | 2400054898 | PVI HBDC-V-3451 | Re-install inside epuipmant (Weld) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 208 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-17 | 2023-12-31 | 2020-11-23 | 520 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Re-install inside epuipmant (Scaff) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 208 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-17 | 2023-12-31 | 2020-11-23 | 530 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-ELEC | 2400054898 | PVI HBDC-V-3451 | Demol vessel light (El) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 13 | 34 |  | 2021-07-23 | 2024-05-06 | 2024-04-23 | 2023-12-31 | 2020-11-23 | 540 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | PRODTECH | 2400054898 | PVI HBDC-V-3451 | Prod inspektion befor closed (Prod) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 5 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-23 | 2023-12-31 | 2020-11-23 | 541 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-WELD | 2400054898 | PVI HBDC-V-3451 | Closed epuipmant (Weld) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 52 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-24 | 2023-12-31 | 2020-11-23 | 550 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Closed epuipmant (Scaff) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 52 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-24 | 2023-12-31 | 2020-11-23 | 560 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-WELD | 2400054898 | PVI HBDC-V-3451 | Demol Flg and Spads (Weld) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 130 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-25 | 2023-12-31 | 2020-11-23 | 580 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Demol Flg and Spads (Scaff) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 130 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-25 | 2023-12-31 | 2020-11-23 | 590 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-ELEC | 2400054898 | PVI HBDC-V-3451 | Re-install Heat Tracing (El) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 52 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-04-28 | 2023-12-31 | 2020-11-23 | 610 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-ELEC | 2400054898 | PVI HBDC-V-3451 | Re-install instruments (EL/inst) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 26 | 64 |  | 2021-07-23 | 2024-05-06 | 2024-05-01 | 2023-12-31 | 2020-11-23 | 621 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | PRODTECH | 2400054898 | PVI HBDC-V-3451 | Safeing and leaktest | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 10 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-05-01 | 2023-12-31 | 2020-11-23 | 642 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-LAGG | 2400054898 | PVI HBDC-V-3451 | Re-install Insulations (Lagger) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 78 | 296 |  | 2021-07-23 | 2024-05-06 | 2021-07-23 | 2023-12-31 | 2020-11-23 | 672 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Demol liftning equipment (Scaff) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 52 | 145 |  | 2021-07-23 | 2024-05-06 | 2024-05-02 | 2023-12-31 | 2020-11-23 | 692 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | QAQCMECH | 2400054898 | PVI HBDC-V-3451 | GASKETS / STUDBOLTS | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 0 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 700 | REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Demol scaffolding (Scaff) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 312 | 599 |  | 2021-07-23 | 2024-05-06 | 2021-07-26 | 2023-12-31 | 2020-11-23 | 702 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | QAQCMECH | 2400054898 | PVI HBDC-V-3451 | Div. Flanger | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 0 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 703 | REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-WELD | 2400054898 | PVI HBDC-V-3451 | Cleaning (Weld) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 78 | 65 |  | 2021-07-23 | 2024-05-06 | 2024-05-02 | 2023-12-31 | 2020-11-23 | 712 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-SCAF | 2400054898 | PVI HBDC-V-3451 | Cleaning (Scaff) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 104 | 114 |  | 2021-07-23 | 2024-05-06 | 2024-05-02 | 2023-12-31 | 2020-11-23 | 722 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | CON-PAIN | 2400054898 | PVI HBDC-V-3451 | Cleaning (Paint) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 78 | 31 |  | 2021-07-23 | 2024-05-06 | 2024-05-02 | 2023-12-31 | 2020-11-23 | 732 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | QAQCMECH | 2400054898 | PVI HBDC-V-3451 | Lagger ACT 0672 | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 0 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 742 | REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBDHPSEP | WPM | QAQCMECH | QAQCMECH | 2400054898 | PVI HBDC-V-3451 | Lagger materialer HBDC-V-3451 | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT DFEX AWDO AWSC RDBL RFRZ* | 0 | 0 |  | 2021-07-23 | 2024-05-06 | 2024-03-15 | 2023-12-31 | 2020-11-23 | 752 | REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Check Permit & Line Walk (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 5 | 0 | PRE | 2024-07-01 | 2024-08-19 | 2024-07-01 | 2026-12-31 | 2020-11-29 | 8 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | QAQCMECH | 2400054892 | PVI HBDB-V-4151 | Matt bestilling 26/8-20 SMEDE | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 0 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-01 | 2026-12-31 | 2020-11-29 | 12 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-SCAF | 2400054892 | PVI HBDB-V-4151 | Check Permit & Line Walk (Scaff) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 5 | 0 | PRE | 2024-07-01 | 2024-08-19 | 2024-07-01 | 2026-12-31 | 2020-11-29 | 40 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-LAGG | 2400054892 | PVI HBDB-V-4151 | Prepare Permit (Lagger) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 13 | 10.5 | PRE | 2024-07-01 | 2024-08-19 | 2024-07-01 | 2026-12-31 | 2020-11-29 | 50 | PCNF REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-ELEC | 2400054892 | PVI HBDB-V-4151 | Check Permit & Line Walk (El) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 5 | 0 | PRE | 2024-07-01 | 2024-08-19 | 2024-07-01 | 2026-12-31 | 2020-11-29 | 70 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-SCAF | 2400054892 | PVI HBDB-V-4151 | Install Scaffolding | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 78 | 0 | PRE | 2024-07-01 | 2024-08-19 | 2024-07-01 | 2026-12-31 | 2020-11-29 | 80 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-SCAF | 2400054892 | PVI HBDB-V-4151 | Check Liftning Proc & Line Walk (Scaff) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 4 | 0 | PRE | 2024-07-01 | 2024-08-19 | 2024-07-01 | 2026-12-31 | 2020-11-29 | 82 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-SCAF | 2400054892 | PVI HBDB-V-4151 | Install liftning equipment | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 26 | 1 | PRE | 2024-07-01 | 2024-08-19 | 2024-07-06 | 2026-12-31 | 2020-11-29 | 90 | PCNF REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Preparing of PVI (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 26 | 0 | PRE | 2024-07-01 | 2024-08-19 | 2024-07-01 | 2026-12-31 | 2020-11-29 | 100 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Layout of tools (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 10 | 6.5 | PRE | 2024-07-01 | 2024-08-19 | 2024-07-03 | 2026-12-31 | 2020-11-29 | 110 | PCNF REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Check materials (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 18 | 0 | PRE | 2024-07-01 | 2024-08-19 | 2024-07-03 | 2026-12-31 | 2020-11-29 | 120 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-LAGG | 2400054892 | PVI HBDB-V-4151 | Remove insulation (Lagger) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 26 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-07 | 2026-12-31 | 2020-11-29 | 130 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-ELEC | 2400054892 | PVI HBDB-V-4151 | Remove Heat Tracing (El) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 16 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-10 | 2026-12-31 | 2020-11-29 | 140 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Install nozzel numbers (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 5 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-06 | 2026-12-31 | 2020-11-29 | 142 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | PRODTECH | 2400054892 | PVI HBDB-V-4151 | Safing (Prod) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 12 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-11 | 2026-12-31 | 2020-11-29 | 150 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Install blind Flg and spades (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 52 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-14 | 2026-12-31 | 2020-11-29 | 160 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | QAQCMECH | 2400054892 | PVI HBDB-V-4151 | Flanger og pakninger | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 0 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-01 | 2026-12-31 | 2020-11-29 | 161 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-SCAF | 2400054892 | PVI HBDB-V-4151 | Scaff ass blind and spades (Scaff) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 52 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-14 | 2026-12-31 | 2020-11-29 | 170 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Inspektion of Flg and lumen (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 5 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-20 | 2026-12-31 | 2020-11-29 | 180 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | QAQCMECH | 2400054892 | PVI HBDB-V-4151 | Demol instrument (El) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 15 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-17 | 2026-12-31 | 2020-11-29 | 182 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Open vessel mannhold (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 20 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-19 | 2026-12-31 | 2020-11-29 | 200 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-ELEC | 2400054892 | PVI HBDB-V-4151 | Install light (EL) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 6 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-20 | 2026-12-31 | 2020-11-29 | 210 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-PAIN | 2400054892 | PVI HBDB-V-4151 | Lugemand (Paint) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 100 | 2 |  | 2024-07-01 | 2024-08-19 | 2024-07-22 | 2026-12-31 | 2020-11-29 | 230 | PCNF REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-ELEC | 2400054892 | PVI HBDB-V-4151 | Cleaning of removede Seal (El/inst) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 26 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-21 | 2026-12-31 | 2020-11-29 | 240 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-PAIN | 2400054892 | PVI HBDB-V-4151 | Cleaning of Levelglas (Paint) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 10 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-21 | 2026-12-31 | 2020-11-29 | 250 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Epuipment removed indside (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 20 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-22 | 2026-12-31 | 2020-11-29 | 260 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-SCAF | 2400054892 | PVI HBDB-V-4151 | Epuipment removed indside (Scaff | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 20 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-22 | 2026-12-31 | 2020-11-29 | 270 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-PAIN | 2400054892 | PVI HBDB-V-4151 | Cleaning of indside equipment (Paint) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 104 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-23 | 2026-12-31 | 2020-11-29 | 280 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-PAIN | 2400054892 | PVI HBDB-V-4151 | Cleaning of equipment (Paint) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 16 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-29 | 2026-12-31 | 2020-11-29 | 282 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | QAQCMECH | 2400054892 | PVI HBDB-V-4151 | Inspektion of equipment/nozzler (Qc) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 8 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-07-30 | 2026-12-31 | 2020-11-29 | 290 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | PRODTECH | 2400054892 | PVI HBDB-V-4151 | Prod inspektion before closed (Prod) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 3 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-08-01 | 2026-12-31 | 2020-11-29 | 300 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Re-install inside epuipmant (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 20 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-08-01 | 2026-12-31 | 2020-11-29 | 310 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-SCAF | 2400054892 | PVI HBDB-V-4151 | Re-install inside epuipmant (Scaff) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 20 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-08-01 | 2026-12-31 | 2020-11-29 | 320 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-ELEC | 2400054892 | PVI HBDB-V-4151 | Demol light (El) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 4 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-08-02 | 2026-12-31 | 2020-11-29 | 330 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Closed epuipmant (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 26 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-08-03 | 2026-12-31 | 2020-11-29 | 340 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-SCAF | 2400054892 | PVI HBDB-V-4151 | Closed epuipmant (Scaff) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 10 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-08-03 | 2026-12-31 | 2020-11-29 | 350 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Demol Flg and Spads (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 52 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-08-04 | 2026-12-31 | 2020-11-29 | 360 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-SCAF | 2400054892 | PVI HBDB-V-4151 | Demol Flg and Spads (Scaff) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 52 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-08-04 | 2026-12-31 | 2020-11-29 | 370 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | PRODTECH | 2400054892 | PVI HBDB-V-4151 | Prod inspektion befor closed (Prod) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 1 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-08-03 | 2026-12-31 | 2020-11-29 | 372 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-ELEC | 2400054892 | PVI HBDB-V-4151 | Re-install Heat Tracing (El) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 14 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-08-07 | 2026-12-31 | 2020-11-29 | 380 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-ELEC | 2400054892 | PVI HBDB-V-4151 | Re-install instruments (EL/inst) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 10 | 0 |  | 2024-07-01 | 2024-08-19 | 2024-08-09 | 2026-12-31 | 2020-11-29 | 390 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | PRODTECH | 2400054892 | PVI HBDB-V-4151 | Safeing and leaktest | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 4 | 0 | POST | 2024-07-01 | 2024-08-19 | 2024-08-10 | 2026-12-31 | 2020-11-29 | 400 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-LAGG | 2400054892 | PVI HBDB-V-4151 | Re-install Insulations (Lagger) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 26 | 0 | POST | 2024-07-01 | 2024-08-19 | 2024-08-11 | 2026-12-31 | 2020-11-29 | 410 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-SCAF | 2400054892 | PVI HBDB-V-4151 | Demol liftning equipment (Scaff) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 12 | 0 | POST | 2024-07-01 | 2024-08-19 | 2024-08-14 | 2026-12-31 | 2020-11-29 | 420 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-SCAF | 2400054892 | PVI HBDB-V-4151 | Demol scaffolding (Scaff) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 39 | 0 | POST | 2024-07-01 | 2024-08-19 | 2024-08-15 | 2026-12-31 | 2020-11-29 | 430 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-WELD | 2400054892 | PVI HBDB-V-4151 | Cleaning (Weld) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 10 | 0 | POST | 2024-07-01 | 2024-08-19 | 2024-08-17 | 2026-12-31 | 2020-11-29 | 440 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-SCAF | 2400054892 | PVI HBDB-V-4151 | Cleaning (Scaff) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 10 | 0 | POST | 2024-07-01 | 2024-08-19 | 2024-08-17 | 2026-12-31 | 2020-11-29 | 450 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-PAIN | 2400054892 | PVI HBDB-V-4151 | Cleaning (Paint) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 10 | 0 | POST | 2024-07-01 | 2024-08-19 | 2024-08-17 | 2026-12-31 | 2020-11-29 | 460 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
2026-W13-14 | B | HBD-IPHP | WPM | QAQCMECH | CON-LAGG | 2400054892 | PVI HBDB-V-4151 | Cleaning (Lagger) | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR SECE PMAT DFAP AWDO AWSC RDBL RFRZ* | 10 | 0 | POST | 2024-07-01 | 2024-08-19 | 2024-08-17 | 2026-12-31 | 2020-11-29 | 470 | REL | APPR OPND | HB /D /32/HBDB-V-4151 | IP FLASH DRUM | 99000119 | D |  | INP | DK50
0 | 3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100097423 | Weight cell defect. HDBM-WAL-03221. | Install rigging equipment | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO SCH RFRZ ROUT RREQ | 3 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-02-24 | 2023-10-12 | 10 | PCNF REL | APPR OPND | HD /B /01/HDBM-WAL-03221 | WEIGHT CELL |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-TELE | 2100097423 | Weight cell defect. HDBM-WAL-03221. | Inhibit load cell | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO SCH RFRZ ROUT RREQ | 0.5 | 1 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-02-24 | 2023-10-12 | 15 | PCNF REL | APPR OPND | HD /B /01/HDBM-WAL-03221 | WEIGHT CELL |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100097423 | Weight cell defect. HDBM-WAL-03221. | Isolate load cell | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO SCH RFRZ ROUT RREQ | 0.5 | 12 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-02-24 | 2023-10-12 | 20 | PCNF REL | APPR OPND | HD /B /01/HDBM-WAL-03221 | WEIGHT CELL |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100097423 | Weight cell defect. HDBM-WAL-03221. | Rigg out/in cillinders | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO SCH RFRZ ROUT RREQ | 2.5 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-02-24 | 2023-10-12 | 30 | PCNF REL | APPR OPND | HD /B /01/HDBM-WAL-03221 | WEIGHT CELL |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100097423 | Weight cell defect. HDBM-WAL-03221. | Install load cell | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO SCH RFRZ ROUT RREQ | 2.5 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-02-24 | 2023-10-12 | 40 | PCNF REL | APPR OPND | HD /B /01/HDBM-WAL-03221 | WEIGHT CELL |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100097423 | Weight cell defect. HDBM-WAL-03221. | De-isolate load cell/Test with CCR | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO SCH RFRZ ROUT RREQ | 1 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-02-24 | 2023-10-12 | 50 | PCNF REL | APPR OPND | HD /B /01/HDBM-WAL-03221 | WEIGHT CELL |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100097423 | Weight cell defect. HDBM-WAL-03221. | Remove rigging equipment | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO SCH RFRZ ROUT RREQ | 1 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-02-24 | 2023-10-12 | 60 | PCNF REL | APPR OPND | HD /B /01/HDBM-WAL-03221 | WEIGHT CELL |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-TELE | 2100097423 | Weight cell defect. HDBM-WAL-03221. | Remove inhibit/reset alarm | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO SCH RFRZ ROUT RREQ | 0.5 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-02-24 | 2023-10-12 | 70 | PCNF REL | APPR OPND | HD /B /01/HDBM-WAL-03221 | WEIGHT CELL |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100097423 | Weight cell defect. HDBM-WAL-03221. | Load cell | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO SCH RFRZ ROUT RREQ | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-02-24 | 2023-10-12 | 80 | PCNF REL | APPR OPND | HD /B /01/HDBM-WAL-03221 | WEIGHT CELL |  | C |  | MIN | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100097423 | Weight cell defect. HDBM-WAL-03221. | New type load cell | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO SCH RFRZ ROUT RREQ | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-02-24 | 2023-10-12 | 90 | REL | APPR OPND | HD /B /01/HDBM-WAL-03221 | WEIGHT CELL |  | C |  | MIN | DK60
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100085882 | HB faulty switch PSL-03064 | Inhibit F&G system | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2023-08-20 | 2023-04-07 | 10 | PCNF REL | APPR OPND | HB /C /01/HBCM-PSL-03064 | PRESSURE SWITCH LOW |  | C |  | MIN | DK50 |  |  | 2024-05-22
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-INST | 2100085882 | HB faulty switch PSL-03064 | Isolate Pressure switch | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2023-08-20 | 2023-04-07 | 20 | PCNF REL | APPR OPND | HB /C /01/HBCM-PSL-03064 | PRESSURE SWITCH LOW |  | C |  | MIN | DK50 |  |  | 2024-05-23
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-INST | 2100085882 | HB faulty switch PSL-03064 | Deisolate pressure switch | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2023-08-20 | 2023-04-07 | 40 | PCNF REL | APPR OPND | HB /C /01/HBCM-PSL-03064 | PRESSURE SWITCH LOW |  | C |  | MIN | DK50 |  |  | 2024-05-24
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100085882 | HB faulty switch PSL-03064 | Remove inhibit from F&G system/reset ala | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2023-08-20 | 2023-04-07 | 50 | PCNF REL | APPR OPND | HB /C /01/HBCM-PSL-03064 | PRESSURE SWITCH LOW |  | C |  | MIN | DK50 |  |  | 2024-05-25
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100085882 | HB faulty switch PSL-03064 | ************************************* | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2023-08-20 | 2023-04-07 | 60 | REL | APPR OPND | HB /C /01/HBCM-PSL-03064 | PRESSURE SWITCH LOW |  | C |  | MIN | DK50 |  |  | 2024-05-26
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100085882 | HB faulty switch PSL-03064 | Inhibit F&G system/remove inhibbit | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2023-08-20 | 2023-04-07 | 70 | REL | APPR OPND | HB /C /01/HBCM-PSL-03064 | PRESSURE SWITCH LOW |  | C |  | MIN | DK50 |  |  | 2024-05-27
2024-W21-22 | 3 | NOSD | WDF | MTN-TELE | MTN-INST | 2100085882 | HB faulty switch PSL-03064 | Install new diaphragrm seal | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2023-08-20 | 2023-04-07 | 80 | REL | APPR OPND | HB /C /01/HBCM-PSL-03064 | PRESSURE SWITCH LOW |  | C |  | MIN | DK50 |  |  | 2024-05-28
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400321319 | 1Y FIRE MEN LOCKERS INSPECTION HDA/B | 1Y FIRE MEN LOCKERS INSPECTION HDA/B | REL GMPS MACM PRC SETC | APPR SECE PMAT AWDO RDBL RFRZ ROUT | 16 | 0 |  | 2024-04-09 | 2024-04-12 | 2024-04-09 | 2024-05-09 | 2024-04-09 | 10 | REL | APPR OPND | HD /A /02/FIRE-MEN-EQUIPMENT | FIRE MENS EQUIPMENT |  | A | DKHD-0021 | MMS | DK60 | MS0033
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400322690 | 1Y ANTI-FOULING PKG TEST HBDB-A-5369 | ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR SECE PMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2024-05-19 | 2024-04-19 | 10 | REL | APPR OPND | HB /D /52/HBDB-A-5369 | ANTI-FOULING PACKAGE |  | C | DKHB-0095 | MMS | DK50 | MS0134
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400322690 | 1Y ANTI-FOULING PKG TEST HBDB-A-5369 | ANTI-FOULING PKG TEST HBDB-A-5369 | REL GMPS MACM PRC SETC | APPR SECE PMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2024-05-19 | 2024-04-19 | 20 | REL | APPR OPND | HB /D /52/HBDB-A-5369 | ANTI-FOULING PACKAGE |  | C | DKHB-0095 | MMS | DK50 | MS0134
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400322690 | 1Y ANTI-FOULING PKG TEST HBDB-A-5369 | DE-ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR SECE PMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-04-19 | 2024-04-20 | 2024-04-20 | 2024-05-19 | 2024-04-19 | 30 | REL | APPR OPND | HB /D /52/HBDB-A-5369 | ANTI-FOULING PACKAGE |  | C | DKHB-0095 | MMS | DK50 | MS0134
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400330051 | 1Y MOB BOAT INSPECTION HBDE-X-0703 | MOB BOAT INSPECTION HBDE-X-0703 | REL GMPS MANC PRC SETC | APPR SECE PMAT AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2024-04-10 | 2024-04-11 | 2024-04-10 | 2024-06-28 | 2024-05-29 | 10 | REL | APPR OPND | HB /D /02/HBDE-X-0703 | MOB BOAT |  | A | DKHB-0041 | MMS | DK50 | MS0044 | PROK | 2024-05-20
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100031724 | DGS:635356 ESDV-34026 replacement | Close valve and isolate hydraulics | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 10 | PCNF REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | Remove top cover and lubricate | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 0 | 24 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 20 | PCNF REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | mount cover | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 30 | PCNF REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100031724 | DGS:635356 ESDV-34026 replacement | de-isolate valve. | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 40 | PCNF REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100031724 | DGS:635356 ESDV-34026 replacement | Close valve and isolate hydraulics | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 50 | PCNF REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | route return hydraulic to drum | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 60 | PCNF REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | Troubbelshuting of valve/actuator | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 2 | 0 | W 37 Thom | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 70 | PCNF REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100031724 | DGS:635356 ESDV-34026 replacement | de-isolate valve. | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 80 | PCNF REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100031724 | DGS:635356 ESDV-34026 replacement | Assist with taking actuator off/on | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 90 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | prep tools and equipment - Mech | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 120 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | prep tools and equipment - Rigg | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 130 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | Build scaff - Scaf | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 140 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | Isolate valve - Prod | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 150 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | Dismount Hydra. panel & EL - Inst | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 155 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | Replace valve - Mech | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 10 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 160 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | Replace valve - Rigg | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 10 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 170 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | Mount Hydra. panal & EL - Inst | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 180 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | De-isolate, leak test etc - Prod | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 190 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | Rig down equipment - Rigg | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 200 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | Remove scaf - Scaf | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 210 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | house keeping - Rigg | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 220 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | house keeping - Scaf | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 230 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | house keeping - Mech | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 240 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | add of mat. | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 250 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100031724 | DGS:635356 ESDV-34026 replacement | add of all mat. again | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-05-05 | 2020-04-30 | 260 | REL | APPR OPND | HB /A /10/HBAA-ESDV-34026 | EMERGENCY SHUTDOWN VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400235384 | 4Y EMERGENCY GENERATOR INSPECTION | SCAFFOLDING CONSTRUCT | REL PRT GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 12.5 | 0 | W15-W16 | 2024-04-08 | 2024-04-18 | 2024-04-08 | 2023-03-16 | 2023-01-02 | 10 | REL | APPR OPND | HB /D /05/HBDE-A-1710 | GENERATOR PACKAGE |  | D | DKHB-0494 | MMR | DK50 | MR0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400235384 | 4Y EMERGENCY GENERATOR INSPECTION | ISOLATION BY PRODUCTION | REL PRT GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-18 | 2024-04-10 | 2023-03-16 | 2023-01-02 | 20 | REL | APPR OPND | HB /D /05/HBDE-A-1710 | GENERATOR PACKAGE |  | D | DKHB-0494 | MMR | DK50 | MR0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235384 | 4Y EMERGENCY GENERATOR INSPECTION | EMERGENCY GENERATOR INSPECTION | REL PRT GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 8 | 0 | W15-W16 | 2024-04-08 | 2024-04-18 | 2024-04-11 | 2023-03-16 | 2023-01-02 | 30 | REL | APPR OPND | HB /D /05/HBDE-A-1710 | GENERATOR PACKAGE |  | D | DKHB-0494 | MMR | DK50 | MR0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400235384 | 4Y EMERGENCY GENERATOR INSPECTION | EMERGENCY GENERATOR INSPECTION | REL PRT GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 10 | 0 | W15-W16 | 2024-04-08 | 2024-04-18 | 2024-04-12 | 2023-03-16 | 2023-01-02 | 40 | REL | APPR OPND | HB /D /05/HBDE-A-1710 | GENERATOR PACKAGE |  | D | DKHB-0494 | MMR | DK50 | MR0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400235384 | 4Y EMERGENCY GENERATOR INSPECTION | DE-ISOLATION BY PRODUCTION | REL PRT GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-18 | 2024-04-15 | 2023-03-16 | 2023-01-02 | 60 | REL | APPR OPND | HB /D /05/HBDE-A-1710 | GENERATOR PACKAGE |  | D | DKHB-0494 | MMR | DK50 | MR0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400235384 | 4Y EMERGENCY GENERATOR INSPECTION | SCAFFOLDING DE-CONSTRUCT | REL PRT GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 12.5 | 0 | W15-W16 | 2024-04-08 | 2024-04-18 | 2024-04-15 | 2023-03-16 | 2023-01-02 | 70 | REL | APPR OPND | HB /D /05/HBDE-A-1710 | GENERATOR PACKAGE |  | D | DKHB-0494 | MMR | DK50 | MR0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263386 | 1Y DELUGE SKID TEST/MAINT - HBDB-A-0380 | ISOLATION BY PRODUCTION | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 10 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | C | DKHB-0089 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263386 | 1Y DELUGE SKID TEST/MAINT - HBDB-A-0380 | DELUGE SKID TEST/MAINT - HBDB-A-0380 | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 10 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 20 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | C | DKHB-0089 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263386 | 1Y DELUGE SKID TEST/MAINT - HBDB-A-0380 | DELUGE SKID TEST/MAINT - HBDB-A-0380 | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 9 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 30 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | C | DKHB-0089 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400263386 | 1Y DELUGE SKID TEST/MAINT - HBDB-A-0380 | DELUGE SKID VENDOR ASSIST - HBDA-A-0380 | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 10 | 27 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 35 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | C | DKHB-0089 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263386 | 1Y DELUGE SKID TEST/MAINT - HBDB-A-0380 | DE-ISOLATION BY PRODUCTION | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 40 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | C | DKHB-0089 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263386 | 1Y DELUGE SKID TEST/MAINT - HBDB-A-0380 | Add. materials | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 50 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | C | DKHB-0089 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284415 | PSV Calibration - HBDC-PSV-345106 | Re-certify PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-12-22 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 60 | PCNF REL | APPR OPND | HB /D /23/HBDC-PSV-345106 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV095 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284415 | PSV Calibration - HBDC-PSV-345106 | Rigging Assist (Install) | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-19 | 2024-12-22 | 2024-12-19 | 2024-12-31 | 2024-10-19 | 70 | PCNF REL | APPR OPND | HB /D /23/HBDC-PSV-345106 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV095 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284415 | PSV Calibration - HBDC-PSV-345106 | Prod Assist (breaking containment) | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-12-22 | 2024-12-21 | 2024-12-31 | 2024-10-19 | 80 | PCNF REL | APPR OPND | HB /D /23/HBDC-PSV-345106 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV095 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284415 | PSV Calibration - HBDC-PSV-345106 | Install re-certified PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-19 | 2024-12-22 | 2024-12-21 | 2024-12-31 | 2024-10-19 | 90 | PCNF REL | APPR OPND | HB /D /23/HBDC-PSV-345106 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV095 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284415 | PSV Calibration - HBDC-PSV-345106 | De-isolation and leak test | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-12-22 | 2024-12-21 | 2024-12-31 | 2024-10-19 | 100 | PCNF REL | APPR OPND | HB /D /23/HBDC-PSV-345106 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV095 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284415 | PSV Calibration - HBDC-PSV-345106 | Documentation & CNF WO | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-12-22 | 2024-12-21 | 2024-12-31 | 2024-10-19 | 110 | PCNF REL | APPR OPND | HB /D /23/HBDC-PSV-345106 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV095 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284415 | PSV Calibration - HBDC-PSV-345106 | Check PSV flanges & alignment | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W09-W10 | 2024-10-19 | 2024-12-22 | 2024-12-21 | 2024-12-31 | 2024-10-19 | 120 | PCNF REL | APPR OPND | HB /D /23/HBDC-PSV-345106 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV095 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284415 | PSV Calibration - HBDC-PSV-345106 | Scaffolding | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 10 | 0 | W09-W10 | 2024-10-19 | 2024-12-22 | 2024-12-21 | 2024-12-31 | 2024-10-19 | 130 | PCNF REL | APPR OPND | HB /D /23/HBDC-PSV-345106 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV095 | MMS | DK50
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284416 | PSV Calibration - HBDC-PSV-365105 | Re-certify PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-01-06 | 2024-03-14 | 2024-03-14 | 2024-12-31 | 2024-10-19 | 60 | PCNF REL | APPR OPND | HB /D /23/HBDC-PSV-365105 | PRESSURE SAFETY RELIEF VALVE |  | F | DKHB-PSV099 | MMS | DK50 |  |  | 2024-05-21
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284418 | PSV Calibration - HBDB-PSV-415203 | Re-certify PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-30 | 2025-01-02 | 2024-11-01 | 2024-12-31 | 2024-10-30 | 60 | PCNF REL | APPR OPND | HB /D /30/HBDB-PSV-415203 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV120 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284418 | PSV Calibration - HBDB-PSV-415203 | Rigging Assist (Install) | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-30 | 2025-01-02 | 2024-12-31 | 2024-12-31 | 2024-10-30 | 70 | PCNF REL | APPR OPND | HB /D /30/HBDB-PSV-415203 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV120 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284418 | PSV Calibration - HBDB-PSV-415203 | Prod Assist (breaking containment) | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2025-01-02 | 2024-12-31 | 2024-12-31 | 2024-10-30 | 80 | PCNF REL | APPR OPND | HB /D /30/HBDB-PSV-415203 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV120 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284418 | PSV Calibration - HBDB-PSV-415203 | Install re-certified PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-30 | 2025-01-02 | 2024-12-31 | 2024-12-31 | 2024-10-30 | 90 | PCNF REL | APPR OPND | HB /D /30/HBDB-PSV-415203 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV120 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284418 | PSV Calibration - HBDB-PSV-415203 | De-isolation and leak test | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-30 | 2025-01-02 | 2025-01-01 | 2024-12-31 | 2024-10-30 | 100 | PCNF REL | APPR OPND | HB /D /30/HBDB-PSV-415203 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV120 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284418 | PSV Calibration - HBDB-PSV-415203 | Documentation & CNF WO | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2025-01-02 | 2025-01-01 | 2024-12-31 | 2024-10-30 | 110 | PCNF REL | APPR OPND | HB /D /30/HBDB-PSV-415203 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV120 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284418 | PSV Calibration - HBDB-PSV-415203 | Check PSV flanges & alignment | REL PCNF CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W09-W10 | 2024-10-30 | 2025-01-02 | 2025-01-01 | 2024-12-31 | 2024-10-30 | 120 | PCNF REL | APPR OPND | HB /D /30/HBDB-PSV-415203 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV120 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284419 | PSV Exchange - HBDB-PSV-416101 | Isolation of PSV | REL CSER GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 10 | REL | APPR OPND | HB /D /30/HBDB-PSV-416101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV122 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284419 | PSV Exchange - HBDB-PSV-416101 | Prod Assist (breaking containment) | REL CSER GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 20 | REL | APPR OPND | HB /D /30/HBDB-PSV-416101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV122 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284419 | PSV Exchange - HBDB-PSV-416101 | Rigging assist (remove) | REL CSER GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 30 | REL | APPR OPND | HB /D /30/HBDB-PSV-416101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV122 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284419 | PSV Exchange - HBDB-PSV-416101 | Remove PSV | REL CSER GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-30 | 2024-11-08 | 2024-11-02 | 2024-12-31 | 2024-10-30 | 40 | REL | APPR OPND | HB /D /30/HBDB-PSV-416101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV122 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284419 | PSV Exchange - HBDB-PSV-416101 | Install blinds | REL CSER GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2024-11-08 | 2024-11-03 | 2024-12-31 | 2024-10-30 | 50 | REL | APPR OPND | HB /D /30/HBDB-PSV-416101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV122 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284419 | PSV Exchange - HBDB-PSV-416101 | Re-certify PSV | REL CSER GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-30 | 2024-11-08 | 2024-11-03 | 2024-12-31 | 2024-10-30 | 60 | REL | APPR OPND | HB /D /30/HBDB-PSV-416101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV122 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284419 | PSV Exchange - HBDB-PSV-416101 | Rigging Assist (Install) | REL CSER GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-30 | 2024-11-08 | 2024-11-04 | 2024-12-31 | 2024-10-30 | 70 | REL | APPR OPND | HB /D /30/HBDB-PSV-416101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV122 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284419 | PSV Exchange - HBDB-PSV-416101 | Prod Assist (breaking containment) | REL CSER GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2024-11-08 | 2024-11-05 | 2024-12-31 | 2024-10-30 | 80 | REL | APPR OPND | HB /D /30/HBDB-PSV-416101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV122 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284419 | PSV Exchange - HBDB-PSV-416101 | Install re-certified PSV | REL CSER GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-30 | 2024-11-08 | 2024-11-06 | 2024-12-31 | 2024-10-30 | 90 | REL | APPR OPND | HB /D /30/HBDB-PSV-416101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV122 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284419 | PSV Exchange - HBDB-PSV-416101 | De-isolation and leak test | REL CSER GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-30 | 2024-11-08 | 2024-11-07 | 2024-12-31 | 2024-10-30 | 100 | REL | APPR OPND | HB /D /30/HBDB-PSV-416101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV122 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284419 | PSV Exchange - HBDB-PSV-416101 | Documentation & CNF WO | REL CSER GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2024-11-08 | 2024-11-07 | 2024-12-31 | 2024-10-30 | 110 | REL | APPR OPND | HB /D /30/HBDB-PSV-416101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV122 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284419 | PSV Exchange - HBDB-PSV-416101 | Check PSV flanges & alignment | REL CSER GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2024-11-08 | 2024-11-08 | 2024-12-31 | 2024-10-30 | 120 | REL | APPR OPND | HB /D /30/HBDB-PSV-416101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV122 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284431 | PSV Calibration - HBDC-PSV-435102 | Re-certify PSV | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-20 | 2024-12-31 | 2024-10-19 | 60 | PCNF REL | APPR OPND | HB /D /32/HBDC-PSV-435102 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV152 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284431 | PSV Calibration - HBDC-PSV-435102 | Rigging Assist (Install) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-19 | 2024-12-31 | 2024-10-19 | 70 | PCNF REL | APPR OPND | HB /D /32/HBDC-PSV-435102 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV152 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284431 | PSV Calibration - HBDC-PSV-435102 | Prod Assist (breaking containment) | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-21 | 2024-12-31 | 2024-10-19 | 80 | PCNF REL | APPR OPND | HB /D /32/HBDC-PSV-435102 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV152 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284431 | PSV Calibration - HBDC-PSV-435102 | Install re-certified PSV | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-21 | 2024-12-31 | 2024-10-19 | 90 | PCNF REL | APPR OPND | HB /D /32/HBDC-PSV-435102 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV152 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284431 | PSV Calibration - HBDC-PSV-435102 | De-isolation and leak test | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-20 | 2024-12-31 | 2024-10-19 | 100 | PCNF REL | APPR OPND | HB /D /32/HBDC-PSV-435102 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV152 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284431 | PSV Calibration - HBDC-PSV-435102 | Documentation & CNF WO | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-20 | 2024-12-31 | 2024-10-19 | 110 | PCNF REL | APPR OPND | HB /D /32/HBDC-PSV-435102 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV152 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284431 | PSV Calibration - HBDC-PSV-435102 | Check PSV flanges & alignment | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W09-W10 | 2024-10-19 | 2024-12-21 | 2024-12-20 | 2024-12-31 | 2024-10-19 | 120 | PCNF REL | APPR OPND | HB /D /32/HBDC-PSV-435102 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV152 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284445 | PSV Exchange - HBDB-PSV-105003 | Isolation of PSV | REL CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /85/HBDB-PSV-105003 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV222 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284445 | PSV Exchange - HBDB-PSV-105003 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /85/HBDB-PSV-105003 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV222 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284445 | PSV Exchange - HBDB-PSV-105003 | Install re-certified PSV | REL CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /85/HBDB-PSV-105003 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV222 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284445 | PSV Exchange - HBDB-PSV-105003 | De-isolation and leak test | REL CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /85/HBDB-PSV-105003 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV222 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284445 | PSV Exchange - HBDB-PSV-105003 | Documentation & CNF WO | REL CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /85/HBDB-PSV-105003 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV222 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284445 | PSV Exchange - HBDB-PSV-105003 | Check PSV flanges & alignment | REL CSER GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /85/HBDB-PSV-105003 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV222 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400307662 | 2Y EMERGENCY GEN. INSPECT-HBCM-A-1731 | ISOLATION BY PRODUCTION | REL PRT GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 | W17-W18 | 2024-04-26 | 2024-05-02 | 2024-04-26 | 2024-02-28 | 2024-01-13 | 10 | REL | APPR OPND | HB /C /05/HBCM-A-1731 | EMERGENCY GENERATOR |  | D | DKHB-0490 | MMR | DK50 | MR0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400307662 | 2Y EMERGENCY GEN. INSPECT-HBCM-A-1731 | EMERGENCY GEN. INSPECT-HBCM-A-1731 | REL PRT GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 15 | 0 | W17-W18 | 2024-04-26 | 2024-05-02 | 2024-04-27 | 2024-02-28 | 2024-01-13 | 20 | REL | APPR OPND | HB /C /05/HBCM-A-1731 | EMERGENCY GENERATOR |  | D | DKHB-0490 | MMR | DK50 | MR0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400307662 | 2Y EMERGENCY GEN. INSPECT-HBCM-A-1731 | EMERGENCY GEN. INSPECT-HBCM-A-1731 | REL PRT GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 | W17-W18 | 2024-04-26 | 2024-05-02 | 2024-04-30 | 2024-02-28 | 2024-01-13 | 30 | REL | APPR OPND | HB /C /05/HBCM-A-1731 | EMERGENCY GENERATOR |  | D | DKHB-0490 | MMR | DK50 | MR0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400307662 | 2Y EMERGENCY GEN. INSPECT-HBCM-A-1731 | EMERGENCY GEN. INSPECT-HBCM-A-1731 | REL PRT GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-05-02 | 2024-05-01 | 2024-02-28 | 2024-01-13 | 40 | REL | APPR OPND | HB /C /05/HBCM-A-1731 | EMERGENCY GENERATOR |  | D | DKHB-0490 | MMR | DK50 | MR0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400307662 | 2Y EMERGENCY GEN. INSPECT-HBCM-A-1731 | DE-ISOLATION BY PRODUCTION | REL PRT GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 | W17-W18 | 2024-04-26 | 2024-05-02 | 2024-05-01 | 2024-02-28 | 2024-01-13 | 50 | REL | APPR OPND | HB /C /05/HBCM-A-1731 | EMERGENCY GENERATOR |  | D | DKHB-0490 | MMR | DK50 | MR0014 | PROK
2024-W21-22 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309037 | 1Y 400V UPS & BATTERIES MAINT HBD | 400V UPS & BATTERIES MAINT HBD | REL GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 14 | 0 |  | 2024-09-18 | 2024-09-22 | 2024-09-18 | 2024-03-18 | 2024-02-17 | 10 | REL | APPR OPND | HB /D /06/UPS-SYSTEMS | UPS SYSTEMS |  | A | DKHB-0098 | MEL | DK50 | EL0034 | PROK | 2024-05-20
2024-W21-22 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309037 | 1Y 400V UPS & BATTERIES MAINT HBD | 400V UPS & BATTERIES MAINT HBD | REL GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 7 | 0 |  | 2024-09-18 | 2024-09-22 | 2024-09-21 | 2024-03-18 | 2024-02-17 | 20 | REL | APPR OPND | HB /D /06/UPS-SYSTEMS | UPS SYSTEMS |  | A | DKHB-0098 | MEL | DK50 | EL0034 | PROK | 2024-05-22
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400322689 | 1Y DIESEL TRANSFER MAINT-HBD | ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-05-13 | 2024-04-13 | 10 | REL | APPR OPND | HB /D /71/HBDC-P-5761 | DIESEL TRANSFER PUMP |  | C | DKHB-0083 | MMR | DK50 | MR0074
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400322689 | 1Y DIESEL TRANSFER MAINT-HBD | DIESEL TRANSFER MAINT-HBD | REL GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-05-13 | 2024-04-13 | 20 | REL | APPR OPND | HB /D /71/HBDC-P-5761 | DIESEL TRANSFER PUMP |  | C | DKHB-0083 | MMR | DK50 | MR0074
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400322689 | 1Y DIESEL TRANSFER MAINT-HBD | DIESEL TRANSFER MAINT-HBD | REL GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-05-13 | 2024-04-13 | 30 | REL | APPR OPND | HB /D /71/HBDC-P-5761 | DIESEL TRANSFER PUMP |  | C | DKHB-0083 | MMR | DK50 | MR0074
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400322689 | 1Y DIESEL TRANSFER MAINT-HBD | DIESEL TRANSFER MAINT-HBD | REL GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2024-05-13 | 2024-04-13 | 40 | REL | APPR OPND | HB /D /71/HBDC-P-5761 | DIESEL TRANSFER PUMP |  | C | DKHB-0083 | MMR | DK50 | MR0074
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400322689 | 1Y DIESEL TRANSFER MAINT-HBD | DE-ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-28 | 2024-05-13 | 2024-04-13 | 50 | REL | APPR OPND | HB /D /71/HBDC-P-5761 | DIESEL TRANSFER PUMP |  | C | DKHB-0083 | MMR | DK50 | MR0074
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325377 | 4Y INSTRUMENT AIR INSPECTION-HBC | INSTRUMENT AIR INSPECTION-HBC | REL GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 15 | 0 |  | 2024-03-13 | 2024-03-19 | 2024-03-13 | 2024-05-25 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /07/INSTRUMENT-AIR-SYSTEM | INSTRUMENT AIR SYSTEM |  | C | DKHB-0042 | MMR | DK50 | MR0034 |  | 2024-05-20
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325377 | 4Y INSTRUMENT AIR INSPECTION-HBC | INSTRUMENT AIR INSPECTION-HBC | REL GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 10 | 0 |  | 2024-03-13 | 2024-03-19 | 2024-03-16 | 2024-05-25 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /07/INSTRUMENT-AIR-SYSTEM | INSTRUMENT AIR SYSTEM |  | C | DKHB-0042 | MMR | DK50 | MR0034 |  | 2024-05-22
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400325377 | 4Y INSTRUMENT AIR INSPECTION-HBC | INSTRUMENT AIR INSPECTION-HBC | REL GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-03-13 | 2024-03-19 | 2024-03-18 | 2024-05-25 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /07/INSTRUMENT-AIR-SYSTEM | INSTRUMENT AIR SYSTEM |  | C | DKHB-0042 | MMR | DK50 | MR0034 |  | 2024-05-24
2024-W21-22 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400325377 | 4Y INSTRUMENT AIR INSPECTION-HBC | INSTRUMENT AIR INSPECTION-HBC | REL GMPS MACM PRC SETC | APPR SECE PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-13 | 2024-03-19 | 2024-03-18 | 2024-05-25 | 2024-03-13 | 40 | REL | APPR OPND | HB /C /07/INSTRUMENT-AIR-SYSTEM | INSTRUMENT AIR SYSTEM |  | C | DKHB-0042 | MMR | DK50 | MR0034 |  | 2024-05-25
2024-W33-34 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200011881 | Inlet cyclone for HBDC-V-3451 MN 1306664 | Inlet cyclone for HBDC-V-3451MN 1306664 | REL GMPS MANC PRC SETC | APPR SECE CMAT RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-03-12 | 2022-10-28 | 10 | REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | A |  | MMS | DK50 |  |  | 2024-05-27
0 | A | HDAFLARE | WPM | MTN-MECH | PRODTECH | 2400126411 | 4Y FLAME ARRESTORS HALFDAN | Safeing plan and safeing of system | REL PRT GMPS MANC PRC SETC | APPR SECE CMAT AWSD AWDO AWSC RDBL RFRZ* | 3 | 0 | Align W 2200006154 | 2024-03-28 | 2024-04-03 | 2024-03-28 | 2021-07-19 | 2021-05-07 | 9 | REL | APPR OPND | HD /C /36/HDCA-FA-4003 | FLAME ARRESTOR | 99000120 | G | DK600021121 | MMS | DK60
0 | A | HDAFLARE | WPM | MTN-MECH | VEN-MECH | 2400126411 | 4Y FLAME ARRESTORS HALFDAN | FLAME ARRESTORS | REL PRT GMPS MANC PRC SETC | APPR SECE CMAT AWSD AWDO AWSC RDBL RFRZ* | 6 | 0 |  | 2024-03-28 | 2024-04-03 | 2024-03-28 | 2021-07-19 | 2021-05-07 | 10 | REL | APPR OPND | HD /C /36/HDCA-FA-4003 | FLAME ARRESTOR | 99000120 | G | DK600021121 | MMS | DK60
0 | A | HDAFLARE | WPM | MTN-MECH | MTN-SCAF | 2400126411 | 4Y FLAME ARRESTORS HALFDAN | FLAME ARRESTORS | REL PRT GMPS MANC PRC SETC | APPR SECE CMAT AWSD AWDO AWSC RDBL RFRZ* | 50 | 0 |  | 2024-03-28 | 2024-04-03 | 2024-03-29 | 2021-07-19 | 2021-05-07 | 20 | REL | APPR OPND | HD /C /36/HDCA-FA-4003 | FLAME ARRESTOR | 99000120 | G | DK600021121 | MMS | DK60
0 | A | HDAFLARE | WPM | MTN-MECH | PRODTECH | 2400126411 | 4Y FLAME ARRESTORS HALFDAN | De-safe & leak check | REL PRT GMPS MANC PRC SETC | APPR SECE CMAT AWSD AWDO AWSC RDBL RFRZ* | 2 | 0 |  | 2024-03-28 | 2024-04-03 | 2024-04-03 | 2021-07-19 | 2021-05-07 | 30 | REL | APPR OPND | HD /C /36/HDCA-FA-4003 | FLAME ARRESTOR | 99000120 | G | DK600021121 | MMS | DK60
2026-W1-2 | A | NOSD | WPM | MTN-ROUS | MTN-ELEC | 2400322687 | 3Y EVACUATION SUIT RECERT - HBD | PERSONAL ISOLATION | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO SCH RDBL RFRZ ROUT | 0.5 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-05-18 | 2024-03-17 | 20 | PCNF REL | APPR OPND | HB /D /02/EVACUATION-SUITS | EVACUATION SUITS |  | A | DKHB-0033 | MMS | DK50 | MS0044
2026-W1-2 | A | NOSD | WPM | MTN-ROUS | MTN-ELEC | 2400322687 | 3Y EVACUATION SUIT RECERT - HBD | EVACUATION SUIT HEAT CHECK - HBD | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-05-18 | 2024-03-17 | 30 | PCNF REL | APPR OPND | HB /D /02/EVACUATION-SUITS | EVACUATION SUITS |  | A | DKHB-0033 | MMS | DK50 | MS0044
2026-W1-2 | A | NOSD | WPM | MTN-ROUS | MTN-ELEC | 2400322687 | 3Y EVACUATION SUIT RECERT - HBD | PERSONAL DE-ISOLATION | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO SCH RDBL RFRZ ROUT | 0.5 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-09 | 2024-05-18 | 2024-03-17 | 40 | PCNF REL | APPR OPND | HB /D /02/EVACUATION-SUITS | EVACUATION SUITS |  | A | DKHB-0033 | MMS | DK50 | MS0044
2024-W19-20 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400308604 | 1Y LIFE-SAVING & SAFETY EQ. RECERT-HBC | LIFE-SAVING & SAFETY EQ. RECERT-HBC | REL GMPS MACM PRC SETC | APPR SECE CMAT AWDO RDBL RFRZ ROUT | 20 | 0 | W19-W20 | 2024-05-02 | 2024-05-04 | 2024-05-02 | 2024-03-12 | 2024-02-11 | 10 | REL | APPR OPND | HB /C /02/LIFE-SAVING-EQUIPMENT | LIFE SAVING EQUIPMENT |  | A | DKHB-0453 | MMS | DK50 | MS0044 |  | 2024-05-06
2024-W19-20 | A | NOSD | WPM | MTN-MECH | MTN-TELE | 2400308604 | 1Y LIFE-SAVING & SAFETY EQ. RECERT-HBC | LIFE-SAVING & SAFETY EQ. CHECK-HBC | REL GMPS MACM PRC SETC | APPR SECE CMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W19-W20 | 2024-05-02 | 2024-05-04 | 2024-05-04 | 2024-03-12 | 2024-02-11 | 20 | REL | APPR OPND | HB /C /02/LIFE-SAVING-EQUIPMENT | LIFE SAVING EQUIPMENT |  | A | DKHB-0453 | MMS | DK50 | MS0044 |  | 2024-05-09
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315191 | 1Y HVAC PPM SUPPLY AIR HDBD-A-1201 | PERSONAL ISOLATION | REL PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-04-11 | 2024-03-12 | 10 | REL | APPR OPND | HD /B /09/HDBD-A-1201 | ACCOMMODATION AIR HANDLING UNIT |  | A | DKHD-2005 | MEL | DK60 | EL0013
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315191 | 1Y HVAC PPM SUPPLY AIR HDBD-A-1201 | HVAC CHECK, BELT DRIVEN HEAT & COOL COIL | REL PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO RDBL RFRZ ROUT | 11 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-04-11 | 2024-03-12 | 20 | REL | APPR OPND | HD /B /09/HDBD-A-1201 | ACCOMMODATION AIR HANDLING UNIT |  | A | DKHD-2005 | MEL | DK60 | EL0013
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315191 | 1Y HVAC PPM SUPPLY AIR HDBD-A-1201 | PERSONAL DE-ISOLATION | REL PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-28 | 2024-04-11 | 2024-03-12 | 30 | REL | APPR OPND | HD /B /09/HDBD-A-1201 | ACCOMMODATION AIR HANDLING UNIT |  | A | DKHD-2005 | MEL | DK60 | EL0013
2026-W13-14 | A | NOSD | WPM | MTN-INST | PRODTECH | 2400329562 | 4Y H2S ANA TEST - HBDC-FP-44531 | ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-06-19 | 2024-04-07 | 10 | REL | APPR OPND | HB /D /36/HBDC-FP-44531 | H2S ANALYSER PANEL |  | D | DKHB-0158 | MIN | DK50 | IN0014
2026-W13-14 | A | NOSD | WPM | MTN-INST | MTN-MECH | 2400329562 | 4Y H2S ANA TEST - HBDC-FP-44531 | H2S ANA REPLACE - HBDC-FP-44531 | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-06-19 | 2024-04-07 | 20 | REL | APPR OPND | HB /D /36/HBDC-FP-44531 | H2S ANALYSER PANEL |  | D | DKHB-0158 | MIN | DK50 | IN0014
2026-W13-14 | A | NOSD | WPM | MTN-INST | MTN-INST | 2400329562 | 4Y H2S ANA TEST - HBDC-FP-44531 | H2S ANA TEST - HBDC-FP-44531 | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO RDBL RFRZ ROUT | 6 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-27 | 2024-06-19 | 2024-04-07 | 30 | REL | APPR OPND | HB /D /36/HBDC-FP-44531 | H2S ANALYSER PANEL |  | D | DKHB-0158 | MIN | DK50 | IN0014
2026-W13-14 | A | NOSD | WPM | MTN-INST | MTN-ELEC | 2400329562 | 4Y H2S ANA TEST - HBDC-FP-44531 | H2S ANA TEST - HBDC-FP-44531 | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-28 | 2024-06-19 | 2024-04-07 | 40 | REL | APPR OPND | HB /D /36/HBDC-FP-44531 | H2S ANALYSER PANEL |  | D | DKHB-0158 | MIN | DK50 | IN0014
2026-W13-14 | A | NOSD | WPM | MTN-INST | PRODTECH | 2400329562 | 4Y H2S ANA TEST - HBDC-FP-44531 | DE-ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-29 | 2024-06-19 | 2024-04-07 | 50 | REL | APPR OPND | HB /D /36/HBDC-FP-44531 | H2S ANALYSER PANEL |  | D | DKHB-0158 | MIN | DK50 | IN0014
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100045474 | Replace air supply ball valve HBD L4 | Isolate accordingly | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | LOTI | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2021-06-01 | 2021-03-03 | 10 | REL | APPR OPND | HB /D /09/HBDE-FD-12421 | FIRE DAMPER | 99000119 | F |  | MEL | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100045474 | Replace air supply ball valve HBD L4 | Replace 1" ball valve NPT | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2021-06-01 | 2021-03-03 | 20 | REL | APPR OPND | HB /D /09/HBDE-FD-12421 | FIRE DAMPER | 99000119 | F |  | MEL | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100045474 | Replace air supply ball valve HBD L4 | De-isolate above | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2021-06-01 | 2021-03-03 | 30 | REL | APPR OPND | HB /D /09/HBDE-FD-12421 | FIRE DAMPER | 99000119 | F |  | MEL | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-MECH | MTN-MECH | 2100085373 | ESDV-345106 leaking in closed position | ESDV-345106 leaking in closed position | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2023-08-05 | 2023-03-23 | 10 | REL | APPR OPND | HB /D /23/HBDB-ESDV-345106 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-MECH | PRODTECH | 2100085373 | ESDV-345106 leaking in closed position | Isolation Production | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2023-08-05 | 2023-03-23 | 50 | REL | APPR OPND | HB /D /23/HBDB-ESDV-345106 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-MECH | MTN-ELEC | 2100085373 | ESDV-345106 leaking in closed position | Demount actuator electrical | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2023-08-05 | 2023-03-23 | 60 | REL | APPR OPND | HB /D /23/HBDB-ESDV-345106 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-MECH | MTN-MECH | 2100085373 | ESDV-345106 leaking in closed position | Demount actuator mechanical | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2023-08-05 | 2023-03-23 | 70 | REL | APPR OPND | HB /D /23/HBDB-ESDV-345106 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100085373 | ESDV-345106 leaking in closed position | Rigger Assistance for demount actuator | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2023-08-05 | 2023-03-23 | 80 | REL | APPR OPND | HB /D /23/HBDB-ESDV-345106 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100085373 | ESDV-345106 leaking in closed position | Rigger Assistance for replacing valve | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2023-08-05 | 2023-03-23 | 90 | REL | APPR OPND | HB /D /23/HBDB-ESDV-345106 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-MECH | MTN-MECH | 2100085373 | ESDV-345106 leaking in closed position | Replace/installation valve | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2023-08-05 | 2023-03-23 | 100 | REL | APPR OPND | HB /D /23/HBDB-ESDV-345106 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-MECH | MTN-MECH | 2100085373 | ESDV-345106 leaking in closed position | Mount actuator mechanical | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2023-08-05 | 2023-03-23 | 110 | REL | APPR OPND | HB /D /23/HBDB-ESDV-345106 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-MECH | MTN-ELEC | 2100085373 | ESDV-345106 leaking in closed position | Mount actuator electrical | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2023-08-05 | 2023-03-23 | 120 | REL | APPR OPND | HB /D /23/HBDB-ESDV-345106 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-MECH | PRODTECH | 2100085373 | ESDV-345106 leaking in closed position | De-Isolation Production | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2023-08-05 | 2023-03-23 | 130 | REL | APPR OPND | HB /D /23/HBDB-ESDV-345106 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-MECH | MTN-MECH | 2100085373 | ESDV-345106 leaking in closed position | Function test | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2023-08-05 | 2023-03-23 | 140 | REL | APPR OPND | HB /D /23/HBDB-ESDV-345106 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-MECH | MTN-MECH | 2100085373 | ESDV-345106 leaking in closed position | Backload valve for refurbishment | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-07 | 2023-08-05 | 2023-03-23 | 150 | REL | APPR OPND | HB /D /23/HBDB-ESDV-345106 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400307651 | 4Y FW PUMP PACKAGE MAINT HBCM-A-0331 | SCAFFOLDING CONSTRUCT | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 | W13-W14 | 2024-03-25 | 2024-04-07 | 2024-03-25 | 2024-03-02 | 2023-12-20 | 10 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D | DKHB-0064 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400307651 | 4Y FW PUMP PACKAGE MAINT HBCM-A-0331 | ISOLATION BY PRODUCTION | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W13-W14 | 2024-03-25 | 2024-04-07 | 2024-03-27 | 2024-03-02 | 2023-12-20 | 20 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D | DKHB-0064 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400307651 | 4Y FW PUMP PACKAGE MAINT HBCM-A-0331 | FW PUMP PACKAGE MAINT HBCM-A-0331 | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 7 | 1 | W13-W14 | 2024-03-25 | 2024-04-07 | 2024-03-30 | 2024-03-02 | 2023-12-20 | 40 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D | DKHB-0064 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400307651 | 4Y FW PUMP PACKAGE MAINT HBCM-A-0331 | FW PUMP PACKAGE MAINT HBCM-A-0331 | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 59 | W13-W14 | 2024-03-25 | 2024-04-07 | 2024-03-31 | 2024-03-02 | 2023-12-20 | 50 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D | DKHB-0064 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400307651 | 4Y FW PUMP PACKAGE MAINT HBCM-A-0331 | FW PUMP PACKAGE VEND ASSIST HBCM-A-0331 | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 0 | W13-W14 | 2024-03-25 | 2024-04-07 | 2024-04-03 | 2024-03-02 | 2023-12-20 | 60 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D | DKHB-0064 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400307651 | 4Y FW PUMP PACKAGE MAINT HBCM-A-0331 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W13-W14 | 2024-03-25 | 2024-04-07 | 2024-04-04 | 2024-03-02 | 2023-12-20 | 70 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D | DKHB-0064 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400307651 | 4Y FW PUMP PACKAGE MAINT HBCM-A-0331 | SCAFFOLDING DE-CONSTRUCT | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 | W13-W14 | 2024-03-25 | 2024-04-07 | 2024-04-05 | 2024-03-02 | 2023-12-20 | 80 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D | DKHB-0064 | MMS | DK50 | MS0014 | PROK
0 | A | HDAFLARE | WPM | MTN-MECH | PRODTECH | 2400309085 | 3Y FLARE SYSTEM INSPECTION HDA | ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-03-21 | 2024-01-19 | 10 | REL | APPR OPND | HD /A /36/HP-FLARE-SYSTEM | HP FLARE SYSTEM |  | A | DKHD-0056 | MMR | DK60 | MR0143 | PROK
0 | A | HDAFLARE | WPM | MTN-MECH | MTN-INST | 2400309085 | 3Y FLARE SYSTEM INSPECTION HDA | FLARE INSTRUMENT CALIBRATION HDA | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-03-21 | 2024-01-19 | 20 | REL | APPR OPND | HD /A /36/HP-FLARE-SYSTEM | HP FLARE SYSTEM |  | A | DKHD-0056 | MMR | DK60 | MR0143 | PROK
0 | A | HDAFLARE | WPM | MTN-MECH | MTN-MECH | 2400309085 | 3Y FLARE SYSTEM INSPECTION HDA | FLARE SYSTEM INSPECTION HDA | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-03-21 | 2024-01-19 | 30 | REL | APPR OPND | HD /A /36/HP-FLARE-SYSTEM | HP FLARE SYSTEM |  | A | DKHD-0056 | MMR | DK60 | MR0143 | PROK
0 | A | HDAFLARE | WPM | MTN-MECH | MTN-ELEC | 2400309085 | 3Y FLARE SYSTEM INSPECTION HDA | FLARE SYSTEM ELEC INSPECTION HDA | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-03-21 | 2024-01-19 | 40 | REL | APPR OPND | HD /A /36/HP-FLARE-SYSTEM | HP FLARE SYSTEM |  | A | DKHD-0056 | MMR | DK60 | MR0143 | PROK
0 | A | HDAFLARE | WPM | MTN-MECH | PRODTECH | 2400309085 | 3Y FLARE SYSTEM INSPECTION HDA | DE-ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-03-21 | 2024-01-19 | 50 | REL | APPR OPND | HD /A /36/HP-FLARE-SYSTEM | HP FLARE SYSTEM |  | A | DKHD-0056 | MMR | DK60 | MR0143 | PROK
0 | A | HDA-IPHP | WPM | MTN-ELEC | MTN-ELEC | 2400235072 | 2Y UPS BATTERY CAPACITY TEST HDA | Caverion Rental | REL PCNF MANC NMAT PPRT PRC SETC | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-05-22 | 2024-05-25 | 2024-05-22 | 2023-03-12 | 2023-01-25 | 30 | REL | APPR OPND | HD /A /06/24V-SYSTEM | 24V SYSTEM FOR HDAB-N-1802 |  | G | DKHD-0039 | MEL | DK60 | EL0033
0 | A | HDA-IPHP | WPM | MTN-ELEC | MTN-ELEC | 2400235072 | 2Y UPS BATTERY CAPACITY TEST HDA | A | REL PCNF MANC NMAT PPRT PRC SETC | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-05-22 | 2024-05-25 | 2024-05-22 | 2023-03-12 | 2023-01-25 | 40 | REL | APPR OPND | HD /A /06/24V-SYSTEM | 24V SYSTEM FOR HDAB-N-1802 |  | G | DKHD-0039 | MEL | DK60 | EL0033
0 | A | HDA-IPHP | WPM | MTN-ELEC | VEN-ELEC | 2400235072 | 2Y UPS BATTERY CAPACITY TEST HDA | Remaning scope Captest / battery test | REL PCNF MANC NMAT PPRT PRC SETC | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | 32 | 0 |  | 2024-05-22 | 2024-05-25 | 2024-05-22 | 2023-03-12 | 2023-01-25 | 50 | REL | APPR OPND | HD /A /06/24V-SYSTEM | 24V SYSTEM FOR HDAB-N-1802 |  | G | DKHD-0039 | MEL | DK60 | EL0033
0 | A | NOSD | WPM | MTN-ELEC | MTN-TELE | 2400308622 | 1Y UPS BATTERY FUNCTION TEST HDA | UPS BATTERY FUNCTION TEST HDA | REL MANC NMAT PRC SETC | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | 0.1 | 0 | W11-W12 | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-12 | 2024-02-11 | 10 | REL | APPR OPND | HD /A /06/24V-SYSTEM | 24V SYSTEM FOR HDAB-N-1802 |  | G | DKHD-0039 | MEL | DK60 | EL0033 | PROK
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308622 | 1Y UPS BATTERY FUNCTION TEST HDA | Site Visit - TBT. | REL MANC NMAT PRC SETC | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W11-W12 | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-12 | 2024-02-11 | 20 | REL | APPR OPND | HD /A /06/24V-SYSTEM | 24V SYSTEM FOR HDAB-N-1802 |  | G | DKHD-0039 | MEL | DK60 | EL0033 | PROK
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308622 | 1Y UPS BATTERY FUNCTION TEST HDA | Conduct the PPM check acc. to WO | REL MANC NMAT PRC SETC | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | 7 | 0 | W11-W12 | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-12 | 2024-02-11 | 30 | REL | APPR OPND | HD /A /06/24V-SYSTEM | 24V SYSTEM FOR HDAB-N-1802 |  | G | DKHD-0039 | MEL | DK60 | EL0033 | PROK
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308622 | 1Y UPS BATTERY FUNCTION TEST HDA | Check up clean up - documentation | REL MANC NMAT PRC SETC | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W11-W12 | 2024-03-18 | 2024-03-19 | 2024-03-19 | 2024-03-12 | 2024-02-11 | 40 | REL | APPR OPND | HD /A /06/24V-SYSTEM | 24V SYSTEM FOR HDAB-N-1802 |  | G | DKHD-0039 | MEL | DK60 | EL0033 | PROK
2026-W13-14 | 2 |  | WGN | VEN-SUBS | PRODTECH | 2200017392 | PIGGING, P4303 14" HBA-HDA OIL ILI Clean | P4303_HBA-HDA | REL MANC NMAT PRC SETC | APPR SECE AWSC RDBL | 4 | 0 |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-03-17 | 2024-02-01 | 10 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A |  | SUB | DK50
2026-W13-14 | 2 |  | WGN | VEN-SUBS | PRODTECH | 2200017393 | PIGGING, P4303 14" HBA-HDA OIL ILI Clean | P4303_HBA-HDA | REL MANC NMAT PRC SETC | APPR SECE AWSC RDBL | 4 | 0 |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-03-17 | 2024-02-01 | 10 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A |  | SUB | DK50
2026-W13-14 | 2 |  | WGN | VEN-SUBS | PRODTECH | 2200017394 | PIGGING, P4303 14" HBA-HDA OIL ILI Clean | P4303_HBA-HDA | REL MANC NMAT PRC SETC | APPR SECE AWSC RDBL | 4 | 0 |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-03-17 | 2024-02-01 | 10 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A |  | SUB | DK50
2026-W13-14 | 2 |  | WGN | VEN-SUBS | PRODTECH | 2200017395 | PIGGING, P4303 14" HBA-HDA OIL ILI Clean | P4303_HBA-HDA | REL MANC NMAT PRC SETC | APPR SECE AWSC RDBL | 4 | 0 |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-03-17 | 2024-02-01 | 10 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A |  | SUB | DK50
2026-W13-14 | 2 |  | WGN | VEN-SUBS | PRODTECH | 2200017396 | PIGGING, P4303 14" HBA-HDA OIL Gauge Pla | P4303_HBA-HDA | REL MANC NMAT PRC SETC | APPR SECE AWSC RDBL | 4 | 0 |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-03-17 | 2024-02-01 | 10 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A |  | SUB | DK50
2026-W1-2 | A | HBDHPSEP | WPM | MTN-MECH | PRODTECH | 2400210984 | 1Y SDV/BDV FUNC TEST HBD-12-20-23-34 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-20 | 2024-04-11 | 2022-09-18 | 2022-08-19 | 10 | REL | APPR OPND | HB /D /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0129 | MMS | DK50 | MS0054
2026-W1-2 | A | HBDHPSEP | WPM | MTN-MECH | MTN-MECH | 2400210984 | 1Y SDV/BDV FUNC TEST HBD-12-20-23-34 | SDV/BDV FUNC TEST HBD-12-20-23-34 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 22 | 0 | W15-W16 | 2024-04-11 | 2024-04-20 | 2024-04-11 | 2022-09-18 | 2022-08-19 | 20 | REL | APPR OPND | HB /D /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0129 | MMS | DK50 | MS0054
2026-W1-2 | A | HBDHPSEP | WPM | MTN-MECH | MTN-INST | 2400210984 | 1Y SDV/BDV FUNC TEST HBD-12-20-23-34 | SDV/BDV INST ASSIST HBD-12-20-23-34 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 22 | 0 | W15-W16 | 2024-04-11 | 2024-04-20 | 2024-04-15 | 2022-09-18 | 2022-08-19 | 30 | REL | APPR OPND | HB /D /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0129 | MMS | DK50 | MS0054
2026-W1-2 | A | HBDHPSEP | WPM | MTN-MECH | PRODTECH | 2400210984 | 1Y SDV/BDV FUNC TEST HBD-12-20-23-34 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-20 | 2024-04-20 | 2022-09-18 | 2022-08-19 | 40 | REL | APPR OPND | HB /D /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0129 | MMS | DK50 | MS0054
2026-W1-2 | A | HBDHPSEP | WPM | MTN-MECH | PRODTECH | 2400211197 | 1Y SDV/BDV INSP/FUNC TEST HBB-10-12 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-15 | 2024-04-11 | 2022-09-26 | 2022-08-27 | 10 | REL | APPR OPND | HB /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0122 | MMS | DK50 | MS0054
2026-W1-2 | A | HBDHPSEP | WPM | MTN-MECH | MTN-MECH | 2400211197 | 1Y SDV/BDV INSP/FUNC TEST HBB-10-12 | SDV/BDV INSP/FUNC TEST HBB-10-12 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 9 | 0 | W15-W16 | 2024-04-11 | 2024-04-15 | 2024-04-11 | 2022-09-26 | 2022-08-27 | 20 | REL | APPR OPND | HB /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0122 | MMS | DK50 | MS0054
2026-W1-2 | A | HBDHPSEP | WPM | MTN-MECH | MTN-INST | 2400211197 | 1Y SDV/BDV INSP/FUNC TEST HBB-10-12 | SDV/BDV INST ASSIST HBB-SYST-10-12 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 9 | 0 | W15-W16 | 2024-04-11 | 2024-04-15 | 2024-04-13 | 2022-09-26 | 2022-08-27 | 30 | REL | APPR OPND | HB /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0122 | MMS | DK50 | MS0054
2026-W1-2 | A | HBDHPSEP | WPM | MTN-MECH | PRODTECH | 2400211197 | 1Y SDV/BDV INSP/FUNC TEST HBB-10-12 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-15 | 2024-04-15 | 2022-09-26 | 2022-08-27 | 40 | REL | APPR OPND | HB /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0122 | MMS | DK50 | MS0054
2026-W1-2 | A | HBAPWELL | WPM | MTN-MECH | PRODTECH | 2400273439 | 1Y SDV INSP/FUNC TEST HBD-27-28 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-17 | 2024-04-11 | 2023-09-04 | 2023-08-05 | 10 | REL | APPR OPND | HB /D /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | C | DKHB-0072 | MMS | DK50 | MS0054
2026-W1-2 | A | HBAPWELL | WPM | MTN-MECH | MTN-MECH | 2400273439 | 1Y SDV INSP/FUNC TEST HBD-27-28 | SDV INSP/FUNC TEST HBD-27-28 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 14 | 0 | W15-W16 | 2024-04-11 | 2024-04-17 | 2024-04-11 | 2023-09-04 | 2023-08-05 | 20 | REL | APPR OPND | HB /D /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | C | DKHB-0072 | MMS | DK50 | MS0054
2026-W1-2 | A | HBAPWELL | WPM | MTN-MECH | MTN-INST | 2400273439 | 1Y SDV INSP/FUNC TEST HBD-27-28 | SDV INST ASSIST HBD-SYST-27-28 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 14 | 0 | W15-W16 | 2024-04-11 | 2024-04-17 | 2024-04-14 | 2023-09-04 | 2023-08-05 | 30 | REL | APPR OPND | HB /D /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | C | DKHB-0072 | MMS | DK50 | MS0054
2026-W1-2 | A | HBAPWELL | WPM | MTN-MECH | PRODTECH | 2400273439 | 1Y SDV INSP/FUNC TEST HBD-27-28 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-17 | 2024-04-17 | 2023-09-04 | 2023-08-05 | 40 | REL | APPR OPND | HB /D /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | C | DKHB-0072 | MMS | DK50 | MS0054
0 | A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400298349 | 18M GAS DETECTORS HDA | IR/CAT GAS DETECTOR CHECK | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W19-W20 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-01-08 | 2023-12-09 | 10 | REL | APPR OPND | HD /A /03/FGS-DETECTORS | FLAME, HEAT, GAS, SMOKE DETECTORS - HDA |  | B | DKHD-7201 | MIN | DK60 | IN0073
2026-W1-2 | A | HB-DANLP | WPM | MTN-MECH | PRODTECH | 2400308608 | 6M ESDV FUNC TEST HBBA-ESDV-38413 | ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-03-11 | 2024-02-24 | 10 | PCNF REL | APPR OPND | HB /B /34/HBBA-ESDV-38413 | EMERGENCY SHUTDOWN VALVE |  | A | DKHB-0664 | MMS | DK50 | MS0054
2026-W1-2 | A | HB-DANLP | WPM | MTN-MECH | MTN-MECH | 2400308608 | 6M ESDV FUNC TEST HBBA-ESDV-38413 | ESDV FUNC TEST HBBA-ESDV-38413 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 1 | 2 | W15-W16 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-03-11 | 2024-02-24 | 20 | PCNF REL | APPR OPND | HB /B /34/HBBA-ESDV-38413 | EMERGENCY SHUTDOWN VALVE |  | A | DKHB-0664 | MMS | DK50 | MS0054
2026-W1-2 | A | HB-DANLP | WPM | MTN-MECH | MTN-INST | 2400308608 | 6M ESDV FUNC TEST HBBA-ESDV-38413 | ESDV INST ASSIST HBBA-ESDV-38413 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-03-11 | 2024-02-24 | 30 | PCNF REL | APPR OPND | HB /B /34/HBBA-ESDV-38413 | EMERGENCY SHUTDOWN VALVE |  | A | DKHB-0664 | MMS | DK50 | MS0054
2026-W1-2 | A | HB-DANLP | WPM | MTN-MECH | PRODTECH | 2400308608 | 6M ESDV FUNC TEST HBBA-ESDV-38413 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-03-25 | 2024-03-26 | 2024-03-26 | 2024-03-11 | 2024-02-24 | 40 | PCNF REL | APPR OPND | HB /B /34/HBBA-ESDV-38413 | EMERGENCY SHUTDOWN VALVE |  | A | DKHB-0664 | MMS | DK50 | MS0054
2026-W1-2 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316090 | 1Y EMERGENCY LIGHT TEST-CELLAR DECK-HBB | PERSONAL ISOLATION | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-20 | 2024-04-22 | 2024-04-20 | 2024-05-01 | 2024-04-01 | 10 | REL | APPR OPND | HB /B /62/EMERGENCY-LIGHTS-CELLAR-DECK | EMERGENCY LIGHTING IN CELLAR DECK HBB |  | C | DKHB-0159 | MEL | DK50 | EL0044
2026-W1-2 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316090 | 1Y EMERGENCY LIGHT TEST-CELLAR DECK-HBB | EMERGENCY LIGHT TEST-CELLAR DECK-HBB | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 12 | 0 | W15-W16 | 2024-04-20 | 2024-04-22 | 2024-04-20 | 2024-05-01 | 2024-04-01 | 20 | REL | APPR OPND | HB /B /62/EMERGENCY-LIGHTS-CELLAR-DECK | EMERGENCY LIGHTING IN CELLAR DECK HBB |  | C | DKHB-0159 | MEL | DK50 | EL0044
2026-W1-2 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316090 | 1Y EMERGENCY LIGHT TEST-CELLAR DECK-HBB | PERSONAL DE-ISOLATION | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-20 | 2024-04-22 | 2024-04-22 | 2024-05-01 | 2024-04-01 | 40 | REL | APPR OPND | HB /B /62/EMERGENCY-LIGHTS-CELLAR-DECK | EMERGENCY LIGHTING IN CELLAR DECK HBB |  | C | DKHB-0159 | MEL | DK50 | EL0044
2026-W1-2 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316091 | 1Y EMERGENCY LIGHT TEST - ROOF DECK-HBB | PERSONAL ISOLATION | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-20 | 2024-04-21 | 2024-04-20 | 2024-05-01 | 2024-04-01 | 10 | REL | APPR OPND | HB /B /62/EMERGENCY-LIGHTS-ROOF-DECK | EMERGENCY LIGHTS ROOF DECK |  | C | DKHB-0161 | MEL | DK50 | EL0044
2026-W1-2 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316091 | 1Y EMERGENCY LIGHT TEST - ROOF DECK-HBB | EMERGENCY LIGHT TEST - ROOF DECK-HBB | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 8 | 0 | W15-W16 | 2024-04-20 | 2024-04-21 | 2024-04-20 | 2024-05-01 | 2024-04-01 | 20 | REL | APPR OPND | HB /B /62/EMERGENCY-LIGHTS-ROOF-DECK | EMERGENCY LIGHTS ROOF DECK |  | C | DKHB-0161 | MEL | DK50 | EL0044
2026-W1-2 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316091 | 1Y EMERGENCY LIGHT TEST - ROOF DECK-HBB | PERSONAL DE-ISOLATION | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-20 | 2024-04-21 | 2024-04-21 | 2024-05-01 | 2024-04-01 | 40 | REL | APPR OPND | HB /B /62/EMERGENCY-LIGHTS-ROOF-DECK | EMERGENCY LIGHTS ROOF DECK |  | C | DKHB-0161 | MEL | DK50 | EL0044
2026-W1-2 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316092 | 1Y EMERGENCY LIGHT TEST - BRIDGE-HBA/HBC | PERSONAL ISOLATION | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-20 | 2024-04-21 | 2024-04-20 | 2024-05-01 | 2024-04-01 | 10 | REL | APPR OPND | HB /B /62/EMERGENCY-LIGHTING | EMERGENCY LIGHTING |  | C | DKHB-0162 | MEL | DK50 | EL0044
2026-W1-2 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316092 | 1Y EMERGENCY LIGHT TEST - BRIDGE-HBA/HBC | EMERGENCY LIGHT TEST - BRIDGE - HBA/HBC | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 8 | 0 | W15-W16 | 2024-04-20 | 2024-04-21 | 2024-04-20 | 2024-05-01 | 2024-04-01 | 20 | REL | APPR OPND | HB /B /62/EMERGENCY-LIGHTING | EMERGENCY LIGHTING |  | C | DKHB-0162 | MEL | DK50 | EL0044
2026-W1-2 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316092 | 1Y EMERGENCY LIGHT TEST - BRIDGE-HBA/HBC | PERSONAL DE-ISOLATION | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-20 | 2024-04-21 | 2024-04-21 | 2024-05-01 | 2024-04-01 | 40 | REL | APPR OPND | HB /B /62/EMERGENCY-LIGHTING | EMERGENCY LIGHTING |  | C | DKHB-0162 | MEL | DK50 | EL0044
2026-W1-2 | A | NOSD | WPM | MTN-INST | MTN-TELE | 2400316093 | 1Y F&G STATUS ALARMS TEST - HBB | F&G STATUS ALARMS TEST - HBB | REL MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 6 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2024-04-30 | 2024-03-31 | 10 | REL | APPR OPND | HB /B /03/VISUAL-AUDIBLE-ALARM | VISUAL AND AUDIBLE ALARMS |  | C | DKHB-0486 | MIN | DK50 | IN0074 | PROK
2026-W1-2 | A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400316095 | 18M IR GAS DETECTOR CHECK HBA/HBB | IR GAS DETECTOR CHECK | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 42.5 | 9 | W17-W18 | 2024-04-22 | 2024-04-30 | 2024-04-22 | 2024-05-04 | 2024-04-04 | 10 | PCNF REL | APPR OPND | HB /A /03/FGS-DETECTORS | FLAME, HEAT, GAS, SMOKE DETECTORS - HBA |  | B | DKHB-7201 | MIN | DK50 | IN0074 | PROK
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400316097 | 6M LIFEBOAT INSPECTION HDBM-X-0701 | LIFEBOAT INSPECTION HDBM-X-0701 | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 16 | 0 | W15-W16 | 2024-04-15 | 2024-04-18 | 2024-04-15 | 2024-05-01 | 2024-04-15 | 10 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A | DKHD-0132 | MMS | DK60 | MS0043 | PROK
0 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400316097 | 6M LIFEBOAT INSPECTION HDBM-X-0701 | LIFEBOAT MOTOR INSPECTION HDBM-X-0701 | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 0.5 | 0 | W15-W16 | 2024-04-15 | 2024-04-18 | 2024-04-18 | 2024-05-01 | 2024-04-15 | 20 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A | DKHD-0132 | MMS | DK60 | MS0043 | PROK
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400316098 | 6M LIFEBOAT INSPECTION HDBM-X-0702 | LIFEBOAT INSPECTION HDBM-X-0702 | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 16 | 0 | W15-W16 | 2024-04-15 | 2024-04-18 | 2024-04-15 | 2024-05-01 | 2024-04-15 | 10 | REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | A | DKHD-0133 | MMS | DK60 | MS0043 | PROK
0 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400316098 | 6M LIFEBOAT INSPECTION HDBM-X-0702 | LIFEBOAT MOTOR INSPECTION HDBM-X-0702 | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 0.5 | 0 | W15-W16 | 2024-04-15 | 2024-04-18 | 2024-04-18 | 2024-05-01 | 2024-04-15 | 20 | REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | A | DKHD-0133 | MMS | DK60 | MS0043 | PROK
2026-W1-2 | A | NOSD | WPM | MTN-ELEC | MTN-TELE | 2400321293 | 1Y NAV AID INSPECTION HBDD-CP-1550 | NAV AID INSPECTION HBDD-CP-1550 | REL NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 13 | 0 | W15-W16 | 2024-04-10 | 2024-04-12 | 2024-04-10 | 2024-05-10 | 2024-04-10 | 10 | REL | APPR OPND | HB /D /64/HBDD-CP-1550 | NAV. AIDS CONTROL PANEL |  | A | DKHB-0003 | MEL | DK50 | EL0044 | PROK
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400321317 | 1Y FIRE DOOR INSPECTION HDA | FIRE DOOR INSPECTION HDA | REL MANC NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 14 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-05-09 | 2024-04-09 | 10 | REL | APPR OPND | HD /A /02/FIRE-DOORS | FIRE DOORS |  | A | DKHD-0011 | MMS | DK60 | FM0033 | PROK
0 | A | NOSD | WPM | MTN-TELE | MTN-SCAF | 2400321322 | 1Y LOS RADIO FUNCTION TEST HDB/C | SCAFFOLDING SETUP | REL PRT NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 26 | 0 | W15-W16 | 2024-04-09 | 2024-04-15 | 2024-04-09 | 2024-05-09 | 2024-04-09 | 9 | REL | APPR OPND | HD /B /08/LOS-RADIO-WITH-ANTENNA | LOS RADIO WITH ANTENNA |  | A | DKHD-0120 | MIN | DK60 | IN0053
0 | A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400321322 | 1Y LOS RADIO FUNCTION TEST HDB/C | LOS RADIO FUNCTION TEST HDB/C | REL PRT NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 8 | 0 | W15-W16 | 2024-04-09 | 2024-04-15 | 2024-04-11 | 2024-05-09 | 2024-04-09 | 10 | REL | APPR OPND | HD /B /08/LOS-RADIO-WITH-ANTENNA | LOS RADIO WITH ANTENNA |  | A | DKHD-0120 | MIN | DK60 | IN0053
0 | A | NOSD | WPM | MTN-TELE | MTN-SCAF | 2400321322 | 1Y LOS RADIO FUNCTION TEST HDB/C | SCAFFOLDING REMOVAL | REL PRT NMAT PRC SETC | APPR SECE AWDO SCH RDBL RFRZ ROUT | 20 | 0 | W15-W16 | 2024-04-09 | 2024-04-15 | 2024-04-13 | 2024-05-09 | 2024-04-09 | 11 | REL | APPR OPND | HD /B /08/LOS-RADIO-WITH-ANTENNA | LOS RADIO WITH ANTENNA |  | A | DKHD-0120 | MIN | DK60 | IN0053
2026-W13-14 | 3 |  | WDF | MTN-LAGG | MTN-LAGG | 2100059038 | ANOCR HBA- Missing Bestobel Seal 6"-DPS- | HBA- Missing Bestobel Seal 6"-DPS-504019 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2021-10-24 | 2021-10-25 | 2021-10-24 | 2022-01-22 | 2021-10-24 | 10 | REL | APPR OPND | HB /A /28/HBA-6-DPS-050-4019-AA-U | 6 CLOSED DRAIN SOUR LINE |  | A |  | MFM | DK50
2026-W13-14 | 3 | NE | WDF | MTN-INST | MTN-PIPF | 2100101115 | FLMR Actuator leaking on Pneumatic FID, | Actuator leaking on Pneumatic FID, HBD | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-04-27 | 2023-12-14 | 10 | REL | APPR OPND | HB /D /02/HBDC-FID-64149 | FIRE DOOR |  | A |  | MIN | DK50
2026-W13-14 | 3 | NE | WDF | MTN-INST | MTN-PIPF | 2100101115 | FLMR Actuator leaking on Pneumatic FID, | Order materials | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-04-27 | 2023-12-14 | 20 | REL | APPR OPND | HB /D /02/HBDC-FID-64149 | FIRE DOOR |  | A |  | MIN | DK50
2026-W13-14 | 3 | NE | WDF | MTN-INST | MTN-PIPF | 2100101115 | FLMR Actuator leaking on Pneumatic FID, | Change door pump | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-04-27 | 2023-12-14 | 30 | REL | APPR OPND | HB /D /02/HBDC-FID-64149 | FIRE DOOR |  | A |  | MIN | DK50
2024-W37-38 | 3 |  | WDF | MTN-PIPF | MTN-MECH | 2100106455 | FLM HBD - Escape to sea missing grating | HBD - Escape to sea missing grating | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-07-26 | 2024-03-13 | 10 | REL | APPR OPND | HB /D /86/JACKET - ESCAPE TO SEA | ESCAPE LADDER AND STAIRS TO SEA |  | A |  | MFM | DK50
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125554 | HDA-27 PIPING EXTERNAL INSP | PIPING INSPECTION AND REPORTING | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 10 | PCNF REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | A | DKHDAPIPE06 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125554 | HDA-27 PIPING EXTERNAL INSP | HDA-CPS-CS-N-2701_INSP & REPORT | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 20 | PCNF REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | A | DKHDAPIPE06 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125554 | HDA-27 PIPING EXTERNAL INSP | HDA-DPS-CS-N-2701_INSP & REPORT | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 5.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 30 | PCNF REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | A | DKHDAPIPE06 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125554 | HDA-27 PIPING EXTERNAL INSP | HDA-FHS-CS-N-2701_INSP & REPORT | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 40 | PCNF REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | A | DKHDAPIPE06 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125554 | HDA-27 PIPING EXTERNAL INSP | HDA-OCS-CS-I-2701_INSP & REPORT | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 50 | PCNF REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | A | DKHDAPIPE06 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125554 | HDA-27 PIPING EXTERNAL INSP | HDA-OCS-CS-N-2701_INSP & REPORT | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-16 | 2021-12-31 | 2021-11-15 | 60 | PCNF REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | A | DKHDAPIPE06 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125554 | HDA-27 PIPING EXTERNAL INSP | HDA-OCS-CS-N-2702_INSP & REPORT | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-16 | 2021-12-31 | 2021-11-15 | 70 | PCNF REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | A | DKHDAPIPE06 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125554 | HDA-27 PIPING EXTERNAL INSP | HDA-OCS-SSMO-N-2701_INSP & REPORT | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-16 | 2021-12-31 | 2021-11-15 | 80 | PCNF REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | A | DKHDAPIPE06 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125554 | HDA-27 PIPING EXTERNAL INSP | HDA-WOS-CS-I-2701_INSP & REPORT | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-16 | 2021-12-31 | 2021-11-15 | 90 | PCNF REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | A | DKHDAPIPE06 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125554 | HDA-27 PIPING EXTERNAL INSP | HDA-WOS-CS-N-2701_INSP & REPORT | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 7 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-16 | 2021-12-31 | 2021-11-15 | 100 | PCNF REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | A | DKHDAPIPE06 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125554 | HDA-27 PIPING EXTERNAL INSP | HDA-WOS-SSMO-I-2701_INSP & REPORT | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-17 | 2021-12-31 | 2021-11-15 | 120 | PCNF REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | A | DKHDAPIPE06 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125554 | HDA-27 PIPING EXTERNAL INSP | HDA-WOS-SSMO-N-2701_INSP & REPORT | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 8.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-18 | 2021-12-31 | 2021-11-15 | 130 | PCNF REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | A | DKHDAPIPE06 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | PIPING INSPECTION AND REPORTING | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 10 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-CPS-CS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 20 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-CPS-SS-N-2802_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 30 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-DO-CS-I-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 40 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-DO-CS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 73 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 50 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-DO-GCS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-23 | 2021-12-31 | 2021-11-15 | 60 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-DO-GRE-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-23 | 2021-12-31 | 2021-11-15 | 70 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-DOS-CS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 7.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-23 | 2021-12-31 | 2021-11-15 | 80 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-DO-SS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-24 | 2021-12-31 | 2021-11-15 | 90 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-DOS-SS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-25 | 2021-12-31 | 2021-11-15 | 100 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-DPS-CS-I-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-25 | 2021-12-31 | 2021-11-15 | 110 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-DPS-CS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 41.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-25 | 2021-12-31 | 2021-11-15 | 120 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-DP-SS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-30 | 2021-12-31 | 2021-11-15 | 130 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-DPS-SS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-30 | 2021-12-31 | 2021-11-15 | 140 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-FHS-CS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-30 | 2021-12-31 | 2021-11-15 | 150 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-FLS-CS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-30 | 2021-12-31 | 2021-11-15 | 160 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-FY-CS-N-2802_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-30 | 2021-12-31 | 2021-11-15 | 170 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-GFS-SS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-30 | 2021-12-31 | 2021-11-15 | 180 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-GLS-CS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-31 | 2021-12-31 | 2021-11-15 | 190 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-GPS-CS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-31 | 2021-12-31 | 2021-11-15 | 200 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-OCS-CS-I-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-03-31 | 2021-12-31 | 2021-11-15 | 210 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-OCS-CS-I-2802_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-04-01 | 2021-12-31 | 2021-11-15 | 220 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-OCS-CS-N-2802_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-04-01 | 2021-12-31 | 2021-11-15 | 230 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-OCS-CS-N-2803_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-04-01 | 2021-12-31 | 2021-11-15 | 240 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-PHS-CS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-04-01 | 2021-12-31 | 2021-11-15 | 250 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-WI-CS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-04-02 | 2021-12-31 | 2021-11-15 | 260 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-WOS-CS-I-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-04-02 | 2021-12-31 | 2021-11-15 | 270 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-WOS-CS-N-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-04-02 | 2021-12-31 | 2021-11-15 | 280 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125555 | HDA-28 PIPING EXTERNAL INSP | HDA-WOS-SSMO-I-2801_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4.5 | 0 |  | 2024-03-15 | 2024-04-03 | 2024-04-02 | 2021-12-31 | 2021-11-15 | 290 | REL | APPR OPND | HD /A /28/P-G | PIPING GROUP |  | A | DKHDAPIPE07 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125559 | HDA-34 PIPING EXTERNAL INSP | PIPING INSPECTION AND REPORTING | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 10 | REL | APPR OPND | HD /A /34/P-G | PIPING GROUP |  | A | DKHDAPIPE11 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125559 | HDA-34 PIPING EXTERNAL INSP | HDA-DO-CS-N-3401_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 20 | REL | APPR OPND | HD /A /34/P-G | PIPING GROUP |  | A | DKHDAPIPE11 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125559 | HDA-34 PIPING EXTERNAL INSP | HDA-DPS-CS-N-3401_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 30 | REL | APPR OPND | HD /A /34/P-G | PIPING GROUP |  | A | DKHDAPIPE11 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125559 | HDA-34 PIPING EXTERNAL INSP | HDA-GPS-CS-I-3401_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 40 | REL | APPR OPND | HD /A /34/P-G | PIPING GROUP |  | A | DKHDAPIPE11 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125559 | HDA-34 PIPING EXTERNAL INSP | HDA-GPS-CS-N-3401_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 50 | REL | APPR OPND | HD /A /34/P-G | PIPING GROUP |  | A | DKHDAPIPE11 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125559 | HDA-34 PIPING EXTERNAL INSP | HDA-GPS-CS-N-3402_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 60 | REL | APPR OPND | HD /A /34/P-G | PIPING GROUP |  | A | DKHDAPIPE11 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125559 | HDA-34 PIPING EXTERNAL INSP | HDA-GPS-CS-N-3403_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 16.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-16 | 2021-12-31 | 2021-11-15 | 70 | REL | APPR OPND | HD /A /34/P-G | PIPING GROUP |  | A | DKHDAPIPE11 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125559 | HDA-34 PIPING EXTERNAL INSP | HDA-GPS-CS-N-3404_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-17 | 2021-12-31 | 2021-11-15 | 80 | REL | APPR OPND | HD /A /34/P-G | PIPING GROUP |  | A | DKHDAPIPE11 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125559 | HDA-34 PIPING EXTERNAL INSP | HDA-GPS-SS-N-3401_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-18 | 2021-12-31 | 2021-11-15 | 90 | REL | APPR OPND | HD /A /34/P-G | PIPING GROUP |  | A | DKHDAPIPE11 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125559 | HDA-34 PIPING EXTERNAL INSP | HDA-PTS-CS-N-3401_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-18 | 2021-12-31 | 2021-11-15 | 100 | REL | APPR OPND | HD /A /34/P-G | PIPING GROUP |  | A | DKHDAPIPE11 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125559 | HDA-34 PIPING EXTERNAL INSP | HDA-WI-CS-I-3401_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-18 | 2021-12-31 | 2021-11-15 | 110 | REL | APPR OPND | HD /A /34/P-G | PIPING GROUP |  | A | DKHDAPIPE11 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125560 | HDA-37 PIPING EXTERNAL INSP | PIPING INSPECTION AND REPORTING | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-15 | 2024-03-18 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 10 | REL | APPR OPND | HD /A /37/P-G | PIPING GROUP |  | A | DKHDAPIPE13 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125560 | HDA-37 PIPING EXTERNAL INSP | HDA-GPS-CS-N-3701_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 36 | 0 |  | 2024-03-15 | 2024-03-18 | 2024-03-15 | 2021-12-31 | 2021-11-15 | 20 | REL | APPR OPND | HD /A /37/P-G | PIPING GROUP |  | A | DKHDAPIPE13 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400125560 | HDA-37 PIPING EXTERNAL INSP | HDA-GPS-SS-N-3701_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-03-18 | 2024-03-18 | 2021-12-31 | 2021-11-15 | 30 | REL | APPR OPND | HD /A /37/P-G | PIPING GROUP |  | A | DKHDAPIPE13 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400200500 | HDB-01 PIPING EXTERNAL INSP | PIPING INSPECTION AND REPORTING | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2022-12-31 | 2022-11-15 | 10 | REL | APPR OPND | HD /B /01/P-G | PIPING GROUP |  | A | DKHDBPIPE01 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400200500 | HDB-01 PIPING EXTERNAL INSP | HDB-DO-CS-N-0101_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 7.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2022-12-31 | 2022-11-15 | 20 | REL | APPR OPND | HD /B /01/P-G | PIPING GROUP |  | A | DKHDBPIPE01 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400200500 | HDB-01 PIPING EXTERNAL INSP | HDB-DO-SSMO-N-0101_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2022-12-31 | 2022-11-15 | 30 | REL | APPR OPND | HD /B /01/P-G | PIPING GROUP |  | A | DKHDBPIPE01 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400200500 | HDB-01 PIPING EXTERNAL INSP | HDB-FY-CS-N-0101_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-16 | 2022-12-31 | 2022-11-15 | 40 | REL | APPR OPND | HD /B /01/P-G | PIPING GROUP |  | A | DKHDBPIPE01 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400200500 | HDB-01 PIPING EXTERNAL INSP | HDB-WF-SSMO-I-0101_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 9.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-16 | 2022-12-31 | 2022-11-15 | 50 | REL | APPR OPND | HD /B /01/P-G | PIPING GROUP |  | A | DKHDBPIPE01 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400200500 | HDB-01 PIPING EXTERNAL INSP | HDB-WF-SSMO-N-0101_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-17 | 2022-12-31 | 2022-11-15 | 60 | REL | APPR OPND | HD /B /01/P-G | PIPING GROUP |  | A | DKHDBPIPE01 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400200500 | HDB-01 PIPING EXTERNAL INSP | HDB-WF-SS-N-0101_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-18 | 2022-12-31 | 2022-11-15 | 70 | REL | APPR OPND | HD /B /01/P-G | PIPING GROUP |  | A | DKHDBPIPE01 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400200500 | HDB-01 PIPING EXTERNAL INSP | HDB-WP-SS-N-0101_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1.5 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-18 | 2022-12-31 | 2022-11-15 | 80 | REL | APPR OPND | HD /B /01/P-G | PIPING GROUP |  | A | DKHDBPIPE01 | INP | DK60
0 | A | NOSD | WPM | INP-SITE | INP-SITE | 2400200500 | HDB-01 PIPING EXTERNAL INSP | HDB-WS-SSMO-N-0101_INSP & REPORT | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-03-15 | 2024-03-19 | 2024-03-18 | 2022-12-31 | 2022-11-15 | 90 | REL | APPR OPND | HD /B /01/P-G | PIPING GROUP |  | A | DKHDBPIPE01 | INP | DK60
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211329 | 4Y 24VDC UPS-DP FUNC TEST HBB | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2022-11-01 | 2022-08-20 | 10 | REL | APPR OPND | HB /B /06/UPS-BOARDS-24V | 24V UPS DISTRIBUTION BOARDS |  | C | DKHB-0472 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211329 | 4Y 24VDC UPS-DP FUNC TEST HBB | 24VDC UPS-DP FUNC TEST HBB | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 31 | 0 | W25-26 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2022-11-01 | 2022-08-20 | 20 | REL | APPR OPND | HB /B /06/UPS-BOARDS-24V | 24V UPS DISTRIBUTION BOARDS |  | C | DKHB-0472 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211329 | 4Y 24VDC UPS-DP FUNC TEST HBB | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2022-11-01 | 2022-08-20 | 30 | REL | APPR OPND | HB /B /06/UPS-BOARDS-24V | 24V UPS DISTRIBUTION BOARDS |  | C | DKHB-0472 | MEL | DK50 | EL0024
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298285 | 6M DELUGE SKID TEST/MAINT - HBCM-A-0335 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /C /01/HBCM-A-0335 | DELUGE SKID |  | A | DKHB-0073 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298285 | 6M DELUGE SKID TEST/MAINT - HBCM-A-0335 | DELUGE SKID TEST/MAINT - HBCM-A-0335 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /C /01/HBCM-A-0335 | DELUGE SKID |  | A | DKHB-0073 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298285 | 6M DELUGE SKID TEST/MAINT - HBCM-A-0335 | DELUGE SKID TEST/MAINT - HBCM-A-0335 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /C /01/HBCM-A-0335 | DELUGE SKID |  | A | DKHB-0073 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298285 | 6M DELUGE SKID TEST/MAINT - HBCM-A-0335 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /C /01/HBCM-A-0335 | DELUGE SKID |  | A | DKHB-0073 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298288 | 6M DELUGE SKID TEST/MAINT - HBDB-A-0380 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-05-02 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | A | DKHB-0089 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298288 | 6M DELUGE SKID TEST/MAINT - HBDB-A-0380 | DELUGE SKID TEST/MAINT - HBDB-A-0380 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 13 | 0 | W17-W18 | 2024-04-26 | 2024-05-02 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | A | DKHB-0089 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298288 | 6M DELUGE SKID TEST/MAINT - HBDB-A-0380 | DELUGE SKID TEST/MAINT - HBDB-A-0380 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 13 | 0 | W17-W18 | 2024-04-26 | 2024-05-02 | 2024-04-29 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | A | DKHB-0089 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298288 | 6M DELUGE SKID TEST/MAINT - HBDB-A-0380 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-05-02 | 2024-05-01 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | A | DKHB-0089 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298292 | 6M HELI DELUGE SKID TEST-HBCM-A-0339 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /C /01/HBCM-A-0339 | DELUGE SKID AVIATION FUEL |  | A | DKHB-0127 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298292 | 6M HELI DELUGE SKID TEST-HBCM-A-0339 | HELI DELUGE SKID TEST-HBCM-A-0339 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2.5 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /C /01/HBCM-A-0339 | DELUGE SKID AVIATION FUEL |  | A | DKHB-0127 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298292 | 6M HELI DELUGE SKID TEST-HBCM-A-0339 | HELI DELUGE SKID TEST-HBCM-A-0339 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2.5 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /C /01/HBCM-A-0339 | DELUGE SKID AVIATION FUEL |  | A | DKHB-0127 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298292 | 6M HELI DELUGE SKID TEST-HBCM-A-0339 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /C /01/HBCM-A-0339 | DELUGE SKID AVIATION FUEL |  | A | DKHB-0127 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298297 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0370 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | A | DKHB-0464 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298297 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0370 | DELUGE SKID TEST/MAINT - HBAA-A-0370 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | A | DKHB-0464 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298297 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0370 | DELUGE SKID TEST/MAINT - HBAA-A-0370 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | A | DKHB-0464 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298297 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0370 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | A | DKHB-0464 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298298 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0371 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0465 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298298 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0371 | DELUGE SKID TEST/MAINT - HBAA-A-0371 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0465 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298298 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0371 | DELUGE SKID TEST/MAINT - HBAA-A-0371 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0465 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298298 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0371 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0465 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298299 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0372 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0466 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298299 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0372 | DELUGE SKID TEST/MAINT - HBAA-A-0372 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0466 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298299 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0372 | DELUGE SKID TEST/MAINT - HBAA-A-0372 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0466 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298299 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0372 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0466 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298300 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0373 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | A | DKHB-0467 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298300 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0373 | DELUGE SKID TEST/MAINT - HBAA-A-0373 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | A | DKHB-0467 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298300 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0373 | DELUGE SKID TEST/MAINT - HBAA-A-0373 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | A | DKHB-0467 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298300 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0373 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | A | DKHB-0467 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298301 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0374 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | A | DKHB-0468 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298301 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0374 | DELUGE SKID TEST/MAINT - HBAA-A-0374 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | A | DKHB-0468 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298301 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0374 | DELUGE SKID TEST/MAINT - HBAA-A-0374 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | A | DKHB-0468 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298301 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0374 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | A | DKHB-0468 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298302 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0375 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0469 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298302 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0375 | DELUGE SKID TEST/MAINT - HBAA-A-0375 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0469 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298302 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0375 | DELUGE SKID TEST/MAINT - HBAA-A-0375 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0469 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298302 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0375 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0469 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298303 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0376 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0474 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298303 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0376 | DELUGE SKID TEST/MAINT - HBAA-A-0376 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0474 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298303 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0376 | DELUGE SKID TEST/MAINT - HBAA-A-0376 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0474 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298303 | 6M DELUGE SKID TEST/MAINT - HBAA-A-0376 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | A | DKHB-0474 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298304 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0310 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | A | DKHB-0476 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298304 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0310 | DELUGE SKID TEST/MAINT - HBBA-A-0310 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | A | DKHB-0476 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298304 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0310 | DELUGE SKID TEST/MAINT - HBBA-A-0310 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | A | DKHB-0476 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298304 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0310 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | A | DKHB-0476 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298305 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0320 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | A | DKHB-0477 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298305 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0320 | DELUGE SKID TEST/MAINT - HBBA-A-0320 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | A | DKHB-0477 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298305 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0320 | DELUGE SKID TEST/MAINT - HBBA-A-0320 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | A | DKHB-0477 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298305 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0320 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | A | DKHB-0477 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298306 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0330 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | A | DKHB-0479 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298306 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0330 | DELUGE SKID TEST/MAINT - HBBA-A-0330 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | A | DKHB-0479 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298306 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0330 | DELUGE SKID TEST/MAINT - HBBA-A-0330 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | A | DKHB-0479 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298306 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0330 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | A | DKHB-0479 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298307 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0340 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | A | DKHB-0480 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298307 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0340 | DELUGE SKID TEST/MAINT - HBBA-A-0340 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | A | DKHB-0480 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298307 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0340 | DELUGE SKID TEST/MAINT - HBBA-A-0340 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | A | DKHB-0480 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298307 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0340 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | A | DKHB-0480 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298308 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0350 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 10 | REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | A | DKHB-0481 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298308 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0350 | DELUGE SKID TEST/MAINT - HBBA-A-0350 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-01-15 | 2023-12-30 | 20 | REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | A | DKHB-0481 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298308 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0350 | DELUGE SKID TEST/MAINT - HBBA-A-0350 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 25 | REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | A | DKHB-0481 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298308 | 6M DELUGE SKID TEST/MAINT - HBBA-A-0350 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2024-01-15 | 2023-12-30 | 30 | REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | A | DKHB-0481 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400308605 | 1Y EMERGENCY GENERATOR INSPECTION | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 | W19-W20 | 2024-04-08 | 2024-04-13 | 2024-04-08 | 2024-03-16 | 2024-02-15 | 20 | REL | APPR OPND | HB /D /05/HBDE-A-1710 | GENERATOR PACKAGE |  | D | DKHB-0494 | MMR | DK50 | MR0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400308605 | 1Y EMERGENCY GENERATOR INSPECTION | EMERGENCY GENERATOR INSPECTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 6 | 0 | W19-W20 | 2024-04-08 | 2024-04-13 | 2024-04-09 | 2024-03-16 | 2024-02-15 | 30 | REL | APPR OPND | HB /D /05/HBDE-A-1710 | GENERATOR PACKAGE |  | D | DKHB-0494 | MMR | DK50 | MR0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400308605 | 1Y EMERGENCY GENERATOR INSPECTION | EMERGENCY GENERATOR INSPECTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 10 | 0 | W19-W20 | 2024-04-08 | 2024-04-13 | 2024-04-10 | 2024-03-16 | 2024-02-15 | 40 | REL | APPR OPND | HB /D /05/HBDE-A-1710 | GENERATOR PACKAGE |  | D | DKHB-0494 | MMR | DK50 | MR0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400308605 | 1Y EMERGENCY GENERATOR INSPECTION | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 | W19-W20 | 2024-04-08 | 2024-04-13 | 2024-04-12 | 2024-03-16 | 2024-02-15 | 50 | REL | APPR OPND | HB /D /05/HBDE-A-1710 | GENERATOR PACKAGE |  | D | DKHB-0494 | MMR | DK50 | MR0014 | PROK
0 | A | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400321318 | 1Y FIRE EXTINGUISHER SERVICING HDB | 1Y FIRE EXTINGUISHER SERVICING HDB | REL PRT NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 24 | 0 | W17-W18 | 2024-05-01 | 2024-05-06 | 2024-05-01 | 2024-05-08 | 2024-04-08 | 10 | REL | APPR OPND | HD /A /02/FIRE-FIGHTING-EQUIPMENT | FIRE FIGHTING EQUIPMENT |  | A | DKHD-0015 | MMS | DK60 | MS0033 | PROK
2024-W15-16 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400322705 | 3M LIFE-SAVING & SAFETY EQ. CHECK-HBA | LIFE-SAVING & SAFETY EQ. CHECK-HBA | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-16 | 2024-05-06 | 10 | REL | APPR OPND | HB /A /02/LIFE-SAVING-EQUIPMENT | LIFE SAVING EQUIPMENT |  | A | DKHB-0452 | MMS | DK50 | MS0044 |  | 2024-04-11
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400322716 | 3M SAFETY SHOWER AND LIFE VESTS HDA/B/C | SAFETY SHOWER AND LIFE VESTS HDA/B/C | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 10 | 0 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-25 | 2024-05-21 | 2024-05-11 | 10 | REL | APPR OPND | HD /A /02/LIFE-SAVING-EQUIPMENT | LIFE SAVING EQUIPMENT |  | A | DKHD-0013 | MMS | DK60 | MS0043 | PROK
0 | A | HDAGEN2 | WPM | MTN-TELE | MTN-TELE | 2400322722 | 1Y DETECTOR, FUNCTIONTEST, HDAF-A-1602 | DETECTOR, FUNCTIONTEST, HDAF-A-1602 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 8 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-05-17 | 2024-04-17 | 10 | REL | APPR OPND | HD /A /03/FZ-247-LVL-4-TURBO-GEN-A-1602 | FIRE ZONE 247 LEVEL 4 TURBO GEN A-1602 |  | D | DKHD-0287 | MIN | DK60 | IN0073
0 | A | HDAGEN2 | WPM | MTN-TELE | MTN-INST | 2400322722 | 1Y DETECTOR, FUNCTIONTEST, HDAF-A-1602 | DETECTOR, FUNCTIONTEST, HDAF-A-1602 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 8 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-27 | 2024-05-17 | 2024-04-17 | 20 | REL | APPR OPND | HD /A /03/FZ-247-LVL-4-TURBO-GEN-A-1602 | FIRE ZONE 247 LEVEL 4 TURBO GEN A-1602 |  | D | DKHD-0287 | MIN | DK60 | IN0073
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325381 | 1Y EMERGENCY LIGHT TEST LEVEL 0 HDA | PERSONAL ISOLATION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-05-23 | 2024-04-23 | 10 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-0 | EMERGENCY LIGHTS LEVEL 0 |  | C | DKHD-0061 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325381 | 1Y EMERGENCY LIGHT TEST LEVEL 0 HDA | EMERGENCY LIGHT TEST LEVEL 0 HDA | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-05-23 | 2024-04-23 | 20 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-0 | EMERGENCY LIGHTS LEVEL 0 |  | C | DKHD-0061 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325381 | 1Y EMERGENCY LIGHT TEST LEVEL 0 HDA | EMERGENCY LIGHT TEST LEVEL 0 HDA | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 11 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-05-23 | 2024-04-23 | 30 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-0 | EMERGENCY LIGHTS LEVEL 0 |  | C | DKHD-0061 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325381 | 1Y EMERGENCY LIGHT TEST LEVEL 0 HDA | PERSONAL DE-ISOLATION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-28 | 2024-05-23 | 2024-04-23 | 40 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-0 | EMERGENCY LIGHTS LEVEL 0 |  | C | DKHD-0061 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325382 | 1Y EMERGENCY LIGHTS LEVEL 2 TEST HDA | PERSONAL ISOLATION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-05-23 | 2024-04-23 | 10 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-2 | EMERGENCY LIGHTS LEVEL 2 |  | C | DKHD-0064 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325382 | 1Y EMERGENCY LIGHTS LEVEL 2 TEST HDA | EMERGENCY LIGHTS LEVEL 2 TEST HDA | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-05-23 | 2024-04-23 | 20 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-2 | EMERGENCY LIGHTS LEVEL 2 |  | C | DKHD-0064 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325382 | 1Y EMERGENCY LIGHTS LEVEL 2 TEST HDA | EMERGENCY LIGHTS LEVEL 2 TEST HDA | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 12 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-05-23 | 2024-04-23 | 30 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-2 | EMERGENCY LIGHTS LEVEL 2 |  | C | DKHD-0064 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325382 | 1Y EMERGENCY LIGHTS LEVEL 2 TEST HDA | PERSONAL DE-ISOLATION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-29 | 2024-05-23 | 2024-04-23 | 40 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-2 | EMERGENCY LIGHTS LEVEL 2 |  | C | DKHD-0064 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325383 | 1Y EMERGENCY LIGHTS TEST LEVEL 3 HDA | PERSONAL ISOLATION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-05-23 | 2024-04-23 | 10 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-3 | EMERGENCY LIGHTS LEVEL 3 |  | C | DKHD-0065 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325383 | 1Y EMERGENCY LIGHTS TEST LEVEL 3 HDA | EMERGENCY LIGHTS TEST LEVEL 3 HDA | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-05-23 | 2024-04-23 | 20 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-3 | EMERGENCY LIGHTS LEVEL 3 |  | C | DKHD-0065 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325383 | 1Y EMERGENCY LIGHTS TEST LEVEL 3 HDA | EMERGENCY LIGHTS TEST LEVEL 3 HDA | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 12 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-05-23 | 2024-04-23 | 30 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-3 | EMERGENCY LIGHTS LEVEL 3 |  | C | DKHD-0065 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325383 | 1Y EMERGENCY LIGHTS TEST LEVEL 3 HDA | PERSONAL DE-ISOLATION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-29 | 2024-05-23 | 2024-04-23 | 40 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-3 | EMERGENCY LIGHTS LEVEL 3 |  | C | DKHD-0065 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325384 | 1Y EMERGENCY LIGHTS LEVEL 5 TEST HDA | PERSONAL ISOLATION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-05-23 | 2024-04-23 | 10 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-5 | EMERGENCY LIGHTS |  | C | DKHD-0067 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325384 | 1Y EMERGENCY LIGHTS LEVEL 5 TEST HDA | EMERGENCY LIGHTS LEVEL 5 TEST HDA | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-05-23 | 2024-04-23 | 20 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-5 | EMERGENCY LIGHTS |  | C | DKHD-0067 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325384 | 1Y EMERGENCY LIGHTS LEVEL 5 TEST HDA | EMERGENCY LIGHTS LEVEL 5 TEST HDA | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 12 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-05-23 | 2024-04-23 | 30 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-5 | EMERGENCY LIGHTS |  | C | DKHD-0067 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325384 | 1Y EMERGENCY LIGHTS LEVEL 5 TEST HDA | PERSONAL DE-ISOLATION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-28 | 2024-05-23 | 2024-04-23 | 40 | REL | APPR OPND | HD /A /62/EMERGENCY-LIGHTS-LEVEL-5 | EMERGENCY LIGHTS |  | C | DKHD-0067 | MEL | DK60 | EL0043
2024-W17-18 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325791 | 3M FW PUMP PACKAGE MAINT HBCM-A-0332 | FW PUMP PACKAGE MAINT HBCM-A-0332 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-05-23 | 2024-05-24 | 2024-05-23 | 2024-06-02 | 2024-05-23 | 10 | REL | APPR OPND | HB /C /01/HBCM-A-0332 | FIREWATER PUMP PACKAGE |  | C | DKHB-0061 | MMS | DK50 | MS0014 |  | 2024-04-22
2024-W15-16 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325792 | 3M FW PUMP PACKAGE MAINT HBCM-A-0331 | FW PUMP PACKAGE MAINT HBCM-A-0331 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-05-23 | 2024-05-24 | 2024-05-23 | 2024-06-02 | 2024-05-23 | 10 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | C | DKHB-0064 | MMS | DK50 | MS0014 |  | 2024-04-08
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400325793 | 6M FW PUMP/MOTOR MAINT HBDB-A-0352 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-12 | 2024-05-14 | 2024-05-12 | 2024-05-28 | 2024-05-12 | 10 | REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | C | DKHB-0092 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400325793 | 6M FW PUMP/MOTOR MAINT HBDB-A-0352 | FW PUMP/MOTOR MAINT HBDB-A-0352 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-12 | 2024-05-14 | 2024-05-12 | 2024-05-28 | 2024-05-12 | 20 | REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | C | DKHB-0092 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325793 | 6M FW PUMP/MOTOR MAINT HBDB-A-0352 | FW PUMP/MOTOR MAINT HBDB-A-0352 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2024-05-12 | 2024-05-14 | 2024-05-13 | 2024-05-28 | 2024-05-12 | 30 | REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | C | DKHB-0092 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400325793 | 6M FW PUMP/MOTOR MAINT HBDB-A-0352 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-12 | 2024-05-14 | 2024-05-14 | 2024-05-28 | 2024-05-12 | 40 | REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | C | DKHB-0092 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400325796 | 6M FW PUMP/MOTOR MAINT HBDB-A-0362 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-12 | 2024-05-14 | 2024-05-12 | 2024-05-28 | 2024-05-12 | 10 | REL | APPR OPND | HB /D /01/HBDB-A-0362 | FIREWATER PUMP MODULE |  | C | DKHB-0114 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400325796 | 6M FW PUMP/MOTOR MAINT HBDB-A-0362 | FW PUMP/MOTOR MAINT HBDB-A-0362 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-12 | 2024-05-14 | 2024-05-12 | 2024-05-28 | 2024-05-12 | 20 | REL | APPR OPND | HB /D /01/HBDB-A-0362 | FIREWATER PUMP MODULE |  | C | DKHB-0114 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325796 | 6M FW PUMP/MOTOR MAINT HBDB-A-0362 | FW PUMP/MOTOR MAINT HBDB-A-0362 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2024-05-12 | 2024-05-14 | 2024-05-13 | 2024-05-28 | 2024-05-12 | 30 | REL | APPR OPND | HB /D /01/HBDB-A-0362 | FIREWATER PUMP MODULE |  | C | DKHB-0114 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400325796 | 6M FW PUMP/MOTOR MAINT HBDB-A-0362 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-12 | 2024-05-14 | 2024-05-14 | 2024-05-28 | 2024-05-12 | 40 | REL | APPR OPND | HB /D /01/HBDB-A-0362 | FIREWATER PUMP MODULE |  | C | DKHB-0114 | MMS | DK50 | MS0014
2024-W15-16 | A | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400325799 | 3M FW HOSEREEL/HYDRANT/MONIT MAINT-HBD | FW HOSEREEL/HYDRANT/MONIT MAINT-HBD | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 5 | 0 |  | 2024-05-18 | 2024-05-19 | 2024-05-18 | 2024-05-28 | 2024-05-18 | 10 | REL | APPR OPND | HB /D /01/FW-HOSEREELS | FIREWATER HOSE REELS |  | A | DKHB-0207 | MMS | DK50 | MS0014 |  | 2024-04-08
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400325801 | 3M EMERGENCY GEN. FUNC TEST-HBCM-A-1731 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2024-05-28 | 2024-05-18 | 10 | REL | APPR OPND | HB /C /05/HBCM-A-1731 | EMERGENCY GENERATOR |  | D | DKHB-0490 | MMR | DK50 | MR0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325801 | 3M EMERGENCY GEN. FUNC TEST-HBCM-A-1731 | EMERGENCY GEN. FUNC TEST-HBCM-A-1731 | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2024-05-28 | 2024-05-18 | 30 | REL | APPR OPND | HB /C /05/HBCM-A-1731 | EMERGENCY GENERATOR |  | D | DKHB-0490 | MMR | DK50 | MR0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400325801 | 3M EMERGENCY GEN. FUNC TEST-HBCM-A-1731 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-23 | 2024-05-28 | 2024-05-18 | 40 | REL | APPR OPND | HB /C /05/HBCM-A-1731 | EMERGENCY GENERATOR |  | D | DKHB-0490 | MMR | DK50 | MR0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400325802 | 3M EMERGENCY GEN. FUNC TEST-HBCM-A-1732 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-18 | 2024-05-19 | 2024-05-18 | 2024-05-28 | 2024-05-18 | 10 | REL | APPR OPND | HB /C /05/HBCM-A-1732 | EMERGENCY GENERATOR |  | D | DKHB-0492 | MMR | DK50 | MR0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325802 | 3M EMERGENCY GEN. FUNC TEST-HBCM-A-1732 | EMERGENCY GEN. FUNC TEST-HBCM-A-1732 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-18 | 2024-05-19 | 2024-05-18 | 2024-05-28 | 2024-05-18 | 20 | REL | APPR OPND | HB /C /05/HBCM-A-1732 | EMERGENCY GENERATOR |  | D | DKHB-0492 | MMR | DK50 | MR0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400325802 | 3M EMERGENCY GEN. FUNC TEST-HBCM-A-1732 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-18 | 2024-05-19 | 2024-05-19 | 2024-05-28 | 2024-05-18 | 30 | REL | APPR OPND | HB /C /05/HBCM-A-1732 | EMERGENCY GENERATOR |  | D | DKHB-0492 | MMR | DK50 | MR0014
2026-W13-14 | A | NOSD | WPM | MTN-TURB | PRODTECH | 2400328645 | 1Y W MIST SKID HBDC-A-0456 FOR A-1650 | ISOLATION/DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-06-01 | 2024-05-02 | 10 | REL | APPR OPND | HB /D /01/HBDC-A-0456 | WATER MIST CABINET (FOR A-1650) |  | D | DKHB-0087 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-TURB | MTN-MECH | 2400328645 | 1Y W MIST SKID HBDC-A-0456 FOR A-1650 | W MIST SKID MAINT HBDC-A-0456 FOR A-1650 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-06-01 | 2024-05-02 | 20 | REL | APPR OPND | HB /D /01/HBDC-A-0456 | WATER MIST CABINET (FOR A-1650) |  | D | DKHB-0087 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-TURB | MTN-INST | 2400328645 | 1Y W MIST SKID HBDC-A-0456 FOR A-1650 | W MIST SKID MAINT HBDC-A-0456 FOR A-1650 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 2024-06-01 | 2024-05-02 | 30 | REL | APPR OPND | HB /D /01/HBDC-A-0456 | WATER MIST CABINET (FOR A-1650) |  | D | DKHB-0087 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-TURB | MTN-ELEC | 2400328645 | 1Y W MIST SKID HBDC-A-0456 FOR A-1650 | W MIST SKID MAINT HBDC-A-0456 FOR A-1650 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 2024-06-01 | 2024-05-02 | 40 | REL | APPR OPND | HB /D /01/HBDC-A-0456 | WATER MIST CABINET (FOR A-1650) |  | D | DKHB-0087 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400328646 | 1Y W MIST SKID HBDB-A-0451 FOR A-0352 | ISOLATION/DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-06-01 | 2024-05-02 | 10 | REL | APPR OPND | HB /D /01/HBDB-A-0451 | WATER MIST CABINET (FOR A-0352) |  | D | DKHB-0196 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400328646 | 1Y W MIST SKID HBDB-A-0451 FOR A-0352 | W MIST SKID MAINT HBDB-A-0451 FOR A-0352 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-06-01 | 2024-05-02 | 20 | REL | APPR OPND | HB /D /01/HBDB-A-0451 | WATER MIST CABINET (FOR A-0352) |  | D | DKHB-0196 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400328646 | 1Y W MIST SKID HBDB-A-0451 FOR A-0352 | W MIST SKID MAINT HBDB-A-0451 FOR A-0352 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 2024-06-01 | 2024-05-02 | 30 | REL | APPR OPND | HB /D /01/HBDB-A-0451 | WATER MIST CABINET (FOR A-0352) |  | D | DKHB-0196 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400328646 | 1Y W MIST SKID HBDB-A-0451 FOR A-0352 | W MIST SKID MAINT HBDB-A-0451 FOR A-0352 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 2024-06-01 | 2024-05-02 | 40 | REL | APPR OPND | HB /D /01/HBDB-A-0451 | WATER MIST CABINET (FOR A-0352) |  | D | DKHB-0196 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400328647 | 1Y W MIST SKID HBDB-A-0452 FOR A-0362 | ISOLATION/DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-06-01 | 2024-05-02 | 10 | REL | APPR OPND | HB /D /01/HBDB-A-0452 | WATER MIST CABINET (FOR A-0362) |  | D | DKHB-0197 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400328647 | 1Y W MIST SKID HBDB-A-0452 FOR A-0362 | W MIST SKID MAINT HBDB-A-0452 FOR A-0362 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-06-01 | 2024-05-02 | 20 | REL | APPR OPND | HB /D /01/HBDB-A-0452 | WATER MIST CABINET (FOR A-0362) |  | D | DKHB-0197 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400328647 | 1Y W MIST SKID HBDB-A-0452 FOR A-0362 | W MIST SKID MAINT HBDB-A-0452 FOR A-0362 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 2024-06-01 | 2024-05-02 | 30 | REL | APPR OPND | HB /D /01/HBDB-A-0452 | WATER MIST CABINET (FOR A-0362) |  | D | DKHB-0197 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400328647 | 1Y W MIST SKID HBDB-A-0452 FOR A-0362 | W MIST SKID MAINT HBDB-A-0452 FOR A-0362 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 2024-06-01 | 2024-05-02 | 40 | REL | APPR OPND | HB /D /01/HBDB-A-0452 | WATER MIST CABINET (FOR A-0362) |  | D | DKHB-0197 | MMS | DK50 | MS0034
2024-W23-24 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400328744 | 6M LIFE-SAVING & SAFETY EQ. CHECK-HBB | LIFE-SAVING & SAFETY EQ. CHECK-HBB | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-06-09 | 2024-05-24 | 10 | REL | APPR OPND | HB /B /02/LIFE-SAVING-EQUIPMENT | LIFE SAVING EQUIPMENT |  | A | DKHB-0018 | MMS | DK50 | MS0044 | PROK | 2024-05-21
2026-W13-14 | A | NOSD | WPM | MTN-INST | PRODTECH | 2400328747 | 1Y SYS 10 & 55 ESD INSTRUMENT MAINT-HBA | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 17 | 0 |  | 2024-05-08 | 2024-05-29 | 2024-05-08 | 2024-06-07 | 2024-05-08 | 10 | REL | APPR OPND | HB /A /10/HC-EXTRACTION-WELLS | HC EXTRACTION WELLS |  | C | DKHB-0243 | MIN | DK50 | IN0064
2026-W13-14 | A | NOSD | WPM | MTN-INST | MTN-INST | 2400328747 | 1Y SYS 10 & 55 ESD INSTRUMENT MAINT-HBA | SYS 10 & 55 ESD INSTRUMENT MAINT-HBA | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 66 | 0 |  | 2024-05-08 | 2024-05-29 | 2024-05-12 | 2024-06-07 | 2024-05-08 | 20 | REL | APPR OPND | HB /A /10/HC-EXTRACTION-WELLS | HC EXTRACTION WELLS |  | C | DKHB-0243 | MIN | DK50 | IN0064
2026-W13-14 | A | NOSD | WPM | MTN-INST | PRODTECH | 2400328747 | 1Y SYS 10 & 55 ESD INSTRUMENT MAINT-HBA | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 17 | 0 |  | 2024-05-08 | 2024-05-29 | 2024-05-25 | 2024-06-07 | 2024-05-08 | 30 | REL | APPR OPND | HB /A /10/HC-EXTRACTION-WELLS | HC EXTRACTION WELLS |  | C | DKHB-0243 | MIN | DK50 | IN0064
2026-W13-14 | A | NE | WPM | MTN-ELEC | PRODTECH | 2400329561 | 1Y FG HEATING & DISTR EQUIP MAINT-HBD | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-14 | 2024-05-19 | 2024-05-14 | 2024-06-13 | 2024-05-14 | 10 | REL | APPR OPND | HB /D /70/FUEL-GAS-DISTRIBUTION | FUEL GAS DISTRIBUTION |  | F | DKHB-0088 | MEL | DK50 | EL0084
2026-W13-14 | A | NE | WPM | MTN-ELEC | MTN-TURB | 2400329561 | 1Y FG HEATING & DISTR EQUIP MAINT-HBD | FG HEATING & DISTR INST MAINT-HBD | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 23 | 0 |  | 2024-05-14 | 2024-05-19 | 2024-05-14 | 2024-06-13 | 2024-05-14 | 20 | REL | APPR OPND | HB /D /70/FUEL-GAS-DISTRIBUTION | FUEL GAS DISTRIBUTION |  | F | DKHB-0088 | MEL | DK50 | EL0084
2026-W13-14 | A | NE | WPM | MTN-ELEC | PRODTECH | 2400329561 | 1Y FG HEATING & DISTR EQUIP MAINT-HBD | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-14 | 2024-05-19 | 2024-05-19 | 2024-06-13 | 2024-05-14 | 30 | REL | APPR OPND | HB /D /70/FUEL-GAS-DISTRIBUTION | FUEL GAS DISTRIBUTION |  | F | DKHB-0088 | MEL | DK50 | EL0084
2024-W15-16 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329565 | 3M LIFE-SAVING & SAFETY EQ. CHECK-HBC | LIFE-SAVING & SAFETY EQ. CHECK-HBC | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2.5 | 0 |  | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-12 | 2024-06-02 | 10 | REL | APPR OPND | HB /C /02/LIFE-SAVING-EQUIPMENT | LIFE SAVING EQUIPMENT |  | A | DKHB-0453 | MMS | DK50 | MS0044 | PROK | 2024-04-10
0 | A | NOSD | WPM | MTN-ELEC | MTN-SCAF | 2400329579 | 1Y NAVIGATION LIGHT INSPECTION HDA/B/C | SCAFFOLD FOR DK.HD.015.HDBC-SL-15030 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 54 | 0 |  | 2024-05-13 | 2024-05-21 | 2024-05-13 | 2024-06-12 | 2024-05-13 | 10 | REL | APPR OPND | HD /B /64/NAVAIDS | NAVAIDS |  | A | DKHD-0116 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400329579 | 1Y NAVIGATION LIGHT INSPECTION HDA/B/C | PERSONAL ISOLATION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-13 | 2024-05-21 | 2024-05-18 | 2024-06-12 | 2024-05-13 | 20 | REL | APPR OPND | HD /B /64/NAVAIDS | NAVAIDS |  | A | DKHD-0116 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-TELE | 2400329579 | 1Y NAVIGATION LIGHT INSPECTION HDA/B/C | NAVIGATION LIGHT INSPECTION HDA/B/C | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-05-13 | 2024-05-21 | 2024-05-18 | 2024-06-12 | 2024-05-13 | 30 | REL | APPR OPND | HD /B /64/NAVAIDS | NAVAIDS |  | A | DKHD-0116 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400329579 | 1Y NAVIGATION LIGHT INSPECTION HDA/B/C | NAVIGATION LIGHT BATTERY PACK HDA | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-13 | 2024-05-21 | 2024-05-20 | 2024-06-12 | 2024-05-13 | 40 | REL | APPR OPND | HD /B /64/NAVAIDS | NAVAIDS |  | A | DKHD-0116 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400329579 | 1Y NAVIGATION LIGHT INSPECTION HDA/B/C | PERSONAL DE-ISOLATION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-13 | 2024-05-21 | 2024-05-20 | 2024-06-12 | 2024-05-13 | 50 | REL | APPR OPND | HD /B /64/NAVAIDS | NAVAIDS |  | A | DKHD-0116 | MEL | DK60 | EL0043
0 | A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400329580 | 1Y EXTERNAL COM INSPECTION HDA/B/C | EXTERNAL COM INSPECTION & TEST HDA/B/C | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 14 | 0 |  | 2024-05-14 | 2024-05-16 | 2024-05-14 | 2024-06-13 | 2024-05-14 | 10 | REL | APPR OPND | HD /A /08/UHF-RADIO-SYSTEM-WITH-ANTENNA | UHF RADIO SYSTEM WITH ANTENNA |  | A | DKHD-0121 | MIN | DK60 | IN0093
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400329582 | 3M EMERGENCY GENSET MAINTENANCE HDB | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-12 | 2024-06-13 | 2024-06-12 | 2024-06-22 | 2024-06-12 | 10 | REL | APPR OPND | HD /B /05/EMERGENCY-POWER-GENERATORS | EMERGENCY-GENERATOR |  | A | DKHD-0320 | MMR | DK60 | MR0013
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329582 | 3M EMERGENCY GENSET MAINTENANCE HDB | HDB EMERGENCY GENSET MAINTENANCE | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2024-06-12 | 2024-06-13 | 2024-06-12 | 2024-06-22 | 2024-06-12 | 20 | REL | APPR OPND | HD /B /05/EMERGENCY-POWER-GENERATORS | EMERGENCY-GENERATOR |  | A | DKHD-0320 | MMR | DK60 | MR0013
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400329582 | 3M EMERGENCY GENSET MAINTENANCE HDB | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-12 | 2024-06-13 | 2024-06-13 | 2024-06-22 | 2024-06-12 | 30 | REL | APPR OPND | HD /B /05/EMERGENCY-POWER-GENERATORS | EMERGENCY-GENERATOR |  | A | DKHD-0320 | MMR | DK60 | MR0013
2024-W15-16 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400330058 | 6M FW HOSEREEL/HYDRANT/MONIT MAINT-HBA | FW HOSEREEL/HYDRANT/MONIT MAINT-HBA | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 10.5 | 0 |  | 2024-06-08 | 2024-06-10 | 2024-06-08 | 2024-06-24 | 2024-06-08 | 10 | REL | APPR OPND | HB /A /01/FW-HOSEREELS | FIREWATER HOSEREELS |  | A | DKHB-0203 | MMS | DK50 | MS0014 |  | 2024-04-08
2024-W15-16 | A | NOSD | WPM | MTN-INST | MTN-TELE | 2400330059 | 1Y MODULE ENTRY LIGHTS MAINT - HBC | MODULE ENTRY LIGHTS MAINT - HBC | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 18 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-06-29 | 2024-05-30 | 10 | REL | APPR OPND | HB /C /03/VISUAL-AUDIBLE-ALARM | VISUAL AND AUDIBLE ALARMS |  | C | DKHB-0259 | MIN | DK50 | IN0074 |  | 2024-04-08
2024-W15-16 | A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400330060 | 1Y FIRE AND GAS CONT PANELS MAINT - HBA | FIRE AND GAS CONT PANELS MAINT - HBA | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-31 | 2024-05-31 | 2024-05-31 | 2024-06-30 | 2024-05-31 | 20 | REL | APPR OPND | HB /A /03/FIRE-GAS-CONTROL-PANELS | FIRE AND GAS CONTROL PANELS |  | C | DKHB-0369 | MIN | DK50 | IN0024 |  | 2024-04-10
0 | A | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400330062 | 3M FWAT HOSEREEL MONITORS HYDRANTS HDAF | FWAT HOSEREEL MONITORS HYDRANTS HDA | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 6 | 0 | W25-W26 | 2024-06-20 | 2024-06-21 | 2024-06-20 | 2024-06-30 | 2024-06-20 | 10 | REL | APPR OPND | HD /A /01/FW-HOSEREELS | FIREWATER HOSEREELS |  | A | DKHD-0173 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400330064 | 3M FIREWATER PUMP PACKAGE HDBD-A-0301 | FIREWATER PUMP PACKAGE HDBD-A-0301 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | 2024-06-24 | 2024-06-14 | 10 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | A | DKHD-0177 | MMS | DK60 | MS0013
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400333183 | 1Y CLOSED DRAIN DISPOSAL MAINT-HBA | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-01 | 2024-06-04 | 2024-06-01 | 2024-07-01 | 2024-06-01 | 10 | REL | APPR OPND | HB /A /28/DRAIN-DISPOSAL | DRAIN DISPOSAL |  | C | DKHB-0040 | MMS | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400333183 | 1Y CLOSED DRAIN DISPOSAL MAINT-HBA | CLOSED DRAIN DISPOSAL MAINT-HBA | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-01 | 2024-06-04 | 2024-06-01 | 2024-07-01 | 2024-06-01 | 20 | REL | APPR OPND | HB /A /28/DRAIN-DISPOSAL | DRAIN DISPOSAL |  | C | DKHB-0040 | MMS | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400333183 | 1Y CLOSED DRAIN DISPOSAL MAINT-HBA | CLOSED DRAIN DISPOSAL MAINT-HBA | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-06-01 | 2024-06-04 | 2024-06-02 | 2024-07-01 | 2024-06-01 | 30 | REL | APPR OPND | HB /A /28/DRAIN-DISPOSAL | DRAIN DISPOSAL |  | C | DKHB-0040 | MMS | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400333183 | 1Y CLOSED DRAIN DISPOSAL MAINT-HBA | CLOSED DRAIN DISPOSAL MAINT-HBA | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-06-01 | 2024-06-04 | 2024-06-02 | 2024-07-01 | 2024-06-01 | 40 | REL | APPR OPND | HB /A /28/DRAIN-DISPOSAL | DRAIN DISPOSAL |  | C | DKHB-0040 | MMS | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400333183 | 1Y CLOSED DRAIN DISPOSAL MAINT-HBA | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-01 | 2024-06-04 | 2024-06-04 | 2024-07-01 | 2024-06-01 | 50 | REL | APPR OPND | HB /A /28/DRAIN-DISPOSAL | DRAIN DISPOSAL |  | C | DKHB-0040 | MMS | DK50 | MR0054
2024-W15-16 | A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400333187 | 1Y RACK-UHF/VHF RAD-WAVE MAP TEST-HBD | RACK-UHF/VHF RAD-WAVE MAP TEST-HBD | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 9 | 0 |  | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-07-05 | 2024-06-05 | 10 | REL | APPR OPND | HB /D /08/TELECOMS-RACKS-PANELS | TELECOMS RACKS PANELS |  | C | DKHB-0180 | MIN | DK50 | IN0094 |  | 2024-04-12
2026-W13-14 | A | NOSD | WPM | MTN-INST | PRODTECH | 2400333188 | 1Y SYS-37 INSTRUMENT/VALVES MAINT - HBA | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-07 | 2024-06-14 | 2024-06-07 | 2024-07-07 | 2024-06-07 | 10 | REL | APPR OPND | HB /A /37/INSTRUMENTS | INSTRUMENTS |  | A | DKHB-0215 | MIN | DK50 | IN0064
2026-W13-14 | A | NOSD | WPM | MTN-INST | MTN-INST | 2400333188 | 1Y SYS-37 INSTRUMENT/VALVES MAINT - HBA | SYS-37 INSTRUMENT/VALVES MAINT - HBA | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 30 | 0 |  | 2024-06-07 | 2024-06-14 | 2024-06-07 | 2024-07-07 | 2024-06-07 | 20 | REL | APPR OPND | HB /A /37/INSTRUMENTS | INSTRUMENTS |  | A | DKHB-0215 | MIN | DK50 | IN0064
2026-W13-14 | A | NOSD | WPM | MTN-INST | PRODTECH | 2400333188 | 1Y SYS-37 INSTRUMENT/VALVES MAINT - HBA | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-07 | 2024-06-14 | 2024-06-14 | 2024-07-07 | 2024-06-07 | 30 | REL | APPR OPND | HB /A /37/INSTRUMENTS | INSTRUMENTS |  | A | DKHB-0215 | MIN | DK50 | IN0064
2024-W15-16 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400333189 | 6M LIFE-SAVING & SAFETY EQ. CHECK-HBD | LIFE-SAVING & SAFETY EQ. CHECK-HBD | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-06-15 | 2024-06-16 | 2024-06-15 | 2024-07-01 | 2024-06-15 | 10 | REL | APPR OPND | HB /D /02/LIFE-SAVING-EQUIPMENT | LIFE SAVING EQUIPMENT |  | A | DKHB-0454 | MMS | DK50 | MS0044 | PROK | 2024-04-08
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334581 | 1Y HYD.CYCL. INST/VLV MAINT-HBDB-A-5070 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-20 | 2024-06-23 | 2024-06-20 | 2024-07-20 | 2024-06-20 | 10 | REL | APPR OPND | HB /D /27/HBDB-A-5070 | HYDROCYCLONE SKID (3 X 50%) |  | A | DKHB-0052 | MMS | DK50 | MS0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334581 | 1Y HYD.CYCL. INST/VLV MAINT-HBDB-A-5070 | HYD.CYCL. INST/VLV MAINT-HBDB-A-5070 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-06-20 | 2024-06-23 | 2024-06-20 | 2024-07-20 | 2024-06-20 | 20 | REL | APPR OPND | HB /D /27/HBDB-A-5070 | HYDROCYCLONE SKID (3 X 50%) |  | A | DKHB-0052 | MMS | DK50 | MS0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334581 | 1Y HYD.CYCL. INST/VLV MAINT-HBDB-A-5070 | HYD.CYCL. INST/VLV MAINT-HBDB-A-5070 | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-20 | 2024-06-23 | 2024-06-22 | 2024-07-20 | 2024-06-20 | 30 | REL | APPR OPND | HB /D /27/HBDB-A-5070 | HYDROCYCLONE SKID (3 X 50%) |  | A | DKHB-0052 | MMS | DK50 | MS0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334581 | 1Y HYD.CYCL. INST/VLV MAINT-HBDB-A-5070 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-20 | 2024-06-23 | 2024-06-22 | 2024-07-20 | 2024-06-20 | 40 | REL | APPR OPND | HB /D /27/HBDB-A-5070 | HYDROCYCLONE SKID (3 X 50%) |  | A | DKHB-0052 | MMS | DK50 | MS0054
0 | A | HBDIGF1 | WPM | MTN-MECH | PRODTECH | 2400334603 | 1Y SDV & BDV VALVES SEPERATION SYS HDA | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-18 | 2024-06-22 | 2024-06-18 | 2024-07-18 | 2024-06-18 | 10 | REL | APPR OPND | HD /A /11 | SLUG CATCHER, MAIN/TEST SEP & METERING |  | F | DKHD-0034 | MMS | DK60 | MS0053
0 | A | HBDIGF1 | WPM | MTN-MECH | MTN-MECH | 2400334603 | 1Y SDV & BDV VALVES SEPERATION SYS HDA | VALVE FUNCTION TESTING HDA | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-06-18 | 2024-06-22 | 2024-06-18 | 2024-07-18 | 2024-06-18 | 20 | REL | APPR OPND | HD /A /11 | SLUG CATCHER, MAIN/TEST SEP & METERING |  | F | DKHD-0034 | MMS | DK60 | MS0053
0 | A | HBDIGF1 | WPM | MTN-MECH | PRODTECH | 2400334603 | 1Y SDV & BDV VALVES SEPERATION SYS HDA | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-18 | 2024-06-22 | 2024-06-21 | 2024-07-18 | 2024-06-18 | 30 | REL | APPR OPND | HD /A /11 | SLUG CATCHER, MAIN/TEST SEP & METERING |  | F | DKHD-0034 | MMS | DK60 | MS0053
0 | A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400335701 | 18M GAS DETECTORS HDB | IR/CAT GAS DETECTOR CHECK | REL NMAT PRC SETC | APPR SECE AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-06-23 | 2024-06-24 | 2024-06-23 | 2024-07-23 | 2024-06-23 | 10 | REL | APPR OPND | HD /B /03/FGS-DETECTORS | FLAME, HEAT, GAS, SMOKE DETECTORS - HDB |  | B | DKHD-7205 | MIN | DK60 | IN0073
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | PRODTECH | 2400205781 | 1Y SDV/BDV INSP/FUNC TEST HBA-10-11-12 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-18 | 2024-04-11 | 2022-07-07 | 2022-06-07 | 10 | REL | APPR OPND | HB /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0115 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | MTN-MECH | 2400205781 | 1Y SDV/BDV INSP/FUNC TEST HBA-10-11-12 | SDV/BDV INSP/FUNC TEST HBA-10-11-12 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 16 | 0 | W15-W16 | 2024-04-11 | 2024-04-18 | 2024-04-11 | 2022-07-07 | 2022-06-07 | 20 | REL | APPR OPND | HB /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0115 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | MTN-INST | 2400205781 | 1Y SDV/BDV INSP/FUNC TEST HBA-10-11-12 | SDV/BDV INST ASSIST HBA-SYST-10-11-12 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 16 | 0 | W15-W16 | 2024-04-11 | 2024-04-18 | 2024-04-14 | 2022-07-07 | 2022-06-07 | 30 | REL | APPR OPND | HB /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0115 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | PRODTECH | 2400205781 | 1Y SDV/BDV INSP/FUNC TEST HBA-10-11-12 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-18 | 2024-04-17 | 2022-07-07 | 2022-06-07 | 40 | REL | APPR OPND | HB /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0115 | MMS | DK50 | MS0054
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211327 | 4Y 24 VDC N-DP FUNC TEST HBAA-DP-1815 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 10 | REL | APPR OPND | HB /A /06/HBAA-DP-1815 | DISTRIBUTION PANEL 24VDC |  | C | DKHB-0414 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211327 | 4Y 24 VDC N-DP FUNC TEST HBAA-DP-1815 | 24 VDC N-DP FUNC TEST HBAA-DP-1815 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 5 | 0 | W25-26 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 20 | REL | APPR OPND | HB /A /06/HBAA-DP-1815 | DISTRIBUTION PANEL 24VDC |  | C | DKHB-0414 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211327 | 4Y 24 VDC N-DP FUNC TEST HBAA-DP-1815 | 24 VDC N-DP FUNC TEST HBAA-DP-1815 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W25-26 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 30 | REL | APPR OPND | HB /A /06/HBAA-DP-1815 | DISTRIBUTION PANEL 24VDC |  | C | DKHB-0414 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211327 | 4Y 24 VDC N-DP FUNC TEST HBAA-DP-1815 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-11-01 | 2022-08-20 | 40 | REL | APPR OPND | HB /A /06/HBAA-DP-1815 | DISTRIBUTION PANEL 24VDC |  | C | DKHB-0414 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211330 | 4Y 24VDC UPS-SWB FUNC TEST HBAA-N-1802 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W25-26 | 2024-05-03 | 2024-05-06 | 2024-05-03 | 2022-10-01 | 2022-07-20 | 10 | REL | APPR OPND | HB /A /06/HBAA-N-1802 | 24 V DC SWITCHBOARD |  | C | DKHB-0412 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211330 | 4Y 24VDC UPS-SWB FUNC TEST HBAA-N-1802 | 24VDC UPS-SWB FUNC TEST HBAA-N-1802 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 30 | 0 | W25-26 | 2024-05-03 | 2024-05-06 | 2024-05-03 | 2022-10-01 | 2022-07-20 | 20 | REL | APPR OPND | HB /A /06/HBAA-N-1802 | 24 V DC SWITCHBOARD |  | C | DKHB-0412 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211330 | 4Y 24VDC UPS-SWB FUNC TEST HBAA-N-1802 | 24VDC UPS-SWB FUNC TEST HBAA-N-1802 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 5 | 0 | W25-26 | 2024-05-03 | 2024-05-06 | 2024-05-05 | 2022-10-01 | 2022-07-20 | 30 | REL | APPR OPND | HB /A /06/HBAA-N-1802 | 24 V DC SWITCHBOARD |  | C | DKHB-0412 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211330 | 4Y 24VDC UPS-SWB FUNC TEST HBAA-N-1802 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W25-26 | 2024-05-03 | 2024-05-06 | 2024-05-06 | 2022-10-01 | 2022-07-20 | 40 | REL | APPR OPND | HB /A /06/HBAA-N-1802 | 24 V DC SWITCHBOARD |  | C | DKHB-0412 | MEL | DK50 | EL0024
2024-W37-38 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211388 | 4Y 400V E-SWB INSP HBCA-N-1840 | ISOLATION BY PRODUCTION | REL MANC PPRT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-10-01 | 2022-07-20 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840 | EMERGENCY SWBD. (RENAMED A&B) |  | C | DKHB-0410 | MEL | DK50 | EL0024
2024-W37-38 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211388 | 4Y 400V E-SWB INSP HBCA-N-1840 | 400V E-SWB INSP HBCA-N-1840 | REL MANC PPRT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 14 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-10-01 | 2022-07-20 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840 | EMERGENCY SWBD. (RENAMED A&B) |  | C | DKHB-0410 | MEL | DK50 | EL0024
2024-W37-38 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211388 | 4Y 400V E-SWB INSP HBCA-N-1840 | 400V E-SWB INSP HBCA-N-1840 | REL MANC PPRT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-10-01 | 2022-07-20 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840 | EMERGENCY SWBD. (RENAMED A&B) |  | C | DKHB-0410 | MEL | DK50 | EL0024
2024-W37-38 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211388 | 4Y 400V E-SWB INSP HBCA-N-1840 | DE-ISOLATION BY PRODUCTION | REL MANC PPRT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-10-01 | 2022-07-20 | 40 | REL | APPR OPND | HB /C /05/HBCA-N-1840 | EMERGENCY SWBD. (RENAMED A&B) |  | C | DKHB-0410 | MEL | DK50 | EL0024
2026-W13-14 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211400 | 4Y 400V E-SWB INSP HBDD-N-1855 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-09-01 | 2022-06-20 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855 | 400V EMERGENCY SWITCHBOARD |  | C | DKHB-0415 | MEL | DK50 | EL0024
2026-W13-14 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211400 | 4Y 400V E-SWB INSP HBDD-N-1855 | 400V E-SWB INSP HBDD-N-1855 | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 18 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-09-01 | 2022-06-20 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855 | 400V EMERGENCY SWITCHBOARD |  | C | DKHB-0415 | MEL | DK50 | EL0024
2026-W13-14 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211400 | 4Y 400V E-SWB INSP HBDD-N-1855 | 400V E-SWB INSP HBDD-N-1855 | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-09-01 | 2022-06-20 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855 | 400V EMERGENCY SWITCHBOARD |  | C | DKHB-0415 | MEL | DK50 | EL0024
2026-W13-14 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211400 | 4Y 400V E-SWB INSP HBDD-N-1855 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-09-01 | 2022-06-20 | 40 | REL | APPR OPND | HB /D /05/HBDD-N-1855 | 400V EMERGENCY SWITCHBOARD |  | C | DKHB-0415 | MEL | DK50 | EL0024
0 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211430 | 4Y 400V E-SWB HDBE-N-1841-04/STAT.SWITCH | ISOLATION BY PRODUCTION | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W13-W14 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2022-08-01 | 2022-05-20 | 10 | PCNF REL | APPR OPND | HD /B /05/HDBE-N-1841 | ELECTRICAL SWITCHBOARD |  | A | DKHD-0255 | MEL | DK60 | EL0023
0 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211430 | 4Y 400V E-SWB HDBE-N-1841-04/STAT.SWITCH | STATIC SWITCH INSPECTION | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | W13-W14 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2022-08-01 | 2022-05-20 | 40 | PCNF REL | APPR OPND | HD /B /05/HDBE-N-1841 | ELECTRICAL SWITCHBOARD |  | A | DKHD-0255 | MEL | DK60 | EL0023
0 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211430 | 4Y 400V E-SWB HDBE-N-1841-04/STAT.SWITCH | DE-ISOLATION BY PRODUCTION | REL PCNF MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W13-W14 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2022-08-01 | 2022-05-20 | 50 | PCNF REL | APPR OPND | HD /B /05/HDBE-N-1841 | ELECTRICAL SWITCHBOARD |  | A | DKHD-0255 | MEL | DK60 | EL0023
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211535 | 4Y 400V UPS-DP FUNC TEST HBB | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 10 | REL | APPR OPND | HB /B /06/UPS-BOARDS-400V | 400V UPS DISTRIBUTION BOARDS |  | C | DKHB-0473 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211535 | 4Y 400V UPS-DP FUNC TEST HBB | 400V UPS-DP FUNC TEST HBB | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 19 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 20 | REL | APPR OPND | HB /B /06/UPS-BOARDS-400V | 400V UPS DISTRIBUTION BOARDS |  | C | DKHB-0473 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211535 | 4Y 400V UPS-DP FUNC TEST HBB | 400V UPS-DP FUNC TEST HBB | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-13 | 2022-11-01 | 2022-08-20 | 30 | REL | APPR OPND | HB /B /06/UPS-BOARDS-400V | 400V UPS DISTRIBUTION BOARDS |  | C | DKHB-0473 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211535 | 4Y 400V UPS-DP FUNC TEST HBB | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-14 | 2022-11-01 | 2022-08-20 | 40 | REL | APPR OPND | HB /B /06/UPS-BOARDS-400V | 400V UPS DISTRIBUTION BOARDS |  | C | DKHB-0473 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211536 | 4Y 400V UPS-DP FUNC TEST HBDD-DP-1960 | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-06-03 | 2024-06-05 | 2024-06-03 | 2022-11-01 | 2022-08-20 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960 | 400/230VAC UPS DISTRIBUTION PANEL |  | C | DKHB-0437 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211536 | 4Y 400V UPS-DP FUNC TEST HBDD-DP-1960 | 400V UPS-DP FUNC TEST HBDD-DP-1960 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 17 | 0 | W25-26 | 2024-06-03 | 2024-06-05 | 2024-06-03 | 2022-11-01 | 2022-08-20 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960 | 400/230VAC UPS DISTRIBUTION PANEL |  | C | DKHB-0437 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211536 | 4Y 400V UPS-DP FUNC TEST HBDD-DP-1960 | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-06-03 | 2024-06-05 | 2024-06-05 | 2022-11-01 | 2022-08-20 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960 | 400/230VAC UPS DISTRIBUTION PANEL |  | C | DKHB-0437 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211537 | 4Y 400V UPS-DP FUNC TEST HBDC-DP-1965 | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 10 | REL | APPR OPND | HB /D /06/HBDC-DP-1965 | 400/230VAC UPS SUB DISTRIBUTION PANEL A |  | C | DKHB-0434 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211537 | 4Y 400V UPS-DP FUNC TEST HBDC-DP-1965 | 400V UPS-DP FUNC TEST HBDC-DP-1965 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 17 | 0 | W25-26 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 20 | REL | APPR OPND | HB /D /06/HBDC-DP-1965 | 400/230VAC UPS SUB DISTRIBUTION PANEL A |  | C | DKHB-0434 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211537 | 4Y 400V UPS-DP FUNC TEST HBDC-DP-1965 | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-03-11 | 2024-03-13 | 2024-03-13 | 2022-11-01 | 2022-08-20 | 30 | REL | APPR OPND | HB /D /06/HBDC-DP-1965 | 400/230VAC UPS SUB DISTRIBUTION PANEL A |  | C | DKHB-0434 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211538 | 4Y 400V UPS-DP FUNC TEST HBDC-DP-1966 | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 10 | REL | APPR OPND | HB /D /06/HBDC-DP-1966 | 400/230VAC UPS SUB DISTRIBUTION PANEL B |  | C | DKHB-0435 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211538 | 4Y 400V UPS-DP FUNC TEST HBDC-DP-1966 | 400V UPS-DP FUNC TEST HBDC-DP-1966 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 17 | 0 | W25-26 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 20 | REL | APPR OPND | HB /D /06/HBDC-DP-1966 | 400/230VAC UPS SUB DISTRIBUTION PANEL B |  | C | DKHB-0435 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211538 | 4Y 400V UPS-DP FUNC TEST HBDC-DP-1966 | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-03-11 | 2024-03-13 | 2024-03-13 | 2022-11-01 | 2022-08-20 | 30 | REL | APPR OPND | HB /D /06/HBDC-DP-1966 | 400/230VAC UPS SUB DISTRIBUTION PANEL B |  | C | DKHB-0435 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211539 | 4Y 400V UPS-DP FUNC TEST HBDD-DP-1967 | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1967 | 400/230VAC UPS SUB DISTRIBUTION PANEL C |  | C | DKHB-0436 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211539 | 4Y 400V UPS-DP FUNC TEST HBDD-DP-1967 | 400V UPS-DP FUNC TEST HBDD-DP-1967 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 17 | 0 | W25-26 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1967 | 400/230VAC UPS SUB DISTRIBUTION PANEL C |  | C | DKHB-0436 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211539 | 4Y 400V UPS-DP FUNC TEST HBDD-DP-1967 | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-03-11 | 2024-03-13 | 2024-03-13 | 2022-11-01 | 2022-08-20 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1967 | 400/230VAC UPS SUB DISTRIBUTION PANEL C |  | C | DKHB-0436 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211540 | 4Y 400V UPS-DP FUNC TEST HBCA-DP-1920/21 | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 10 | REL | APPR OPND | HB /C /06/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | C | DKHB-0433 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211540 | 4Y 400V UPS-DP FUNC TEST HBCA-DP-1920/21 | 400V UPS-DP FUNC TEST HBCA-DP-1920/21 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 36 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 20 | REL | APPR OPND | HB /C /06/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | C | DKHB-0433 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211540 | 4Y 400V UPS-DP FUNC TEST HBCA-DP-1920/21 | 400V UPS-DP FUNC TEST HBCA-DP-1920/21 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-13 | 2022-11-01 | 2022-08-20 | 30 | REL | APPR OPND | HB /C /06/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | C | DKHB-0433 | MEL | DK50 | EL0024
2024-W25-26 | A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211540 | 4Y 400V UPS-DP FUNC TEST HBCA-DP-1920/21 | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-13 | 2022-11-01 | 2022-08-20 | 40 | REL | APPR OPND | HB /C /06/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | C | DKHB-0433 | MEL | DK50 | EL0024
0 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211551 | 4Y UPS-DP HDB | UPS-DP HDB INSPECTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 36 | 0 | W11-W12 | 2024-03-11 | 2024-03-16 | 2024-03-11 | 2022-11-01 | 2022-08-20 | 10 | REL | APPR OPND | HD /B /06/HDBE-DP-1924 | UPS POWER DISTRIBUTION BOARD |  | C | DKHD-0263 | MEL | DK60 | EL0023
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400211551 | 4Y UPS-DP HDB | UPS-DP HDB INSPECTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | W11-W12 | 2024-03-11 | 2024-03-16 | 2024-03-15 | 2022-11-01 | 2022-08-20 | 20 | REL | APPR OPND | HD /B /06/HDBE-DP-1924 | UPS POWER DISTRIBUTION BOARD |  | C | DKHD-0263 | MEL | DK60 | EL0023
2024-W47-48 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400211720 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0330 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W47-49 IOP 24/11-8/12-22 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-07-02 | 10 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0479 | MMS | DK50 | MS0014
2024-W47-48 | A | NOSD | WPM | MTN-MECH | VEN-ELEC | 2400211720 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0330 | DELUGE SKID HEATER CHECK - HBBA-A-0330 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W47-49 IOP 24/11-8/12-22 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-07-02 | 20 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0479 | MMS | DK50 | MS0014
2024-W47-48 | A | NOSD | WPM | MTN-MECH | VEN-INST | 2400211720 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0330 | DELUGE SKID TEST/MAINT - HBBA-A-0330 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W47-49 IOP 24/11-8/12-22 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-07-02 | 30 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0479 | MMS | DK50 | MS0014
2024-W47-48 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400211720 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0330 | DELUGE SKID TEST/MAINT - HBBA-A-0330 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W47-49 IOP 24/11-8/12-22 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-07-02 | 40 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0479 | MMS | DK50 | MS0014
2024-W47-48 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400211720 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0330 | DELUGE SKID VEND ASSIST - HBBA-A-0330 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W47-49 IOP 24/11-8/12-22 | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-08-01 | 2022-07-02 | 50 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0479 | MMS | DK50 | MS0014
2024-W47-48 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400211720 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0330 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W47-49 IOP 24/11-8/12-22 | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-08-01 | 2022-07-02 | 60 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0479 | MMS | DK50 | MS0014
2026-W13-14 | A | HBD-GLY | WPM | MTN-MECH | PRODTECH | 2400218592 | 3Y GLYCOL REG. TEST - HBDB-A-4160 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-23 | 2024-04-11 | 2022-12-11 | 2022-10-10 | 10 | REL | APPR OPND | HB /D /30/HBDB-A-4160 | GLYCOL REGENERATION PACKAGE |  | E | DKHB-0218 | MMR | DK50 | MR0134 | PROK
2026-W13-14 | A | HBD-GLY | WPM | MTN-MECH | MTN-ELEC | 2400218592 | 3Y GLYCOL REG. TEST - HBDB-A-4160 | GLYCOL REG. TEST - HBDB-A-4160 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 24 | 0 | W15-W16 | 2024-04-11 | 2024-04-23 | 2024-04-11 | 2022-12-11 | 2022-10-10 | 20 | REL | APPR OPND | HB /D /30/HBDB-A-4160 | GLYCOL REGENERATION PACKAGE |  | E | DKHB-0218 | MMR | DK50 | MR0134 | PROK
2026-W13-14 | A | HBD-GLY | WPM | MTN-MECH | MTN-MECH | 2400218592 | 3Y GLYCOL REG. TEST - HBDB-A-4160 | GLYCOL REG. TEST - HBDB-A-4160 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 49 | 0 | W15-W16 | 2024-04-11 | 2024-04-23 | 2024-04-13 | 2022-12-11 | 2022-10-10 | 30 | REL | APPR OPND | HB /D /30/HBDB-A-4160 | GLYCOL REGENERATION PACKAGE |  | E | DKHB-0218 | MMR | DK50 | MR0134 | PROK
2026-W13-14 | A | HBD-GLY | WPM | MTN-MECH | MTN-INST | 2400218592 | 3Y GLYCOL REG. TEST - HBDB-A-4160 | GLYCOL REG. TEST - HBDB-A-4160 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 43 | 0 | W15-W16 | 2024-04-11 | 2024-04-23 | 2024-04-18 | 2022-12-11 | 2022-10-10 | 40 | REL | APPR OPND | HB /D /30/HBDB-A-4160 | GLYCOL REGENERATION PACKAGE |  | E | DKHB-0218 | MMR | DK50 | MR0134 | PROK
2026-W13-14 | A | HBD-GLY | WPM | MTN-MECH | PRODTECH | 2400218592 | 3Y GLYCOL REG. TEST - HBDB-A-4160 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-23 | 2024-04-23 | 2022-12-11 | 2022-10-10 | 50 | REL | APPR OPND | HB /D /30/HBDB-A-4160 | GLYCOL REGENERATION PACKAGE |  | E | DKHB-0218 | MMR | DK50 | MR0134 | PROK
2026-W13-14 | A | HB-FLARE | WPM | MTN-MECH | PRODTECH | 2400221232 | 3Y FLARE PACKAGE MAINT - HBD | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2023-01-21 | 2022-11-20 | 10 | REL | APPR OPND | HB /D /36/FLARE-SYSTEM | FLARE SYSTEM | 99000119 | F | DKHB-0175 | MMS | DK50 | MR0144
2026-W13-14 | A | HB-FLARE | WPM | MTN-MECH | MTN-INST | 2400221232 | 3Y FLARE PACKAGE MAINT - HBD | FLARE PACKAGE MAINT - HBD | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2023-01-21 | 2022-11-20 | 20 | REL | APPR OPND | HB /D /36/FLARE-SYSTEM | FLARE SYSTEM | 99000119 | F | DKHB-0175 | MMS | DK50 | MR0144
2026-W13-14 | A | HB-FLARE | WPM | MTN-MECH | MTN-MECH | 2400221232 | 3Y FLARE PACKAGE MAINT - HBD | FLARE PACKAGE MAINT - HBD | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-07-01 | 2024-07-04 | 2024-07-02 | 2023-01-21 | 2022-11-20 | 30 | REL | APPR OPND | HB /D /36/FLARE-SYSTEM | FLARE SYSTEM | 99000119 | F | DKHB-0175 | MMS | DK50 | MR0144
2026-W13-14 | A | HB-FLARE | WPM | MTN-MECH | MTN-ELEC | 2400221232 | 3Y FLARE PACKAGE MAINT - HBD | FLARE PACKAGE MAINT - HBD | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-07-01 | 2024-07-04 | 2024-07-02 | 2023-01-21 | 2022-11-20 | 40 | REL | APPR OPND | HB /D /36/FLARE-SYSTEM | FLARE SYSTEM | 99000119 | F | DKHB-0175 | MMS | DK50 | MR0144
2026-W13-14 | A | HB-FLARE | WPM | MTN-MECH | PRODTECH | 2400221232 | 3Y FLARE PACKAGE MAINT - HBD | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-01 | 2024-07-04 | 2024-07-04 | 2023-01-21 | 2022-11-20 | 50 | REL | APPR OPND | HB /D /36/FLARE-SYSTEM | FLARE SYSTEM | 99000119 | F | DKHB-0175 | MMS | DK50 | MR0144
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263385 | 1Y DELUGE SKID TEST/MAINT - HBCM-A-0335 | ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 10 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0335 | DELUGE SKID |  | C | DKHB-0073 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263385 | 1Y DELUGE SKID TEST/MAINT - HBCM-A-0335 | DELUGE SKID TEST/MAINT - HBCM-A-0335 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 20 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0335 | DELUGE SKID |  | C | DKHB-0073 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263385 | 1Y DELUGE SKID TEST/MAINT - HBCM-A-0335 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 50 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0335 | DELUGE SKID |  | C | DKHB-0073 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263388 | 1Y HELI DELUGE SKID TEST-HBCM-A-0339 | ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 10 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0339 | DELUGE SKID AVIATION FUEL |  | C | DKHB-0127 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263388 | 1Y HELI DELUGE SKID TEST-HBCM-A-0339 | HELI DELUGE SKID TEST-HBCM-A-0339 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2.5 | 12 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 30 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0339 | DELUGE SKID AVIATION FUEL |  | C | DKHB-0127 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263388 | 1Y HELI DELUGE SKID TEST-HBCM-A-0339 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 50 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0339 | DELUGE SKID AVIATION FUEL |  | C | DKHB-0127 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263389 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0370 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | C | DKHB-0464 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263389 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0370 | DELUGE SKID HEATER CHECK - HBAA-A-0370 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | C | DKHB-0464 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263389 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0370 | DELUGE SKID TEST/MAINT - HBAA-A-0370 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | C | DKHB-0464 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263389 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0370 | DELUGE SKID TEST/MAINT - HBAA-A-0370 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | C | DKHB-0464 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400263389 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0370 | DELUGE SKID VEND ASSIST - HBAA-A-0370 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | C | DKHB-0464 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263389 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0370 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | C | DKHB-0464 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263390 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0371 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0465 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263390 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0371 | DELUGE SKID HEATER CHECK - HBAA-A-0371 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0465 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263390 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0371 | DELUGE SKID TEST/MAINT - HBAA-A-0371 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0465 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263390 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0371 | DELUGE SKID TEST/MAINT - HBAA-A-0371 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0465 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400263390 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0371 | DELUGE SKID VEND ASSIST - HBAA-A-0371 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0465 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263390 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0371 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0465 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263391 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0372 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0466 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263391 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0372 | DELUGE SKID HEATER CHECK - HBAA-A-0372 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0466 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263391 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0372 | DELUGE SKID TEST/MAINT - HBAA-A-0372 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0466 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263391 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0372 | DELUGE SKID TEST/MAINT - HBAA-A-0372 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0466 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400263391 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0372 | DELUGE SKID VEND ASSIST - HBAA-A-0372 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0466 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263391 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0372 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0466 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263392 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0373 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | C | DKHB-0467 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263392 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0373 | DELUGE SKID HEATER CHECK - HBAA-A-0373 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | C | DKHB-0467 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263392 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0373 | DELUGE SKID TEST/MAINT - HBAA-A-0373 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | C | DKHB-0467 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263392 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0373 | DELUGE SKID TEST/MAINT - HBAA-A-0373 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | C | DKHB-0467 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400263392 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0373 | DELUGE SKID VEND ASSIST - HBAA-A-0373 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | C | DKHB-0467 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263392 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0373 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | C | DKHB-0467 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263393 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0374 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | C | DKHB-0468 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263393 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0374 | DELUGE SKID HEATER CHECK - HBAA-A-0374 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | C | DKHB-0468 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263393 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0374 | DELUGE SKID TEST/MAINT - HBAA-A-0374 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | C | DKHB-0468 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263393 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0374 | DELUGE SKID TEST/MAINT - HBAA-A-0374 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | C | DKHB-0468 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400263393 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0374 | DELUGE SKID VEND ASSIST - HBAA-A-0374 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | C | DKHB-0468 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263393 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0374 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | C | DKHB-0468 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263394 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0375 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0469 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263394 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0375 | DELUGE SKID HEATER CHECK - HBAA-A-0375 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0469 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263394 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0375 | DELUGE SKID TEST/MAINT - HBAA-A-0375 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0469 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263394 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0375 | DELUGE SKID TEST/MAINT - HBAA-A-0375 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0469 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400263394 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0375 | DELUGE SKID VEND ASSIST - HBAA-A-0375 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0469 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263394 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0375 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0469 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263395 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0376 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0474 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263395 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0376 | DELUGE SKID HEATER CHECK - HBAA-A-0376 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0474 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263395 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0376 | DELUGE SKID TEST/MAINT - HBAA-A-0376 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0474 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263395 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0376 | DELUGE SKID TEST/MAINT - HBAA-A-0376 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-07-15 | 2023-06-15 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0474 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400263395 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0376 | DELUGE SKID VEND ASSIST - HBAA-A-0376 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0474 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263395 | 1Y DELUGE SKID TEST/MAINT - HBAA-A-0376 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2023-07-15 | 2023-06-15 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0474 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263396 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0310 | ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 10 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0476 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263396 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0310 | DELUGE SKID HEATER CHECK - HBBA-A-0310 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 20 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0476 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263396 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0310 | DELUGE SKID TEST/MAINT - HBBA-A-0310 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 30 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0476 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263396 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0310 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 60 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0476 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263397 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0320 | ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 10 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0477 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263397 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0320 | DELUGE SKID HEATER CHECK - HBBA-A-0320 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 20 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0477 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263397 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0320 | DELUGE SKID TEST/MAINT - HBBA-A-0320 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 30 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0477 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263397 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0320 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 60 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0477 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263399 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0340 | ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 10 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0480 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263399 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0340 | DELUGE SKID HEATER CHECK - HBBA-A-0340 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 20 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0480 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263399 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0340 | DELUGE SKID TEST/MAINT - HBBA-A-0340 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 30 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0480 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263399 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0340 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 60 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0480 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263400 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0350 | ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 10 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | C | DKHB-0481 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263400 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0350 | DELUGE SKID HEATER CHECK - HBBA-A-0350 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 20 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | C | DKHB-0481 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263400 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0350 | DELUGE SKID TEST/MAINT - HBBA-A-0350 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 30 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | C | DKHB-0481 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263400 | 1Y DELUGE SKID TEST/MAINT - HBBA-A-0350 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-07-15 | 2023-06-15 | 60 | PCNF REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | C | DKHB-0481 | MMS | DK50 | MS0014 | PROK
2026-W13-14 | A | NOSD | WPM | VEN-INSP | PRODTECH | 2400269576 | ILI-PIGGING-LAUNCHING_P4303_14"_HBA-HDA | PRODUCTION_PIG-LAUNCHING | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 20 | 0 |  | 2024-05-24 | 2024-05-31 | 2024-05-24 | 2024-12-31 | 2024-10-30 | 10 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A | DKPLILI15 | INP | DK50
2026-W13-14 | A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400269576 | ILI-PIGGING-LAUNCHING_P4303_14"_HBA-HDA | CONTRACTOR_PIG-LAUNCHING | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 48 | 0 |  | 2024-05-24 | 2024-05-31 | 2024-05-26 | 2024-12-31 | 2024-10-30 | 20 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A | DKPLILI15 | INP | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400274089 | 1Y GALLEY FIRE TEST HBCB-A-0437/38 | GALLEY FIRE TEST HBCB-A-0437/38 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-09-18 | 2023-08-19 | 10 | REL | APPR OPND | HB /C /02/HBCB-A-0437 | PACKAGE EQUIPMENT - POWER SKID |  | A | DKHB-0043 | MMS | DK50 | MS0044
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400274089 | 1Y GALLEY FIRE TEST HBCB-A-0437/38 | GALLEY FIRE TEST HBCB-A-0437/38 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-09-18 | 2023-08-19 | 20 | REL | APPR OPND | HB /C /02/HBCB-A-0437 | PACKAGE EQUIPMENT - POWER SKID |  | A | DKHB-0043 | MMS | DK50 | MS0044
2026-W13-14 | A | HBBPWELL | WPM | MTN-MECH | PRODTECH | 2400274712 | 1Y SDV/BDV INSP/FUNC TEST HBB-28-34-37 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-14 | 2024-04-11 | 2023-09-26 | 2023-08-27 | 10 | REL | APPR OPND | HB /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | C | DKHB-0075 | MMS | DK50 | MS0054
2026-W13-14 | A | HBBPWELL | WPM | MTN-MECH | MTN-MECH | 2400274712 | 1Y SDV/BDV INSP/FUNC TEST HBB-28-34-37 | SDV/BDV INSP/FUNC TEST HBB-28-34-37 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6 | 0 | W15-W16 | 2024-04-11 | 2024-04-14 | 2024-04-11 | 2023-09-26 | 2023-08-27 | 20 | REL | APPR OPND | HB /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | C | DKHB-0075 | MMS | DK50 | MS0054
2026-W13-14 | A | HBBPWELL | WPM | MTN-MECH | MTN-INST | 2400274712 | 1Y SDV/BDV INSP/FUNC TEST HBB-28-34-37 | SDV/BDV INST ASSIST HBB-SYST-28-34-37 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6 | 0 | W15-W16 | 2024-04-11 | 2024-04-14 | 2024-04-12 | 2023-09-26 | 2023-08-27 | 30 | REL | APPR OPND | HB /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | C | DKHB-0075 | MMS | DK50 | MS0054
2026-W13-14 | A | HBBPWELL | WPM | MTN-MECH | PRODTECH | 2400274712 | 1Y SDV/BDV INSP/FUNC TEST HBB-28-34-37 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-14 | 2024-04-13 | 2023-09-26 | 2023-08-27 | 40 | REL | APPR OPND | HB /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | C | DKHB-0075 | MMS | DK50 | MS0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284411 | PSV Calibration - HBAA-PSV-394210 | Isolation of PSV | REL CSER NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 10 | REL | APPR OPND | HB /A /75/HBAA-PSV-394210 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV034 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284411 | PSV Calibration - HBAA-PSV-394210 | Prod Assist (breaking containment) | REL CSER NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 20 | REL | APPR OPND | HB /A /75/HBAA-PSV-394210 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV034 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284411 | PSV Calibration - HBAA-PSV-394210 | Install re-certified PSV | REL CSER NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 30 | REL | APPR OPND | HB /A /75/HBAA-PSV-394210 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV034 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284411 | PSV Calibration - HBAA-PSV-394210 | De-isolation and leak test | REL CSER NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 40 | REL | APPR OPND | HB /A /75/HBAA-PSV-394210 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV034 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284411 | PSV Calibration - HBAA-PSV-394210 | Documentation & CNF WO | REL CSER NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 50 | REL | APPR OPND | HB /A /75/HBAA-PSV-394210 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV034 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284411 | PSV Calibration - HBAA-PSV-394210 | Check PSV flanges & alignment | REL CSER NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 60 | REL | APPR OPND | HB /A /75/HBAA-PSV-394210 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV034 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284412 | PSV Exchange - HBAA-PSV-394220 | Isolation of PSV | REL CSER NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 10 | REL | APPR OPND | HB /A /75/HBAA-PSV-394220 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV035 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284412 | PSV Exchange - HBAA-PSV-394220 | Prod Assist (breaking containment) | REL CSER NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 20 | REL | APPR OPND | HB /A /75/HBAA-PSV-394220 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV035 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284412 | PSV Exchange - HBAA-PSV-394220 | Install re-certified PSV | REL CSER NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 30 | REL | APPR OPND | HB /A /75/HBAA-PSV-394220 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV035 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284412 | PSV Exchange - HBAA-PSV-394220 | De-isolation and leak test | REL CSER NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 40 | REL | APPR OPND | HB /A /75/HBAA-PSV-394220 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV035 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284412 | PSV Exchange - HBAA-PSV-394220 | Documentation & CNF WO | REL CSER NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 50 | REL | APPR OPND | HB /A /75/HBAA-PSV-394220 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV035 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284412 | PSV Exchange - HBAA-PSV-394220 | Check PSV flanges & alignment | REL CSER NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 60 | REL | APPR OPND | HB /A /75/HBAA-PSV-394220 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV035 | MMS | DK50
2026-W13-14 | A | HBDHPSEP | WPM | MTN-MECH | PRODTECH | 2400293799 | 6M ESDV FUNC TEST HBAA-ESDV-38024 | ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-12 | 2024-04-11 | 2023-12-28 | 2023-12-12 | 10 | PCNF REL | APPR OPND | HB /A /12/HBAA-ESDV-38024 | EMERGENCY SHUTDOWN VALVE |  | A | DKHB-0011 | MMS | DK50 | MS0054
2026-W13-14 | A | HBDHPSEP | WPM | MTN-MECH | MTN-MECH | 2400293799 | 6M ESDV FUNC TEST HBAA-ESDV-38024 | ESDV FUNC TEST HBAA-ESDV-38024 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 2 | W15-W16 | 2024-04-11 | 2024-04-12 | 2024-04-11 | 2023-12-28 | 2023-12-12 | 20 | PCNF REL | APPR OPND | HB /A /12/HBAA-ESDV-38024 | EMERGENCY SHUTDOWN VALVE |  | A | DKHB-0011 | MMS | DK50 | MS0054
2026-W13-14 | A | HBDHPSEP | WPM | MTN-MECH | MTN-INST | 2400293799 | 6M ESDV FUNC TEST HBAA-ESDV-38024 | ESDV INST ASSIST HBAA-ESDV-38024 | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-11 | 2024-04-12 | 2024-04-11 | 2023-12-28 | 2023-12-12 | 30 | PCNF REL | APPR OPND | HB /A /12/HBAA-ESDV-38024 | EMERGENCY SHUTDOWN VALVE |  | A | DKHB-0011 | MMS | DK50 | MS0054
2026-W13-14 | A | HBDHPSEP | WPM | MTN-MECH | PRODTECH | 2400293799 | 6M ESDV FUNC TEST HBAA-ESDV-38024 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-12 | 2024-04-11 | 2023-12-28 | 2023-12-12 | 40 | PCNF REL | APPR OPND | HB /A /12/HBAA-ESDV-38024 | EMERGENCY SHUTDOWN VALVE |  | A | DKHB-0011 | MMS | DK50 | MS0054
2026-W13-14 | A | HB-FLARE | WPM | MTN-MECH | PRODTECH | 2400298295 | 1Y FLARE PACKAGE MAINT - HBD | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-28 | 2024-03-30 | 2024-03-28 | 2024-01-21 | 2023-12-22 | 10 | REL | APPR OPND | HB /D /36/FLARE-SYSTEM | FLARE SYSTEM |  | C | DKHB-0175 | MMR | DK50 | MR0144 | PROK
2026-W13-14 | A | HB-FLARE | WPM | MTN-MECH | MTN-INST | 2400298295 | 1Y FLARE PACKAGE MAINT - HBD | FLARE PACKAGE MAINT - HBD | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-03-28 | 2024-03-30 | 2024-03-28 | 2024-01-21 | 2023-12-22 | 20 | REL | APPR OPND | HB /D /36/FLARE-SYSTEM | FLARE SYSTEM |  | C | DKHB-0175 | MMR | DK50 | MR0144 | PROK
2026-W13-14 | A | HB-FLARE | WPM | MTN-MECH | MTN-MECH | 2400298295 | 1Y FLARE PACKAGE MAINT - HBD | FLARE PACKAGE MAINT - HBD | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-03-28 | 2024-03-30 | 2024-03-29 | 2024-01-21 | 2023-12-22 | 30 | REL | APPR OPND | HB /D /36/FLARE-SYSTEM | FLARE SYSTEM |  | C | DKHB-0175 | MMR | DK50 | MR0144 | PROK
2026-W13-14 | A | HB-FLARE | WPM | MTN-MECH | MTN-ELEC | 2400298295 | 1Y FLARE PACKAGE MAINT - HBD | FLARE PACKAGE MAINT - HBD | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-03-28 | 2024-03-30 | 2024-03-29 | 2024-01-21 | 2023-12-22 | 40 | REL | APPR OPND | HB /D /36/FLARE-SYSTEM | FLARE SYSTEM |  | C | DKHB-0175 | MMR | DK50 | MR0144 | PROK
2026-W13-14 | A | HB-FLARE | WPM | MTN-MECH | PRODTECH | 2400298295 | 1Y FLARE PACKAGE MAINT - HBD | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-28 | 2024-03-30 | 2024-03-30 | 2024-01-21 | 2023-12-22 | 50 | REL | APPR OPND | HB /D /36/FLARE-SYSTEM | FLARE SYSTEM |  | C | DKHB-0175 | MMR | DK50 | MR0144 | PROK
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307673 | 1Y UPS SYSTEM FUNCTION TEST HDBE-AE-192 | UPS SYSTEM FUNCTION TEST HDBE-AE-1920 | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-25 | 2024-03-05 | 2024-02-04 | 10 | REL | APPR OPND | HD /B /06/HDBE-AE-1920 | UPS SYSTEM FOR HDBE-DP-1924 |  | A | DKHD-0038 | MEL | DK60 | EL0033 | PROK
0 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307673 | 1Y UPS SYSTEM FUNCTION TEST HDBE-AE-192 | UPS SYSTEM FUNCTION TEST HDBE-AE-1920 | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 9 | 0 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-25 | 2024-03-05 | 2024-02-04 | 20 | REL | APPR OPND | HD /B /06/HDBE-AE-1920 | UPS SYSTEM FOR HDBE-DP-1924 |  | A | DKHD-0038 | MEL | DK60 | EL0033 | PROK
2024-W15-16 | A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400308690 | 6M_CRANE_INSPECTION_HBCO-A-6101 | 6M_INSPECTION_HBCO-A-6101 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 0 | 0 | W15-16 DK50-M-6370 | 2024-04-05 | 2024-04-06 | 2024-04-05 | 2024-05-16 | 2024-04-30 | 10 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKCRINSP032 | INP | DK50 |  |  | 2024-04-21
2024-W15-16 | A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400308690 | 6M_CRANE_INSPECTION_HBCO-A-6101 | 6M_INSPECTION_HBCO-A-6101_GVI | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 12 | 0 | W15-16 DK50-M-6370 | 2024-04-05 | 2024-04-06 | 2024-04-05 | 2024-05-16 | 2024-04-30 | 20 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKCRINSP032 | INP | DK50 |  |  | 2024-04-22
2026-W13-14 | A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400308691 | 6M_CRANE_INSPECTION_HBDE-A-6150 | 6M_INSPECTION_HBDE-A-6150 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 0 | 0 | W22 - DK50-M-6990 | 2024-05-17 | 2024-05-18 | 2024-05-17 | 2024-05-16 | 2024-04-30 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | C | DKCRINSP033 | INP | DK50
2026-W13-14 | A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400308691 | 6M_CRANE_INSPECTION_HBDE-A-6150 | 6M_INSPECTION_HBDE-A-6150_GVI | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 12 | 0 | W22 - DK50-M-6990 | 2024-05-17 | 2024-05-18 | 2024-05-17 | 2024-05-16 | 2024-04-30 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | C | DKCRINSP033 | INP | DK50
2024-W15-16 | A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400308692 | 1Y_CRANE_LOAD-TEST_INSP_HBCO-A-6101 | 1Y_LOADTEST_HBCO-A-6101 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 0 | 0 | W15-16 DK50-M-6370 | 2024-04-05 | 2024-04-09 | 2024-04-05 | 2024-05-16 | 2024-04-16 | 10 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKCRINSP082 | INP | DK50 |  |  | 2024-04-21
2024-W15-16 | A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400308692 | 1Y_CRANE_LOAD-TEST_INSP_HBCO-A-6101 | 1Y_LOADTEST_HBCO-A-6101_CVI BEFORE LT | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 36 | 0 | W15-16 DK50-M-6370 | 2024-04-05 | 2024-04-09 | 2024-04-05 | 2024-05-16 | 2024-04-16 | 20 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKCRINSP082 | INP | DK50 |  |  | 2024-04-22
2024-W15-16 | A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400308692 | 1Y_CRANE_LOAD-TEST_INSP_HBCO-A-6101 | 1Y_LOADTEST_HBCO-A-6101_LT WITNESS | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6 | 0 | W15-16 DK50-M-6370 | 2024-04-05 | 2024-04-09 | 2024-04-06 | 2024-05-16 | 2024-04-16 | 30 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKCRINSP082 | INP | DK50 |  |  | 2024-04-28
2024-W15-16 | A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400308692 | 1Y_CRANE_LOAD-TEST_INSP_HBCO-A-6101 | 1Y_LOADTEST_HBCO-A-6101_CVI AFTER LT | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 72 | 0 | W15-16 DK50-M-6370 | 2024-04-05 | 2024-04-09 | 2024-04-06 | 2024-05-16 | 2024-04-16 | 40 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKCRINSP082 | INP | DK50 |  |  | 2024-04-30
2024-W15-16 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309043 | 1Y 24VDC BATT AND CHAR MAINT HBB | 24VDC BATT AND CHAR MAINT HBB | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 10 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2024-03-19 | 2024-02-18 | 10 | REL | APPR OPND | HB /B /06/UPS-SYSTEM | UPS SYSTEM FOR HBBA-N-1922 |  | A | DKHB-0394 | MEL | DK50 | EL0034 | PROK | 2024-04-08
2024-W15-16 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309043 | 1Y 24VDC BATT AND CHAR MAINT HBB | 24VDC BATT AND CHAR MAINT HBB | REL MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-10 | 2024-03-19 | 2024-02-18 | 20 | REL | APPR OPND | HB /B /06/UPS-SYSTEM | UPS SYSTEM FOR HBBA-N-1922 |  | A | DKHB-0394 | MEL | DK50 | EL0034 | PROK | 2024-04-10
2026-W13-14 | A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309044 | 1Y 24VDC BATT & CHARG MAINT HBA | 24VDC BATT & CHARG MAINT HBA | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 22 | 0 |  | 2024-03-25 | 2024-03-28 | 2024-03-25 | 2024-03-19 | 2024-02-18 | 10 | REL | APPR OPND | HB /A /06/UPS-SYSTEM | UPS SYSTEM FOR HBAA-N-1802 |  | A | DKHB-0398 | MEL | DK50 | EL0034 | PROK
2026-W13-14 | A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309044 | 1Y 24VDC BATT & CHARG MAINT HBA | 24VDC BATT & CHARG MAINT HBA | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-03-25 | 2024-03-28 | 2024-03-27 | 2024-03-19 | 2024-02-18 | 20 | REL | APPR OPND | HB /A /06/UPS-SYSTEM | UPS SYSTEM FOR HBAA-N-1802 |  | A | DKHB-0398 | MEL | DK50 | EL0034 | PROK
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | PRODTECH | 2400314611 | 1Y SDV INSP/FUNC TEST HBD-SYST-76 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-13 | 2024-04-11 | 2024-04-03 | 2024-03-04 | 10 | REL | APPR OPND | HB /D /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0128 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | MTN-MECH | 2400314611 | 1Y SDV INSP/FUNC TEST HBD-SYST-76 | SDV INSP/FUNC TEST HBD-SYST-76 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | W15-W16 | 2024-04-11 | 2024-04-13 | 2024-04-11 | 2024-04-03 | 2024-03-04 | 20 | REL | APPR OPND | HB /D /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0128 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | MTN-INST | 2400314611 | 1Y SDV INSP/FUNC TEST HBD-SYST-76 | SDV INST ASSIST HBD-SYST-76 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | W15-W16 | 2024-04-11 | 2024-04-13 | 2024-04-12 | 2024-04-03 | 2024-03-04 | 30 | REL | APPR OPND | HB /D /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0128 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | PRODTECH | 2400314611 | 1Y SDV INSP/FUNC TEST HBD-SYST-76 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-11 | 2024-04-13 | 2024-04-13 | 2024-04-03 | 2024-03-04 | 40 | REL | APPR OPND | HB /D /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0128 | MMS | DK50 | MS0054
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400315190 | 6M ESDV PARTIAL STROKE HDCA-ESDV-38002 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W13-W14 | 2024-03-30 | 2024-03-31 | 2024-03-30 | 2024-04-15 | 2024-03-30 | 10 | REL | APPR OPND | HD /C /34/HDCA-ESDV-38002 | EMERGENCY SHUTDOWN VALVE |  | A | DKHD-0351 | MMS | DK60 | MS0053
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400315190 | 6M ESDV PARTIAL STROKE HDCA-ESDV-38002 | ESDV PARTIAL STROKE HDCA-ESDV-38002 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W13-W14 | 2024-03-30 | 2024-03-31 | 2024-03-30 | 2024-04-15 | 2024-03-30 | 20 | REL | APPR OPND | HD /C /34/HDCA-ESDV-38002 | EMERGENCY SHUTDOWN VALVE |  | A | DKHD-0351 | MMS | DK60 | MS0053
0 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400315190 | 6M ESDV PARTIAL STROKE HDCA-ESDV-38002 | ASSISTANCE TO MECHANICAL | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W13-W14 | 2024-03-30 | 2024-03-31 | 2024-03-30 | 2024-04-15 | 2024-03-30 | 30 | REL | APPR OPND | HD /C /34/HDCA-ESDV-38002 | EMERGENCY SHUTDOWN VALVE |  | A | DKHD-0351 | MMS | DK60 | MS0053
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400315190 | 6M ESDV PARTIAL STROKE HDCA-ESDV-38002 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W13-W14 | 2024-03-30 | 2024-03-31 | 2024-03-31 | 2024-04-15 | 2024-03-30 | 40 | REL | APPR OPND | HD /C /34/HDCA-ESDV-38002 | EMERGENCY SHUTDOWN VALVE |  | A | DKHD-0351 | MMS | DK60 | MS0053
0 | A | HDA-IPHP | WPM | MTN-MECH | PRODTECH | 2400316100 | 1Y ESDV LEAK TEST HDA HP GAS TRANSFER | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-04-05 | 2024-04-08 | 2024-04-05 | 2024-05-05 | 2024-04-05 | 10 | REL | APPR OPND | HD /A /34/ESDV | ESDV PRODUCED GAS TRANSFER |  | F | DKHD-0350 | MMS | DK60 | MS0053
0 | A | HDA-IPHP | WPM | MTN-MECH | MTN-MECH | 2400316100 | 1Y ESDV LEAK TEST HDA HP GAS TRANSFER | ESDV LEAK TEST HDA HP GAS TRANSFER | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-04-05 | 2024-04-08 | 2024-04-05 | 2024-05-05 | 2024-04-05 | 20 | REL | APPR OPND | HD /A /34/ESDV | ESDV PRODUCED GAS TRANSFER |  | F | DKHD-0350 | MMS | DK60 | MS0053
0 | A | HDA-IPHP | WPM | MTN-MECH | MTN-INST | 2400316100 | 1Y ESDV LEAK TEST HDA HP GAS TRANSFER | CALIBRATION CHECK & ASSIST TO MECHANICAL | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-04-05 | 2024-04-08 | 2024-04-06 | 2024-05-05 | 2024-04-05 | 30 | REL | APPR OPND | HD /A /34/ESDV | ESDV PRODUCED GAS TRANSFER |  | F | DKHD-0350 | MMS | DK60 | MS0053
0 | A | HDA-IPHP | WPM | MTN-MECH | PRODTECH | 2400316100 | 1Y ESDV LEAK TEST HDA HP GAS TRANSFER | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-04-05 | 2024-04-08 | 2024-04-07 | 2024-05-05 | 2024-04-05 | 40 | REL | APPR OPND | HD /A /34/ESDV | ESDV PRODUCED GAS TRANSFER |  | F | DKHD-0350 | MMS | DK60 | MS0053
2026-W13-14 | A | HNEPWELL | WPM | MTN-INST | MTN-SCAF | 2400321315 | 1Y HIPPS SYSTEM-FUNCTION TEST-HBA | SCAFFOLDING CONSTRUCT | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 15 | 0 |  | 2024-04-06 | 2024-04-15 | 2024-04-06 | 2024-05-06 | 2024-04-06 | 10 | REL | APPR OPND | HB /A /03/HIPS-SYSTEM | HIPS SYSTEM |  | F | DKHB-2034 | MIN | DK50 | IN0044
2026-W13-14 | A | HNEPWELL | WPM | MTN-INST | PRODTECH | 2400321315 | 1Y HIPPS SYSTEM-FUNCTION TEST-HBA | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-04-06 | 2024-04-15 | 2024-04-09 | 2024-05-06 | 2024-04-06 | 20 | REL | APPR OPND | HB /A /03/HIPS-SYSTEM | HIPS SYSTEM |  | F | DKHB-2034 | MIN | DK50 | IN0044
2026-W13-14 | A | HNEPWELL | WPM | MTN-INST | MTN-INST | 2400321315 | 1Y HIPPS SYSTEM-FUNCTION TEST-HBA | HIPPS SYSTEM-FUNCTION TEST-HBA | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-04-06 | 2024-04-15 | 2024-04-09 | 2024-05-06 | 2024-04-06 | 30 | REL | APPR OPND | HB /A /03/HIPS-SYSTEM | HIPS SYSTEM |  | F | DKHB-2034 | MIN | DK50 | IN0044
2026-W13-14 | A | HNEPWELL | WPM | MTN-INST | PRODTECH | 2400321315 | 1Y HIPPS SYSTEM-FUNCTION TEST-HBA | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-04-06 | 2024-04-15 | 2024-04-11 | 2024-05-06 | 2024-04-06 | 40 | REL | APPR OPND | HB /A /03/HIPS-SYSTEM | HIPS SYSTEM |  | F | DKHB-2034 | MIN | DK50 | IN0044
2026-W13-14 | A | HNEPWELL | WPM | MTN-INST | MTN-SCAF | 2400321315 | 1Y HIPPS SYSTEM-FUNCTION TEST-HBA | SCAFFOLDING DE-CONSTRUCT | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 15 | 0 |  | 2024-04-06 | 2024-04-15 | 2024-04-12 | 2024-05-06 | 2024-04-06 | 50 | REL | APPR OPND | HB /A /03/HIPS-SYSTEM | HIPS SYSTEM |  | F | DKHB-2034 | MIN | DK50 | IN0044
2026-W13-14 | A | HCAPWELL | WPM | MTN-MECH | PRODTECH | 2400325526 | 1Y ESDV LEAK TEST HBBA-ESDV-38201 | ESDV LEAK TEST HBBA-ESDV-38201 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2.5 | 0 | W15-W16 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2024-05-13 | 2024-04-13 | 10 | REL | APPR OPND | HB /B /23/HBBA-ESDV-38201 | EMERGENCY SHUTDOWN VALVE |  | C | DKHB-0662 | MMS | DK50 | MS0054
2026-W13-14 | A | HCAPWELL | WPM | MTN-MECH | PRODTECH | 2400325527 | 1Y ESDV LEAK TEST HBBA-ESDV-38301 | ESDV LEAK TEST HBBA-ESDV-38301 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2.5 | 0 |  | 2024-04-13 | 2024-04-13 | 2024-04-13 | 2024-05-13 | 2024-04-13 | 10 | REL | APPR OPND | HB /B /34/HBBA-ESDV-38301 | EMERGENCY SHUTDOWN VALVE |  | C | DKHB-0663 | MMS | DK50 | MS0054
2026-W13-14 | A | HCAPWELL | WPM | MTN-MECH | PRODTECH | 2400325528 | 1Y ESDV LEAK TEST HBBA-ESDV-38413 | ESDV LEAK TEST HBBA-ESDV-38413 | REL PRT MANC NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6 | 0 | W15-W16 | 2024-04-11 | 2024-04-12 | 2024-04-11 | 2024-05-13 | 2024-04-13 | 10 | REL | APPR OPND | HB /B /34/HBBA-ESDV-38413 | EMERGENCY SHUTDOWN VALVE |  | C | DKHB-0664 | MMS | DK50 | MS0054
2026-W13-14 | A | HBHPGAS | WPM | MTN-MECH | PRODTECH | 2400325552 | 1Y ESDV LEAK TEST HBAA-ESDV-38041 | ESDV LEAK TEST HBAA-ESDV-38041 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3.5 | 0 |  | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-10-06 | 2024-09-06 | 10 | REL | APPR OPND | HB /A /34/HBAA-ESDV-38041 | EMERGENCY SHUTDOWN VALVE |  | F | DKHB-0661 | MMS | DK50 | MS0054
0 | A | HDA-TFO | WPM | MTN-MECH | MTN-MECH | 2400325553 | 1Y ESDV LEAK TEST HDCA-ESDV-38002 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-11-04 | 2024-10-05 | 10 | REL | APPR OPND | HD /C /34/HDCA-ESDV-38002 | EMERGENCY SHUTDOWN VALVE |  | F | DKHD-0351 | MMS | DK60 | MS0053
0 | A | HDA-TFO | WPM | MTN-MECH | MTN-MECH | 2400325553 | 1Y ESDV LEAK TEST HDCA-ESDV-38002 | ESDV LEAK TEST HDCA-ESDV-38002 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-11-04 | 2024-10-05 | 20 | REL | APPR OPND | HD /C /34/HDCA-ESDV-38002 | EMERGENCY SHUTDOWN VALVE |  | F | DKHD-0351 | MMS | DK60 | MS0053
0 | A | HDA-TFO | WPM | MTN-MECH | MTN-INST | 2400325553 | 1Y ESDV LEAK TEST HDCA-ESDV-38002 | CALIBRATION CHECK & ASSIST TO MECHANICAL | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-11-04 | 2024-10-05 | 30 | REL | APPR OPND | HD /C /34/HDCA-ESDV-38002 | EMERGENCY SHUTDOWN VALVE |  | F | DKHD-0351 | MMS | DK60 | MS0053
0 | A | HDA-TFO | WPM | MTN-MECH | PRODTECH | 2400325553 | 1Y ESDV LEAK TEST HDCA-ESDV-38002 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-10-05 | 2024-10-06 | 2024-10-06 | 2024-11-04 | 2024-10-05 | 40 | REL | APPR OPND | HD /C /34/HDCA-ESDV-38002 | EMERGENCY SHUTDOWN VALVE |  | F | DKHD-0351 | MMS | DK60 | MS0053
2026-W13-14 | A | NOSD | WPM | MTN-TURB | PRODTECH | 2400328649 | 1Y W MIST SKID HBDC-A-0457 FOR A-1660 | ISOLATION/DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-06-01 | 2024-05-02 | 10 | REL | APPR OPND | HB /D /01/HBDC-A-0457 | WATER MIST CABINET (FOR A-1660) |  | D | DKHB-0209 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-TURB | MTN-MECH | 2400328649 | 1Y W MIST SKID HBDC-A-0457 FOR A-1660 | W MIST SKID MAINT HBDC-A-0457 FOR A-1660 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-06-01 | 2024-05-02 | 20 | REL | APPR OPND | HB /D /01/HBDC-A-0457 | WATER MIST CABINET (FOR A-1660) |  | D | DKHB-0209 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-TURB | MTN-INST | 2400328649 | 1Y W MIST SKID HBDC-A-0457 FOR A-1660 | W MIST SKID MAINT HBDC-A-0457 FOR A-1660 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 2024-06-01 | 2024-05-02 | 30 | REL | APPR OPND | HB /D /01/HBDC-A-0457 | WATER MIST CABINET (FOR A-1660) |  | D | DKHB-0209 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-TURB | MTN-ELEC | 2400328649 | 1Y W MIST SKID HBDC-A-0457 FOR A-1660 | W MIST SKID MAINT HBDC-A-0457 FOR A-1660 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 2024-06-01 | 2024-05-02 | 40 | REL | APPR OPND | HB /D /01/HBDC-A-0457 | WATER MIST CABINET (FOR A-1660) |  | D | DKHB-0209 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400328650 | 1Y W MIST SKID HBDE-A-0458 FOR A-1710 | ISOLATION/DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-06-01 | 2024-05-02 | 10 | REL | APPR OPND | HB /D /01/HBDE-A-0458 | WATERMIST PACKAGE |  | F | DKHB-0214 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400328650 | 1Y W MIST SKID HBDE-A-0458 FOR A-1710 | W MIST SKID MAINT HBDE-A-0458 FOR A-1710 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-06-01 | 2024-05-02 | 20 | REL | APPR OPND | HB /D /01/HBDE-A-0458 | WATERMIST PACKAGE |  | F | DKHB-0214 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400328650 | 1Y W MIST SKID HBDE-A-0458 FOR A-1710 | W MIST SKID MAINT HBDE-A-0458 FOR A-1710 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 2024-06-01 | 2024-05-02 | 30 | REL | APPR OPND | HB /D /01/HBDE-A-0458 | WATERMIST PACKAGE |  | F | DKHB-0214 | MMS | DK50 | MS0034
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400328650 | 1Y W MIST SKID HBDE-A-0458 FOR A-1710 | W MIST SKID MAINT HBDE-A-0458 FOR A-1710 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 2024-06-01 | 2024-05-02 | 40 | REL | APPR OPND | HB /D /01/HBDE-A-0458 | WATERMIST PACKAGE |  | F | DKHB-0214 | MMS | DK50 | MS0034
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | PRODTECH | 2400333184 | 1Y SDV/BDV INSP/FUNC TEST HBA-34-37-75 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-07 | 2024-06-09 | 2024-06-07 | 2024-07-07 | 2024-06-07 | 10 | REL | APPR OPND | HB /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | C | DKHB-0086 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | MTN-MECH | 2400333184 | 1Y SDV/BDV INSP/FUNC TEST HBA-34-37-75 | SDV/BDV INSP/FUNC TEST HBA-34-37-75 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-07 | 2024-06-09 | 2024-06-07 | 2024-07-07 | 2024-06-07 | 20 | REL | APPR OPND | HB /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | C | DKHB-0086 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | MTN-INST | 2400333184 | 1Y SDV/BDV INSP/FUNC TEST HBA-34-37-75 | SDV/BDV INST ASSIST HBA-SYST-34-37-75 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-07 | 2024-06-09 | 2024-06-08 | 2024-07-07 | 2024-06-07 | 30 | REL | APPR OPND | HB /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | C | DKHB-0086 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | PRODTECH | 2400333184 | 1Y SDV/BDV INSP/FUNC TEST HBA-34-37-75 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-07 | 2024-06-09 | 2024-06-09 | 2024-07-07 | 2024-06-07 | 40 | REL | APPR OPND | HB /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | C | DKHB-0086 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | PRODTECH | 2400333186 | 1Y SDV/BDV INSP/FUNC TEST HBA-10-11-12 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-07 | 2024-06-14 | 2024-06-07 | 2024-07-07 | 2024-06-07 | 10 | REL | APPR OPND | HB /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0115 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | MTN-MECH | 2400333186 | 1Y SDV/BDV INSP/FUNC TEST HBA-10-11-12 | SDV/BDV INSP/FUNC TEST HBA-10-11-12 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 16 | 0 |  | 2024-06-07 | 2024-06-14 | 2024-06-07 | 2024-07-07 | 2024-06-07 | 20 | REL | APPR OPND | HB /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0115 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | MTN-INST | 2400333186 | 1Y SDV/BDV INSP/FUNC TEST HBA-10-11-12 | SDV/BDV INST ASSIST HBA-SYST-10-11-12 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 16 | 0 |  | 2024-06-07 | 2024-06-14 | 2024-06-10 | 2024-07-07 | 2024-06-07 | 30 | REL | APPR OPND | HB /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0115 | MMS | DK50 | MS0054
2026-W13-14 | A | HBAPWELL | WPM | MTN-MECH | PRODTECH | 2400333186 | 1Y SDV/BDV INSP/FUNC TEST HBA-10-11-12 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-07 | 2024-06-14 | 2024-06-13 | 2024-07-07 | 2024-06-07 | 40 | REL | APPR OPND | HB /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | F | DKHB-0115 | MMS | DK50 | MS0054
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400333194 | 2Y DELUGE SKID HDBM-A-0304 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-16 | 2024-05-20 | 2024-05-16 | 2024-07-01 | 2024-05-16 | 10 | REL | APPR OPND | HD /B /01/HDBM-A-0304 | DELUGE VALVE SKID |  | B | DKHD-0170 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400333194 | 2Y DELUGE SKID HDBM-A-0304 | DELUGE SKID, WET TEST, HDBM-A-0304 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-05-16 | 2024-05-20 | 2024-05-16 | 2024-07-01 | 2024-05-16 | 20 | REL | APPR OPND | HD /B /01/HDBM-A-0304 | DELUGE VALVE SKID |  | B | DKHD-0170 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400333194 | 2Y DELUGE SKID HDBM-A-0304 | VENDOR SUPPORT | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-05-16 | 2024-05-20 | 2024-05-18 | 2024-07-01 | 2024-05-16 | 30 | REL | APPR OPND | HD /B /01/HDBM-A-0304 | DELUGE VALVE SKID |  | B | DKHD-0170 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400333194 | 2Y DELUGE SKID HDBM-A-0304 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-16 | 2024-05-20 | 2024-05-20 | 2024-07-01 | 2024-05-16 | 40 | REL | APPR OPND | HD /B /01/HDBM-A-0304 | DELUGE VALVE SKID |  | B | DKHD-0170 | MMS | DK60 | MS0013
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334358 | 1Y HELIDECK FOAM SKID MAINT-HBCR-A-0336 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-08 | 2024-06-11 | 2024-06-08 | 2024-07-08 | 2024-06-08 | 10 | REL | APPR OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | C | DKHB-0076 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334358 | 1Y HELIDECK FOAM SKID MAINT-HBCR-A-0336 | HELIDECK FOAM SKID MAINT-HBCR-A-0336 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-08 | 2024-06-11 | 2024-06-08 | 2024-07-08 | 2024-06-08 | 20 | REL | APPR OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | C | DKHB-0076 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334358 | 1Y HELIDECK FOAM SKID MAINT-HBCR-A-0336 | HELIDECK FOAM SKID MAINT-HBCR-A-0336 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-08 | 2024-06-11 | 2024-06-08 | 2024-07-08 | 2024-06-08 | 30 | REL | APPR OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | C | DKHB-0076 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334358 | 1Y HELIDECK FOAM SKID MAINT-HBCR-A-0336 | HELIDECK FOAM SKID MAINT-HBCR-A-0336 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-06-08 | 2024-06-11 | 2024-06-09 | 2024-07-08 | 2024-06-08 | 40 | REL | APPR OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | C | DKHB-0076 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334358 | 1Y HELIDECK FOAM SKID MAINT-HBCR-A-0336 | HELIDECK FOAM SKID MAINT-HBCR-A-0336 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-06-08 | 2024-06-11 | 2024-06-10 | 2024-07-08 | 2024-06-08 | 50 | REL | APPR OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | C | DKHB-0076 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334358 | 1Y HELIDECK FOAM SKID MAINT-HBCR-A-0336 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-08 | 2024-06-11 | 2024-06-11 | 2024-07-08 | 2024-06-08 | 60 | REL | APPR OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | C | DKHB-0076 | MMS | DK50 | MS0014
0 | A | HDA-IPHP | WPM | MTN-TELE | MTN-TELE | 2400334415 | 8000H F&G DETECTOR, ENCL, HDAF-A-4301 | F&G DETECTOR, ENCLOSURE, HDAF-A-4301 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2024-06-11 | 2024-06-14 | 2024-06-11 | 2024-07-11 | 2024-06-11 | 10 | REL | APPR OPND | HD /A /03/FZ-245-LVL-4-GAS-COMP-ENCLOS | FIRE ZONE 245 LEVEL 4 GAS COMP ENCLOS |  | F | DKHD-0284 | MIN | DK60 | IN0073
0 | A | HDA-IPHP | WPM | MTN-TELE | MTN-INST | 2400334415 | 8000H F&G DETECTOR, ENCL, HDAF-A-4301 | SUPPORT, DETECTOR CHECK, HDAF-A-4301 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2024-06-11 | 2024-06-14 | 2024-06-12 | 2024-07-11 | 2024-06-11 | 20 | REL | APPR OPND | HD /A /03/FZ-245-LVL-4-GAS-COMP-ENCLOS | FIRE ZONE 245 LEVEL 4 GAS COMP ENCLOS |  | F | DKHD-0284 | MIN | DK60 | IN0073
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334583 | 2Y DELUGE SKID TEST/MAINT - HBCM-A-0335 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /C /01/HBCM-A-0335 | DELUGE SKID |  | C | DKHB-0073 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334583 | 2Y DELUGE SKID TEST/MAINT - HBCM-A-0335 | DELUGE SKID TEST/MAINT - HBCM-A-0335 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /C /01/HBCM-A-0335 | DELUGE SKID |  | C | DKHB-0073 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334583 | 2Y DELUGE SKID TEST/MAINT - HBCM-A-0335 | DELUGE SKID TEST/MAINT - HBCM-A-0335 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /C /01/HBCM-A-0335 | DELUGE SKID |  | C | DKHB-0073 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334583 | 2Y DELUGE SKID TEST/MAINT - HBCM-A-0335 | DELUGE SKID VENDOR ASSIST - HBCM-A-0335 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /C /01/HBCM-A-0335 | DELUGE SKID |  | C | DKHB-0073 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334583 | 2Y DELUGE SKID TEST/MAINT - HBCM-A-0335 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /C /01/HBCM-A-0335 | DELUGE SKID |  | C | DKHB-0073 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334585 | 2Y DELUGE SKID TEST/MAINT - HBDB-A-0380 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | C | DKHB-0089 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334585 | 2Y DELUGE SKID TEST/MAINT - HBDB-A-0380 | DELUGE SKID TEST/MAINT - HBDB-A-0380 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 10 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | C | DKHB-0089 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334585 | 2Y DELUGE SKID TEST/MAINT - HBDB-A-0380 | DELUGE SKID TEST/MAINT - HBDB-A-0380 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | C | DKHB-0089 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334585 | 2Y DELUGE SKID TEST/MAINT - HBDB-A-0380 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-02 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | C | DKHB-0089 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334588 | 2Y HELI DELUGE SKID TEST-HBCM-A-0339 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /C /01/HBCM-A-0339 | DELUGE SKID AVIATION FUEL |  | C | DKHB-0127 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334588 | 2Y HELI DELUGE SKID TEST-HBCM-A-0339 | HELI DELUGE SKID TEST-HBCM-A-0339 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2.5 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /C /01/HBCM-A-0339 | DELUGE SKID AVIATION FUEL |  | C | DKHB-0127 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334588 | 2Y HELI DELUGE SKID TEST-HBCM-A-0339 | HELI DELUGE SKID TEST-HBCM-A-0339 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /C /01/HBCM-A-0339 | DELUGE SKID AVIATION FUEL |  | C | DKHB-0127 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334588 | 2Y HELI DELUGE SKID TEST-HBCM-A-0339 | HELI DELUGE SKID VEN ASSIST-HBCM-A-0339 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /C /01/HBCM-A-0339 | DELUGE SKID AVIATION FUEL |  | C | DKHB-0127 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334588 | 2Y HELI DELUGE SKID TEST-HBCM-A-0339 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /C /01/HBCM-A-0339 | DELUGE SKID AVIATION FUEL |  | C | DKHB-0127 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334590 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0370 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | C | DKHB-0464 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334590 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0370 | DELUGE SKID HEATER CHECK - HBAA-A-0370 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | C | DKHB-0464 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334590 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0370 | DELUGE SKID TEST/MAINT - HBAA-A-0370 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | C | DKHB-0464 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334590 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0370 | DELUGE SKID TEST/MAINT - HBAA-A-0370 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | C | DKHB-0464 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334590 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0370 | DELUGE SKID VEND ASSIST - HBAA-A-0370 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | C | DKHB-0464 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334590 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0370 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0370 | DELUGE SKID, CELLAR DECK WEST |  | C | DKHB-0464 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334591 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0371 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0465 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334591 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0371 | DELUGE SKID HEATER CHECK - HBAA-A-0371 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0465 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334591 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0371 | DELUGE SKID TEST/MAINT - HBAA-A-0371 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0465 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334591 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0371 | DELUGE SKID TEST/MAINT - HBAA-A-0371 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0465 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334591 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0371 | DELUGE SKID VEND ASSIST - HBAA-A-0371 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0465 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334591 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0371 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0465 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334592 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0372 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0466 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334592 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0372 | DELUGE SKID HEATER CHECK - HBAA-A-0372 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0466 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334592 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0372 | DELUGE SKID TEST/MAINT - HBAA-A-0372 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0466 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334592 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0372 | DELUGE SKID TEST/MAINT - HBAA-A-0372 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0466 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334592 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0372 | DELUGE SKID VEND ASSIST - HBAA-A-0372 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0466 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334592 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0372 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0372 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0466 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334593 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0373 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | C | DKHB-0467 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334593 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0373 | DELUGE SKID HEATER CHECK - HBAA-A-0373 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | C | DKHB-0467 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334593 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0373 | DELUGE SKID TEST/MAINT - HBAA-A-0373 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | C | DKHB-0467 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334593 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0373 | DELUGE SKID TEST/MAINT - HBAA-A-0373 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | C | DKHB-0467 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334593 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0373 | DELUGE SKID VEND ASSIST - HBAA-A-0373 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | C | DKHB-0467 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334593 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0373 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0373 | DELUGE SKID CELLAR DECK |  | C | DKHB-0467 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334594 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0374 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | C | DKHB-0468 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334594 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0374 | DELUGE SKID HEATER CHECK - HBAA-A-0374 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | C | DKHB-0468 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334594 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0374 | DELUGE SKID TEST/MAINT - HBAA-A-0374 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | C | DKHB-0468 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334594 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0374 | DELUGE SKID TEST/MAINT - HBAA-A-0374 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | C | DKHB-0468 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334594 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0374 | DELUGE SKID VEND ASSIST - HBAA-A-0374 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | C | DKHB-0468 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334594 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0374 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-02 | 2024-07-15 | 2024-05-30 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK |  | C | DKHB-0468 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334595 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0375 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0469 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334595 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0375 | DELUGE SKID HEATER CHECK - HBAA-A-0375 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0469 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334595 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0375 | DELUGE SKID TEST/MAINT - HBAA-A-0375 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0469 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334595 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0375 | DELUGE SKID TEST/MAINT - HBAA-A-0375 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0469 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334595 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0375 | DELUGE SKID VEND ASSIST - HBAA-A-0375 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0469 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334595 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0375 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-02 | 2024-07-15 | 2024-05-30 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0469 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334596 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0376 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0474 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334596 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0376 | DELUGE SKID HEATER CHECK - HBAA-A-0376 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0474 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334596 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0376 | DELUGE SKID TEST/MAINT - HBAA-A-0376 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0474 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334596 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0376 | DELUGE SKID TEST/MAINT - HBAA-A-0376 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0474 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334596 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0376 | DELUGE SKID VEND ASSIST - HBAA-A-0376 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0474 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334596 | 2Y DELUGE SKID TEST/MAINT - HBAA-A-0376 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-01 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK |  | C | DKHB-0474 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334597 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0310 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0476 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334597 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0310 | DELUGE SKID HEATER CHECK - HBBA-A-0310 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0476 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334597 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0310 | DELUGE SKID TEST/MAINT - HBBA-A-0310 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0476 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334597 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0310 | DELUGE SKID TEST/MAINT - HBBA-A-0310 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6.5 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0476 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334597 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0310 | DELUGE SKID VEND ASSIST - HBBA-A-0310 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6.5 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0476 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334597 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0310 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-02 | 2024-07-15 | 2024-05-30 | 60 | REL | APPR OPND | HB /B /01/HBBA-A-0310 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0476 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334598 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0320 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0477 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334598 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0320 | DELUGE SKID HEATER CHECK - HBBA-A-0320 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0477 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334598 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0320 | DELUGE SKID TEST/MAINT - HBBA-A-0320 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0477 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334598 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0320 | DELUGE SKID TEST/MAINT - HBBA-A-0320 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6.5 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0477 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334598 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0320 | DELUGE SKID VEND ASSIST - HBBA-A-0320 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 6.5 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0477 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334598 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0320 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-02 | 2024-07-15 | 2024-05-30 | 60 | REL | APPR OPND | HB /B /01/HBBA-A-0320 | DELUGE SKID, CELAR DECK, SOUTH EAST |  | C | DKHB-0477 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334599 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0330 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0479 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334599 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0330 | DELUGE SKID HEATER CHECK - HBBA-A-0330 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0479 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334599 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0330 | DELUGE SKID TEST/MAINT - HBBA-A-0330 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0479 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334599 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0330 | DELUGE SKID TEST/MAINT - HBBA-A-0330 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0479 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334599 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0330 | DELUGE SKID VEND ASSIST - HBBA-A-0330 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0479 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334599 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0330 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 60 | REL | APPR OPND | HB /B /01/HBBA-A-0330 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0479 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334600 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0340 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0480 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334600 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0340 | DELUGE SKID HEATER CHECK - HBBA-A-0340 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0480 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334600 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0340 | DELUGE SKID TEST/MAINT - HBBA-A-0340 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0480 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334600 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0340 | DELUGE SKID TEST/MAINT - HBBA-A-0340 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0480 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334600 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0340 | DELUGE SKID VEND ASSIST - HBBA-A-0340 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0480 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334600 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0340 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 60 | REL | APPR OPND | HB /B /01/HBBA-A-0340 | DELLUGE SKID, CELLAR DECK, BRIDGE |  | C | DKHB-0480 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334601 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0350 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 10 | REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | C | DKHB-0481 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400334601 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0350 | DELUGE SKID HEATER CHECK - HBBA-A-0350 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 20 | REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | C | DKHB-0481 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400334601 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0350 | DELUGE SKID TEST/MAINT - HBBA-A-0350 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-30 | 2024-07-15 | 2024-05-30 | 30 | REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | C | DKHB-0481 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334601 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0350 | DELUGE SKID TEST/MAINT - HBBA-A-0350 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-05-31 | 2024-07-15 | 2024-05-30 | 40 | REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | C | DKHB-0481 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400334601 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0350 | DELUGE SKID VEND ASSIST - HBBA-A-0350 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 50 | REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | C | DKHB-0481 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400334601 | 2Y DELUGE SKID TEST/MAINT - HBBA-A-0350 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-30 | 2024-06-02 | 2024-06-01 | 2024-07-15 | 2024-05-30 | 60 | REL | APPR OPND | HB /B /01/HBBA-A-0350 | DELUGE SKID, MEZZANINE DECK |  | C | DKHB-0481 | MMS | DK50 | MS0014
2026-W13-14 | A | HB-GEN2 | WPM | MTN-INST | VEN-ELEC | 2400335819 | 4000H FG DETECTORS, FZ-845 - HBDC-A-1660 | FGS DETECTORS, HBDC-A-1660 FZ-845 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2024-07-11 | 2024-07-13 | 2024-07-11 | 2024-07-27 | 2024-07-11 | 10 | REL | APPR OPND | HB /D /03/FZ-845-POWER-GEN-TURBINE | FIRE ZONE 845 POWER GEN TURBINE |  | C | DKHB-2037 | MIN | DK50 | IN0074
2026-W13-14 | A | HB-GEN2 | WPM | MTN-INST | MTN-INST | 2400335819 | 4000H FG DETECTORS, FZ-845 - HBDC-A-1660 | SUPPORT 4000H, FG DETECTORS, HBDC-A-1660 | REL NMAT PRC SETC | APPR SECE AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2024-07-11 | 2024-07-13 | 2024-07-12 | 2024-07-27 | 2024-07-11 | 20 | REL | APPR OPND | HB /D /03/FZ-845-POWER-GEN-TURBINE | FIRE ZONE 845 POWER GEN TURBINE |  | C | DKHB-2037 | MIN | DK50 | IN0074
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095246 | Defect RCCB's HBDD-LP-1811 | Defect RCCB's HBDD-LP-1811 | REL MANC PRC SETC | APPR SECE APOG WMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-01-23 | 2023-09-10 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | D |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100095246 | Defect RCCB's HBDD-LP-1811 | Isolate Equipment. | REL MANC PRC SETC | APPR SECE APOG WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-01-23 | 2023-09-10 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | D |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095246 | Defect RCCB's HBDD-LP-1811 | Replace defective parts | REL MANC PRC SETC | APPR SECE APOG WMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-01-23 | 2023-09-10 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | D |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100095246 | Defect RCCB's HBDD-LP-1811 | De-isolate Equipment | REL MANC PRC SETC | APPR SECE APOG WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2024-01-23 | 2023-09-10 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1811 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | D |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095246 | Defect RCCB's HBDD-LP-1811 | Test & put back in service | REL MANC PRC SETC | APPR SECE APOG WMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2024-01-23 | 2023-09-10 | 50 | REL | APPR OPND | HB /D /05/HBDD-LP-1811 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | D |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095246 | Defect RCCB's HBDD-LP-1811 | Add materials | REL MANC PRC SETC | APPR SECE APOG WMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2024-01-23 | 2023-09-10 | 60 | REL | INIT OPND | HB /D /05/HBDD-LP-1811 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | D |  | MEL | DK50 |  | PROK
2024-W15-16 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095247 | Defect RCCB's HBDD-LP-1813 | Isolate LP-1813 | REL GMPS MANC PRC SETC | APPR SECE APOG SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W09-W10 | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-01-23 | 2023-09-10 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1813 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | D |  | MEL | DK50 |  | PROK | 2024-04-16
2024-W15-16 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095247 | Defect RCCB's HBDD-LP-1813 | Replace Breakers | REL GMPS MANC PRC SETC | APPR SECE APOG SMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W09-W10 | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-01-23 | 2023-09-10 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1813 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | D |  | MEL | DK50 |  | PROK | 2024-04-17
2024-W15-16 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095247 | Defect RCCB's HBDD-LP-1813 | De Isolate and test | REL GMPS MANC PRC SETC | APPR SECE APOG SMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W09-W10 | 2024-09-03 | 2024-09-04 | 2024-09-04 | 2024-01-23 | 2023-09-10 | 40 | REL | APPR OPND | HB /D /05/HBDD-LP-1813 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | D |  | MEL | DK50 |  | PROK | 2024-04-18
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067649 | Replace light bulb in HBCH-SL-15141 | Additional materials | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-08-26 | 2022-05-28 | 40 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15141 | HELIDECK STATUS LIGHT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100067649 | Replace light bulb in HBCH-SL-15141 | Build scaffolding on existing | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 28 | 28 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-08-26 | 2022-05-28 | 45 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15141 | HELIDECK STATUS LIGHT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067649 | Replace light bulb in HBCH-SL-15141 | Demol HBCH-SL-15141 | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-08-26 | 2022-05-28 | 60 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15141 | HELIDECK STATUS LIGHT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067649 | Replace light bulb in HBCH-SL-15141 | Isolate helideck light HBCH-SL-15141 | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-08-26 | 2022-05-28 | 100 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15141 | HELIDECK STATUS LIGHT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067649 | Replace light bulb in HBCH-SL-15141 | Remount junction box | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-08-26 | 2022-05-28 | 110 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15141 | HELIDECK STATUS LIGHT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067649 | Replace light bulb in HBCH-SL-15141 | Mount HBCH-SL-15141 | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-08-26 | 2022-05-28 | 120 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15141 | HELIDECK STATUS LIGHT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067649 | Replace light bulb in HBCH-SL-15141 | Deisolate helideck light HBCH-SL-15141 | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-08-26 | 2022-05-28 | 130 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15141 | HELIDECK STATUS LIGHT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067649 | Replace light bulb in HBCH-SL-15141 | Test | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-08-26 | 2022-05-28 | 140 | PCNF REL | APPR OPND | HB /C /62/HBCH-SL-15141 | HELIDECK STATUS LIGHT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067649 | Replace light bulb in HBCH-SL-15141 | Additional parts | REL PCNF GMPS MANC PPRT PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-08-26 | 2022-05-28 | 150 | REL | APPR OPND | HB /C /62/HBCH-SL-15141 | HELIDECK STATUS LIGHT |  | C |  | MEL | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-SCAF | 2100106042 | Foam bladder is leaking | Pre/post Scaffold Erection | REL GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-07-07 | 2024-07-11 | 2024-07-07 | 2024-07-20 | 2024-03-07 | 10 | REL | APPR OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100106042 | Foam bladder is leaking | Production isolation | REL GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-07-07 | 2024-07-11 | 2024-07-07 | 2024-07-20 | 2024-03-07 | 20 | REL | APPR OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100106042 | Foam bladder is leaking | Rigger assistance | REL GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-07-07 | 2024-07-11 | 2024-07-08 | 2024-07-20 | 2024-03-07 | 30 | REL | APPR OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100106042 | Foam bladder is leaking | Replace Bladder | REL GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 16 | 0 |  | 2024-07-07 | 2024-07-11 | 2024-07-09 | 2024-07-20 | 2024-03-07 | 40 | REL | APPR OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100106042 | Foam bladder is leaking | Production deisolation w Leak/func. test | REL GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-07-07 | 2024-07-11 | 2024-07-07 | 2024-07-20 | 2024-03-07 | 50 | REL | APPR OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100106042 | Foam bladder is leaking | Function test | REL GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-07-07 | 2024-07-11 | 2024-07-07 | 2024-07-20 | 2024-03-07 | 60 | REL | APPR OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100106042 | Foam bladder is leaking | Add. foam liquid | REL GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-07-07 | 2024-07-11 | 2024-07-07 | 2024-07-20 | 2024-03-07 | 70 | REL | INIT OPND | HB /C /01/HBCR-A-0336 | FOAM GENERATOR SKID |  | A |  | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400207464 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0362 | ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 1 | 0 | DK50-M-7530 | 2024-11-17 | 2024-11-19 | 2024-11-17 | 2022-07-22 | 2022-04-22 | 10 | REL | APPR OPND | HB /D /01/HBDB-A-0362 | FIREWATER PUMP MODULE |  | D | DKHB-0653 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400207464 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0362 | FWP ANODE REPLACEMENT-HBDB-A-0362 | REL GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 6 | 0 | DK50-M-7530 | 2024-11-17 | 2024-11-19 | 2024-11-17 | 2022-07-22 | 2022-04-22 | 20 | REL | APPR OPND | HB /D /01/HBDB-A-0362 | FIREWATER PUMP MODULE |  | D | DKHB-0653 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400207464 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0362 | FWP ANODE REPLACEMENT-HBDB-A-0362 | REL GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 6 | 0 | DK50-M-7530 | 2024-11-17 | 2024-11-19 | 2024-11-18 | 2022-07-22 | 2022-04-22 | 30 | REL | APPR OPND | HB /D /01/HBDB-A-0362 | FIREWATER PUMP MODULE |  | D | DKHB-0653 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400207464 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0362 | DE-ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 1 | 0 | DK50-M-7530 | 2024-11-17 | 2024-11-19 | 2024-11-19 | 2022-07-22 | 2022-04-22 | 40 | REL | APPR OPND | HB /D /01/HBDB-A-0362 | FIREWATER PUMP MODULE |  | D | DKHB-0653 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291849 | PSV Calibration - HBDC-PSV-415202 | Isolation of PSV | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 2 | 0 |  | 2024-10-19 | 2024-12-23 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 10 | REL | APPR OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291849 | PSV Calibration - HBDC-PSV-415202 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 2 | 0 |  | 2024-10-19 | 2024-12-23 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 20 | REL | APPR OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400291849 | PSV Calibration - HBDC-PSV-415202 | Rigging assist (remove) | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 24 | 0 |  | 2024-10-19 | 2024-12-23 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 30 | REL | APPR OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291849 | PSV Calibration - HBDC-PSV-415202 | Remove PSV | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 5 | 0 |  | 2024-10-19 | 2024-12-23 | 2024-10-20 | 2024-12-31 | 2024-10-19 | 40 | REL | APPR OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291849 | PSV Calibration - HBDC-PSV-415202 | Install blinds | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 2 | 0 |  | 2024-10-19 | 2024-12-23 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 50 | REL | APPR OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291849 | PSV Calibration - HBDC-PSV-415202 | Backload PSV to Norspie Workshop | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 1 | 0 |  | 2024-10-19 | 2024-12-23 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 51 | REL | INIT OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291849 | PSV Calibration - HBDC-PSV-415202 | Re-certify PSV | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 4 | 0 |  | 2024-10-19 | 2024-12-23 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 60 | REL | APPR OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400291849 | PSV Calibration - HBDC-PSV-415202 | Rigging Assist (Install) | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 12 | 0 |  | 2024-10-19 | 2024-12-23 | 2024-12-21 | 2024-12-31 | 2024-10-19 | 70 | REL | APPR OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291849 | PSV Calibration - HBDC-PSV-415202 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 2 | 0 |  | 2024-10-19 | 2024-12-23 | 2024-12-22 | 2024-12-31 | 2024-10-19 | 80 | REL | APPR OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291849 | PSV Calibration - HBDC-PSV-415202 | Install re-certified PSV | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 5 | 0 |  | 2024-10-19 | 2024-12-23 | 2024-12-22 | 2024-12-31 | 2024-10-19 | 90 | REL | APPR OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291849 | PSV Calibration - HBDC-PSV-415202 | De-isolation and leak test | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 4 | 0 |  | 2024-10-19 | 2024-12-23 | 2024-12-22 | 2024-12-31 | 2024-10-19 | 100 | REL | APPR OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291849 | PSV Calibration - HBDC-PSV-415202 | Documentation & CNF WO | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 2 | 0 |  | 2024-10-19 | 2024-12-23 | 2024-12-22 | 2024-12-31 | 2024-10-19 | 110 | REL | APPR OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400291849 | PSV Calibration - HBDC-PSV-415202 | Check PSV flanges & alignment | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 2 | 0 | W09-W10 | 2024-10-19 | 2024-12-23 | 2024-12-22 | 2024-12-31 | 2024-10-19 | 120 | REL | APPR OPND | HB /D /30/HBDC-PSV-415202 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV138 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291850 | PSV Calibration - HBDC-PSV-415103 | Isolation of PSV | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 2 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 10 | REL | APPR OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291850 | PSV Calibration - HBDC-PSV-415103 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 2 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 20 | REL | APPR OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400291850 | PSV Calibration - HBDC-PSV-415103 | Rigging assist (remove) | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 24 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 30 | REL | APPR OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291850 | PSV Calibration - HBDC-PSV-415103 | Remove PSV | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 5 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 40 | REL | APPR OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291850 | PSV Calibration - HBDC-PSV-415103 | Install blinds | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 2 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-20 | 2024-12-31 | 2024-10-19 | 50 | REL | APPR OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291850 | PSV Calibration - HBDC-PSV-415103 | Backload PSV to Norspie Workshop | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 1 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-20 | 2024-12-31 | 2024-10-19 | 51 | REL | INIT OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291850 | PSV Calibration - HBDC-PSV-415103 | Re-certify PSV | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 4 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-20 | 2024-12-31 | 2024-10-19 | 60 | REL | APPR OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400291850 | PSV Calibration - HBDC-PSV-415103 | Rigging Assist (Install) | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 12 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-19 | 2024-12-31 | 2024-10-19 | 70 | REL | APPR OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291850 | PSV Calibration - HBDC-PSV-415103 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 2 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-20 | 2024-12-31 | 2024-10-19 | 80 | REL | APPR OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291850 | PSV Calibration - HBDC-PSV-415103 | Install re-certified PSV | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 5 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-19 | 2024-12-31 | 2024-10-19 | 90 | REL | APPR OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291850 | PSV Calibration - HBDC-PSV-415103 | De-isolation and leak test | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 4 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-20 | 2024-12-31 | 2024-10-19 | 100 | REL | APPR OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291850 | PSV Calibration - HBDC-PSV-415103 | Documentation & CNF WO | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 2 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-20 | 2024-12-31 | 2024-10-19 | 110 | REL | APPR OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400291850 | PSV Calibration - HBDC-PSV-415103 | Check PSV flanges & alignment | REL CSER GMPS MANC PRC SETC | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ* | 2 | 0 | W09-W10 | 2024-10-19 | 2024-12-21 | 2024-12-21 | 2024-12-31 | 2024-10-19 | 120 | REL | APPR OPND | HB /D /32/HBDC-PSV-415103 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV149 | MMS | DK50
0 | 3 | NOSD | WDF | MTN-TELE | PRODTECH | 2100072397 | Change HDB secondary light | Isolate and prove dead | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE APOG CMAT AWDO SCH RDBL RFRZ* | 1 | 0 | W47-48 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-01-30 | 2022-09-17 | 10 | PCNF REL | APPR OPND | HD /B /64/HDBC-SL-15031 | MAIN/SECONDARY LANTERN NV |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100072397 | Change HDB secondary light | Change and program print card | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE APOG CMAT AWDO SCH RDBL RFRZ* | 16 | 29 | W47-48 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-01-30 | 2022-09-17 | 20 | PCNF REL | APPR OPND | HD /B /64/HDBC-SL-15031 | MAIN/SECONDARY LANTERN NV |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-TELE | MTN-ELEC | 2100072397 | Change HDB secondary light | Change secundary lamp | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE APOG CMAT AWDO SCH RDBL RFRZ* | 6 | 0 | W47-48 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-01-30 | 2022-09-17 | 30 | PCNF REL | APPR OPND | HD /B /64/HDBC-SL-15031 | MAIN/SECONDARY LANTERN NV |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100072397 | Change HDB secondary light | De-isolate and test | REL PCNF PRT GMPS MANC PRC SETC | APPR SECE APOG CMAT AWDO SCH RDBL RFRZ* | 1 | 0 | W47-48 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-01-30 | 2022-09-17 | 40 | PCNF REL | APPR OPND | HD /B /64/HDBC-SL-15031 | MAIN/SECONDARY LANTERN NV |  | C |  | MEL | DK60
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075348 | damage on flame path | damage on flame pat | REL MANC NMAT PRC SETC | APPR SECE APOG AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-03-26 | 2022-11-11 | 10 | REL | APPR OPND | HB /B /06/HBBA-AE-1921A | UPS CHARGERS |  | A |  | MEL | DK50 |  |  | 2024-05-04
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088918 | Outletblower 1283 HBC accom. is noisy | Outletblower HBC accom. is noisy | REL MANC NMAT PRC SETC | APPR SCH RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2023-10-05 | 2023-05-23 | 10 | REL | APPR OPND | HB /C /09/HBCC-BM-1283 | ACCOMMODATION OUTLET BLOWER |  | A |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088918 | Outletblower 1283 HBC accom. is noisy | Isolate | REL MANC NMAT PRC SETC | APPR SCH RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2023-10-05 | 2023-05-23 | 20 | REL | APPR OPND | HB /C /09/HBCC-BM-1283 | ACCOMMODATION OUTLET BLOWER |  | A |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088918 | Outletblower 1283 HBC accom. is noisy | Troubleshoot & rep if possible | REL MANC NMAT PRC SETC | APPR SCH RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2023-10-05 | 2023-05-23 | 30 | REL | APPR OPND | HB /C /09/HBCC-BM-1283 | ACCOMMODATION OUTLET BLOWER |  | A |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088918 | Outletblower 1283 HBC accom. is noisy | De - Isolate | REL MANC NMAT PRC SETC | APPR SCH RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-09 | 2023-10-05 | 2023-05-23 | 40 | REL | APPR OPND | HB /C /09/HBCC-BM-1283 | ACCOMMODATION OUTLET BLOWER |  | A |  | MEL | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-ELEC | MTN-INST | 2100089391 | Periodic malfunction on glycol heater. | Periodic malfunction on glycol heater. | REL MANC NMAT PRC SETC | APPR SCH RDBL | 6 | 0 | W49-50 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2023-10-10 | 2023-05-28 | 10 | REL | APPR OPND | HB /D /30/HBDB-E-4168 | GLYCOL REGENERATION HEATER (50%) |  | A |  | MEL | DK50 |  | PROK
2026-W1-2 | 2 | NOSD | WDF | MTN-INST | MTN-INST | 2100096134 | Cooling water Flow transmitter unstabile | Flow transmitter investigation | REL PCNF MANC NMAT PRC SETC | APPR SCH RDBL | 6 | 6 | W43-44 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-16 | 2023-08-02 | 10 | PCNF REL | APPR OPND | HB /D /76/HBDB-FIT-535501 | FLOW INDICATOR TRANSMITTER |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096137 | RCB Q17 in HBB-N-1821B tripped | Isolate Equipment. | REL PCNF MANC NMAT PRC SETC | APPR SCH RDBL | 1 | 0.5 | W51-52 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2023-11-03 | 2023-06-21 | 20 | PCNF REL | APPR OPND | HB /B /61/HBBB-N-1821B-Q17 | NORMAL LIGHTING ROOF DK (1821-1817) |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096137 | RCB Q17 in HBB-N-1821B tripped | Replace Light fixtures | REL PCNF MANC NMAT PRC SETC | APPR SCH RDBL | 20 | 5 | W51-52 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2023-11-03 | 2023-06-21 | 30 | PCNF REL | APPR OPND | HB /B /61/HBBB-N-1821B-Q17 | NORMAL LIGHTING ROOF DK (1821-1817) |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096137 | RCB Q17 in HBB-N-1821B tripped | De-isolate Equipment | REL PCNF MANC NMAT PRC SETC | APPR SCH RDBL | 1 | 0.5 | W51-52 | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2023-11-03 | 2023-06-21 | 40 | PCNF REL | APPR OPND | HB /B /61/HBBB-N-1821B-Q17 | NORMAL LIGHTING ROOF DK (1821-1817) |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096137 | RCB Q17 in HBB-N-1821B tripped | Test & put back in service | REL PCNF MANC NMAT PRC SETC | APPR SCH RDBL | 1 | 0.5 | W51-52 | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2023-11-03 | 2023-06-21 | 50 | PCNF REL | APPR OPND | HB /B /61/HBBB-N-1821B-Q17 | NORMAL LIGHTING ROOF DK (1821-1817) |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100096932 | FLMR HBA - Install Join Link Stair EL. 3 | HBA - Install Join Link Stair EL. 31.240 | REL MANC NMAT PRC SETC | APPR SCH RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2026-08-07 | 2024-02-19 | 10 | REL | APPR OPND | HB /A /86/31240 - HANDRAILS | 31240 - HANDRAILS |  | A |  | MFM | DK50
2026-W1-2 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100096932 | FLMR HBA - Install Join Link Stair EL. 3 | Survey number of missing handrail links | REL MANC NMAT PRC SETC | APPR SCH RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2026-08-07 | 2024-02-19 | 20 | REL | APPR OPND | HB /A /86/31240 - HANDRAILS | 31240 - HANDRAILS |  | A |  | MFM | DK50
2026-W1-2 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100096932 | FLMR HBA - Install Join Link Stair EL. 3 | Order materials | REL MANC NMAT PRC SETC | APPR SCH RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2026-08-07 | 2024-02-19 | 30 | REL | APPR OPND | HB /A /86/31240 - HANDRAILS | 31240 - HANDRAILS |  | A |  | MFM | DK50
2026-W1-2 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100096932 | FLMR HBA - Install Join Link Stair EL. 3 | Install missing handrail links | REL MANC NMAT PRC SETC | APPR SCH RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-09 | 2026-08-07 | 2024-02-19 | 40 | REL | APPR OPND | HB /A /86/31240 - HANDRAILS | 31240 - HANDRAILS |  | A |  | MFM | DK50
0 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100097066 | WiFi AP's not working | WiFi AP's not working | REL PCNF PRT MANC NMAT PRC SETC | APPR SCH RDBL | 0 | 104 | W47-48 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-02-27 | 2023-10-15 | 10 | PCNF REL | APPR OPND | HD /B /08/HDBE-AS-14001 | MDF/DATA RACK 1 |  | A |  | MIN | DK60
2026-W1-2 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100098680 | Earth faults HBA ESD system | Earth faults troubleshooting FP-0210A | REL PCNF PRT MANC NMAT PRC SETC | APPR SCH RDBL | 5 | 45 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-03-17 | 2023-11-03 | 10 | PCNF REL | APPR OPND | HB /A /03/HBAA-FP-0210A | 24VDC DIST. PANEL ESD POWER SUPPLY |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100098680 | Earth faults HBA ESD system | Earth faults troubleshooting FP-0210A | REL PCNF PRT MANC NMAT PRC SETC | APPR SCH RDBL | 5 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-03-17 | 2023-11-03 | 20 | PCNF REL | APPR OPND | HB /A /03/HBAA-FP-0210A | 24VDC DIST. PANEL ESD POWER SUPPLY |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100098680 | Earth faults HBA ESD system | Earth faults troubleshooting FP-0210A | REL PCNF PRT MANC NMAT PRC SETC | APPR SCH RDBL | 5 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-03-17 | 2023-11-03 | 30 | PCNF REL | APPR OPND | HB /A /03/HBAA-FP-0210A | 24VDC DIST. PANEL ESD POWER SUPPLY |  | A |  | MIN | DK50
2026-W1-2 | 3 | NE | WDF | MTN-INST | MTN-TURB | 2100104222 | HBD G-1660 indication fault | Troubleshooting | REL MANC NMAT PRC SETC | APPR SCH RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2024-05-01 | 2023-12-18 | 10 | REL | APPR OPND | HB /D /60/HBDC-CP-1660 | POWER GENERATOR UNIT CONTROL PANEL |  | A |  | MMR | DK50
2026-W1-2 | 3 | NE | WDF | MTN-INST | MTN-TELE | 2100104222 | HBD G-1660 indication fault | Support Turb dept. | REL MANC NMAT PRC SETC | APPR SCH RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2024-05-01 | 2023-12-18 | 20 | REL | APPR OPND | HB /D /60/HBDC-CP-1660 | POWER GENERATOR UNIT CONTROL PANEL |  | A |  | MMR | DK50
2026-W1-2 | 3 | HBD-GLY | WGN | MTN-ROPE | CON-LAGG | 2200007088 | FFS scanning of HBDB-V-4184 Stahl Column | FFS scanning of HBDB-V-4184 Stahl Column | REL PCNF MANC PRC SETC | APPR SCH RDBL | 0 | 0 |  | 2024-01-01 | 2024-01-01 | 2024-01-01 | 2021-08-25 | 2021-05-27 | 10 | PCNF REL | APPR OPND | HB /D /30/HBDB-V-4184 | STAHL COLUMN | 99000119 | A |  | INP | DK50
2026-W1-2 | 3 | HBD-GLY | WGN | MTN-ROPE | MTN-ROPE | 2200007088 | FFS scanning of HBDB-V-4184 Stahl Column | MPM - Remove insulation | REL PCNF MANC PRC SETC | APPR SCH RDBL | 3 | 0 |  | 2024-01-01 | 2024-01-01 | 2024-01-01 | 2021-08-25 | 2021-05-27 | 30 | PCNF REL | APPR OPND | HB /D /30/HBDB-V-4184 | STAHL COLUMN | 99000119 | A |  | INP | DK50
2026-W1-2 | 3 | HBD-GLY | WGN | MTN-ROPE | MTN-ROPE | 2200007088 | FFS scanning of HBDB-V-4184 Stahl Column | MPM - mount new insulation | REL PCNF MANC PRC SETC | APPR SCH RDBL | 12 | 0 |  | 2024-01-01 | 2024-01-01 | 2024-01-01 | 2021-08-25 | 2021-05-27 | 40 | PCNF REL | APPR OPND | HB /D /30/HBDB-V-4184 | STAHL COLUMN | 99000119 | A |  | INP | DK50
2026-W1-2 | 3 | HBD-GLY | WGN | MTN-ROPE | MTN-ROPE | 2200007088 | FFS scanning of HBDB-V-4184 Stahl Column | Isolation materials V-4184 | REL PCNF MANC PRC SETC | APPR SCH RDBL | 0 | 0 |  | 2024-01-01 | 2024-01-01 | 2024-01-01 | 2021-08-25 | 2021-05-27 | 50 | PCNF REL | APPR OPND | HB /D /30/HBDB-V-4184 | STAHL COLUMN | 99000119 | A |  | INP | DK50
2026-W1-2 | 3 | HBD-GLY | WGN | MTN-ROPE | MTN-ROPE | 2200007088 | FFS scanning of HBDB-V-4184 Stahl Column | House keeping | REL PCNF MANC PRC SETC | APPR SCH RDBL | 3 | 0 |  | 2024-01-01 | 2024-01-01 | 2024-01-01 | 2021-08-25 | 2021-05-27 | 60 | PCNF REL | APPR OPND | HB /D /30/HBDB-V-4184 | STAHL COLUMN | 99000119 | A |  | INP | DK50
2026-W1-2 | 3 | NOSD | WGN | MTN-SCAF | MTN-ROPE | 2200008621 | Scaff assist Bilfinger | Scaff assist Bilfinger Build & remove | REL MANC NMAT PRC SETC | APPR SCH RDBL | 80 | 0 |  | 2023-04-24 | 2023-04-28 | 2023-04-24 | 2021-12-18 | 2021-11-28 | 10 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | INP | DK50
2026-W1-2 | 2 | NOSD | WGN | VEN-MECH | MTN-MECH | 2200011466 | Acid clean of sewage system | Acid clean of sewage system | REL MANC PRC SETC | APPR SCH RDBL | 0 | 0 |  | 2023-12-11 | 2023-12-28 | 2023-12-11 | 2022-08-10 | 2022-07-26 | 10 | REL | APPR OPND | HB /C /82/HBCM-A-5132 | SEWAGE TREATMENT UNIT |  | A |  | MMS | DK50
2026-W1-2 | 2 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200011466 | Acid clean of sewage system | Acid clean | REL MANC PRC SETC | APPR SCH RDBL | 336 | 0 | W37-38 | 2023-12-11 | 2023-12-28 | 2023-12-11 | 2022-08-10 | 2022-07-26 | 20 | REL | APPR OPND | HB /C /82/HBCM-A-5132 | SEWAGE TREATMENT UNIT |  | A |  | MMS | DK50
2026-W1-2 | 2 | NE | WGN | MTN-INST | MTN-INST | 2200016265 | HBC Change certificate on Cisco IP phone | HBC Change certificate on Cisco IP phone | REL MANC NMAT PRC SETC | APPR SCH RDBL | 5 | 0 | W47-48 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-12-14 | 2023-10-30 | 10 | REL | APPR OPND | HB /C /08 | COMMUNICATION/TELECOM |  | A |  | MIN | DK50
0 | 3 | NOSD | WGN | MTN-TELE | MTN-TELE | 2200016562 | CCTV system survey | CCTV system survey | REL PCNF PRT MANC NMAT PRC SETC | APPR SCH RDBL | 16 | 11 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-05-11 | 2023-12-28 | 10 | PCNF REL | APPR OPND | HD /A /08/CCTV | CCTV |  | A |  | MIN | DK60
0 | 1 | NE | WGN | MTN-TELE | MTN-TELE | 2200017030 | RM707 - HDA Telecom assistance | RM707 - HDA Telecom assistance | REL PCNF MANC NMAT PRC SETC | APPR SCH RDBL | 36 | 51 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-01-20 | 2024-01-05 | 10 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | ENG | DK60
2026-W1-2 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300001251 | C55 HBB05 upd. of Vcone application data | C55 HBB update of Vcone application data | REL PCNF PRT MANC NMAT PRC SETC | APPR SCH RDBL | 5 | 8 | Tele Udsat... | 2024-07-30 | 2024-07-30 | 2024-07-30 |  | 2019-10-18 | 10 | PCNF REL | APPR OPND | HB /B /04/HBBA-CP-2030 | SCADA PANEL / NODE C55 |  | A |  | MIN | DK50
2026-W1-2 | 2 | NE | WRO | MTN-TELE | MTN-TELE | 2300008255 | Investigation and test for reinstatement | Reinstatement of HMI ring network HBx | REL PCNF PRT MANC NMAT PRC SETC | APPR SCH RDBL | 0 | 26.5 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-05-03 | 2024-03-19 | 10 | PCNF REL | APPR OPND | HB /D /04/HBDC-DT-200074 | SCALENCE HMI #1 HBD |  | A |  | MIN | DK50
2026-W1-2 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211342 | 4Y 3KV N-SWB MAINT HBDC-N-1852-M08 | ISOLATION ELECTRICAL | REL MANC PPRT PRC SETC | APPR SCH RDBL | 1 | 0 | W49-50 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M08 | M08 |  | C | DKHB-0557 | MEL | DK50 | EL0024
2026-W1-2 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211342 | 4Y 3KV N-SWB MAINT HBDC-N-1852-M08 | 3KV N-SWB MAINT HBDC-N-1852-M08 | REL MANC PPRT PRC SETC | APPR SCH RDBL | 3 | 0 | W49-50 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M08 | M08 |  | C | DKHB-0557 | MEL | DK50 | EL0024
2026-W1-2 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211342 | 4Y 3KV N-SWB MAINT HBDC-N-1852-M08 | DE-ISOLATION ELECTRICAL | REL MANC PPRT PRC SETC | APPR SCH RDBL | 1 | 0 | W49-50 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M08 | M08 |  | C | DKHB-0557 | MEL | DK50 | EL0024
2026-W1-2 | D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400281944 | 1Y HVAC LAB EXT FAN CHECK HBDC-B-1215 | HVAC LAB EXT FAN CHECK HBDC-B-1215 | REL PCNF PRT MANC NMAT PRC SETC | APPR SCH RDBL | 8 | 5 | W43-44 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-16 | 2023-08-30 | 20 | PCNF REL | APPR OPND | HB /D /09/HBDC-B-1215 | LABORATORY EXTRACT FAN |  | A | DKHB-2014 | MEL | DK50 | EL0014 | PROK
2026-W1-2 | D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400282123 | 1Y AIR QUALITY TESTING - HBC/HBD | AIR QUALITY TESTING - HBC/HBD | REL PCNF PRT MANC NMAT PRC SETC | APPR SCH RDBL | 4 | 0 | W41-42 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-28 | 2023-09-11 | 10 | PCNF REL | APPR OPND | HB /C /07/INSTRUMENT-AIR-SYSTEM | INSTRUMENT AIR SYSTEM |  | A | DKHB-2061 | MMR | DK50 | MR0024 | PROK
0 | B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400302708 | 6M FW-JOCKEY PUMPS HDBC-P-0302/0303 | FW-JOCKEY PUMPS HDBC-P-0302/0303 | REL MANC NMAT PRC SETC | APPR SCH RDBL | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-02-12 | 2024-01-27 | 10 | REL | APPR OPND | HD /B /01/FW-JOCKEY PUMPS | FIREWATER JOCKEY PUMPS |  | A | DKHD-0178 | MMS | DK60 | MS0013
2026-W1-2 | B | NOSD | WPM | MTN-MECH | PRODTECH | 2400316088 | 3M WELLHEAD HPU & CONT PNL MAINT-HBBA | ISOLATION BY PRODUCTION | REL PRT NMAT PRC SETC | APPR SCH RDBL | 1 | 0 | W15-W16 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-29 | 2024-04-19 | 10 | REL | APPR OPND | HB /B /07/HBBA-A-5929 | HYDRAULIC POWER PACKAGE |  | C | DKHB-0102 | MMS | DK50 | MS0064
2026-W1-2 | B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400316088 | 3M WELLHEAD HPU & CONT PNL MAINT-HBBA | WELLHEAD HPU & CONT PNL MAINT-HBBA | REL PRT NMAT PRC SETC | APPR SCH RDBL | 2 | 0 | W15-W16 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-29 | 2024-04-19 | 20 | REL | APPR OPND | HB /B /07/HBBA-A-5929 | HYDRAULIC POWER PACKAGE |  | C | DKHB-0102 | MMS | DK50 | MS0064
2026-W1-2 | B | NOSD | WPM | MTN-MECH | PRODTECH | 2400316088 | 3M WELLHEAD HPU & CONT PNL MAINT-HBBA | DE-ISOLATION BY PRODUCTION | REL PRT NMAT PRC SETC | APPR SCH RDBL | 1 | 0 | W15-W16 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-29 | 2024-04-19 | 30 | REL | APPR OPND | HB /B /07/HBBA-A-5929 | HYDRAULIC POWER PACKAGE |  | C | DKHB-0102 | MMS | DK50 | MS0064
2026-W1-2 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400321294 | 6M HAZARDOUS OPEN DRAIN MAINT-HBC | HAZARDOUS OPEN DRAIN MAINT-HBC | REL NMAT PRC SETC | APPR SCH RDBL | 6 | 0 | W15-W16 | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2024-05-08 | 2024-04-19 | 10 | REL | APPR OPND | HB /C /28/HAZARDOUS-OPEN-DRAIN | DRAIN DISPOSAL |  | C | DKHB-0059 | MMR | DK50 | MR0054 | PROK
2026-W1-2 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400321295 | 6M TEST METER CHOKE MTN HBBB-CVA-37403 | TEST METER CHOKE MTN HBBB-CVA-37403 | REL PRT NMAT PRC SETC | APPR SCH RDBL | 2 | 0 | W15-W16 | 2024-04-21 | 2024-04-21 | 2024-04-21 | 2024-05-10 | 2024-04-21 | 10 | REL | APPR OPND | HB /B /11/HBBB-CVA-37403 | CHOKE VALVE |  | A | DKHB-0084 | MMS | DK50 | MS0074
2026-W1-2 | D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400329568 | 1Y L-AUS TOOLS MAINT CHECK - HBC | L-AUS TOOLS MAINT CHECK - HBC | REL MANC NMAT PRC SETC | APPR SCH RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-06-15 | 2024-04-29 | 10 | REL | APPR OPND | HB /C /84 | WORKSHOP/WAREHOUSE |  | A | DKHB-2042 | MEL | DK50 | EL0044 | PROK
2026-W1-2 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100024779 | SMAT:3KV frequency meter in malfunction | Isolate | REL MANC PPRT PRC SETC | APPR SCH | 3 | 0 | W49-50 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2020-05-15 | 2019-12-17 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100024779 | SMAT:3KV frequency meter in malfunction | Replace transducer | REL MANC PPRT PRC SETC | APPR SCH | 3 | 0 | W49-50 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2020-05-15 | 2019-12-17 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100024779 | SMAT:3KV frequency meter in malfunction | De-isolate | REL MANC PPRT PRC SETC | APPR SCH | 2 | 0 | W49-50 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2020-05-15 | 2019-12-17 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100024779 | SMAT:3KV frequency meter in malfunction | Test - and cleanup worksite | REL MANC PPRT PRC SETC | APPR SCH | 2 | 0 | W49-50 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2020-05-15 | 2019-12-17 | 40 | REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | MTN-PIPF | 2100023573 | HBA Lift gas ventil intern utæt | Matrials are available and checked | REL PRT MANC PRC SETC | APPR RFRZ | 4 | 0 |  | 2023-01-01 | 2023-01-06 | 2023-01-01 | 2018-04-20 | 2018-01-20 | 10 | REL | APPR OPND | HB /A /37/HBAA-HCV-29204 | DOUBLE BLOCK VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | PRODTECH | 2100023573 | HBA Lift gas ventil intern utæt | Safing | REL PRT MANC PRC SETC | APPR RFRZ | 4 | 0 |  | 2023-01-01 | 2023-01-06 | 2023-01-01 | 2018-04-20 | 2018-01-20 | 15 | REL | APPR OPND | HB /A /37/HBAA-HCV-29204 | DOUBLE BLOCK VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | MTN-SCAF | 2100023573 | HBA Lift gas ventil intern utæt | Rigger ass to Valves + cleaning | REL PRT MANC PRC SETC | APPR RFRZ | 10.7 | 0 |  | 2023-01-01 | 2023-01-06 | 2023-01-02 | 2018-04-20 | 2018-01-20 | 20 | REL | APPR OPND | HB /A /37/HBAA-HCV-29204 | DOUBLE BLOCK VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | MTN-PIPF | 2100023573 | HBA Lift gas ventil intern utæt | Install new Valve + cleaning | REL PRT MANC PRC SETC | APPR RFRZ | 10.7 | 0 |  | 2023-01-01 | 2023-01-06 | 2023-01-04 | 2018-04-20 | 2018-01-20 | 30 | REL | APPR OPND | HB /A /37/HBAA-HCV-29204 | DOUBLE BLOCK VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | PRODTECH | 2100023573 | HBA Lift gas ventil intern utæt | Desafing/leaktest. | REL PRT MANC PRC SETC | APPR RFRZ | 4 | 0 |  | 2023-01-01 | 2023-01-06 | 2023-01-05 | 2018-04-20 | 2018-01-20 | 40 | REL | APPR OPND | HB /A /37/HBAA-HCV-29204 | DOUBLE BLOCK VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100026257 | SDBB valve on HBB-HCV-290403 passing | Safing af ventil | REL MANC PPRT PRC SETC | APPR RFRZ | 4 | 0 | OIM 10 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2020-09-21 | 2019-09-27 | 10 | REL | APPR OPND | HB /B /37/HBBB-HCV-290403 | HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100026257 | SDBB valve on HBB-HCV-290403 passing | Udskiftning af bleed ventil | REL MANC PPRT PRC SETC | APPR RFRZ | 6 | 0 | OIM 10 | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2020-09-21 | 2019-09-27 | 20 | REL | APPR OPND | HB /B /37/HBBB-HCV-290403 | HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100026257 | SDBB valve on HBB-HCV-290403 passing | Desafing og leaktest | REL MANC PPRT PRC SETC | APPR RFRZ | 4 | 0 | OIM 10 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2020-09-21 | 2019-09-27 | 30 | REL | APPR OPND | HB /B /37/HBBB-HCV-290403 | HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100026257 | SDBB valve on HBB-HCV-290403 passing | SDBB / R18 | REL MANC PPRT PRC SETC | APPR RFRZ | 0 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2020-09-21 | 2019-09-27 | 40 | REL | APPR OPND | HB /B /37/HBBB-HCV-290403 | HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | VEN-MECH | 2100026261 | SMAT:64 Udskift HBB09 liftgas HCV-2909 | flush & greas valve - Vendor | REL MANC PRC SETC | APPR RFRZ | 12 | 0 |  | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2017-08-08 | 2017-05-10 | 4 | REL | APPR OPND | HB /B /37/HBBB-HCV-290903 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-SCAF | 2100026261 | SMAT:64 Udskift HBB09 liftgas HCV-2909 | Opsætning af taljer for rigging | REL MANC PRC SETC | APPR RFRZ | 2 | 0 |  | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2017-08-08 | 2017-05-10 | 5 | REL | APPR OPND | HB /B /37/HBBB-HCV-290903 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100026261 | SMAT:64 Udskift HBB09 liftgas HCV-2909 | Safing af HCV-290903 | REL MANC PRC SETC | APPR RFRZ | 2 | 0 |  | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2017-08-08 | 2017-05-10 | 10 | REL | APPR OPND | HB /B /37/HBBB-HCV-290903 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-SCAF | 2100026261 | SMAT:64 Udskift HBB09 liftgas HCV-2909 | Rigger assistance til skift af ventil | REL MANC PRC SETC | APPR RFRZ | 6 | 0 |  | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2017-08-08 | 2017-05-10 | 15 | REL | APPR OPND | HB /B /37/HBBB-HCV-290903 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100026261 | SMAT:64 Udskift HBB09 liftgas HCV-2909 | Udskiftning af HCV290903 | REL MANC PRC SETC | APPR RFRZ | 6 | 0 |  | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2017-08-08 | 2017-05-10 | 20 | REL | APPR OPND | HB /B /37/HBBB-HCV-290903 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100026261 | SMAT:64 Udskift HBB09 liftgas HCV-2909 | Desafing og leaktest | REL MANC PRC SETC | APPR RFRZ | 2 | 0 |  | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2017-08-08 | 2017-05-10 | 30 | REL | APPR OPND | HB /B /37/HBBB-HCV-290903 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-SCAF | 2100026261 | SMAT:64 Udskift HBB09 liftgas HCV-2909 | Nedtagning af taljer | REL MANC PRC SETC | APPR RFRZ | 2 | 0 |  | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2017-08-08 | 2017-05-10 | 60 | REL | APPR OPND | HB /B /37/HBBB-HCV-290903 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | VEN-MECH | 2100026262 | SMAT:64 Udskiftning af HCV-290703 | flush & greas valve - Vendor | REL MANC PRC SETC | APPR RFRZ | 12 | 0 |  | 2024-09-15 | 2024-11-18 | 2024-09-15 | 2017-08-08 | 2017-05-10 | 4 | REL | APPR OPND | HB /B /37/HBBB-HCV-290703 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-SCAF | 2100026262 | SMAT:64 Udskiftning af HCV-290703 | Opsætning af taljer for rigging | REL MANC PRC SETC | APPR RFRZ | 2 | 0 |  | 2024-09-15 | 2024-11-18 | 2024-11-14 | 2017-08-08 | 2017-05-10 | 5 | REL | APPR OPND | HB /B /37/HBBB-HCV-290703 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100026262 | SMAT:64 Udskiftning af HCV-290703 | Safing af HCV-290703 | REL MANC PRC SETC | APPR RFRZ | 2 | 0 |  | 2024-09-15 | 2024-11-18 | 2024-11-14 | 2017-08-08 | 2017-05-10 | 10 | REL | APPR OPND | HB /B /37/HBBB-HCV-290703 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-SCAF | 2100026262 | SMAT:64 Udskiftning af HCV-290703 | Rigger assistance til skift af ventil | REL MANC PRC SETC | APPR RFRZ | 6 | 0 |  | 2024-09-15 | 2024-11-18 | 2024-11-15 | 2017-08-08 | 2017-05-10 | 15 | REL | APPR OPND | HB /B /37/HBBB-HCV-290703 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100026262 | SMAT:64 Udskiftning af HCV-290703 | Udskiftning af HCV-290703 | REL MANC PRC SETC | APPR RFRZ | 6 | 0 |  | 2024-09-15 | 2024-11-18 | 2024-11-16 | 2017-08-08 | 2017-05-10 | 20 | REL | APPR OPND | HB /B /37/HBBB-HCV-290703 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100026262 | SMAT:64 Udskiftning af HCV-290703 | Desafing og leaktest | REL MANC PRC SETC | APPR RFRZ | 2 | 0 |  | 2024-09-15 | 2024-11-18 | 2024-11-17 | 2017-08-08 | 2017-05-10 | 30 | REL | APPR OPND | HB /B /37/HBBB-HCV-290703 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-SCAF | 2100026262 | SMAT:64 Udskiftning af HCV-290703 | Nedtagning af taljer | REL MANC PRC SETC | APPR RFRZ | 2 | 0 |  | 2024-09-15 | 2024-11-18 | 2024-11-18 | 2017-08-08 | 2017-05-10 | 60 | REL | APPR OPND | HB /B /37/HBBB-HCV-290703 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100022381 | Survey on WHCP Halfdan A & B | L3 Survey on WHCP Halfdan A & B | REL MANC NMAT PRC SETC | APPR RDBL | 39 | 0 |  | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2020-05-12 | 2019-05-18 | 10 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MMS | DK50
0 | 3 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100022448 | L1053577 - missing insulattion attached. | L3 Insulate spool on heattrace potable H | REL MANC NMAT PRC SETC | APPR RDBL | 2.7 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2019-08-11 | 2019-07-22 | 10 | REL | APPR OPND | HD /A /85 | SOFT WATER |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022515 | CMAT:Replace 4 Bellow(s) for HDBD-FAN-12 | L3 Scaff up HDBD-FAN-1217A/B | REL PRT MANC PRC SETC | APPR RDBL | 21 | 0 | W49-50 | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2022-03-05 | 2020-03-15 | 10 | REL | APPR OPND | HD /B /09/HDBD-FAN-1217A | AXIAL FAN |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100022515 | CMAT:Replace 4 Bellow(s) for HDBD-FAN-12 | L3 Replace 4 Bellow(s) for HDBD-FAN-1217 | REL PRT MANC PRC SETC | APPR RDBL | 26 | 0 | W49-50 | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2022-03-05 | 2020-03-15 | 20 | REL | APPR OPND | HD /B /09/HDBD-FAN-1217A | AXIAL FAN |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022515 | CMAT:Replace 4 Bellow(s) for HDBD-FAN-12 | L3 Scaff remove HDBD-FAN-1217A/B | REL PRT MANC PRC SETC | APPR RDBL | 14 | 0 | W49-50 | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2022-03-05 | 2020-03-15 | 30 | REL | APPR OPND | HD /B /09/HDBD-FAN-1217A | AXIAL FAN |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100022752 | SMAT:Leak on potwater system HDA lev.1 | Permit Preparation - Lagg | REL PCNF PRT MANC PRC SETC | APPR RDBL | 4.4 | 0 | W03-04 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2019-02-09 | 2019-01-20 | 41 | PCNF REL | APPR OPND | HD /A /85 | SOFT WATER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022752 | SMAT:Leak on potwater system HDA lev.1 | Build scaffold for change spool - scaf | REL PCNF PRT MANC PRC SETC | APPR RDBL | 26 | 0 | W03-04 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2019-02-09 | 2019-01-20 | 51 | PCNF REL | APPR OPND | HD /A /85 | SOFT WATER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100022752 | SMAT:Leak on potwater system HDA lev.1 | Remove insulate - Lagg | REL PCNF PRT MANC PRC SETC | APPR RDBL | 4.4 | 0 | W03-04 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2019-02-09 | 2019-01-20 | 52 | PCNF REL | APPR OPND | HD /A /85 | SOFT WATER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100022752 | SMAT:Leak on potwater system HDA lev.1 | Replace Insulate - Lagg | REL PCNF PRT MANC PRC SETC | APPR RDBL | 8.7 | 0 | W03-04 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2019-02-09 | 2019-01-20 | 100 | PCNF REL | APPR OPND | HD /A /85 | SOFT WATER |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022752 | SMAT:Leak on potwater system HDA lev.1 | Remove Scaffolding - Scaf | REL PCNF PRT MANC PRC SETC | APPR RDBL | 26 | 0 | W03-04 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2019-02-09 | 2019-01-20 | 110 | PCNF REL | APPR OPND | HD /A /85 | SOFT WATER |  | A |  | MMS | DK60
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022765 | Flowline well 13 HB ASTF finding | Flowline well 13 HB ASTF finding | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2025-01-23 | 2025-01-27 | 2025-01-23 | 2018-10-19 | 2018-07-21 | 10 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022765 | Flowline well 13 HB ASTF finding | build scaffold - Scaf | REL MANC NMAT PRC SETC | APPR RDBL | 26 | 0 |  | 2025-01-23 | 2025-01-27 | 2025-01-23 | 2018-10-19 | 2018-07-21 | 20 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022765 | Flowline well 13 HB ASTF finding | insert Teflon plate, between clamp and s | REL MANC NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2025-01-23 | 2025-01-27 | 2025-01-25 | 2018-10-19 | 2018-07-21 | 30 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022765 | Flowline well 13 HB ASTF finding | Ass. mech with teflon plate | REL MANC NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2025-01-23 | 2025-01-27 | 2025-01-25 | 2018-10-19 | 2018-07-21 | 40 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022765 | Flowline well 13 HB ASTF finding | remove scaffold - Scaf | REL MANC NMAT PRC SETC | APPR RDBL | 26 | 0 |  | 2025-01-23 | 2025-01-27 | 2025-01-25 | 2018-10-19 | 2018-07-21 | 50 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MMS | DK50
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-PIPF | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | Prepare Permit | REL PCNF CSER MANC PRC SETC | APPR RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-02-03 | 2018-09-06 | 1 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-SCAF | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | Prepare Permit | REL PCNF CSER MANC PRC SETC | APPR RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-02-03 | 2018-09-06 | 2 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-LAGG | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | Prepare Permit | REL PCNF CSER MANC PRC SETC | APPR RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-02-03 | 2018-09-06 | 3 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-SCAF | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | L3-Errect scaffold | REL PCNF CSER MANC PRC SETC | APPR RDBL | 50.3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2019-02-03 | 2018-09-06 | 20 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | PRODTECH | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | L3-Safe firesystem | REL PCNF CSER MANC PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-02-03 | 2018-09-06 | 25 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-LAGG | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | L3-Remove insulation | REL PCNF CSER MANC PRC SETC | APPR RDBL | 2.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-02-03 | 2018-09-06 | 30 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-PIPF | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | L1-Cut-off/remove old spool | REL PCNF CSER MANC PRC SETC | APPR RDBL | 5.4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-02-03 | 2018-09-06 | 40 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-PIPF | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | L1-Weld acc dwg | REL PCNF CSER MANC PRC SETC | APPR RDBL | 6.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-02-03 | 2018-09-06 | 50 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-PIPF | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | L1-Install new spool | REL PCNF CSER MANC PRC SETC | APPR RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-02-03 | 2018-09-06 | 60 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-PIPF | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | L1-Test | REL PCNF CSER MANC PRC SETC | APPR RDBL | 2.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-02-03 | 2018-09-06 | 70 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | QAQCELEC | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | L1-3rd party QC | REL PCNF CSER MANC PRC SETC | APPR RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-02-03 | 2018-09-06 | 80 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | PRODTECH | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | L3-Desafe firesystem | REL PCNF CSER MANC PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-02-03 | 2018-09-06 | 85 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-LAGG | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | L3-Re-install insulation | REL PCNF CSER MANC PRC SETC | APPR RDBL | 2.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-02-03 | 2018-09-06 | 90 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 4 | HD-DIFF | WDF | MTN-PIPF | MTN-SCAF | 2100023437 | CMAT:Extern leak on piping to WHR-0303 | L3-Dismantle scaffold | REL PCNF CSER MANC PRC SETC | APPR RDBL | 30.2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-02-03 | 2018-09-06 | 100 | PCNF REL | APPR OPND | HD /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION |  | C |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100023534 | ANOC CMAT:Genmontering af isolation lev | L3 Insulation reassembled + Cleaning | REL PCNF CSER MANC PRC SETC | APPR RDBL | 18.4 | 7 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2018-01-19 | 2017-12-10 | 50 | PCNF REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100023534 | ANOC CMAT:Genmontering af isolation lev | L3 cleaning | REL PCNF CSER MANC PRC SETC | APPR RDBL | 4 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2018-01-19 | 2017-12-10 | 60 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | VEN-ELEC | MTN-LAGG | 2100023651 | CMAT:HDB Skumstation Roof. HDBR-HCV-0335 | L3 Installation Isolation | REL PCNF CSER MANC PPRT PRC SETC | APPR RDBL | 6 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2018-12-15 | 2018-11-05 | 40 | REL | APPR OPND | HD /B /79 | INSULATION/TRACE HEATING |  | C |  | COW | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 509 | REL PCNF MANC PRC SETC | APPR RDBL | 200 | 156 | Move to next vendor visit | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 5 | PCNF REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 609 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 6 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 501 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 10 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 502 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 20 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 503 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 30 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 504 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 40 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 505 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 50 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 506 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 60 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 507 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 70 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 508 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 80 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 510 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 100 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 511 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 110 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 512 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 120 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 513 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 130 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 514 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 140 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 515 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 150 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 516 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 160 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 601 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 170 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 602 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 180 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 603 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 190 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 604 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 200 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 605 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 210 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 606 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 220 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 607 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 230 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 608 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 240 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 610 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 260 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 611 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 270 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 612 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 280 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 613 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 290 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 614 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 300 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 615 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 310 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100023757 | SMAT:HDA Vendor rep rust i ALL bathroom | fix corrosion in room 616 | REL PCNF MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-10-06 | 2024-09-15 | 2018-08-28 | 2018-07-19 | 320 | REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MMS | DK60
2024-W23-24 | 3 | HBB03-GL | WDF | MTN-INST | MTN-INST | 2100023848 | HBB03- piping on inforce and SSSV clash. | L3 isolate pipe. | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2018-01-01 | 2017-11-22 | 10 | REL | APPR OPND | HB /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER |  | C |  | MMS | DK50
2024-W23-24 | 3 | HBB03-GL | WDF | MTN-INST | MTN-INST | 2100023848 | HBB03- piping on inforce and SSSV clash. | L2 refit or change pipe | REL MANC NMAT PRC SETC | APPR RDBL | 13.4 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2018-01-01 | 2017-11-22 | 20 | REL | APPR OPND | HB /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER |  | C |  | MMS | DK50
2024-W23-24 | 3 | HBB03-GL | WDF | MTN-INST | MTN-INST | 2100023848 | HBB03- piping on inforce and SSSV clash. | L3 deisolate pipe and test | REL MANC NMAT PRC SETC | APPR RDBL | 0.7 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2018-01-01 | 2017-11-22 | 30 | REL | APPR OPND | HB /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER |  | C |  | MMS | DK50
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024364 | ANOS Replace severly corroded handrail H | L3 Permit & Preparation | REL PCNF PRT MANC PRC SETC | APPR RDBL | 8.7 | 4 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2020-02-28 | 2019-10-01 | 5 | PCNF REL | APPR OPND | HD /A /86/HANDRAIL | HANDRAIL | DK0500014729 | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024364 | ANOS Replace severly corroded handrail H | L3 Replace severly corroded handrail HDA | REL PCNF PRT MANC PRC SETC | APPR RDBL | 17.4 | 6 | MPM Team W21-22 | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2020-02-28 | 2019-10-01 | 10 | PCNF REL | APPR OPND | HD /A /86/HANDRAIL | HANDRAIL | DK0500014729 | A |  | MFM | DK60
2026-W13-14 | 4 | HB-DIFF | WDF | MTN-ROPE | PRODTECH | 2100024570 | ANOP Repair of hot water pipe leakage. | L3 isolate pipe for repair with pyplok | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-07-10 | 2019-02-10 | 10 | REL | APPR OPND | HB /C /72 | HOT WATER GENERATION AND DISTRIBUTION | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HB-DIFF | WDF | MTN-ROPE | VEN-MECH | 2100024570 | ANOP Repair of hot water pipe leakage. | L3 repair pipe - VENDOR scope | REL MANC NMAT PRC SETC | APPR RDBL | 10 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-07-10 | 2019-02-10 | 20 | REL | APPR OPND | HB /C /72 | HOT WATER GENERATION AND DISTRIBUTION | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HB-DIFF | WDF | MTN-ROPE | PRODTECH | 2100024570 | ANOP Repair of hot water pipe leakage. | L3 deisolate pipe after repair with pyp | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-07-10 | 2019-02-10 | 30 | REL | APPR OPND | HB /C /72 | HOT WATER GENERATION AND DISTRIBUTION | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HB-DIFF | WDF | MTN-ROPE | VEN-MECH | 2100024570 | ANOP Repair of hot water pipe leakage. | L3 insulate pipe after repair | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-07-10 | 2019-02-10 | 40 | REL | APPR OPND | HB /C /72 | HOT WATER GENERATION AND DISTRIBUTION | 99000087 | C |  | MFM | DK50
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100024582 | SMAT:Small leakage from spindel HDBM-A-1 | L3 Build repo | REL MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2019-05-28 | 2019-05-08 | 5 | REL | APPR OPND | HD /B /85/HDBM-A-1208 | CONDENSER PACKAGE |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100024582 | SMAT:Small leakage from spindel HDBM-A-1 | L3 Isolation HDBM-A-1208 | REL MANC PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2019-05-28 | 2019-05-08 | 10 | REL | APPR OPND | HD /B /85/HDBM-A-1208 | CONDENSER PACKAGE |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100024582 | SMAT:Small leakage from spindel HDBM-A-1 | L3 Change seal HDBM-A-1208 | REL MANC PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2019-05-28 | 2019-05-08 | 20 | REL | APPR OPND | HD /B /85/HDBM-A-1208 | CONDENSER PACKAGE |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100024582 | SMAT:Small leakage from spindel HDBM-A-1 | L3 De-Isolation HDBM-A-1208 | REL MANC PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2019-05-28 | 2019-05-08 | 30 | REL | APPR OPND | HD /B /85/HDBM-A-1208 | CONDENSER PACKAGE |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100024582 | SMAT:Small leakage from spindel HDBM-A-1 | L3 Test leak HDBM-A-1208 | REL MANC PRC SETC | APPR RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2019-05-28 | 2019-05-08 | 40 | REL | APPR OPND | HD /B /85/HDBM-A-1208 | CONDENSER PACKAGE |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100024582 | SMAT:Small leakage from spindel HDBM-A-1 | L3 REmove repo | REL MANC PRC SETC | APPR RDBL | 4 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2019-05-28 | 2019-05-08 | 50 | REL | APPR OPND | HD /B /85/HDBM-A-1208 | CONDENSER PACKAGE |  | A |  | MMS | DK60
2024-W27-28 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024745 | SMAT:CHNG multifunction network analyzer | L3 isolate display | REL PRT MANC PRC SETC | APPR RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2020-10-17 | 2019-10-23 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-3-1 | SUPPLY TO HBCA-N-1840B |  | C |  | MEL | DK50 |  |  | 2024-06-02
2024-W27-28 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024745 | SMAT:CHNG multifunction network analyzer | L2 change display | REL PRT MANC PRC SETC | APPR RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2020-10-17 | 2019-10-23 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-3-1 | SUPPLY TO HBCA-N-1840B |  | C |  | MEL | DK50 |  |  | 2024-06-04
2024-W27-28 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024745 | SMAT:CHNG multifunction network analyzer | L3 deisolate display | REL PRT MANC PRC SETC | APPR RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2020-10-17 | 2019-10-23 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-3-1 | SUPPLY TO HBCA-N-1840B |  | C |  | MEL | DK50 |  |  | 2024-06-06
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100024746 | CMAT:Change multifunction network analyz | L3 isolate display | REL MANC PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2020-10-17 | 2019-10-23 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-4-1 | INCOMING FROM HBCM-G-1732 (52-GA) |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100024746 | CMAT:Change multifunction network analyz | L2 change display | REL MANC PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2020-10-17 | 2019-10-23 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-4-1 | INCOMING FROM HBCM-G-1732 (52-GA) |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100024746 | CMAT:Change multifunction network analyz | L3 deisolate display | REL MANC PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2020-10-17 | 2019-10-23 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-4-1 | INCOMING FROM HBCM-G-1732 (52-GA) |  | C |  | MEL | DK50
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100026445 | CMAT:Repair AHU for HVAC ACC HDB | L3 isolate system | REL MANC PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2018-11-29 | 2018-10-20 | 15 | REL | APPR OPND | HD /B /09/HDBD-A-1201 | ACCOMMODATION AIR HANDLING UNIT |  | A |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100026445 | CMAT:Repair AHU for HVAC ACC HDB | L3 Close gap | REL MANC PRC SETC | APPR RDBL | 48 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2018-11-29 | 2018-10-20 | 20 | REL | APPR OPND | HD /B /09/HDBD-A-1201 | ACCOMMODATION AIR HANDLING UNIT |  | A |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100026445 | CMAT:Repair AHU for HVAC ACC HDB | L3 deisolate system | REL MANC PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2018-11-29 | 2018-10-20 | 25 | REL | APPR OPND | HD /B /09/HDBD-A-1201 | ACCOMMODATION AIR HANDLING UNIT |  | A |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100026445 | CMAT:Repair AHU for HVAC ACC HDB | L3 Clean up after work. | REL MANC PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2018-11-29 | 2018-10-20 | 30 | REL | APPR OPND | HD /B /09/HDBD-A-1201 | ACCOMMODATION AIR HANDLING UNIT |  | A |  | MEL | DK60
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100026955 | HBBA-A-39570 / 39580 Failure-Vendor vi | L3 Isolate HBBA-A-39570 | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-21 | 2024-03-11 | 2019-08-11 | 2019-05-13 | 20 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100026955 | HBBA-A-39570 / 39580 Failure-Vendor vi | L2 Vendor service-regulating valves | REL MANC NMAT PRC SETC | APPR RDBL | 30 | 0 |  | 2024-03-11 | 2024-03-21 | 2024-03-11 | 2019-08-11 | 2019-05-13 | 30 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026955 | HBBA-A-39570 / 39580 Failure-Vendor vi | L3 Vendor assist | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2024-03-11 | 2024-03-21 | 2024-03-11 | 2019-08-11 | 2019-05-13 | 35 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100026955 | HBBA-A-39570 / 39580 Failure-Vendor vi | L3 De-isolate/test HBBA-A-39570 | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-21 | 2024-03-14 | 2019-08-11 | 2019-05-13 | 40 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026955 | HBBA-A-39570 / 39580 Failure-Vendor vi | L2 Vendor update documentation | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-21 | 2024-03-15 | 2019-08-11 | 2019-05-13 | 50 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100026955 | HBBA-A-39570 / 39580 Failure-Vendor vi | L3 Isolate HBBA-A-39580 | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-21 | 2024-03-16 | 2019-08-11 | 2019-05-13 | 60 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100026955 | HBBA-A-39570 / 39580 Failure-Vendor vi | L2 Vendor service-regulating valves | REL MANC NMAT PRC SETC | APPR RDBL | 30 | 0 |  | 2024-03-11 | 2024-03-21 | 2024-03-16 | 2019-08-11 | 2019-05-13 | 70 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026955 | HBBA-A-39570 / 39580 Failure-Vendor vi | L3 Vendor assist | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-21 | 2024-03-16 | 2019-08-11 | 2019-05-13 | 75 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100026955 | HBBA-A-39570 / 39580 Failure-Vendor vi | L3 De-isolate/test HBBA-A-39580 | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-21 | 2024-03-20 | 2019-08-11 | 2019-05-13 | 80 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026955 | HBBA-A-39570 / 39580 Failure-Vendor vi | L2 Vendor update documentation | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-21 | 2024-03-20 | 2019-08-11 | 2019-05-13 | 90 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | PRODTECH | MTN-ELEC | 2100032003 | Level glass on HP seperator dirty | Isolate heat tracing | REL PRT MANC NMAT PRC SETC | APPR RDBL | 0.5 | 0 |  | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2021-04-25 | 2020-08-28 | 10 | REL | APPR OPND | HB /D /20/HBDC-LG-345132 | LEVEL GLASS |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | PRODTECH | PRODTECH | 2100032003 | Level glass on HP seperator dirty | Isolate level glass | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2021-04-25 | 2020-08-28 | 20 | REL | APPR OPND | HB /D /20/HBDC-LG-345132 | LEVEL GLASS |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | PRODTECH | PRODTECH | 2100032003 | Level glass on HP seperator dirty | Clean level glass | REL PRT MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2021-04-25 | 2020-08-28 | 30 | REL | APPR OPND | HB /D /20/HBDC-LG-345132 | LEVEL GLASS |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | PRODTECH | PRODTECH | 2100032003 | Level glass on HP seperator dirty | De-isolate level glass | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2021-04-25 | 2020-08-28 | 40 | REL | APPR OPND | HB /D /20/HBDC-LG-345132 | LEVEL GLASS |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | PRODTECH | MTN-ELEC | 2100032003 | Level glass on HP seperator dirty | De-isolate heat tracing | REL PRT MANC NMAT PRC SETC | APPR RDBL | 0.5 | 0 |  | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2021-04-25 | 2020-08-28 | 50 | REL | APPR OPND | HB /D /20/HBDC-LG-345132 | LEVEL GLASS |  | A |  | MIN | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100035820 | Corroded antenna supports | Corroded Helideck Nav Supports & Cables | REL PCNF CSER MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2022-11-07 | 2022-11-08 | 2022-11-07 | 2020-11-19 | 2020-08-21 | 10 | PCNF REL | APPR OPND | HB /C /02/HELIDECK-EQUIPMENT | HELIDECK EQUIPMENT |  | A |  | MIN | DK50 |  |  | 2024-06-02
2024-W21-22 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100035820 | Corroded antenna supports | Work to be done at HBC Helideck | REL PCNF CSER MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2022-11-07 | 2022-11-08 | 2022-11-07 | 2020-11-19 | 2020-08-21 | 20 | PCNF REL | APPR OPND | HB /C /02/HELIDECK-EQUIPMENT | HELIDECK EQUIPMENT |  | A |  | MIN | DK50 |  |  | 2024-06-03
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038402 | Installation of mcb on batt bank 17022 | Setup UNISTRUT and box for MCB | REL PRT MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2021-01-09 | 2020-10-11 | 10 | REL | APPR OPND | HD /B /05/HDBD-BAT-17022 | STARTER BATTERY BANK |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100038402 | Installation of mcb on batt bank 17022 | Isolate battery chargers | REL PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2021-01-09 | 2020-10-11 | 20 | REL | APPR OPND | HD /B /05/HDBD-BAT-17022 | STARTER BATTERY BANK |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038402 | Installation of mcb on batt bank 17022 | Install MCB and cables | REL PRT MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-01-09 | 2020-10-11 | 30 | REL | APPR OPND | HD /B /05/HDBD-BAT-17022 | STARTER BATTERY BANK |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100038402 | Installation of mcb on batt bank 17022 | De-isolate above | REL PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-01-09 | 2020-10-11 | 40 | REL | APPR OPND | HD /B /05/HDBD-BAT-17022 | STARTER BATTERY BANK |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038402 | Installation of mcb on batt bank 17022 | AS BUILT update drawings | REL PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-01-09 | 2020-10-11 | 50 | REL | APPR OPND | HD /B /05/HDBD-BAT-17022 | STARTER BATTERY BANK |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038403 | Installation of mcb on batt bank 17039 | Setup UNISTRUT and box for MCB | REL PRT MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2021-01-09 | 2020-10-11 | 10 | REL | APPR OPND | HD /B /05/HDBD-BAT-17039 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100038403 | Installation of mcb on batt bank 17039 | Isolate battery chargers | REL PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2021-01-09 | 2020-10-11 | 20 | REL | APPR OPND | HD /B /05/HDBD-BAT-17039 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038403 | Installation of mcb on batt bank 17039 | Install MCB and cables | REL PRT MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-01-09 | 2020-10-11 | 30 | REL | APPR OPND | HD /B /05/HDBD-BAT-17039 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100038403 | Installation of mcb on batt bank 17039 | De-isolate above | REL PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-01-09 | 2020-10-11 | 40 | REL | APPR OPND | HD /B /05/HDBD-BAT-17039 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038403 | Installation of mcb on batt bank 17039 | AS BUILT update drawings | REL PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-01-09 | 2020-10-11 | 50 | REL | APPR OPND | HD /B /05/HDBD-BAT-17039 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038404 | Installation of mcb on batt bank 17040 | Setup UNISTRUT and box for MCB | REL PRT MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2021-01-09 | 2020-10-11 | 10 | REL | APPR OPND | HD /B /05/HDBD-BAT-17040 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100038404 | Installation of mcb on batt bank 17040 | Isolate battery chargers | REL PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2021-01-09 | 2020-10-11 | 20 | REL | APPR OPND | HD /B /05/HDBD-BAT-17040 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038404 | Installation of mcb on batt bank 17040 | Install MCB and cables | REL PRT MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-01-09 | 2020-10-11 | 30 | REL | APPR OPND | HD /B /05/HDBD-BAT-17040 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100038404 | Installation of mcb on batt bank 17040 | De-isolate above | REL PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-01-09 | 2020-10-11 | 40 | REL | APPR OPND | HD /B /05/HDBD-BAT-17040 | STARTER BATTERY |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100038404 | Installation of mcb on batt bank 17040 | AS BUILT update drawings | REL PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-01-09 | 2020-10-11 | 50 | REL | APPR OPND | HD /B /05/HDBD-BAT-17040 | STARTER BATTERY |  | C |  | MEL | DK60
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100040962 | FLMPR. Attach Loose Deluge pipework Clam | Attach Loose Deluge pipework Clamp | REL NMAT PRC SETC | APPR RDBL | 18 | 0 |  | 2022-03-28 | 2022-03-29 | 2022-03-28 | 2021-10-30 | 2021-03-04 | 10 | REL | APPR OPND | HB /B /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | 99000087 | A |  | MFM | DK50
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100041185 | ANOS HDA - Loose wind walls EL+28,000 | HDA - Loose wind walls EL+28,000 | REL CSER MANC NMAT PRC SETC | APPR RDBL | 8 | 0 |  | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2021-07-04 | 2021-02-04 | 10 | REL | APPR OPND | HD /A /86/TOPSIDES | TOPSIDE STRUCTURES |  | A |  | MFM | DK60
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Inspection of valve and actuatot | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-01 | 2021-05-11 | 2021-02-10 | 10 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | prep. for permit, site visit, job - Mech | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 | Job requires Material | 2025-01-01 | 2025-02-09 | 2025-01-01 | 2021-05-11 | 2021-02-10 | 20 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | prep. for permit, site visit, job - Rigg | REL MANC NMAT PRC SETC | APPR RDBL | 10 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-02 | 2021-05-11 | 2021-02-10 | 30 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | prep tools and equipment - Mech | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-04 | 2021-05-11 | 2021-02-10 | 40 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | prep tools and equipment - Rigg | REL MANC NMAT PRC SETC | APPR RDBL | 10 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-05 | 2021-05-11 | 2021-02-10 | 50 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Build scaff - Scaf | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-07 | 2021-05-11 | 2021-02-10 | 55 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Isolate valve - Prod | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-08 | 2021-05-11 | 2021-02-10 | 60 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Remove valve - Mech | REL MANC NMAT PRC SETC | APPR RDBL | 24 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-08 | 2021-05-11 | 2021-02-10 | 70 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Remove valve - Rigg | REL MANC NMAT PRC SETC | APPR RDBL | 50 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-13 | 2021-05-11 | 2021-02-10 | 80 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Install blinds - Mech | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-17 | 2021-05-11 | 2021-02-10 | 90 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Ship valve for Service | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-19 | 2021-05-11 | 2021-02-10 | 100 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Rig down equipment - Rigg | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-20 | 2021-05-11 | 2021-02-10 | 110 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Leaktest - Prod | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-20 | 2021-05-11 | 2021-02-10 | 120 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | prep. for permit, site visit, job - Mech | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-21 | 2021-05-11 | 2021-02-10 | 130 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | prep. for permit, site visit, job - Rigg | REL MANC NMAT PRC SETC | APPR RDBL | 10 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-22 | 2021-05-11 | 2021-02-10 | 140 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | prep tools and equipment - Rigg | REL MANC NMAT PRC SETC | APPR RDBL | 10 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-24 | 2021-05-11 | 2021-02-10 | 150 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | prep tools and equipment - Mech | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-26 | 2021-05-11 | 2021-02-10 | 160 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Isolate blinds - Prod | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-27 | 2021-05-11 | 2021-02-10 | 170 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Build scaff - Scaf | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-27 | 2021-05-11 | 2021-02-10 | 175 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Install valve - Mech | REL MANC NMAT PRC SETC | APPR RDBL | 24 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-01-28 | 2021-05-11 | 2021-02-10 | 180 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Install valve - Rigg | REL MANC NMAT PRC SETC | APPR RDBL | 50 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-02-02 | 2021-05-11 | 2021-02-10 | 190 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Mount Hydra. panel & El - INST | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-02-05 | 2021-05-11 | 2021-02-10 | 200 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | De-isolate, leak test etc - Prod | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-02-06 | 2021-05-11 | 2021-02-10 | 210 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | Rig down equipment - Rigg | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-02-07 | 2021-05-11 | 2021-02-10 | 220 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | house keeping - Mech | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-02-08 | 2021-05-11 | 2021-02-10 | 230 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | house keeping - Rigg | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-02-08 | 2021-05-11 | 2021-02-10 | 240 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100044427 | Inspection of valve and actuator | house keeping - Scaf | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2025-01-01 | 2025-02-09 | 2025-02-09 | 2021-05-11 | 2021-02-10 | 250 | REL | APPR OPND | HB /A /10/HBAA-HCV-34016 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2025-W11-12 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100050077 | Diagnostic alarms in FG-ESD-SCADA | Faultfinding on the systems W10-11 2024 | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 30 | 0 | W10-11 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2021-05-03 | 2021-03-24 | 40 | PCNF REL | APPR OPND | HB /D /03 | ESD AND FIRE & GAS |  | A |  | MIN | DK50
2024-W15-16 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100050151 | Siemens SCADA HMI errors | Siemens SCADA HMI errors | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-09-09 | 2021-06-11 | 10 | PCNF REL | APPR OPND | HB /D /04/HBDC-OS-2050 | SERVICE & MAINTENANCE OPERATOR STATION |  | A |  | MIN | DK50 |  |  | 2024-04-13
2024-W15-16 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100050151 | Siemens SCADA HMI errors | Faultfinding by Telecom | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 6 | 5 | W11-12 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-09-09 | 2021-06-11 | 20 | PCNF REL | APPR OPND | HB /D /04/HBDC-OS-2050 | SERVICE & MAINTENANCE OPERATOR STATION |  | A |  | MIN | DK50 |  |  | 2024-04-14
2026-W13-14 | 4 | HBOIL-SD | WDF | MTN-MECH | VEN-MECH | 2100051522 | Replace grease nipple on HCV-30118 | prep for job | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-06-11 | 2021-10-14 | 10 | REL | APPR OPND | HB /A /10/HBAA-XCV-30118 | 8" 2500# T PLUG VALVE FROM WELL 11 |  | A |  | MMS | DK50
2026-W13-14 | 4 | HBOIL-SD | WDF | MTN-MECH | PRODTECH | 2100051522 | Replace grease nipple on HCV-30118 | isolate valve | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-06-11 | 2021-10-14 | 20 | REL | APPR OPND | HB /A /10/HBAA-XCV-30118 | 8" 2500# T PLUG VALVE FROM WELL 11 |  | A |  | MMS | DK50
2026-W13-14 | 4 | HBOIL-SD | WDF | MTN-MECH | VEN-MECH | 2100051522 | Replace grease nipple on HCV-30118 | replace grease nippel / check valve | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-06-11 | 2021-10-14 | 30 | REL | APPR OPND | HB /A /10/HBAA-XCV-30118 | 8" 2500# T PLUG VALVE FROM WELL 11 |  | A |  | MMS | DK50
2026-W13-14 | 4 | HBOIL-SD | WDF | MTN-MECH | PRODTECH | 2100051522 | Replace grease nipple on HCV-30118 | de-isolate, leak test, etc. | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2022-06-11 | 2021-10-14 | 40 | REL | APPR OPND | HB /A /10/HBAA-XCV-30118 | 8" 2500# T PLUG VALVE FROM WELL 11 |  | A |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100051607 | HBBB-HCV-290103 internal leak | Greasing of valves | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2022-10-11 | 2021-12-15 | 10 | REL | APPR OPND | HB /B /37/HBBB-HCV-290103 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100051607 | HBBB-HCV-290103 internal leak | Inflow Test valves | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-09 | 2022-10-11 | 2021-12-15 | 20 | REL | APPR OPND | HB /B /37/HBBB-HCV-290103 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | MTN-MECH | 2100051608 | HBB-03 HCV-290303 internal leaking | Greasing of valves | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2022-10-11 | 2021-12-15 | 10 | REL | APPR OPND | HB /B /37/HBBB-HCV-290303 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | MTN-MECH | PRODTECH | 2100051608 | HBB-03 HCV-290303 internal leaking | Inflow Test valves | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-09 | 2022-10-11 | 2021-12-15 | 20 | REL | APPR OPND | HB /B /37/HBBB-HCV-290303 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100054897 | FLMR HBD - Repair of Handrail EL +40500 | HBD - Repair of Handrail EL +40500 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2021-12-25 | 2021-12-27 | 2021-12-25 | 2022-08-22 | 2021-12-25 | 10 | REL | APPR OPND | HB /D /86/40500 - GRATINGS | 40500 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100054897 | FLMR HBD - Repair of Handrail EL +40500 | Mechanical prep/bristle blast | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2021-12-25 | 2021-12-27 | 2021-12-25 | 2022-08-22 | 2021-12-25 | 20 | REL | APPR OPND | HB /D /86/40500 - GRATINGS | 40500 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100054897 | FLMR HBD - Repair of Handrail EL +40500 | Paint up to spec | REL NMAT PRC SETC | APPR RDBL | 12 | 0 |  | 2021-12-25 | 2021-12-27 | 2021-12-25 | 2022-08-22 | 2021-12-25 | 30 | REL | APPR OPND | HB /D /86/40500 - GRATINGS | 40500 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100054897 | FLMR HBD - Repair of Handrail EL +40500 | Clean up worksite | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2021-12-25 | 2021-12-27 | 2021-12-27 | 2022-08-22 | 2021-12-25 | 40 | REL | APPR OPND | HB /D /86/40500 - GRATINGS | 40500 - GRATINGS |  | A |  | MFM | DK50
2024-W47-48 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100059466 | Seep in Acc. Skid HBBA-A-5914 | ICC | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W47-48 BL Team SD!!! | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-03-26 | 2021-12-26 | 10 | REL | APPR OPND | HB /B /07/HBBA-A-5914 | HYDRAULIC ACCUMULATOR PACKAGE |  | A |  | MMS | DK50
2024-W47-48 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100059466 | Seep in Acc. Skid HBBA-A-5914 | Retighten fitting nut's | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W47-48 BL Team SD!!! | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-03-26 | 2021-12-26 | 20 | REL | APPR OPND | HB /B /07/HBBA-A-5914 | HYDRAULIC ACCUMULATOR PACKAGE |  | A |  | MMS | DK50
2024-W47-48 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100059466 | Seep in Acc. Skid HBBA-A-5914 | De-isolate, leak test | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W47-48 BL Team SD!!! | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2022-03-26 | 2021-12-26 | 30 | REL | APPR OPND | HB /B /07/HBBA-A-5914 | HYDRAULIC ACCUMULATOR PACKAGE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100059895 | LOTI ANOP External leak in pipe Pot wate | External leak in pipe Pot water distrib. | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-30 | 2023-04-24 | 2022-04-03 | 2022-01-03 | 10 | REL | APPR OPND | HB /D /85 | SOFT WATER | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059895 | LOTI ANOP External leak in pipe Pot wate | Remove panels and isolation for finding | REL MANC NMAT PRC SETC | APPR RDBL | 100 | 0 |  | 2023-04-24 | 2023-04-30 | 2023-04-24 | 2022-04-03 | 2022-01-03 | 20 | REL | APPR OPND | HB /D /85 | SOFT WATER | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059895 | LOTI ANOP External leak in pipe Pot wate | Install wrap or straub coupling to stop | REL MANC NMAT PRC SETC | APPR RDBL | 36 | 0 |  | 2023-04-24 | 2023-04-30 | 2023-04-27 | 2022-04-03 | 2022-01-03 | 30 | REL | APPR OPND | HB /D /85 | SOFT WATER | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059895 | LOTI ANOP External leak in pipe Pot wate | MPM permits | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 |  | 2023-04-24 | 2023-04-30 | 2023-04-29 | 2022-04-03 | 2022-01-03 | 40 | REL | APPR OPND | HB /D /85 | SOFT WATER | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HBB07-GL | WDF | MTN-MECH | PRODTECH | 2100060506 | Minor hydraulic seep from actuator | Production Isolation | REL MANC PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2022-08-14 | 2022-03-17 | 10 | REL | APPR OPND | HB /B /37/HBBB-FCV-290702 | GAS LIFT CONTROL VALVE, HBB-07 |  | C |  | MMS | DK50
2026-W13-14 | 4 | HBB07-GL | WDF | MTN-MECH | MTN-INST | 2100060506 | Minor hydraulic seep from actuator | Instrument assistance | REL MANC PRC SETC | APPR RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-08-14 | 2022-03-17 | 20 | REL | APPR OPND | HB /B /37/HBBB-FCV-290702 | GAS LIFT CONTROL VALVE, HBB-07 |  | C |  | MMS | DK50
2026-W13-14 | 4 | HBB07-GL | WDF | MTN-MECH | MTN-MECH | 2100060506 | Minor hydraulic seep from actuator | Replace FCV Actuator | REL MANC PRC SETC | APPR RDBL | 12 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-08-14 | 2022-03-17 | 30 | REL | APPR OPND | HB /B /37/HBBB-FCV-290702 | GAS LIFT CONTROL VALVE, HBB-07 |  | C |  | MMS | DK50
2026-W13-14 | 4 | HBB07-GL | WDF | MTN-MECH | PRODTECH | 2100060506 | Minor hydraulic seep from actuator | Production De-isolation w Func. test | REL MANC PRC SETC | APPR RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2022-08-14 | 2022-03-17 | 40 | REL | APPR OPND | HB /B /37/HBBB-FCV-290702 | GAS LIFT CONTROL VALVE, HBB-07 |  | C |  | MMS | DK50
2026-W13-14 | 3 | HBA23-GL | WDF | MTN-ROPE | MTN-ROPE | 2100061653 | Instrument pipe rubbing against metal | Install paralel piping | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-03-13 | 2022-02-01 | 9 | REL | APPR OPND | HB /A /10/HBAA-XCV-30238 | 8" 2500# T PLUG VALVE FROM WELL 23 | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HBA23-GL | WDF | MTN-ROPE | PRODTECH | 2100061653 | Instrument pipe rubbing against metal | Isolate Valve | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-03-13 | 2022-02-01 | 10 | REL | APPR OPND | HB /A /10/HBAA-XCV-30238 | 8" 2500# T PLUG VALVE FROM WELL 23 | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HBA23-GL | WDF | MTN-ROPE | MTN-ROPE | 2100061653 | Instrument pipe rubbing against metal | Connect new piping to control panel | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-03-13 | 2022-02-01 | 50 | REL | APPR OPND | HB /A /10/HBAA-XCV-30238 | 8" 2500# T PLUG VALVE FROM WELL 23 | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HBA23-GL | WDF | MTN-ROPE | PRODTECH | 2100061653 | Instrument pipe rubbing against metal | Deisolate and test Valve | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-03-13 | 2022-02-01 | 60 | REL | APPR OPND | HB /A /10/HBAA-XCV-30238 | 8" 2500# T PLUG VALVE FROM WELL 23 | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HBA23-GL | WDF | MTN-ROPE | MTN-ROPE | 2100061653 | Instrument pipe rubbing against metal | Remove old Piping | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-03-13 | 2022-02-01 | 69 | REL | APPR OPND | HB /A /10/HBAA-XCV-30238 | 8" 2500# T PLUG VALVE FROM WELL 23 | 99000119 | E |  | MIN | DK50
0 | 4 | NE | WDF | MTN-MECH | MTN-ROPE | 2100062364 | DWESR HDA - Replace of Handrail EL +1925 | HDA - Replace of Handrail EL +19250 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-04 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 10 | REL | APPR OPND | HD /A /86/18500 - HANDRAILS | 18500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062364 | DWESR HDA - Replace of Handrail EL +1925 | Build Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 16 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-04 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 20 | REL | APPR OPND | HD /A /86/18500 - HANDRAILS | 18500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062364 | DWESR HDA - Replace of Handrail EL +1925 | Cut horisontal ends of handrails | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-04 | 2024-07-31 | 2022-09-21 | 2022-04-24 | 30 | REL | APPR OPND | HD /A /86/18500 - HANDRAILS | 18500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062364 | DWESR HDA - Replace of Handrail EL +1925 | Install new handrail | REL MANC NMAT PRC SETC | APPR RDBL | 28 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-04 | 2024-07-31 | 2022-09-21 | 2022-04-24 | 40 | REL | APPR OPND | HD /A /86/18500 - HANDRAILS | 18500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100062364 | DWESR HDA - Replace of Handrail EL +1925 | Paint open spots | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-04 | 2024-08-02 | 2022-09-21 | 2022-04-24 | 50 | REL | APPR OPND | HD /A /86/18500 - HANDRAILS | 18500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062364 | DWESR HDA - Replace of Handrail EL +1925 | Remove Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-04 | 2024-08-03 | 2022-09-21 | 2022-04-24 | 60 | REL | APPR OPND | HD /A /86/18500 - HANDRAILS | 18500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062364 | DWESR HDA - Replace of Handrail EL +1925 | Installation Report | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-04 | 2024-08-03 | 2022-09-21 | 2022-04-24 | 70 | REL | APPR OPND | HD /A /86/18500 - HANDRAILS | 18500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | HDA - Replace of Handrail EL +28000 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 10 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | HDA-L2-HR-10 - Not in report | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 20 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | Build Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 30 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | Install new handrail | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-07-31 | 2022-09-21 | 2022-04-24 | 40 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | Remove Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 9 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-01 | 2022-09-21 | 2022-04-24 | 50 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | Installation Report | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-02 | 2022-09-21 | 2022-04-24 | 60 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | HDA-L2-HR-11 - Photo 9 in report | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-02 | 2022-09-21 | 2022-04-24 | 70 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | Build Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-02 | 2022-09-21 | 2022-04-24 | 80 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | Cut horisontal ends of handrails | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-04 | 2022-09-21 | 2022-04-24 | 90 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | Paint open spots | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-04 | 2022-09-21 | 2022-04-24 | 100 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | Install new handrail | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-05 | 2022-09-21 | 2022-04-24 | 110 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | Remove Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 9 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-05 | 2022-09-21 | 2022-04-24 | 120 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | Installation Report | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-06 | 2022-09-21 | 2022-04-24 | 130 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062367 | DWESR HDA - Replace of Handrail EL +2800 | Mount clamps (23pcs) | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-06 | 2022-09-21 | 2022-04-24 | 140 | REL | APPR OPND | HD /A /86/28000 - HANDRAILS | 28000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-ROPE | 2100062368 | DWESR HDA - Replace of Handrail EL +3950 | HDA - Replace of Handrail EL +39500 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 10 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062368 | DWESR HDA - Replace of Handrail EL +3950 | Build Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 32 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 20 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062368 | DWESR HDA - Replace of Handrail EL +3950 | Remove existing handrails | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-02 | 2022-09-21 | 2022-04-24 | 30 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062368 | DWESR HDA - Replace of Handrail EL +3950 | Install new handrails | REL MANC NMAT PRC SETC | APPR RDBL | 46 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-02 | 2022-09-21 | 2022-04-24 | 50 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062368 | DWESR HDA - Replace of Handrail EL +3950 | Remove Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 16 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-05 | 2022-09-21 | 2022-04-24 | 60 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062368 | DWESR HDA - Replace of Handrail EL +3950 | Installation Report | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-06 | 2022-09-21 | 2022-04-24 | 70 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062368 | DWESR HDA - Replace of Handrail EL +3950 | Mount clamps (10pcs) | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-07 | 2024-08-06 | 2022-09-21 | 2022-04-24 | 80 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062369 | DWESR HDA - Replace of Handrail EL +4700 | HDA - Replace of Handrail EL +47000 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-09 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 10 | REL | APPR OPND | HD /A /86/47000 - HANDRAILS | 47000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062369 | DWESR HDA - Replace of Handrail EL +4700 | Build Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 30.6 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-09 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 20 | REL | APPR OPND | HD /A /86/47000 - HANDRAILS | 47000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062369 | DWESR HDA - Replace of Handrail EL +4700 | Cut horisontal ends of handrails | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-09 | 2024-08-02 | 2022-09-21 | 2022-04-24 | 30 | REL | APPR OPND | HD /A /86/47000 - HANDRAILS | 47000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100062369 | DWESR HDA - Replace of Handrail EL +4700 | Paint open spots | REL MANC NMAT PRC SETC | APPR RDBL | 16 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-09 | 2024-08-02 | 2022-09-21 | 2022-04-24 | 31 | REL | APPR OPND | HD /A /86/47000 - HANDRAILS | 47000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062369 | DWESR HDA - Replace of Handrail EL +4700 | Drill holes for handrail base/mount | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-09 | 2024-08-03 | 2022-09-21 | 2022-04-24 | 40 | REL | APPR OPND | HD /A /86/47000 - HANDRAILS | 47000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100062369 | DWESR HDA - Replace of Handrail EL +4700 | Paint/prime drilled holes | REL MANC NMAT PRC SETC | APPR RDBL | 9 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-09 | 2024-08-04 | 2022-09-21 | 2022-04-24 | 41 | REL | APPR OPND | HD /A /86/47000 - HANDRAILS | 47000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062369 | DWESR HDA - Replace of Handrail EL +4700 | Install new handrail | REL MANC NMAT PRC SETC | APPR RDBL | 46 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-09 | 2024-08-04 | 2022-09-21 | 2022-04-24 | 50 | REL | APPR OPND | HD /A /86/47000 - HANDRAILS | 47000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062369 | DWESR HDA - Replace of Handrail EL +4700 | Remove Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 15.3 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-09 | 2024-08-07 | 2022-09-21 | 2022-04-24 | 60 | REL | APPR OPND | HD /A /86/47000 - HANDRAILS | 47000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062369 | DWESR HDA - Replace of Handrail EL +4700 | Installation Report | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-09 | 2024-08-08 | 2022-09-21 | 2022-04-24 | 70 | REL | APPR OPND | HD /A /86/47000 - HANDRAILS | 47000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062369 | DWESR HDA - Replace of Handrail EL +4700 | Mount clamps (18pcs) | REL MANC NMAT PRC SETC | APPR RDBL | 9 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-09 | 2024-08-08 | 2022-09-21 | 2022-04-24 | 180 | REL | APPR OPND | HD /A /86/47000 - HANDRAILS | 47000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062370 | DWESR HDA - Replace of Handrail EL +3500 | HDA - Replace of Handrail EL +35000 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | 24-W03-04 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 10 | REL | APPR OPND | HD /A /86/35000 - HANDRAILS | 35000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062370 | DWESR HDA - Replace of Handrail EL +3500 | Mount clamps (11pcs) | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 | 24-W03-04 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 20 | REL | APPR OPND | HD /A /86/35000 - HANDRAILS | 35000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-ROPE | 2100062372 | DWESR HDB - Repl of Handrail EL +22000 | HDB - Replace of Handrail EL +22000 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-14 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 10 | REL | APPR OPND | HD /B /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062372 | DWESR HDB - Repl of Handrail EL +22000 | Build Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 48 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-14 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 20 | REL | APPR OPND | HD /B /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062372 | DWESR HDB - Repl of Handrail EL +22000 | Cut horisoltal ends of handrails | REL MANC NMAT PRC SETC | APPR RDBL | 16 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-14 | 2024-08-03 | 2022-09-21 | 2022-04-24 | 30 | REL | APPR OPND | HD /B /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100062372 | DWESR HDB - Repl of Handrail EL +22000 | Paint open spots | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-14 | 2024-08-04 | 2022-09-21 | 2022-04-24 | 31 | REL | APPR OPND | HD /B /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062372 | DWESR HDB - Repl of Handrail EL +22000 | Drill holes for handrail mount | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-14 | 2024-08-05 | 2022-09-21 | 2022-04-24 | 40 | REL | APPR OPND | HD /B /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100062372 | DWESR HDB - Repl of Handrail EL +22000 | Paint/prime drilled holes | REL MANC NMAT PRC SETC | APPR RDBL | 9 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-14 | 2024-08-05 | 2022-09-21 | 2022-04-24 | 41 | REL | APPR OPND | HD /B /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062372 | DWESR HDB - Repl of Handrail EL +22000 | Install new handrail | REL MANC NMAT PRC SETC | APPR RDBL | 94 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-14 | 2024-08-06 | 2022-09-21 | 2022-04-24 | 50 | REL | APPR OPND | HD /B /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062372 | DWESR HDB - Repl of Handrail EL +22000 | Remove Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 24 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-14 | 2024-08-11 | 2022-09-21 | 2022-04-24 | 60 | REL | APPR OPND | HD /B /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062372 | DWESR HDB - Repl of Handrail EL +22000 | Installation Report | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-14 | 2024-08-13 | 2022-09-21 | 2022-04-24 | 70 | REL | APPR OPND | HD /B /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062372 | DWESR HDB - Repl of Handrail EL +22000 | Mount clamps (18pcs) | REL MANC NMAT PRC SETC | APPR RDBL | 10 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-14 | 2024-08-13 | 2022-09-21 | 2022-04-24 | 80 | REL | APPR OPND | HD /B /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-ROPE | 2100062373 | DWESR HDB - Repl of Handrail EL +36900 | HDB - Replace of Handrail EL +36900 | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-03 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 10 | REL | APPR OPND | HD /B /86/36900 - HANDRAILS | 36900 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062373 | DWESR HDB - Repl of Handrail EL +36900 | Build Scaffold | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 24 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-03 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 20 | REL | APPR OPND | HD /B /86/36900 - HANDRAILS | 36900 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062373 | DWESR HDB - Repl of Handrail EL +36900 | Cut horisoltal ends of handrails | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 12 | 7 | 24-W03-04 | 2024-07-30 | 2024-08-03 | 2024-07-31 | 2022-09-21 | 2022-04-24 | 30 | PCNF REL | APPR OPND | HD /B /86/36900 - HANDRAILS | 36900 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100062373 | DWESR HDB - Repl of Handrail EL +36900 | Paint open spots | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 12 | 8 | 24-W03-04 | 2024-07-30 | 2024-08-03 | 2024-07-31 | 2022-09-21 | 2022-04-24 | 31 | PCNF REL | APPR OPND | HD /B /86/36900 - HANDRAILS | 36900 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062373 | DWESR HDB - Repl of Handrail EL +36900 | Drill holes for handrail base/mount | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 12 | 7 | 24-W03-04 | 2024-07-30 | 2024-08-03 | 2024-07-31 | 2022-09-21 | 2022-04-24 | 40 | PCNF REL | APPR OPND | HD /B /86/36900 - HANDRAILS | 36900 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062373 | DWESR HDB - Repl of Handrail EL +36900 | Paint/prime drilled holes | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 9 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-03 | 2024-07-31 | 2022-09-21 | 2022-04-24 | 41 | REL | APPR OPND | HD /B /86/36900 - HANDRAILS | 36900 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062373 | DWESR HDB - Repl of Handrail EL +36900 | Install new handrail | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 28 | 4 | 24-W03-04 | 2024-07-30 | 2024-08-03 | 2024-08-01 | 2022-09-21 | 2022-04-24 | 50 | PCNF REL | APPR OPND | HD /B /86/36900 - HANDRAILS | 36900 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062373 | DWESR HDB - Repl of Handrail EL +36900 | Remove Scaffold | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 8 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-03 | 2024-08-02 | 2022-09-21 | 2022-04-24 | 60 | REL | APPR OPND | HD /B /86/36900 - HANDRAILS | 36900 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-ROPE | 2100062373 | DWESR HDB - Repl of Handrail EL +36900 | Installation Report | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 2 | 2 | 24-W03-04 | 2024-07-30 | 2024-08-03 | 2024-08-02 | 2022-09-21 | 2022-04-24 | 70 | PCNF REL | APPR OPND | HD /B /86/36900 - HANDRAILS | 36900 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062373 | DWESR HDB - Repl of Handrail EL +36900 | Mount clamps (30pcs) | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 15 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-03 | 2024-08-02 | 2022-09-21 | 2022-04-24 | 80 | REL | APPR OPND | HD /B /86/36900 - HANDRAILS | 36900 - HANDRAILS |  | A |  | MFM | DK60
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100063040 | FLMR ANOS HBA - Repair Handrail EL +3650 | HBA - Repair Handrail EL +36500 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-10-01 | 2022-05-04 | 10 | REL | APPR OPND | HB /A /86/36500 - HANDRAILS | 36500 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-ROPE | 2100063040 | FLMR ANOS HBA - Repair Handrail EL +3650 | Reinstall handrail | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-10-01 | 2022-05-04 | 20 | REL | APPR OPND | HB /A /86/36500 - HANDRAILS | 36500 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100063041 | FLMR HBB - Replace steps EL +26800 ST015 | HBB - Replace steps EL +26800 ST015 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2022-05-04 | 2022-05-05 | 2022-05-04 | 2022-10-01 | 2022-05-04 | 10 | REL | APPR OPND | HB /B /86/26800 - GRATINGS | 26800 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100063041 | FLMR HBB - Replace steps EL +26800 ST015 | Measure steps incl. drawings | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2022-05-04 | 2022-05-05 | 2022-05-04 | 2022-10-01 | 2022-05-04 | 20 | REL | APPR OPND | HB /B /86/26800 - GRATINGS | 26800 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100063041 | FLMR HBB - Replace steps EL +26800 ST015 | Order materials | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2022-05-04 | 2022-05-05 | 2022-05-04 | 2022-10-01 | 2022-05-04 | 30 | REL | APPR OPND | HB /B /86/26800 - GRATINGS | 26800 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100063041 | FLMR HBB - Replace steps EL +26800 ST015 | Change steps | REL NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2022-05-04 | 2022-05-05 | 2022-05-04 | 2022-10-01 | 2022-05-04 | 40 | REL | APPR OPND | HB /B /86/26800 - GRATINGS | 26800 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100063041 | FLMR HBB - Replace steps EL +26800 ST015 | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2022-05-04 | 2022-05-05 | 2022-05-05 | 2022-10-01 | 2022-05-04 | 50 | REL | APPR OPND | HB /B /86/26800 - GRATINGS | 26800 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100064131 | FLMR HBA - Replacement of handrail EL +1 | HBA - Replacement of handrail EL +18600 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2022-05-23 | 2022-05-24 | 2022-05-23 | 2022-10-20 | 2022-05-23 | 10 | REL | APPR OPND | HB /A /86/18600 - HANDRAILS | 18600 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100064131 | FLMR HBA - Replacement of handrail EL +1 | Order materials | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2022-05-23 | 2022-05-24 | 2022-05-23 | 2022-10-20 | 2022-05-23 | 20 | REL | APPR OPND | HB /A /86/18600 - HANDRAILS | 18600 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100064131 | FLMR HBA - Replacement of handrail EL +1 | Erect scaffold hardbarrier | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2022-05-23 | 2022-05-24 | 2022-05-23 | 2022-10-20 | 2022-05-23 | 30 | REL | APPR OPND | HB /A /86/18600 - HANDRAILS | 18600 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100064131 | FLMR HBA - Replacement of handrail EL +1 | Change handrail | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2022-05-23 | 2022-05-24 | 2022-05-23 | 2022-10-20 | 2022-05-23 | 40 | REL | APPR OPND | HB /A /86/18600 - HANDRAILS | 18600 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100064131 | FLMR HBA - Replacement of handrail EL +1 | Install handrail link | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2022-05-23 | 2022-05-24 | 2022-05-24 | 2022-10-20 | 2022-05-23 | 50 | REL | APPR OPND | HB /A /86/18600 - HANDRAILS | 18600 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100064131 | FLMR HBA - Replacement of handrail EL +1 | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2022-05-23 | 2022-05-24 | 2022-05-24 | 2022-10-20 | 2022-05-23 | 60 | REL | APPR OPND | HB /A /86/18600 - HANDRAILS | 18600 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064132 | ANOSR HBA - Replacement of handrails EL | HBA - Replacement of handrails EL +22000 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-08 | 2022-10-20 | 2022-05-23 | 10 | REL | APPR OPND | HB /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064132 | ANOSR HBA - Replacement of handrails EL | Prepare work area | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-08 | 2022-10-20 | 2022-05-23 | 20 | REL | APPR OPND | HB /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064132 | ANOSR HBA - Replacement of handrails EL | Remove old handrails | REL MANC NMAT PRC SETC | APPR RDBL | 36 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-08 | 2022-10-20 | 2022-05-23 | 30 | REL | APPR OPND | HB /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064132 | ANOSR HBA - Replacement of handrails EL | Remove old sockets | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-10 | 2022-10-20 | 2022-05-23 | 40 | REL | APPR OPND | HB /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064132 | ANOSR HBA - Replacement of handrails EL | Install new sockets | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-11 | 2022-10-20 | 2022-05-23 | 50 | REL | APPR OPND | HB /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064132 | ANOSR HBA - Replacement of handrails EL | Install new handrails | REL MANC NMAT PRC SETC | APPR RDBL | 24 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-11 | 2022-10-20 | 2022-05-23 | 60 | REL | APPR OPND | HB /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064132 | ANOSR HBA - Replacement of handrails EL | Install all socket bolts | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-13 | 2022-10-20 | 2022-05-23 | 70 | REL | APPR OPND | HB /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064132 | ANOSR HBA - Replacement of handrails EL | Tidy up work area | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-13 | 2022-10-20 | 2022-05-23 | 80 | REL | APPR OPND | HB /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064133 | ANOSR HBA - Replacement of handrails EL | HBA - Replacement of handrails EL +24370 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-08 | 2022-10-20 | 2022-05-23 | 10 | REL | APPR OPND | HB /A /86/26900 - HANDRAILS | 26900 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064133 | ANOSR HBA - Replacement of handrails EL | Prepare work area | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-08 | 2022-10-20 | 2022-05-23 | 20 | REL | APPR OPND | HB /A /86/26900 - HANDRAILS | 26900 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064133 | ANOSR HBA - Replacement of handrails EL | Remove old handrails | REL MANC NMAT PRC SETC | APPR RDBL | 36 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-08 | 2022-10-20 | 2022-05-23 | 30 | REL | APPR OPND | HB /A /86/26900 - HANDRAILS | 26900 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064133 | ANOSR HBA - Replacement of handrails EL | Remove old sockets | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-10 | 2022-10-20 | 2022-05-23 | 40 | REL | APPR OPND | HB /A /86/26900 - HANDRAILS | 26900 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064133 | ANOSR HBA - Replacement of handrails EL | Install new sockets | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-11 | 2022-10-20 | 2022-05-23 | 50 | REL | APPR OPND | HB /A /86/26900 - HANDRAILS | 26900 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064133 | ANOSR HBA - Replacement of handrails EL | Install new handrails | REL MANC NMAT PRC SETC | APPR RDBL | 24 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-11 | 2022-10-20 | 2022-05-23 | 60 | REL | APPR OPND | HB /A /86/26900 - HANDRAILS | 26900 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064133 | ANOSR HBA - Replacement of handrails EL | Install all socket bolts | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-13 | 2022-10-20 | 2022-05-23 | 70 | REL | APPR OPND | HB /A /86/26900 - HANDRAILS | 26900 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100064133 | ANOSR HBA - Replacement of handrails EL | Tidy up work area | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-13 | 2024-04-13 | 2022-10-20 | 2022-05-23 | 80 | REL | APPR OPND | HB /A /86/26900 - HANDRAILS | 26900 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100065019 | FLMPR remove strap from unistrut | remove strap from unistrut | REL NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2022-03-28 | 2022-03-28 | 2022-03-28 | 2022-11-05 | 2022-06-08 | 10 | REL | APPR OPND | HB /A /86/26900 - PRIM AND SEC STRUCT | STRUCTURE LEVEL 2 EL +26900 | 99000087 | A |  | MFM | DK50
2024-W23-24 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100065684 | FLM ANOS HBD - Repair of handrails EL +2 | HBD - Repair of handrails EL +22000 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2022-06-20 | 2022-06-20 | 2022-06-20 | 2022-11-17 | 2022-06-20 | 10 | REL | APPR OPND | HB /D /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100067142 | HBDB-PM-5361 sea water lift pump trips | Isolate accordingly | REL PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-05-19 | 2022-04-29 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M04 | HBDB-PM-5361 SEA WATER LIFT PUMP MOTOR |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100067142 | HBDB-PM-5361 sea water lift pump trips | Troubleshoot/test according to not. text | REL PRT MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-05-19 | 2022-04-29 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M04 | HBDB-PM-5361 SEA WATER LIFT PUMP MOTOR |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067142 | HBDB-PM-5361 sea water lift pump trips | De-Isolate above | REL PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2022-05-19 | 2022-04-29 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M04 | HBDB-PM-5361 SEA WATER LIFT PUMP MOTOR |  | C |  | MEL | DK50
2024-W39-40 | 3 | NOSD | WDF | MTN-TELE | PRODTECH | 2100067580 | Power fault in HBDD--N-1851 A02 | Isolate accordingly | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W39-40 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-08-22 | 2022-05-24 | 10 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851-A | SECTION A |  | C |  | MEL | DK50
2024-W39-40 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100067580 | Power fault in HBDD--N-1851 A02 | Troubleshooting fault | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 3 | 23 | W29-30 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-08-22 | 2022-05-24 | 20 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851-A | SECTION A |  | C |  | MEL | DK50
2024-W39-40 | 3 | NOSD | WDF | MTN-TELE | MTN-ELEC | 2100067580 | Power fault in HBDD--N-1851 A02 | Assist MTN-ELEC | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W39-40 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-08-22 | 2022-05-24 | 30 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851-A | SECTION A |  | C |  | MEL | DK50
2024-W39-40 | 3 | NOSD | WDF | MTN-TELE | MTN-ELEC | 2100067580 | Power fault in HBDD--N-1851 A02 | Correct fault if possible | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 3 | 0 | W39-40 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-08-22 | 2022-05-24 | 40 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851-A | SECTION A |  | C |  | MEL | DK50
2024-W39-40 | 3 | NOSD | WDF | MTN-TELE | PRODTECH | 2100067580 | Power fault in HBDD--N-1851 A02 | De-Isolate above | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W39-40 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-08-22 | 2022-05-24 | 50 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851-A | SECTION A |  | C |  | MEL | DK50
2024-W17-18 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100067581 | Earth fault in HBDD-N-1854 A04 | Isolate accordingly | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W17-18 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-08-22 | 2022-05-24 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A04 | CUBICLE A04 |  | C |  | MEL | DK50 |  |  | 2024-05-05
2024-W17-18 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100067581 | Earth fault in HBDD-N-1854 A04 | Troubleshooting fault w 47-48 | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W17-18 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-08-22 | 2022-05-24 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A04 | CUBICLE A04 |  | C |  | MEL | DK50 |  |  | 2024-05-07
2024-W17-18 | 3 | NOSD | WDF | MTN-ELEC | MTN-TELE | 2100067581 | Earth fault in HBDD-N-1854 A04 | Assist VEN-ELEC w47-48 | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 12 | 11 | W17-18 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-08-22 | 2022-05-24 | 30 | PCNF REL | APPR OPND | HB /D /61/HBDD-N-1854-A04 | CUBICLE A04 |  | C |  | MEL | DK50 |  |  | 2024-05-10
2024-W17-18 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100067581 | Earth fault in HBDD-N-1854 A04 | Correct fault if possible | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 3 | 0 | W17-18 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2022-08-22 | 2022-05-24 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A04 | CUBICLE A04 |  | C |  | MEL | DK50 |  |  | 2024-05-12
2024-W17-18 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100067581 | Earth fault in HBDD-N-1854 A04 | De-Isolate above | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W17-18 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2022-08-22 | 2022-05-24 | 50 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A04 | CUBICLE A04 |  | C |  | MEL | DK50 |  |  | 2024-05-14
2024-W17-18 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100067582 | Earth fault in HBDD-N-1854 B10 | Isolate accordingly | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W17-18 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-08-22 | 2022-05-24 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B10 | CUBICLE B10 |  | C |  | MEL | DK50 |  |  | 2024-05-05
2024-W17-18 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100067582 | Earth fault in HBDD-N-1854 B10 | Troubleshooting fault w 47-48 | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W17-18 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-08-22 | 2022-05-24 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B10 | CUBICLE B10 |  | C |  | MEL | DK50 |  |  | 2024-05-07
2024-W17-18 | 3 | NOSD | WDF | MTN-ELEC | MTN-TELE | 2100067582 | Earth fault in HBDD-N-1854 B10 | Assist VEN-ELEC w47-48 | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 12 | 2 | W17-18 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-08-22 | 2022-05-24 | 30 | PCNF REL | APPR OPND | HB /D /61/HBDD-N-1854-B10 | CUBICLE B10 |  | C |  | MEL | DK50 |  |  | 2024-05-10
2024-W17-18 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100067582 | Earth fault in HBDD-N-1854 B10 | Correct fault if possible | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 3 | 0 | W17-18 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2022-08-22 | 2022-05-24 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B10 | CUBICLE B10 |  | C |  | MEL | DK50 |  |  | 2024-05-13
2024-W17-18 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100067582 | Earth fault in HBDD-N-1854 B10 | De-Isolate above | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W17-18 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2022-08-22 | 2022-05-24 | 50 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B10 | CUBICLE B10 |  | C |  | MEL | DK50 |  |  | 2024-05-15
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100070679 | FLMR ANOS HDB - Repair Handrail EL +4330 | HDB - Repair Handrail EL +43300 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-09-02 | 2024-08-25 | 2025-06-13 | 2022-12-26 | 10 | REL | APPR OPND | HD /B /86/43300 - HANDRAILS | 43300 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100070679 | FLMR ANOS HDB - Repair Handrail EL +4330 | Install missing handrail links | REL MANC NMAT PRC SETC | APPR RDBL | 42 | 0 | W19-W20 | 2024-08-25 | 2024-09-02 | 2024-08-25 | 2025-06-13 | 2022-12-26 | 20 | REL | APPR OPND | HD /B /86/43300 - HANDRAILS | 43300 - HANDRAILS |  | A |  | MFM | DK60
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100071439 | ANOSR HBA - Replace GRP Grating EL +1860 | HBA - Replace GRP Grating EL +18600 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-04-18 | 2024-05-06 | 2024-04-18 | 2023-12-31 | 2023-01-04 | 10 | REL | APPR OPND | HB /A /86/18600 - GRATINGS | 18600 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100071439 | ANOSR HBA - Replace GRP Grating EL +1860 | Prepare work area | REL MANC NMAT PRC SETC | APPR RDBL | 20 | 0 |  | 2024-04-18 | 2024-05-06 | 2024-04-18 | 2023-12-31 | 2023-01-04 | 20 | REL | APPR OPND | HB /A /86/18600 - GRATINGS | 18600 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100071439 | ANOSR HBA - Replace GRP Grating EL +1860 | Remove old grating | REL MANC NMAT PRC SETC | APPR RDBL | 152 | 0 |  | 2024-04-18 | 2024-05-06 | 2024-04-19 | 2023-12-31 | 2023-01-04 | 30 | REL | APPR OPND | HB /A /86/18600 - GRATINGS | 18600 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100071439 | ANOSR HBA - Replace GRP Grating EL +1860 | Install new grating (cut to fit) | REL MANC NMAT PRC SETC | APPR RDBL | 152 | 0 |  | 2024-04-18 | 2024-05-06 | 2024-04-27 | 2023-12-31 | 2023-01-04 | 40 | REL | APPR OPND | HB /A /86/18600 - GRATINGS | 18600 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100071439 | ANOSR HBA - Replace GRP Grating EL +1860 | Tidy up work area | REL MANC NMAT PRC SETC | APPR RDBL | 20 | 0 |  | 2024-04-18 | 2024-05-06 | 2024-05-05 | 2023-12-31 | 2023-01-04 | 50 | REL | APPR OPND | HB /A /86/18600 - GRATINGS | 18600 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-PIPF | 2100071440 | FLM HBA -Replace ST009B Steps/Bolts EL+2 | HBA -Replace ST009B Steps/Bolts EL+26900 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-01-04 | 2023-01-07 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 10 | REL | APPR OPND | HB /A /86/26900 - GRATINGS | 26900 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-PIPF | 2100071440 | FLM HBA -Replace ST009B Steps/Bolts EL+2 | Prepare work area | REL NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2023-01-04 | 2023-01-07 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 20 | REL | APPR OPND | HB /A /86/26900 - GRATINGS | 26900 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-PIPF | 2100071440 | FLM HBA -Replace ST009B Steps/Bolts EL+2 | Remove old steps | REL NMAT PRC SETC | APPR RDBL | 24 | 0 |  | 2023-01-04 | 2023-01-07 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 30 | REL | APPR OPND | HB /A /86/26900 - GRATINGS | 26900 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-PIPF | 2100071440 | FLM HBA -Replace ST009B Steps/Bolts EL+2 | Install new steps | REL NMAT PRC SETC | APPR RDBL | 24 | 0 |  | 2023-01-04 | 2023-01-07 | 2023-01-05 | 2023-12-31 | 2023-01-04 | 40 | REL | APPR OPND | HB /A /86/26900 - GRATINGS | 26900 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-PIPF | 2100071440 | FLM HBA -Replace ST009B Steps/Bolts EL+2 | Tidy up work area | REL NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2023-01-04 | 2023-01-07 | 2023-01-06 | 2023-12-31 | 2023-01-04 | 50 | REL | APPR OPND | HB /A /86/26900 - GRATINGS | 26900 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-PIPF | 2100071441 | FLM HBA -Replace ST009A Steps&bolts ELlt | HBA -Replace ST009A Steps&bolts EL+26900 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-01-04 | 2023-01-07 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 10 | REL | APPR OPND | HB /A /86/26900 - GRATINGS | 26900 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-PIPF | 2100071441 | FLM HBA -Replace ST009A Steps&bolts ELlt | Prepare work area | REL NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2023-01-04 | 2023-01-07 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 20 | REL | APPR OPND | HB /A /86/26900 - GRATINGS | 26900 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-PIPF | 2100071441 | FLM HBA -Replace ST009A Steps&bolts ELlt | Remove old steps | REL NMAT PRC SETC | APPR RDBL | 24 | 0 |  | 2023-01-04 | 2023-01-07 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 30 | REL | APPR OPND | HB /A /86/26900 - GRATINGS | 26900 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-PIPF | 2100071441 | FLM HBA -Replace ST009A Steps&bolts ELlt | Install new steps | REL NMAT PRC SETC | APPR RDBL | 24 | 0 |  | 2023-01-04 | 2023-01-07 | 2023-01-05 | 2023-12-31 | 2023-01-04 | 40 | REL | APPR OPND | HB /A /86/26900 - GRATINGS | 26900 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-PIPF | 2100071441 | FLM HBA -Replace ST009A Steps&bolts ELlt | Tidy up work area | REL NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2023-01-04 | 2023-01-07 | 2023-01-06 | 2023-12-31 | 2023-01-04 | 50 | REL | APPR OPND | HB /A /86/26900 - GRATINGS | 26900 - GRATINGS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100071442 | FLMR ANOS HBA-HBD Bridge - Repair Handra | HBA-HBD Bridge - Repair Handrail Socket | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-01-04 | 2023-01-05 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 10 | REL | APPR OPND | HB /A /86/31240 - HANDRAILS | 31240 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-ROPE | 2100071442 | FLMR ANOS HBA-HBD Bridge - Repair Handra | Clean and prep handrails for paint | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2023-01-04 | 2023-01-05 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 20 | REL | APPR OPND | HB /A /86/31240 - HANDRAILS | 31240 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-ROPE | 2100071442 | FLMR ANOS HBA-HBD Bridge - Repair Handra | Paint handrails | REL NMAT PRC SETC | APPR RDBL | 12 | 0 |  | 2023-01-04 | 2023-01-05 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 30 | REL | APPR OPND | HB /A /86/31240 - HANDRAILS | 31240 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100071443 | FLMR ANOS HBB - Inst. Join Link Handrail | HBB - Inst. Join Link Handrail EL+36500 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-01-04 | 2023-01-05 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 10 | REL | APPR OPND | HB /B /86/36500 - HANDRAILS | 36500 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100071443 | FLMR ANOS HBB - Inst. Join Link Handrail | Install missing handrail links | REL NMAT PRC SETC | APPR RDBL | 24 | 0 |  | 2023-01-04 | 2023-01-05 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 20 | REL | APPR OPND | HB /B /86/36500 - HANDRAILS | 36500 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100071445 | FLMR HBD - Repair of Handrail EL +18260 | HBD - Repair of Handrail EL +18260 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-01-04 | 2023-01-05 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 10 | REL | APPR OPND | HB /D /86/18260 - HANDRAILS | 18260 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100071445 | FLMR HBD - Repair of Handrail EL +18260 | Measure handrail and links incl. drawing | REL NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2023-01-04 | 2023-01-05 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 20 | REL | APPR OPND | HB /D /86/18260 - HANDRAILS | 18260 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100071445 | FLMR HBD - Repair of Handrail EL +18260 | Order materials | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-01-04 | 2023-01-05 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 30 | REL | APPR OPND | HB /D /86/18260 - HANDRAILS | 18260 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100071445 | FLMR HBD - Repair of Handrail EL +18260 | Install missing handrail bar | REL NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2023-01-04 | 2023-01-05 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 40 | REL | APPR OPND | HB /D /86/18260 - HANDRAILS | 18260 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100071445 | FLMR HBD - Repair of Handrail EL +18260 | Install handrail links | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2023-01-04 | 2023-01-05 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 50 | REL | APPR OPND | HB /D /86/18260 - HANDRAILS | 18260 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100071445 | FLMR HBD - Repair of Handrail EL +18260 | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-01-04 | 2023-01-05 | 2023-01-05 | 2023-12-31 | 2023-01-04 | 60 | REL | APPR OPND | HB /D /86/18260 - HANDRAILS | 18260 - HANDRAILS |  | A |  | MFM | DK50
2024-W29-30 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100071446 | FLMR ANOS HBD - Replace Handrail EL +305 | HBD - Replace Handrail EL +30500 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-01-04 | 2023-01-04 | 2023-01-04 | 2023-12-31 | 2023-01-04 | 10 | REL | APPR OPND | HB /D /86/30500 - HANDRAILS | 30500 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-ROPE | MTN-PAIN | 2100072659 | ANOCR HBC - Paint corrosion on Crane win | HBC - Paint corrosion on Crane winch | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2022-09-19 | 2022-09-26 | 2022-09-19 | 2023-02-01 | 2022-09-19 | 10 | REL | APPR OPND | HB /C /78/HBCO-A-6101-0201 | MAIN HOIST |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-ROPE | MTN-ROPE | 2100072659 | ANOCR HBC - Paint corrosion on Crane win | Rig up ropes | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2022-09-19 | 2022-09-26 | 2022-09-19 | 2023-02-01 | 2022-09-19 | 20 | REL | APPR OPND | HB /C /78/HBCO-A-6101-0201 | MAIN HOIST |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-ROPE | MTN-ROPE | 2100072659 | ANOCR HBC - Paint corrosion on Crane win | Needle gun / Bristle blast areas | REL NMAT PRC SETC | APPR RDBL | 24 | 0 |  | 2022-09-19 | 2022-09-26 | 2022-09-19 | 2023-02-01 | 2022-09-19 | 30 | REL | APPR OPND | HB /C /78/HBCO-A-6101-0201 | MAIN HOIST |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-ROPE | MTN-ROPE | 2100072659 | ANOCR HBC - Paint corrosion on Crane win | Coating Application | REL NMAT PRC SETC | APPR RDBL | 36 | 0 |  | 2022-09-19 | 2022-09-26 | 2022-09-22 | 2023-02-01 | 2022-09-19 | 40 | REL | APPR OPND | HB /C /78/HBCO-A-6101-0201 | MAIN HOIST |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-ROPE | MTN-ROPE | 2100072659 | ANOCR HBC - Paint corrosion on Crane win | De-Rig Ropes | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2022-09-19 | 2022-09-26 | 2022-09-26 | 2023-02-01 | 2022-09-19 | 50 | REL | APPR OPND | HB /C /78/HBCO-A-6101-0201 | MAIN HOIST |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073053 | Replace vibration dampers on HBCM-A-1264 | Recover refrigerant into receiver | REL MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-04-19 | 2024-04-26 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 10 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073053 | Replace vibration dampers on HBCM-A-1264 | Isolate compressor breaker | REL MANC PRC SETC | APPR RDBL | 1 | 0 |  | 2024-04-19 | 2024-04-26 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 20 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100073053 | Replace vibration dampers on HBCM-A-1264 | Cover / scaf / "tent" before weld | REL MANC PRC SETC | APPR RDBL | 24 | 0 |  | 2024-04-19 | 2024-04-26 | 2024-04-20 | 2023-02-13 | 2022-10-01 | 30 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100073053 | Replace vibration dampers on HBCM-A-1264 | Cut out / weld in flex pipes in system | REL MANC PRC SETC | APPR RDBL | 24 | 0 |  | 2024-04-19 | 2024-04-26 | 2024-04-22 | 2023-02-13 | 2022-10-01 | 40 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | CON-NDTI | 2100073053 | Replace vibration dampers on HBCM-A-1264 | X-ray (100%) of 4 welds | REL MANC PRC SETC | APPR RDBL | 12 | 0 |  | 2024-04-19 | 2024-04-26 | 2024-04-23 | 2023-02-13 | 2022-10-01 | 45 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073053 | Replace vibration dampers on HBCM-A-1264 | Leak test @10 bar with N2 | REL MANC PRC SETC | APPR RDBL | 12 | 0 |  | 2024-04-19 | 2024-04-26 | 2024-04-24 | 2023-02-13 | 2022-10-01 | 50 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073053 | Replace vibration dampers on HBCM-A-1264 | Apply vacuum, recharge refrigerant, chan | REL MANC PRC SETC | APPR RDBL | 8 | 0 |  | 2024-04-19 | 2024-04-26 | 2024-04-25 | 2023-02-13 | 2022-10-01 | 60 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073053 | Replace vibration dampers on HBCM-A-1264 | Deisolate / test / top up refrigerant | REL MANC PRC SETC | APPR RDBL | 1 | 0 |  | 2024-04-19 | 2024-04-26 | 2024-04-26 | 2023-02-13 | 2022-10-01 | 70 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-PAIN | 2100073053 | Replace vibration dampers on HBCM-A-1264 | Paint | REL MANC PRC SETC | APPR RDBL | 2 | 0 |  | 2024-04-19 | 2024-04-26 | 2024-04-26 | 2023-02-13 | 2022-10-01 | 90 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073053 | Replace vibration dampers on HBCM-A-1264 | Insulate pipes | REL MANC PRC SETC | APPR RDBL | 2 | 0 |  | 2024-04-19 | 2024-04-26 | 2024-04-26 | 2023-02-13 | 2022-10-01 | 100 | REL | APPR OPND | HB /C /09/HBCM-A-1264 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073054 | Replace vibration dampers on HBCM-A-1265 | Recover refrigerant into receiver | REL MANC PRC SETC | APPR RDBL | 8 | 0 | W05-06 IOP 14-25/11-22 | 2024-04-19 | 2024-04-28 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 10 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073054 | Replace vibration dampers on HBCM-A-1265 | Isolate compressor breaker | REL MANC PRC SETC | APPR RDBL | 1 | 0 | W05-06 IOP 14-25/11-22 | 2024-04-19 | 2024-04-28 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 20 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100073054 | Replace vibration dampers on HBCM-A-1265 | Cover / scaf / "tent" before weld | REL MANC PRC SETC | APPR RDBL | 24 | 0 | W05-06 IOP 14-25/11-22 | 2024-04-19 | 2024-04-28 | 2024-04-20 | 2023-02-13 | 2022-10-01 | 30 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100073054 | Replace vibration dampers on HBCM-A-1265 | Cut out / weld in flex pipes in system | REL MANC PRC SETC | APPR RDBL | 24 | 0 | W05-06 IOP 14-25/11-22 | 2024-04-19 | 2024-04-28 | 2024-04-22 | 2023-02-13 | 2022-10-01 | 40 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | CON-NDTI | 2100073054 | Replace vibration dampers on HBCM-A-1265 | X-ray (100%) of 4 welds | REL MANC PRC SETC | APPR RDBL | 12 | 0 |  | 2024-04-19 | 2024-04-28 | 2024-04-23 | 2023-02-13 | 2022-10-01 | 45 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073054 | Replace vibration dampers on HBCM-A-1265 | Leak test @10 bar with N2 | REL MANC PRC SETC | APPR RDBL | 12 | 0 | W05-06 IOP 14-25/11-22 | 2024-04-19 | 2024-04-28 | 2024-04-24 | 2023-02-13 | 2022-10-01 | 50 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073054 | Replace vibration dampers on HBCM-A-1265 | Apply vacuum, recharge refrigerant | REL MANC PRC SETC | APPR RDBL | 8 | 0 | W05-06 IOP 14-25/11-22 | 2024-04-19 | 2024-04-28 | 2024-04-26 | 2023-02-13 | 2022-10-01 | 60 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073054 | Replace vibration dampers on HBCM-A-1265 | Deisolate / test / top up refrigerant | REL MANC PRC SETC | APPR RDBL | 8 | 0 | W05-06 IOP 14-25/11-22 | 2024-04-19 | 2024-04-28 | 2024-04-27 | 2023-02-13 | 2022-10-01 | 70 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-PAIN | 2100073054 | Replace vibration dampers on HBCM-A-1265 | Paint | REL MANC PRC SETC | APPR RDBL | 2 | 0 | W05-06 IOP 14-25/11-22 | 2024-04-19 | 2024-04-28 | 2024-04-28 | 2023-02-13 | 2022-10-01 | 90 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073054 | Replace vibration dampers on HBCM-A-1265 | Insulate pipes | REL MANC PRC SETC | APPR RDBL | 2 | 0 | W05-06 IOP 14-25/11-22 | 2024-04-19 | 2024-04-28 | 2024-04-28 | 2023-02-13 | 2022-10-01 | 100 | REL | APPR OPND | HB /C /09/HBCM-A-1265 | TECHNICAL ROOM CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100074434 | New handles for HVAC HBB-A-1213 | New handles for HVAC HBB-A-1213 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-03-10 | 2022-10-26 | 10 | REL | APPR OPND | HB /B /09/HBBB-A-1213 | HVAC UNIT |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100074434 | New handles for HVAC HBB-A-1213 | Replace Handles | REL MANC NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-03-10 | 2022-10-26 | 20 | REL | APPR OPND | HB /B /09/HBBB-A-1213 | HVAC UNIT |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | HBD-GLY | WDF | MTN-ELEC | MTN-ELEC | 2100074435 | glycol heater Thyriston act spurios | Troubleshoot on thyrister/Heater | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 10 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-03-08 | 2022-10-24 | 10 | PCNF REL | APPR OPND | HB /D /30/HBDD-FP-4160 | GLYCOL REGEN. PACKAGE HEATER THYRISTER C | 99000119 | C |  | MEL | DK50
2026-W13-14 | 3 | HBD-GLY | WDF | MTN-ELEC | PRODTECH | 2100074435 | glycol heater Thyriston act spurios | Isolate and prove dead | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W02 IPHPSD | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-03-08 | 2022-10-24 | 20 | PCNF REL | APPR OPND | HB /D /30/HBDD-FP-4160 | GLYCOL REGEN. PACKAGE HEATER THYRISTER C | 99000119 | C |  | MEL | DK50
2026-W13-14 | 3 | HBD-GLY | WDF | MTN-ELEC | MTN-ELEC | 2100074435 | glycol heater Thyriston act spurios | Troubleshoot on thyrister/Heater | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 4 | 0 | W02 IPHPSD | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-03-08 | 2022-10-24 | 30 | PCNF REL | APPR OPND | HB /D /30/HBDD-FP-4160 | GLYCOL REGEN. PACKAGE HEATER THYRISTER C | 99000119 | C |  | MEL | DK50
2026-W13-14 | 3 | HBD-GLY | WDF | MTN-ELEC | PRODTECH | 2100074435 | glycol heater Thyriston act spurios | De-Isolate above and test | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W02 IPHPSD | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2023-03-08 | 2022-10-24 | 40 | PCNF REL | APPR OPND | HB /D /30/HBDD-FP-4160 | GLYCOL REGEN. PACKAGE HEATER THYRISTER C | 99000119 | C |  | MEL | DK50
2024-W23-24 | 2 | HBBPWELL | WDF | MTN-TELE | MTN-TELE | 2100074992 | HBB ESD glitch on HBB05,06,07 | HBB ESD glitch on HBB05,06,07 | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-11-06 | 2022-09-22 | 10 | REL | APPR OPND | HB /B /03/HBBB-FP-0237 | FIELD PANEL ESD RIO EEX DE |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100076564 | Testblock for gd-0153208 loose | Prepare rope access | REL NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2023-04-19 | 2023-04-19 | 2023-04-19 | 2025-10-05 | 2023-04-19 | 10 | REL | APPR OPND | HB /D /03 | ESD AND FIRE & GAS |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100076564 | Testblock for gd-0153208 loose | Repair test tube fitting | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2023-04-19 | 2023-04-19 | 2023-04-19 | 2025-10-05 | 2023-04-19 | 20 | REL | APPR OPND | HB /D /03 | ESD AND FIRE & GAS |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100076564 | Testblock for gd-0153208 loose | Remove rope access | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-04-19 | 2023-04-19 | 2023-04-19 | 2025-10-05 | 2023-04-19 | 30 | REL | APPR OPND | HB /D /03 | ESD AND FIRE & GAS |  | A |  | MIN | DK50
2024-W45-46 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100076715 | Faultfinding earthleak F<(>&<)>G system | Faultfinding for earth leak | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 6 | 20 | W45-46 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-04-21 | 2022-12-07 | 10 | PCNF REL | APPR OPND | HB /A /03/HBAA-FP-0110 | 24VDC DIST. PANEL F&G POWER SUPPLY |  | A |  | MIN | DK50
2024-W49-50 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-TURB | 2100077376 | Vib. meas HBDC-VE-445204 spiky | Vib. meas HBDC-VE-445204 spiky | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W49-50 | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2023-05-01 | 2022-12-17 | 10 | REL | APPR OPND | HB /D /31/HBDC-VT-445204 | PROXIMITOR, HP COMPR NDE BEARING(Y-AXIS) |  | A |  | MMR | DK50
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078026 | FLMR HDA - Repair Step/Hand. ST003 EL 18 | HDA - Repair Step/Hand. ST003 EL 18.500 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 10 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078026 | FLMR HDA - Repair Step/Hand. ST003 EL 18 | Measure steps incl. drawings | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 20 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078026 | FLMR HDA - Repair Step/Hand. ST003 EL 18 | Order materials | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 30 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-SCAF | 2100078026 | FLMR HDA - Repair Step/Hand. ST003 EL 18 | Erect scaffold hardbarrier | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 40 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PAIN | 2100078026 | FLMR HDA - Repair Step/Hand. ST003 EL 18 | Mechanical prep/bristle blast | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-14 | 2023-12-31 | 2023-05-13 | 50 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PAIN | 2100078026 | FLMR HDA - Repair Step/Hand. ST003 EL 18 | Paint up to spec | REL NMAT PRC SETC | APPR RDBL | 12 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-14 | 2023-12-31 | 2023-05-13 | 60 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PAIN | 2100078026 | FLMR HDA - Repair Step/Hand. ST003 EL 18 | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-15 | 2023-12-31 | 2023-05-13 | 70 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078026 | FLMR HDA - Repair Step/Hand. ST003 EL 18 | Change steps 1 by 1 | REL NMAT PRC SETC | APPR RDBL | 32 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-16 | 2023-12-31 | 2023-05-13 | 80 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078026 | FLMR HDA - Repair Step/Hand. ST003 EL 18 | Install handrail links | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-17 | 2023-12-31 | 2023-05-13 | 90 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078026 | FLMR HDA - Repair Step/Hand. ST003 EL 18 | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-17 | 2023-12-31 | 2023-05-13 | 100 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-SCAF | 2100078026 | FLMR HDA - Repair Step/Hand. ST003 EL 18 | Remove hardbarrier | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-18 | 2023-12-31 | 2023-05-13 | 110 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078027 | FLMR HDA - Repair Step/Hand. ST010 EL 18 | HDA - Repair Step/Hand. ST010 EL 18.500 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 10 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078027 | FLMR HDA - Repair Step/Hand. ST010 EL 18 | Measure steps incl. drawings | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 20 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078027 | FLMR HDA - Repair Step/Hand. ST010 EL 18 | Order materials | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 30 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078027 | FLMR HDA - Repair Step/Hand. ST010 EL 18 | Erect scaffold hardbarrier | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 40 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078027 | FLMR HDA - Repair Step/Hand. ST010 EL 18 | Mechanical prep/bristle blast | REL NMAT PRC SETC | APPR RDBL | 8 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 50 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078027 | FLMR HDA - Repair Step/Hand. ST010 EL 18 | Paint up to spec | REL NMAT PRC SETC | APPR RDBL | 16 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-14 | 2023-12-31 | 2023-05-13 | 60 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078027 | FLMR HDA - Repair Step/Hand. ST010 EL 18 | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-16 | 2023-12-31 | 2023-05-13 | 70 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078027 | FLMR HDA - Repair Step/Hand. ST010 EL 18 | Change steps 1 by 1 | REL NMAT PRC SETC | APPR RDBL | 30 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-16 | 2023-12-31 | 2023-05-13 | 80 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078027 | FLMR HDA - Repair Step/Hand. ST010 EL 18 | Install handrail links | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-18 | 2023-12-31 | 2023-05-13 | 90 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078027 | FLMR HDA - Repair Step/Hand. ST010 EL 18 | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-18 | 2023-12-31 | 2023-05-13 | 100 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078027 | FLMR HDA - Repair Step/Hand. ST010 EL 18 | Remove hardbarrier | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-05-13 | 2023-05-18 | 2023-05-18 | 2023-12-31 | 2023-05-13 | 110 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078029 | FLMR HDA - Replace Steps ST2424 EL 19.25 | HDA - Replace Steps ST2424 EL 19.250 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-05-13 | 2023-05-15 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 10 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078029 | FLMR HDA - Replace Steps ST2424 EL 19.25 | Measure steps incl. drawings | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-05-13 | 2023-05-15 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 20 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078029 | FLMR HDA - Replace Steps ST2424 EL 19.25 | Order materials | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-05-13 | 2023-05-15 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 30 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078029 | FLMR HDA - Replace Steps ST2424 EL 19.25 | Erect scaffold hardbarrier | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-05-13 | 2023-05-15 | 2023-05-13 | 2023-12-31 | 2023-05-13 | 40 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078029 | FLMR HDA - Replace Steps ST2424 EL 19.25 | Change steps 1 by 1 | REL NMAT PRC SETC | APPR RDBL | 30 | 0 |  | 2023-05-13 | 2023-05-15 | 2023-05-14 | 2023-12-31 | 2023-05-13 | 50 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078029 | FLMR HDA - Replace Steps ST2424 EL 19.25 | Remove hardbarrier | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-05-13 | 2023-05-15 | 2023-05-15 | 2023-12-31 | 2023-05-13 | 60 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100078029 | FLMR HDA - Replace Steps ST2424 EL 19.25 | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-05-13 | 2023-05-15 | 2023-05-15 | 2023-12-31 | 2023-05-13 | 70 | REL | APPR OPND | HD /A /86/18500 - GRATINGS | 18500 - GRATINGS |  | A |  | MFM | DK60
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100080210 | FLM HBA - Repair GRP Grating on Jacket | HBA - Repair GRP Grating on Jacket | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-04-18 | 2024-04-21 | 2024-04-18 | 2025-12-31 | 2023-06-25 | 10 | REL | APPR OPND | HB /A /86/JACKET - GRATINGS | SPIDERDECK EL +12000 - GRATINGS LADDER |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100080210 | FLM HBA - Repair GRP Grating on Jacket | Replace gratings outboard | REL MANC NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2024-04-18 | 2024-04-21 | 2024-04-18 | 2025-12-31 | 2023-06-25 | 20 | REL | APPR OPND | HB /A /86/JACKET - GRATINGS | SPIDERDECK EL +12000 - GRATINGS LADDER |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100080210 | FLM HBA - Repair GRP Grating on Jacket | Replace grating fixings | REL MANC NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2024-04-18 | 2024-04-21 | 2024-04-18 | 2025-12-31 | 2023-06-25 | 30 | REL | APPR OPND | HB /A /86/JACKET - GRATINGS | SPIDERDECK EL +12000 - GRATINGS LADDER |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100080210 | FLM HBA - Repair GRP Grating on Jacket | Set up ropes | REL MANC NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2024-04-18 | 2024-04-21 | 2024-04-19 | 2025-12-31 | 2023-06-25 | 40 | REL | APPR OPND | HB /A /86/JACKET - GRATINGS | SPIDERDECK EL +12000 - GRATINGS LADDER |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100080210 | FLM HBA - Repair GRP Grating on Jacket | Remove ropes | REL MANC NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2024-04-18 | 2024-04-21 | 2024-04-20 | 2025-12-31 | 2023-06-25 | 50 | REL | APPR OPND | HB /A /86/JACKET - GRATINGS | SPIDERDECK EL +12000 - GRATINGS LADDER |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100080210 | FLM HBA - Repair GRP Grating on Jacket | Tidy work site | REL MANC NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2024-04-18 | 2024-04-21 | 2024-04-21 | 2025-12-31 | 2023-06-25 | 60 | REL | APPR OPND | HB /A /86/JACKET - GRATINGS | SPIDERDECK EL +12000 - GRATINGS LADDER |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100080212 | FLMR ANOS HBB - Missing Join Link EL. 19 | HBB - Missing Join Link EL. 19.000 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-06-25 | 2023-06-26 | 2023-06-25 | 2025-12-31 | 2023-06-25 | 10 | REL | APPR OPND | HB /B /86/19000 - HANDRAILS | 19000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100080212 | FLMR ANOS HBB - Missing Join Link EL. 19 | Install missing handrail links 15 pcs | REL NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2023-06-25 | 2023-06-26 | 2023-06-25 | 2025-12-31 | 2023-06-25 | 20 | REL | APPR OPND | HB /B /86/19000 - HANDRAILS | 19000 - HANDRAILS |  | A |  | MFM | DK50
2024-W17-18 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100081838 | Faulty reading on HBBB-FIT-290102 | Process manual mode (or gaslift SD) | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W17-18 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-07-19 | 2023-03-06 | 10 | PCNF REL | APPR OPND | HB /B /37/HBBB-FIT-290102 | FLOW INDICATOR TRANSMITTER (METERING) |  | C |  | MIN | DK50 |  |  | 2024-05-05
2024-W17-18 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081838 | Faulty reading on HBBB-FIT-290102 | Isolate Flow transmitter (Orifice Plate) | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 0.5 | 0 | W17-18 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-07-19 | 2023-03-06 | 15 | PCNF REL | APPR OPND | HB /B /37/HBBB-FIT-290102 | FLOW INDICATOR TRANSMITTER (METERING) |  | C |  | MIN | DK50 |  |  | 2024-05-07
2024-W17-18 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081838 | Faulty reading on HBBB-FIT-290102 | Calibrate Flow transmitter (Orifice Plat | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 2.5 | 3 | W11-12 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-07-19 | 2023-03-06 | 20 | PCNF REL | APPR OPND | HB /B /37/HBBB-FIT-290102 | FLOW INDICATOR TRANSMITTER (METERING) |  | C |  | MIN | DK50 |  |  | 2024-05-08
2024-W17-18 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081838 | Faulty reading on HBBB-FIT-290102 | Deisolate Flow transmitter (Orifice Plat | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 0.5 | 0 | W17-18 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-07-19 | 2023-03-06 | 30 | PCNF REL | APPR OPND | HB /B /37/HBBB-FIT-290102 | FLOW INDICATOR TRANSMITTER (METERING) |  | C |  | MIN | DK50 |  |  | 2024-05-09
2024-W17-18 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100081838 | Faulty reading on HBBB-FIT-290102 | Put process back in normal | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W17-18 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-07-19 | 2023-03-06 | 40 | PCNF REL | APPR OPND | HB /B /37/HBBB-FIT-290102 | FLOW INDICATOR TRANSMITTER (METERING) |  | C |  | MIN | DK50 |  |  | 2024-05-10
2024-W17-18 | 3 | NOSD | WDF | MTN-INST | MTN-TELE | 2100081838 | Faulty reading on HBBB-FIT-290102 | Faultfinding in Siemens system | REL PCNF PRT MANC NMAT PRC SETC | APPR RDBL | 3 | 6 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-07-19 | 2023-03-06 | 50 | PCNF REL | APPR OPND | HB /B /37/HBBB-FIT-290102 | FLOW INDICATOR TRANSMITTER (METERING) |  | C |  | MIN | DK50 |  |  | 2024-05-12
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100081884 | Leak from seawater filter motor 5368 | Setup rigging equipment | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-09 | 2023-07-25 | 2023-03-12 | 10 | REL | APPR OPND | HB /D /51/HBDB-XM-5368 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081884 | Leak from seawater filter motor 5368 | Prepare matr/tool | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-09 | 2023-07-25 | 2023-03-12 | 20 | REL | APPR OPND | HB /D /51/HBDB-XM-5368 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100081884 | Leak from seawater filter motor 5368 | Isolation of equipment | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-09 | 2023-07-25 | 2023-03-12 | 30 | REL | APPR OPND | HB /D /51/HBDB-XM-5368 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100081884 | Leak from seawater filter motor 5368 | Rigger assistance rig up/down | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-10 | 2023-07-25 | 2023-03-12 | 40 | REL | APPR OPND | HB /D /51/HBDB-XM-5368 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100081884 | Leak from seawater filter motor 5368 | Electrical assisance on cable | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-10 | 2023-07-25 | 2023-03-12 | 50 | REL | APPR OPND | HB /D /51/HBDB-XM-5368 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081884 | Leak from seawater filter motor 5368 | Removal of gear/motor | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-11 | 2023-07-25 | 2023-03-12 | 60 | REL | APPR OPND | HB /D /51/HBDB-XM-5368 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081884 | Leak from seawater filter motor 5368 | Replace worn out parts | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-11 | 2023-07-25 | 2023-03-12 | 70 | REL | APPR OPND | HB /D /51/HBDB-XM-5368 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081884 | Leak from seawater filter motor 5368 | re-install gear/motor | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-11 | 2023-07-25 | 2023-03-12 | 80 | REL | APPR OPND | HB /D /51/HBDB-XM-5368 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100081884 | Leak from seawater filter motor 5368 | Leak-test & de-isolation | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-11 | 2023-07-25 | 2023-03-12 | 90 | REL | APPR OPND | HB /D /51/HBDB-XM-5368 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081884 | Leak from seawater filter motor 5368 | Function test | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-12 | 2023-07-25 | 2023-03-12 | 100 | REL | APPR OPND | HB /D /51/HBDB-XM-5368 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | HBB05-GL | WDF | MTN-INST | MTN-MECH | 2100086084 | Minor hydr leak from supl. HBB05 cho | Invistigate wich gasket to use | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2026-01-08 | 2023-07-23 | 5 | REL | APPR OPND | HB /B /10/HBBB-CVA-300507 | CHOKE VALVE - NO VALVE INSTALLED |  | C |  | MMS | DK50
2026-W13-14 | 4 | HBB05-GL | WDF | MTN-INST | PRODTECH | 2100086084 | Minor hydr leak from supl. HBB05 cho | Isolater hydraulics | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2026-01-08 | 2023-07-23 | 10 | REL | APPR OPND | HB /B /10/HBBB-CVA-300507 | CHOKE VALVE - NO VALVE INSTALLED |  | C |  | MMS | DK50
2026-W13-14 | 4 | HBB05-GL | WDF | MTN-INST | MTN-MECH | 2100086084 | Minor hydr leak from supl. HBB05 cho | Mount new gasket | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2026-01-08 | 2023-07-23 | 20 | REL | APPR OPND | HB /B /10/HBBB-CVA-300507 | CHOKE VALVE - NO VALVE INSTALLED |  | C |  | MMS | DK50
2026-W13-14 | 4 | HBB05-GL | WDF | MTN-INST | PRODTECH | 2100086084 | Minor hydr leak from supl. HBB05 cho | deisolate | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-10 | 2026-01-08 | 2023-07-23 | 30 | REL | APPR OPND | HB /B /10/HBBB-CVA-300507 | CHOKE VALVE - NO VALVE INSTALLED |  | C |  | MMS | DK50
2024-W23-24 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086868 | Main switch not cennected to thyrister | Main switch not cennected to thyrister | REL NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2026-02-03 | 2023-08-18 | 10 | REL | APPR OPND | HB /D /09/HBDD-UCP-1263 | HEATER PANEL |  | A |  | MEL | DK50 |  | PROK | 2024-05-17
2024-W23-24 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086868 | Main switch not cennected to thyrister | Replace handle & rod | REL NMAT PRC SETC | APPR RDBL | 2 | 0 | W19-W20 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2026-02-03 | 2023-08-18 | 20 | REL | APPR OPND | HB /D /09/HBDD-UCP-1263 | HEATER PANEL |  | A |  | MEL | DK50 |  | PROK | 2024-05-18
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100091980 | HBCM-A-1248, remove start up filter | HBCM-A-1248, remove start up filter | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2023-11-26 | 2023-07-14 | 10 | REL | APPR OPND | HB /C /09/HBCM-A-1248 | AHU-2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100091980 | HBCM-A-1248, remove start up filter | Isolate | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2023-11-26 | 2023-07-14 | 20 | REL | APPR OPND | HB /C /09/HBCM-A-1248 | AHU-2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100091980 | HBCM-A-1248, remove start up filter | Recover refrigerant | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2023-11-26 | 2023-07-14 | 30 | REL | APPR OPND | HB /C /09/HBCM-A-1248 | AHU-2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100091980 | HBCM-A-1248, remove start up filter | Remove filter | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2023-11-26 | 2023-07-14 | 40 | REL | APPR OPND | HB /C /09/HBCM-A-1248 | AHU-2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100091980 | HBCM-A-1248, remove start up filter | Charge refrigerant | REL MANC NMAT PRC SETC | APPR RDBL | 0.5 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2023-11-26 | 2023-07-14 | 50 | REL | APPR OPND | HB /C /09/HBCM-A-1248 | AHU-2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100091980 | HBCM-A-1248, remove start up filter | De-isolate | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2023-11-26 | 2023-07-14 | 60 | REL | APPR OPND | HB /C /09/HBCM-A-1248 | AHU-2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100091980 | HBCM-A-1248, remove start up filter | Leak test | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-23 | 2024-04-23 | 2023-11-26 | 2023-07-14 | 70 | REL | APPR OPND | HB /C /09/HBCM-A-1248 | AHU-2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092143 | FLMR HDA - Install Join Link ST044 EL. 2 | HDA - Install Join Link ST044 EL. 24.625 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2025-12-31 | 2023-11-06 | 10 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092143 | FLMR HDA - Install Join Link ST044 EL. 2 | Install missing handrail links | REL MANC NMAT PRC SETC | APPR RDBL | 4 | 0 | W19-W20 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2025-12-31 | 2023-11-06 | 20 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092144 | FLMR HDA - Rep. Step and JL ST014 EL. 22 | HDA - Rep. Step and JL ST014 EL. 22.000 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-09-03 | 2024-08-25 | 2025-12-31 | 2023-11-06 | 10 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092144 | FLMR HDA - Rep. Step and JL ST014 EL. 22 | Install missing handrail links | REL MANC NMAT PRC SETC | APPR RDBL | 20 | 0 | W19-W20 | 2024-08-25 | 2024-09-03 | 2024-08-25 | 2025-12-31 | 2023-11-06 | 20 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092144 | FLMR HDA - Rep. Step and JL ST014 EL. 22 | Change out steps | REL MANC NMAT PRC SETC | APPR RDBL | 40 | 0 | W19-W20 | 2024-08-25 | 2024-09-03 | 2024-08-27 | 2025-12-31 | 2023-11-06 | 30 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100092144 | FLMR HDA - Rep. Step and JL ST014 EL. 22 | Erect scaffold barriers | REL MANC NMAT PRC SETC | APPR RDBL | 25 | 0 | W19-W20 | 2024-08-25 | 2024-09-03 | 2024-08-29 | 2025-12-31 | 2023-11-06 | 40 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100092144 | FLMR HDA - Rep. Step and JL ST014 EL. 22 | Dismantle scaffold barriers | REL MANC NMAT PRC SETC | APPR RDBL | 20 | 0 | W19-W20 | 2024-08-25 | 2024-09-03 | 2024-09-01 | 2025-12-31 | 2023-11-06 | 50 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092145 | FLMR HDA - Rep. Step Bolt/JL ST012 EL. 2 | HDA - Rep. Step Bolt/JL ST012 EL. 22.000 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-08-30 | 2024-08-25 | 2025-12-31 | 2023-11-06 | 10 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092145 | FLMR HDA - Rep. Step Bolt/JL ST012 EL. 2 | Install missing handrail links | REL MANC NMAT PRC SETC | APPR RDBL | 20 | 0 | W19-W20 | 2024-08-25 | 2024-08-30 | 2024-08-25 | 2025-12-31 | 2023-11-06 | 20 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092145 | FLMR HDA - Rep. Step Bolt/JL ST012 EL. 2 | Change corroded bolts | REL MANC NMAT PRC SETC | APPR RDBL | 20 | 0 | W19-W20 | 2024-08-25 | 2024-08-30 | 2024-08-27 | 2025-12-31 | 2023-11-06 | 30 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100092145 | FLMR HDA - Rep. Step Bolt/JL ST012 EL. 2 | Clean and prep handrail for paint | REL MANC NMAT PRC SETC | APPR RDBL | 20 | 0 | W19-W20 | 2024-08-25 | 2024-08-30 | 2024-08-28 | 2025-12-31 | 2023-11-06 | 40 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100092145 | FLMR HDA - Rep. Step Bolt/JL ST012 EL. 2 | Paint handrail | REL MANC NMAT PRC SETC | APPR RDBL | 30 | 0 | W19-W20 | 2024-08-25 | 2024-08-30 | 2024-08-29 | 2025-12-31 | 2023-11-06 | 50 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-MECH | 2100092146 | FLMR HDA - Rep. Stair ST22/25/46 EL. 24. | HDA - Rep. Stair ST22/25/46 EL. 24.625 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-11-06 | 2023-11-07 | 2023-11-06 | 2025-12-31 | 2023-11-06 | 10 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092146 | FLMR HDA - Rep. Stair ST22/25/46 EL. 24. | Install handrail links | REL NMAT PRC SETC | APPR RDBL | 12 | 0 |  | 2023-11-06 | 2023-11-07 | 2023-11-06 | 2025-12-31 | 2023-11-06 | 20 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092146 | FLMR HDA - Rep. Stair ST22/25/46 EL. 24. | Clean worksites | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2025-12-31 | 2023-11-06 | 30 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092147 | FLMR HDA - Rep. Step Bolts ST009 EL. 22. | HDA - Rep. Step Bolts ST009 EL. 22.000 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-11-05 | 2023-11-07 | 2023-11-05 | 2025-12-31 | 2023-11-05 | 10 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092147 | FLMR HDA - Rep. Step Bolts ST009 EL. 22. | Install missing handrail links | REL NMAT PRC SETC | APPR RDBL | 20 | 0 |  | 2023-11-05 | 2023-11-07 | 2023-11-05 | 2025-12-31 | 2023-11-05 | 20 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092147 | FLMR HDA - Rep. Step Bolts ST009 EL. 22. | Change corroded bolts | REL NMAT PRC SETC | APPR RDBL | 20 | 0 |  | 2023-11-05 | 2023-11-07 | 2023-11-06 | 2025-12-31 | 2023-11-05 | 30 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092147 | FLMR HDA - Rep. Step Bolts ST009 EL. 22. | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2025-12-31 | 2023-11-05 | 40 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092148 | FLMR HDA - Rep. Step Bolt/JL ST006 EL. 2 | HDA - Rep. Step Bolt/JL ST006 EL. 22.000 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2025-12-31 | 2023-11-05 | 10 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092148 | FLMR HDA - Rep. Step Bolt/JL ST006 EL. 2 | Install missing handrail links | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2025-12-31 | 2023-11-05 | 20 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092148 | FLMR HDA - Rep. Step Bolt/JL ST006 EL. 2 | Change corroded bolts | REL MANC NMAT PRC SETC | APPR RDBL | 20 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-26 | 2025-12-31 | 2023-11-05 | 30 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092149 | FLMR HDA - Rep. Step Bolts ST002 EL. 22. | HDA - Rep. Step Bolts ST002 EL. 22.000 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2025-12-31 | 2023-11-05 | 10 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092149 | FLMR HDA - Rep. Step Bolts ST002 EL. 22. | Install missing handrail links | REL MANC NMAT PRC SETC | APPR RDBL | 20 | 0 | W19-W20 | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2025-12-31 | 2023-11-05 | 20 | REL | APPR OPND | HD /A /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092151 | FLMR HDA - Replace Step STCOMP05 EL. 39. | HDA - Replace Step STCOMP05 EL. 39.500 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-11-07 | 2023-11-08 | 2023-11-07 | 2025-12-31 | 2023-11-07 | 10 | REL | APPR OPND | HD /A /86/35000 - GRATINGS | 35000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092151 | FLMR HDA - Replace Step STCOMP05 EL. 39. | Measure steps incl. drawings | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-11-07 | 2023-11-08 | 2023-11-07 | 2025-12-31 | 2023-11-07 | 20 | REL | APPR OPND | HD /A /86/35000 - GRATINGS | 35000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092151 | FLMR HDA - Replace Step STCOMP05 EL. 39. | Order materials | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-07 | 2023-11-08 | 2023-11-07 | 2025-12-31 | 2023-11-07 | 30 | REL | APPR OPND | HD /A /86/35000 - GRATINGS | 35000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092151 | FLMR HDA - Replace Step STCOMP05 EL. 39. | Change steps 1 by 1 | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2023-11-07 | 2023-11-08 | 2023-11-07 | 2025-12-31 | 2023-11-07 | 40 | REL | APPR OPND | HD /A /86/35000 - GRATINGS | 35000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092151 | FLMR HDA - Replace Step STCOMP05 EL. 39. | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2025-12-31 | 2023-11-07 | 50 | REL | APPR OPND | HD /A /86/35000 - GRATINGS | 35000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092154 | FLMR HDA - Replace Grating EL. 35.000 | HDA - Replace Grating EL. 35.000 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-11-06 | 2023-11-07 | 2023-11-06 | 2025-12-31 | 2023-11-06 | 10 | REL | APPR OPND | HD /A /86/35000 - GRATINGS | 35000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092154 | FLMR HDA - Replace Grating EL. 35.000 | Measure grating incl. drawings | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-11-06 | 2023-11-07 | 2023-11-06 | 2025-12-31 | 2023-11-06 | 20 | REL | APPR OPND | HD /A /86/35000 - GRATINGS | 35000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092154 | FLMR HDA - Replace Grating EL. 35.000 | Order materials | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-06 | 2023-11-07 | 2023-11-06 | 2025-12-31 | 2023-11-06 | 30 | REL | APPR OPND | HD /A /86/35000 - GRATINGS | 35000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-SCAF | 2100092154 | FLMR HDA - Replace Grating EL. 35.000 | Erect scaffold hardbarrier | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-06 | 2023-11-07 | 2023-11-06 | 2025-12-31 | 2023-11-06 | 40 | REL | APPR OPND | HD /A /86/35000 - GRATINGS | 35000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092154 | FLMR HDA - Replace Grating EL. 35.000 | Change grating | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2025-12-31 | 2023-11-06 | 50 | REL | APPR OPND | HD /A /86/35000 - GRATINGS | 35000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092154 | FLMR HDA - Replace Grating EL. 35.000 | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2025-12-31 | 2023-11-06 | 60 | REL | APPR OPND | HD /A /86/35000 - GRATINGS | 35000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092154 | FLMR HDA - Replace Grating EL. 35.000 | Remove hardbarrier | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2025-12-31 | 2023-11-06 | 70 | REL | APPR OPND | HD /A /86/35000 - GRATINGS | 35000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092155 | FLMR ANOS HDA - Repair Handrail ST040 EL | HDA - Repair Handrail ST040 EL. 43.275 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-08-29 | 2024-08-25 | 2025-12-31 | 2023-11-07 | 10 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092155 | FLMR ANOS HDA - Repair Handrail ST040 EL | Install missing handrail links | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W19-W20 | 2024-08-25 | 2024-08-29 | 2024-08-25 | 2025-12-31 | 2023-11-07 | 20 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100092155 | FLMR ANOS HDA - Repair Handrail ST040 EL | Clean and prep handrail for paint | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W19-W20 | 2024-08-25 | 2024-08-29 | 2024-08-27 | 2025-12-31 | 2023-11-07 | 30 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100092155 | FLMR ANOS HDA - Repair Handrail ST040 EL | Paint handrail | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W19-W20 | 2024-08-25 | 2024-08-29 | 2024-08-28 | 2025-12-31 | 2023-11-07 | 40 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092157 | FLMR HDA - Repair Handrail ST039 EL. 39. | HDA - Repair Handrail ST039 EL. 39.500 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2025-12-31 | 2023-11-07 | 10 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092157 | FLMR HDA - Repair Handrail ST039 EL. 39. | Install missing handrail links | REL MANC NMAT PRC SETC | APPR RDBL | 4 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2025-12-31 | 2023-11-07 | 20 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092157 | FLMR HDA - Repair Handrail ST039 EL. 39. | Clean and prep handrail for paint | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2025-12-31 | 2023-11-07 | 30 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092157 | FLMR HDA - Repair Handrail ST039 EL. 39. | Paint handrail | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-27 | 2025-12-31 | 2023-11-07 | 40 | REL | APPR OPND | HD /A /86/43275 - HANDRAILS | 43275 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092170 | FLMR HDB - Repair Stair ST004 EL. 22.000 | HDB - Repair Stair ST004 EL. 22.000 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2025-12-31 | 2023-11-08 | 10 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L1 | GRATING STAIRS LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092170 | FLMR HDB - Repair Stair ST004 EL. 22.000 | Install missing handrail links | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2025-12-31 | 2023-11-08 | 20 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L1 | GRATING STAIRS LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092170 | FLMR HDB - Repair Stair ST004 EL. 22.000 | Change corroded bolts | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-26 | 2025-12-31 | 2023-11-08 | 30 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L1 | GRATING STAIRS LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092171 | FLM HDB - Replace Steps ST001 EL. 22.000 | HDB - Replace Steps ST001 EL. 22.000 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-08-31 | 2024-08-25 | 2025-12-31 | 2023-11-08 | 10 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L1 | GRATING STAIRS LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092171 | FLM HDB - Replace Steps ST001 EL. 22.000 | Install missing handrail links | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W19-W20 | 2024-08-25 | 2024-08-31 | 2024-08-25 | 2025-12-31 | 2023-11-08 | 20 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L1 | GRATING STAIRS LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092171 | FLM HDB - Replace Steps ST001 EL. 22.000 | Change corroded bolts | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W19-W20 | 2024-08-25 | 2024-08-31 | 2024-08-26 | 2025-12-31 | 2023-11-08 | 30 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L1 | GRATING STAIRS LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092171 | FLM HDB - Replace Steps ST001 EL. 22.000 | Change u-bolts on lighting support | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W19-W20 | 2024-08-25 | 2024-08-31 | 2024-08-28 | 2025-12-31 | 2023-11-08 | 40 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L1 | GRATING STAIRS LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100092171 | FLM HDB - Replace Steps ST001 EL. 22.000 | Prpe and paint handrail pots/brackets | REL MANC NMAT PRC SETC | APPR RDBL | 40 | 0 | W19-W20 | 2024-08-25 | 2024-08-31 | 2024-08-29 | 2025-12-31 | 2023-11-08 | 50 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L1 | GRATING STAIRS LEVEL 1 EL +22000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092172 | FLMR HDB - Replace of Grating EL. 26.000 | HDB - Replace of Grating EL. 26.000 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-08 | 2025-12-31 | 2023-11-08 | 10 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092172 | FLMR HDB - Replace of Grating EL. 26.000 | Measure grating incl. drawings | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-08 | 2025-12-31 | 2023-11-08 | 20 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092172 | FLMR HDB - Replace of Grating EL. 26.000 | Order materials | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-08 | 2025-12-31 | 2023-11-08 | 30 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-SCAF | 2100092172 | FLMR HDB - Replace of Grating EL. 26.000 | Erect scaffold hardbarrier | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-08 | 2025-12-31 | 2023-11-08 | 40 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-SCAF | 2100092172 | FLMR HDB - Replace of Grating EL. 26.000 | Erect scaffold liting frame | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-08 | 2025-12-31 | 2023-11-08 | 50 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-SCAF | 2100092172 | FLMR HDB - Replace of Grating EL. 26.000 | Mount rigging equipment | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-09 | 2025-12-31 | 2023-11-08 | 60 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-SCAF | 2100092172 | FLMR HDB - Replace of Grating EL. 26.000 | Rig pipe | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-09 | 2025-12-31 | 2023-11-08 | 70 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092172 | FLMR HDB - Replace of Grating EL. 26.000 | Change grating | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-09 | 2025-12-31 | 2023-11-08 | 80 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-SCAF | 2100092172 | FLMR HDB - Replace of Grating EL. 26.000 | Reinstate pipe | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-09 | 2025-12-31 | 2023-11-08 | 90 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-SCAF | 2100092172 | FLMR HDB - Replace of Grating EL. 26.000 | Remove Rigging equipment | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-09 | 2025-12-31 | 2023-11-08 | 100 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-SCAF | 2100092172 | FLMR HDB - Replace of Grating EL. 26.000 | Remove scaffolds | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-10 | 2025-12-31 | 2023-11-08 | 110 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092172 | FLMR HDB - Replace of Grating EL. 26.000 | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-10 | 2025-12-31 | 2023-11-08 | 120 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-MECH | 2100092173 | FLMR HDB - Repair Stair ST005 EL. 26.000 | HDB - Repair Stair ST005 EL. 26.000 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-08 | 2025-12-31 | 2023-11-08 | 10 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092173 | FLMR HDB - Repair Stair ST005 EL. 26.000 | Measure lighting support | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-08 | 2025-12-31 | 2023-11-08 | 20 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092173 | FLMR HDB - Repair Stair ST005 EL. 26.000 | Order materials | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-08 | 2025-12-31 | 2023-11-08 | 30 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092173 | FLMR HDB - Repair Stair ST005 EL. 26.000 | Change lighting bracket | REL NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-08 | 2025-12-31 | 2023-11-08 | 40 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092173 | FLMR HDB - Repair Stair ST005 EL. 26.000 | Change corroded bolts | REL NMAT PRC SETC | APPR RDBL | 12 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-08 | 2025-12-31 | 2023-11-08 | 50 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100092173 | FLMR HDB - Repair Stair ST005 EL. 26.000 | Install missing handrail links | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2023-11-08 | 2023-11-10 | 2023-11-09 | 2025-12-31 | 2023-11-08 | 60 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L2 | GRATING STAIRS LEVEL 2 EL +26000 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092174 | FLM HDB - Repair Stair ST008 EL. 32.400 | HDB - Repair Stair ST008 EL. 32.400 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2026-06-01 | 2023-11-08 | 10 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L3 | GRATING STAIRS LEVEL 3 EL +33400 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092174 | FLM HDB - Repair Stair ST008 EL. 32.400 | Install missing handrail links | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 | W19-W20 | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2026-06-01 | 2023-11-08 | 20 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L3 | GRATING STAIRS LEVEL 3 EL +33400 |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100092174 | FLM HDB - Repair Stair ST008 EL. 32.400 | Change corroded bolts | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W19-W20 | 2024-08-25 | 2024-08-27 | 2024-08-26 | 2026-06-01 | 2023-11-08 | 30 | REL | APPR OPND | HD /B /86/GRATING-STAIRS-L3 | GRATING STAIRS LEVEL 3 EL +33400 |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100093168 | FLMR HDC - Grating repair EL+22000 | HDC - Grating repair EL+22000 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-11-20 | 2023-11-22 | 2023-11-20 | 2026-06-01 | 2023-11-20 | 10 | REL | APPR OPND | HD /C /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100093168 | FLMR HDC - Grating repair EL+22000 | Measure gratings incl. drawings | REL NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2023-11-20 | 2023-11-22 | 2023-11-20 | 2026-06-01 | 2023-11-20 | 20 | REL | APPR OPND | HD /C /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100093168 | FLMR HDC - Grating repair EL+22000 | Order materials | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-20 | 2023-11-22 | 2023-11-20 | 2026-06-01 | 2023-11-20 | 30 | REL | APPR OPND | HD /C /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-SCAF | 2100093168 | FLMR HDC - Grating repair EL+22000 | Erect scaffold hardbarrier | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-11-20 | 2023-11-22 | 2023-11-20 | 2026-06-01 | 2023-11-20 | 40 | REL | APPR OPND | HD /C /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100093168 | FLMR HDC - Grating repair EL+22000 | Change gratings | REL NMAT PRC SETC | APPR RDBL | 8 | 0 |  | 2023-11-20 | 2023-11-22 | 2023-11-21 | 2026-06-01 | 2023-11-20 | 50 | REL | APPR OPND | HD /C /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100093168 | FLMR HDC - Grating repair EL+22000 | Clean worksite | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-20 | 2023-11-22 | 2023-11-21 | 2026-06-01 | 2023-11-20 | 60 | REL | APPR OPND | HD /C /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 |  | WDF | MTN-PIPF | MTN-SCAF | 2100093168 | FLMR HDC - Grating repair EL+22000 | Remove hardbarrier | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2023-11-20 | 2023-11-22 | 2023-11-21 | 2026-06-01 | 2023-11-20 | 70 | REL | APPR OPND | HD /C /86/22000 - GRATINGS | 22000 - GRATINGS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100093170 | FLM HDC - Install Join Link EL. 29.000 | HDC - Install Join Link EL. 29.000 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2026-06-01 | 2023-11-20 | 10 | REL | APPR OPND | HD /C /86/29500 - HANDRAILS | 29500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100093170 | FLM HDC - Install Join Link EL. 29.000 | Install missing handrail links | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W19-W20 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2026-06-01 | 2023-11-20 | 20 | REL | APPR OPND | HD /C /86/29500 - HANDRAILS | 29500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100093171 | FLMR HDC - Missing Handrail Bolts EL. 29 | HDC - Missing Handrail Bolts EL. 29.500 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2026-06-01 | 2023-11-20 | 10 | REL | APPR OPND | HD /C /86/29500 - HANDRAILS | 29500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100093171 | FLMR HDC - Missing Handrail Bolts EL. 29 | Install missing bolts | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2026-06-01 | 2023-11-20 | 20 | REL | APPR OPND | HD /C /86/29500 - HANDRAILS | 29500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100093171 | FLMR HDC - Missing Handrail Bolts EL. 29 | Prep and paint handrails | REL MANC NMAT PRC SETC | APPR RDBL | 50 | 0 | W19-W20 | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2026-06-01 | 2023-11-20 | 30 | REL | APPR OPND | HD /C /86/29500 - HANDRAILS | 29500 - HANDRAILS |  | A |  | MFM | DK60
2024-W35-36 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093870 | Faultfinding signal DHG not updating | Troubleshooting on DHG system offshore | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W35-36 | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2023-12-19 | 2023-08-06 | 10 | REL | APPR OPND | HB /B /10/HBBB-FP-30410 | SAU PANEL |  | A |  | MIN | DK50
2024-W35-36 | 3 | NOSD | WDF | MTN-TELE | VEN-ELEC | 2100093870 | Faultfinding signal DHG not updating | Troubleshooting on DHG system onshore | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W35-36 | 2024-03-09 | 2024-03-10 | 2024-03-10 | 2023-12-19 | 2023-08-06 | 20 | REL | APPR OPND | HB /B /10/HBBB-FP-30410 | SAU PANEL |  | A |  | MIN | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-MECH | 2100093878 | FLM HBA - Install Handrails Links on ST0 | HBA - Install Handrails Links on ST026 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-12-25 | 2023-12-25 | 2023-12-25 | 2025-12-31 | 2023-12-25 | 10 | REL | APPR OPND | HB /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100093878 | FLM HBA - Install Handrails Links on ST0 | Install missing handrail links | REL NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2023-12-25 | 2023-12-25 | 2023-12-25 | 2025-12-31 | 2023-12-25 | 20 | REL | APPR OPND | HB /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | MTN-PAIN | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | HBC - Paint Tertiary Str. EL. 36.700 | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-10-12 | 2024-02-24 | 2023-10-12 | 10 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | MTN-PAIN | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | HBC- Satellite brackets prep and paint | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 85 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-10-12 | 2024-02-24 | 2023-10-12 | 20 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | HBC- Support brackets prep and paint | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 85 | 48 |  | 2023-10-12 | 2024-01-25 | 2023-10-16 | 2024-02-24 | 2023-10-12 | 30 | PCNF REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | QC Paint report | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-10-16 | 2024-02-24 | 2023-10-12 | 40 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | North- Remove and replace light bracket | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 16 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-10-18 | 2024-02-24 | 2023-10-12 | 50 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | Replace cable tray support - (window) | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 32 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-10-19 | 2024-02-24 | 2023-10-12 | 60 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | Replace cable tray support x 3 | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 48 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-10-23 | 2024-02-24 | 2023-10-12 | 70 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | Smoke detector support prep and paint | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 64 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-10-28 | 2024-02-24 | 2023-10-12 | 80 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | QA-QC | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-11-04 | 2024-02-24 | 2023-10-12 | 90 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | South- Cable tray frame prep and paint | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 64 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-11-05 | 2024-02-24 | 2023-10-12 | 100 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | Stainless box frame - replace | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 32 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-11-12 | 2024-02-24 | 2023-10-12 | 110 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | replace light fixture | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 16 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-11-15 | 2024-02-24 | 2023-10-12 | 120 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | replace cable tray supports | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 48 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-11-17 | 2024-02-24 | 2023-10-12 | 130 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | Box section pipe support prep and paint | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 120 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-11-22 | 2024-02-24 | 2023-10-12 | 140 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | QA/QC | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-12-05 | 2024-02-24 | 2023-10-12 | 150 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | West - 20 x replace supports | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 168 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-12-06 | 2024-02-24 | 2023-10-12 | 160 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | prep and paint pipe supports | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 168 | 0 |  | 2023-10-12 | 2024-01-25 | 2023-12-24 | 2024-02-24 | 2023-10-12 | 170 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | QA/QC | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2023-10-12 | 2024-01-25 | 2024-01-11 | 2024-02-24 | 2023-10-12 | 180 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | Fab offshore of uni-strut supports | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 50 | 0 |  | 2023-10-12 | 2024-01-25 | 2024-01-12 | 2024-02-24 | 2023-10-12 | 190 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | INP-SITE | INP-SITE | 2100096927 | ANOCR HBC - Paint Tertiary Str. EL. 36.7 | Scaffold requirements | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 70 | 0 |  | 2023-10-12 | 2024-01-25 | 2024-01-17 | 2024-02-24 | 2023-10-12 | 200 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | INP | DK50
2026-W13-14 | 3 |  | WDF | MTN-PAIN | MTN-PAIN | 2100096928 | HBC - Paint Tertiary Str. EL. 33.000 | HBC - Paint Tertiary Str. EL. 33.000 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-10-12 | 2023-10-28 | 2023-10-12 | 2024-02-24 | 2023-10-12 | 10 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PAIN | MTN-ROPE | 2100096928 | HBC - Paint Tertiary Str. EL. 33.000 | HBC- Replace light bracket | REL NMAT PRC SETC | APPR RDBL | 40 | 0 |  | 2023-10-12 | 2023-10-28 | 2023-10-12 | 2024-02-24 | 2023-10-12 | 20 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PAIN | MTN-PAIN | 2100096928 | HBC - Paint Tertiary Str. EL. 33.000 | Prep and paint of support brackets | REL NMAT PRC SETC | APPR RDBL | 100 | 0 |  | 2023-10-12 | 2023-10-28 | 2023-10-14 | 2024-02-24 | 2023-10-12 | 30 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PAIN | MTN-ROPE | 2100096928 | HBC - Paint Tertiary Str. EL. 33.000 | Replace support brackets if required | REL NMAT PRC SETC | APPR RDBL | 100 | 0 |  | 2023-10-12 | 2023-10-28 | 2023-10-19 | 2024-02-24 | 2023-10-12 | 40 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PAIN | MTN-PAIN | 2100096928 | HBC - Paint Tertiary Str. EL. 33.000 | QC Paint report | REL NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2023-10-12 | 2023-10-28 | 2023-10-24 | 2024-02-24 | 2023-10-12 | 50 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PAIN | INP-SITE | 2100096928 | HBC - Paint Tertiary Str. EL. 33.000 | QC report for replaced brackets | REL NMAT PRC SETC | APPR RDBL | 15 | 0 |  | 2023-10-12 | 2023-10-28 | 2023-10-26 | 2024-02-24 | 2023-10-12 | 60 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | MFM | DK50
2024-W23-24 | 4 |  | WDF | MTN-ROPE | MTN-PAIN | 2100096936 | FLMR HBB - Repair/Paint Handrails EL. 31 | HBB - Repair/Paint Handrails EL. 31.500 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2026-08-07 | 2024-02-19 | 10 | REL | APPR OPND | HB /B /86/31500 - HANDRAILS | 31500 - HANDRAILS |  | A |  | MFM | DK50
2024-W15-16 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100097400 | Vibr. dampers worn down HBDB-P-1067/68 | Isolate | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-02-26 | 2023-10-14 | 10 | REL | APPR OPND | HB /D /85/HBDB-P-1067 | HIGH PRESSURE PUMP B1 |  | C |  | MMS | DK50 |  |  | 2024-04-10
2024-W15-16 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100097400 | Vibr. dampers worn down HBDB-P-1067/68 | Replace vibration dampers HBDB-P-1067/68 | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-02-26 | 2023-10-14 | 20 | REL | APPR OPND | HB /D /85/HBDB-P-1067 | HIGH PRESSURE PUMP B1 |  | C |  | MMS | DK50 |  |  | 2024-04-11
2024-W15-16 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100097400 | Vibr. dampers worn down HBDB-P-1067/68 | De-isolate | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-27 | 2024-02-26 | 2023-10-14 | 30 | REL | APPR OPND | HB /D /85/HBDB-P-1067 | HIGH PRESSURE PUMP B1 |  | C |  | MMS | DK50 |  |  | 2024-04-12
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-MECH | 2100097401 | FLM HBB - Install Join Link EL. 19.000 | HBB - Install Join Link EL. 19.000 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2026-08-15 | 2024-02-27 | 10 | REL | APPR OPND | HB /B /86/19000 - HANDRAILS | 19000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100097401 | FLM HBB - Install Join Link EL. 19.000 | Survey number of missing handrail links | REL NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2026-08-15 | 2024-02-27 | 20 | REL | APPR OPND | HB /B /86/19000 - HANDRAILS | 19000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100097401 | FLM HBB - Install Join Link EL. 19.000 | Order materials | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2026-08-15 | 2024-02-27 | 30 | REL | APPR OPND | HB /B /86/19000 - HANDRAILS | 19000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100097401 | FLM HBB - Install Join Link EL. 19.000 | Install missing handrail links | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2026-08-15 | 2024-02-27 | 40 | REL | APPR OPND | HB /B /86/19000 - HANDRAILS | 19000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097402 | ANOCR HBC - Repair Tert. Str. EL. 25.000 | HBC - Repair Tert. Str. EL. 25.000 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-02-25 | 2024-04-06 | 2024-02-25 | 2026-08-13 | 2024-02-25 | 10 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097402 | ANOCR HBC - Repair Tert. Str. EL. 25.000 | Set Up habitats and cleaning station | REL NMAT PRC SETC | APPR RDBL | 40 | 0 |  | 2024-02-25 | 2024-04-06 | 2024-02-25 | 2026-08-13 | 2024-02-25 | 20 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097402 | ANOCR HBC - Repair Tert. Str. EL. 25.000 | Prep and prime corroded areas | REL NMAT PRC SETC | APPR RDBL | 300 | 0 |  | 2024-02-25 | 2024-04-06 | 2024-02-27 | 2026-08-13 | 2024-02-25 | 30 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097402 | ANOCR HBC - Repair Tert. Str. EL. 25.000 | Paint to spec corroded areas | REL NMAT PRC SETC | APPR RDBL | 400 | 0 |  | 2024-02-25 | 2024-04-06 | 2024-03-14 | 2026-08-13 | 2024-02-25 | 40 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097402 | ANOCR HBC - Repair Tert. Str. EL. 25.000 | QC Paint report | REL NMAT PRC SETC | APPR RDBL | 16 | 0 |  | 2024-02-25 | 2024-04-06 | 2024-04-04 | 2026-08-13 | 2024-02-25 | 50 | REL | APPR OPND | HB /C /86/TOPS-TERTIARY-STRUCT | STRUCTURE TOPSIDES TERTIARY |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098349 | HBCM-A-1247, Leak in PSV connection | HBCM-A-1247, Leak in PSV connection | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-03-09 | 2023-10-26 | 10 | REL | APPR OPND | HB /C /09/HBCM-A-1247 | 2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098349 | HBCM-A-1247, Leak in PSV connection | Isolate | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-03-09 | 2023-10-26 | 20 | REL | APPR OPND | HB /C /09/HBCM-A-1247 | 2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100098349 | HBCM-A-1247, Leak in PSV connection | Recover refrigerant | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-03-09 | 2023-10-26 | 30 | REL | APPR OPND | HB /C /09/HBCM-A-1247 | 2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100098349 | HBCM-A-1247, Leak in PSV connection | Replace PSV connection | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-03-09 | 2023-10-26 | 40 | REL | APPR OPND | HB /C /09/HBCM-A-1247 | 2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100098349 | HBCM-A-1247, Leak in PSV connection | Charge refrigerant | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-03-09 | 2023-10-26 | 50 | REL | APPR OPND | HB /C /09/HBCM-A-1247 | 2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100098349 | HBCM-A-1247, Leak in PSV connection | Leak test | REL MANC NMAT PRC SETC | APPR RDBL | 0.5 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-03-09 | 2023-10-26 | 60 | REL | APPR OPND | HB /C /09/HBCM-A-1247 | 2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098349 | HBCM-A-1247, Leak in PSV connection | De-isolate | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-03-09 | 2023-10-26 | 70 | REL | APPR OPND | HB /C /09/HBCM-A-1247 | 2 ACCOMMODATION CONDENSING UNIT |  | A |  | MEL | DK50 |  | PROK
2024-W15-16 | 4 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100102030 | Not used satellite ant. to be demolished | Not used satellite ant. to be demolished | REL NMAT PRC SETC | APPR RDBL | 1 | 0 | W19-W20 | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2026-10-30 | 2024-05-13 | 10 | REL | APPR OPND | HB /C /08/HBCC-ET-14066 | SATELLITE ANTENNA 19.2* EAST - ASTRA |  | A |  | MIN | DK50 |  |  | 2024-04-17
2024-W15-16 | 4 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100102030 | Not used satellite ant. to be demolished | Update documents as built | REL NMAT PRC SETC | APPR RDBL | 5 | 0 | W19-W20 | 2024-05-13 | 2024-05-14 | 2024-05-13 | 2026-10-30 | 2024-05-13 | 20 | REL | APPR OPND | HB /C /08/HBCC-ET-14066 | SATELLITE ANTENNA 19.2* EAST - ASTRA |  | A |  | MIN | DK50 |  |  | 2024-04-18
0 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100103184 | The contactor for wacuumpump is defect. | The contactor for wacuumpump is defect. | REL MANC PRC SETC | APPR RDBL | 0 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-06-01 | 2024-01-18 | 10 | REL | APPR OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NE | WDF | MTN-ELEC | PRODTECH | 2100103184 | The contactor for wacuumpump is defect. | Isollate equipment | REL MANC PRC SETC | APPR RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-06-01 | 2024-01-18 | 20 | REL | APPR OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100103184 | The contactor for wacuumpump is defect. | Replace defective parts | REL MANC PRC SETC | APPR RDBL | 2 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-06-01 | 2024-01-18 | 30 | REL | APPR OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NE | WDF | MTN-ELEC | PRODTECH | 2100103184 | The contactor for wacuumpump is defect. | Deisolate equipment | REL MANC PRC SETC | APPR RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-26 | 2024-06-01 | 2024-01-18 | 40 | REL | APPR OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100103184 | The contactor for wacuumpump is defect. | Test and put back in service | REL MANC PRC SETC | APPR RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-26 | 2024-06-01 | 2024-01-18 | 50 | REL | APPR OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | A |  | MEL | DK60 |  | PROK
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100103421 | Switch for springs charged 1801-A01 | Switch for springs charged 1801-A01 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-06-05 | 2024-01-22 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1801-A01 | FEEDER TO HBCA-TN-1801 3/0.4KV |  | A |  | MEL | DK50 |  |  | 2024-04-20
2024-W31-32 | 4 |  | WDF | MTN-PIPF | MTN-MECH | 2100104226 | FLM HBC - Inst. JL on ST059 EL. 50.600 | HBC - Inst. JL on ST059 EL. 50.600 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2026-11-15 | 2024-05-29 | 10 | REL | APPR OPND | HB /C /86/50600 - GRATINGS | 50600 - GRATINGS |  | A |  | MFM | DK50
2024-W23-24 | 4 |  | WDF | MTN-PIPF | MTN-MECH | 2100104227 | FLM HBC - Inst. JL - Grating Clips EL. 5 | HBC - Inst. JL - Grating Clips EL. 50.60 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2026-11-15 | 2024-05-29 | 10 | REL | APPR OPND | HB /C /86/50600 - GRATINGS | 50600 - GRATINGS |  | A |  | MFM | DK50
2024-W23-24 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100104726 | FLM HBD - Inst. Handrail JL EL. 45.500 | HBD - Inst. Handrail JL EL. 45.500 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2026-11-15 | 2024-05-29 | 10 | REL | APPR OPND | HB /D /86/45500 - HANDRAILS | 45500 - HANDRAILS |  | A |  | MFM | DK50
0 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100104892 | FLM HDA - Repair Grating EL. 47.000 | HDA - Repair Grating EL. 47.000 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2026-11-15 | 2024-05-29 | 10 | REL | APPR OPND | HD /A /86/47000 - GRATINGS | 47000 - GRATINGS |  | A |  | MFM | DK60
2024-W37-38 | 3 |  | WDF | VEN-ELEC | VEN-ELEC | 2100105568 | IT-Switch caused SD to N-1853B | IT-Switch caused SD to N-1853B | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-07-05 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B02-TA | IT-SWITCH |  | A |  | MEL | DK50
2024-W15-16 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106047 | FLM When open LCV can not maintain pos. | Test of Siemens controller LY-445101 | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-05-25 | 2024-01-11 | 10 | REL | APPR OPND | HB /D /32/HBDB-LCV-445101 | LEVEL CONTROL VALVE |  | A |  | MIN | DK50 |  |  | 2024-04-08
2024-W33-34 | 2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100106415 | GE Power Manegment Relay A-1650 | GE Power Manegment Relay A-1650 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-03-15 | 2024-01-30 | 10 | REL | APPR OPND | HB /D /60/HBDC-G-1650 | MAIN GENERATOR |  | C |  | MEL | DK50 |  |  | 2024-05-04
2024-W29-30 | 2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100106417 | GE Power Manegment Relay P-3651 | GE Power Manegment Relay P-3651 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-03-15 | 2024-01-30 | 10 | REL | APPR OPND | HB /D /23/HBDB-PM-3651 | ELEC. PUMP MOTOR |  | C |  | MEL | DK50 |  |  | 2024-05-03
2024-W23-24 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106456 | Termostat tag nr wrong in display | Termostat tag nr wrong in display | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2027-01-14 | 2024-07-28 | 10 | REL | APPR OPND | HB /C /09/HBCM-LCP-1265 | LOCAL CONTROL PANEL |  | A |  | MEL | DK50 |  |  | 2024-05-03
2024-W23-24 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106456 | Termostat tag nr wrong in display | Correct settings in plc | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2027-01-14 | 2024-07-28 | 20 | REL | APPR OPND | HB /C /09/HBCM-LCP-1265 | LOCAL CONTROL PANEL |  | A |  | MEL | DK50 |  |  | 2024-05-04
2024-W35-36 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107162 | EMG light HBD L0 and 1 LP-1811-Q37 | EMG light HBD L0 and 1 LP-1811-Q37 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-08-08 | 2024-03-26 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811-37 | EMERG. LIGHTING PLATFORM LEVEL 0 |  | C |  | MEL | DK50 |  |  | 2024-05-12
0 | 3 |  | WDF | MTN-PIPF | MTN-MECH | 2100107168 | FLM Kick plate missing on flare bridge | Kick plate missing on flare bridge | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-08-04 | 2024-03-22 | 10 | REL | APPR OPND | HD /C /86/A-C_HANDRAILS | BRIDGE_A-C_HANDRAILS |  | A |  | MFM | DK60
2026-W13-14 | 3 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200003016 | SMAT:HBA Manglende isolering instrument | L3 Disassembly of old insulation | REL MANC PRC SETC | APPR RDBL | 10.1 | 0 | LAGG competency | 2023-04-24 | 2023-04-29 | 2023-04-24 | 2018-09-19 | 2018-06-21 | 10 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | CON | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200003016 | SMAT:HBA Manglende isolering instrument | L3 Mounting new Insulation | REL MANC PRC SETC | APPR RDBL | 37.5 | 0 | LAGG competency | 2023-04-24 | 2023-04-29 | 2023-04-25 | 2018-09-19 | 2018-06-21 | 20 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | CON | DK50
2024-W45-46 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200004657 | Prep Handheld vibration data collection | Foto doc. machine familirazation | REL MANC PRC SETC | APPR RDBL | 25 | 0 | W45-46 | 2023-11-06 | 2023-11-08 | 2023-11-06 | 2020-12-17 | 2020-09-18 | 10 | REL | APPR OPND | HB /B /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK50
0 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200004658 | Prep Handheld vibration data collection | Foto doc. machine familirazation | REL MANC PRC SETC | APPR RDBL | 25 | 0 |  | 2023-04-24 | 2023-04-26 | 2023-04-24 | 2020-12-17 | 2020-09-18 | 10 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK60
0 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200005881 | Offshore survey - hoses - Halfdan A | Offshore survey - hoses - Halfdan A | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-18 | 2020-12-09 | 10 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM |  | A |  | MMS | DK60
2026-W13-14 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007059 | Handheld vib meas. on rotating Equipment | Handheld vib meas. on rotating Equipment | REL PCNF MANC PRC SETC | APPR RDBL | 0 | 0 |  | 2023-01-02 | 2023-01-02 | 2023-01-02 | 2021-06-21 | 2021-05-12 | 10 | PCNF REL | APPR OPND | HB /B /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK50
2026-W13-14 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007059 | Handheld vib meas. on rotating Equipment | Make sure equipment is operating stable | REL PCNF MANC PRC SETC | APPR RDBL | 12 | 18 |  | 2023-01-02 | 2023-01-02 | 2023-01-02 | 2021-06-21 | 2021-05-12 | 20 | PCNF REL | APPR OPND | HB /B /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK50
2026-W13-14 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007059 | Handheld vib meas. on rotating Equipment | Take vib meas with handheld data collect | REL PCNF MANC PRC SETC | APPR RDBL | 36 | 48 |  | 2023-01-02 | 2023-01-02 | 2023-01-02 | 2021-06-21 | 2021-05-12 | 30 | PCNF REL | APPR OPND | HB /B /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK50
2026-W13-14 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007059 | Handheld vib meas. on rotating Equipment | Data Analysis, db optimization | REL PCNF MANC PRC SETC | APPR RDBL | 0 | 0 |  | 2023-01-02 | 2023-01-02 | 2023-01-02 | 2021-06-21 | 2021-05-12 | 40 | PCNF REL | APPR OPND | HB /B /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK50
0 | 3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200007300 | Temporary epoxy changing facilities HDA | Temporary epoxy changing facilities HDA | REL MACM PRC SETC | APPR RDBL | 0 | 0 |  | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-07-26 | 2021-06-16 | 10 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MFM | DK60
2024-W39-40 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200008624 | ANOC Halfdan B Painting Scope | ANOC Halfdan B ainting Scope | REL PCNF NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2022-03-02 | 2022-03-02 | 2022-03-02 | 2022-10-28 | 2022-03-02 | 10 | PCNF REL | APPR OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50 |  |  | 2024-04-21
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009257 | insulation assist Bilfinger 18200 | insulation assist FORCE 18200 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-26 | 2023-04-24 | 2022-11-05 | 2022-03-10 | 10 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4231-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009257 | insulation assist Bilfinger 18200 | Remove Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 |  | 2023-04-24 | 2023-04-26 | 2023-04-24 | 2022-11-05 | 2022-03-10 | 20 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4231-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | VEN-MECH | 2200009257 | insulation assist Bilfinger 18200 | Bilfinger Scan | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-04-24 | 2023-04-26 | 2023-04-25 | 2022-11-05 | 2022-03-10 | 30 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4231-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009257 | insulation assist Bilfinger 18200 | Refit Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 |  | 2023-04-24 | 2023-04-26 | 2023-04-25 | 2022-11-05 | 2022-03-10 | 40 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4231-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009258 | Insulation assist Bilfinger Pack: 18199 | Insulation assist Bilfinger Pack: 18199 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-28 | 2023-04-24 | 2022-11-06 | 2022-03-11 | 10 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4231-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009258 | Insulation assist Bilfinger Pack: 18199 | Erect Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 |  | 2023-04-24 | 2023-04-28 | 2023-04-24 | 2022-11-06 | 2022-03-11 | 20 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4231-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009258 | Insulation assist Bilfinger Pack: 18199 | Remove Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 9 | 0 |  | 2023-04-24 | 2023-04-28 | 2023-04-25 | 2022-11-06 | 2022-03-11 | 30 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4231-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | VEN-MECH | 2200009258 | Insulation assist Bilfinger Pack: 18199 | Bilfinger - Scan | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-04-24 | 2023-04-28 | 2023-04-26 | 2022-11-06 | 2022-03-11 | 40 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4231-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009258 | Insulation assist Bilfinger Pack: 18199 | Refit Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 |  | 2023-04-24 | 2023-04-28 | 2023-04-26 | 2022-11-06 | 2022-03-11 | 50 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4231-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009258 | Insulation assist Bilfinger Pack: 18199 | Dismantle Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 |  | 2023-04-24 | 2023-04-28 | 2023-04-27 | 2022-11-06 | 2022-03-11 | 60 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4231-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009261 | Insulation assist Bilfinger 19771 | Insulation assist FORCE 19772 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-04-24 | 2023-06-01 | 2023-04-24 | 2022-11-05 | 2022-03-10 | 10 | REL | APPR OPND | HB /A /28/HBA-6-DPS-050-4019-AA-U | 6 CLOSED DRAIN SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009261 | Insulation assist Bilfinger 19771 | Erect Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 78 | 0 |  | 2023-04-24 | 2023-06-01 | 2023-04-24 | 2022-11-05 | 2022-03-10 | 20 | REL | APPR OPND | HB /A /28/HBA-6-DPS-050-4019-AA-U | 6 CLOSED DRAIN SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009261 | Insulation assist Bilfinger 19771 | Remove Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 16 | 0 |  | 2023-04-24 | 2023-06-01 | 2023-05-02 | 2022-11-05 | 2022-03-10 | 30 | REL | APPR OPND | HB /A /28/HBA-6-DPS-050-4019-AA-U | 6 CLOSED DRAIN SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | VEN-MECH | 2200009261 | Insulation assist Bilfinger 19771 | Bilfinger - Scan | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-04-24 | 2023-06-01 | 2023-05-03 | 2022-11-05 | 2022-03-10 | 40 | REL | APPR OPND | HB /A /28/HBA-6-DPS-050-4019-AA-U | 6 CLOSED DRAIN SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009261 | Insulation assist Bilfinger 19771 | Refit Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 32 | 0 |  | 2023-04-24 | 2023-06-01 | 2023-05-04 | 2022-11-05 | 2022-03-10 | 50 | REL | APPR OPND | HB /A /28/HBA-6-DPS-050-4019-AA-U | 6 CLOSED DRAIN SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009261 | Insulation assist Bilfinger 19771 | Dismantle Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 50 | 0 |  | 2023-04-24 | 2023-06-01 | 2023-05-07 | 2022-11-05 | 2022-03-10 | 60 | REL | APPR OPND | HB /A /28/HBA-6-DPS-050-4019-AA-U | 6 CLOSED DRAIN SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009261 | Insulation assist Bilfinger 19771 | Rope Access Insulation Removal | REL MANC NMAT PRC SETC | APPR RDBL | 144 | 0 |  | 2023-04-24 | 2023-06-01 | 2023-05-12 | 2022-11-05 | 2022-03-10 | 70 | REL | APPR OPND | HB /A /28/HBA-6-DPS-050-4019-AA-U | 6 CLOSED DRAIN SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009261 | Insulation assist Bilfinger 19771 | Altrad Rope Access Level 3 Assisstance | REL MANC NMAT PRC SETC | APPR RDBL | 120 | 0 |  | 2023-04-24 | 2023-06-01 | 2023-05-19 | 2022-11-05 | 2022-03-10 | 80 | REL | APPR OPND | HB /A /28/HBA-6-DPS-050-4019-AA-U | 6 CLOSED DRAIN SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009261 | Insulation assist Bilfinger 19771 | Material Handling Altrad | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-04-24 | 2023-06-01 | 2023-06-01 | 2022-11-05 | 2022-03-10 | 90 | REL | APPR OPND | HB /A /28/HBA-6-DPS-050-4019-AA-U | 6 CLOSED DRAIN SOUR LINE | 99000099 | A |  | INP | DK50
2024-W29-30 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009268 | insulation assist Bilfinger 19208 (COMP | insulation assist Bilfinger 19208 | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2022-08-31 | 2022-08-31 | 2022-08-31 | 2022-11-05 | 2022-03-10 | 10 | REL | APPR OPND | HB /A /55/HBA-6-WI-035-4220-GFW-U | 6 INJECTION WATER LINE | 99000099 | A |  | INP | DK50 |  |  | 2024-05-05
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009270 | Insulation assist Bilfinger 18163 (COMP | Insulation assist FORCE 18163 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-04-24 | 2023-05-10 | 2023-04-24 | 2022-11-05 | 2022-03-10 | 10 | REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0801-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009270 | Insulation assist Bilfinger 18163 (COMP | Erect Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 52 | 0 |  | 2023-04-24 | 2023-05-10 | 2023-04-24 | 2022-11-05 | 2022-03-10 | 20 | REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0801-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009270 | Insulation assist Bilfinger 18163 (COMP | Remove Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 27 | 0 |  | 2023-04-24 | 2023-05-10 | 2023-04-29 | 2022-11-05 | 2022-03-10 | 30 | REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0801-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | VEN-MECH | 2200009270 | Insulation assist Bilfinger 18163 (COMP | Bilfinger - Scan | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-04-24 | 2023-05-10 | 2023-05-02 | 2022-11-05 | 2022-03-10 | 40 | REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0801-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009270 | Insulation assist Bilfinger 18163 (COMP | Refit Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 54 | 0 |  | 2023-04-24 | 2023-05-10 | 2023-05-02 | 2022-11-05 | 2022-03-10 | 50 | REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0801-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009270 | Insulation assist Bilfinger 18163 (COMP | Dismantle Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 26 | 0 |  | 2023-04-24 | 2023-05-10 | 2023-05-08 | 2022-11-05 | 2022-03-10 | 60 | REL | APPR OPND | HB /B /55/HBB-6-PHS-030-0801-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009274 | Insulation assist Bilfinger 17466 (COMP | Insulation assist FORCE 17466 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-30 | 2023-04-24 | 2022-11-05 | 2022-03-10 | 10 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2507-BD-T | 2 CRUDE OIL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009274 | Insulation assist Bilfinger 17466 (COMP | Erect Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 26 | 0 |  | 2023-04-24 | 2023-04-30 | 2023-04-24 | 2022-11-05 | 2022-03-10 | 20 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2507-BD-T | 2 CRUDE OIL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009274 | Insulation assist Bilfinger 17466 (COMP | Remove Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2023-04-24 | 2023-04-30 | 2023-04-26 | 2022-11-05 | 2022-03-10 | 30 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2507-BD-T | 2 CRUDE OIL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | VEN-MECH | 2200009274 | Insulation assist Bilfinger 17466 (COMP | Bilfinger - Scan | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-04-24 | 2023-04-30 | 2023-04-27 | 2022-11-05 | 2022-03-10 | 40 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2507-BD-T | 2 CRUDE OIL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009274 | Insulation assist Bilfinger 17466 (COMP | Refit Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 |  | 2023-04-24 | 2023-04-30 | 2023-04-27 | 2022-11-05 | 2022-03-10 | 50 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2507-BD-T | 2 CRUDE OIL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009274 | Insulation assist Bilfinger 17466 (COMP | Dismantle Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 |  | 2023-04-24 | 2023-04-30 | 2023-04-29 | 2022-11-05 | 2022-03-10 | 60 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2507-BD-T | 2 CRUDE OIL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009275 | Insulation assist Bilfinger 14467 | Insulation assist Bilfinger 14467 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-01-08 | 2024-01-25 | 2024-01-08 | 2022-11-06 | 2022-03-11 | 10 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2536-DD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009275 | Insulation assist Bilfinger 14467 | Erect Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 52 | 0 |  | 2024-01-08 | 2024-01-25 | 2024-01-08 | 2022-11-06 | 2022-03-11 | 20 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2536-DD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009275 | Insulation assist Bilfinger 14467 | Remove Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 |  | 2024-01-08 | 2024-01-25 | 2024-01-13 | 2022-11-06 | 2022-03-11 | 30 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2536-DD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-ELEC | 2200009275 | Insulation assist Bilfinger 14467 | Isolate & Remove Trace Htg | REL MANC NMAT PRC SETC | APPR RDBL | 7 | 0 |  | 2024-01-08 | 2024-01-25 | 2024-01-15 | 2022-11-06 | 2022-03-11 | 40 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2536-DD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | VEN-MECH | 2200009275 | Insulation assist Bilfinger 14467 | Bilfinger - Scan | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-01-08 | 2024-01-25 | 2024-01-16 | 2022-11-06 | 2022-03-11 | 50 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2536-DD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-ELEC | 2200009275 | Insulation assist Bilfinger 14467 | Refit Trace Htg, Megger Test & Energise | REL MANC NMAT PRC SETC | APPR RDBL | 9 | 0 |  | 2024-01-08 | 2024-01-25 | 2024-01-16 | 2022-11-06 | 2022-03-11 | 60 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2536-DD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009275 | Insulation assist Bilfinger 14467 | Refit Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 27 | 0 |  | 2024-01-08 | 2024-01-25 | 2024-01-18 | 2022-11-06 | 2022-03-11 | 70 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2536-DD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009275 | Insulation assist Bilfinger 14467 | Dismantle Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 40 | 0 |  | 2024-01-08 | 2024-01-25 | 2024-01-21 | 2022-11-06 | 2022-03-11 | 80 | REL | APPR OPND | HB /D /23/HBD-2-OCS-036-2536-DD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009283 | Insulation assist Bilfinger 17471 | Insulation assist FORCE 17471 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-01-08 | 2024-01-17 | 2024-01-08 | 2022-11-05 | 2022-03-10 | 10 | REL | APPR OPND | HB /D /27/HBD-2-WOS-034-4020-AD-T | 2 PRODUCED WATER LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009283 | Insulation assist Bilfinger 17471 | Erect Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 24 | 0 |  | 2024-01-08 | 2024-01-17 | 2024-01-08 | 2022-11-05 | 2022-03-10 | 20 | REL | APPR OPND | HB /D /27/HBD-2-WOS-034-4020-AD-T | 2 PRODUCED WATER LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009283 | Insulation assist Bilfinger 17471 | Remove Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 |  | 2024-01-08 | 2024-01-17 | 2024-01-12 | 2022-11-05 | 2022-03-10 | 30 | REL | APPR OPND | HB /D /27/HBD-2-WOS-034-4020-AD-T | 2 PRODUCED WATER LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | VEN-MECH | 2200009283 | Insulation assist Bilfinger 17471 | Bilfinger - Scan | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-01-08 | 2024-01-17 | 2024-01-13 | 2022-11-05 | 2022-03-10 | 40 | REL | APPR OPND | HB /D /27/HBD-2-WOS-034-4020-AD-T | 2 PRODUCED WATER LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009283 | Insulation assist Bilfinger 17471 | Refit Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 16 | 0 |  | 2024-01-08 | 2024-01-17 | 2024-01-13 | 2022-11-05 | 2022-03-10 | 50 | REL | APPR OPND | HB /D /27/HBD-2-WOS-034-4020-AD-T | 2 PRODUCED WATER LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009283 | Insulation assist Bilfinger 17471 | Dismantle Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 |  | 2024-01-08 | 2024-01-17 | 2024-01-15 | 2022-11-05 | 2022-03-10 | 60 | REL | APPR OPND | HB /D /27/HBD-2-WOS-034-4020-AD-T | 2 PRODUCED WATER LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009289 | Insulation assist Bilfinger Pack 17464 | Insulation assist Bilfinger Pack 17464 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-08 | 2022-11-06 | 2022-03-11 | 10 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2289-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009289 | Insulation assist Bilfinger Pack 17464 | Erect Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 26 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-08 | 2022-11-06 | 2022-03-11 | 20 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2289-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009289 | Insulation assist Bilfinger Pack 17464 | Remove Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 9 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-10 | 2022-11-06 | 2022-03-11 | 30 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2289-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-ELEC | 2200009289 | Insulation assist Bilfinger Pack 17464 | Isolate & Remove Trace Htg | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-11 | 2022-11-06 | 2022-03-11 | 40 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2289-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | VEN-MECH | 2200009289 | Insulation assist Bilfinger Pack 17464 | Bilfinger - Scan | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-12 | 2022-11-06 | 2022-03-11 | 50 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2289-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-ELEC | 2200009289 | Insulation assist Bilfinger Pack 17464 | Refit Trace Htg, Megger Test & Energise | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-13 | 2022-11-06 | 2022-03-11 | 60 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2289-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009289 | Insulation assist Bilfinger Pack 17464 | Refit Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-14 | 2022-11-06 | 2022-03-11 | 70 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2289-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009289 | Insulation assist Bilfinger Pack 17464 | Dismantle Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-16 | 2022-11-06 | 2022-03-11 | 80 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2289-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009290 | Insulation assist Bilfinger 17465 | Insulation assist FORCE 17465 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-08 | 2022-11-05 | 2022-03-10 | 10 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2313-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009290 | Insulation assist Bilfinger 17465 | Erect Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 26 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-08 | 2022-11-05 | 2022-03-10 | 20 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2313-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009290 | Insulation assist Bilfinger 17465 | Remove Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-10 | 2022-11-05 | 2022-03-10 | 30 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2313-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | VEN-MECH | 2200009290 | Insulation assist Bilfinger 17465 | Bilfinger - Scan | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-12 | 2022-11-05 | 2022-03-10 | 40 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2313-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009290 | Insulation assist Bilfinger 17465 | Refit Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 36 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-12 | 2022-11-05 | 2022-03-10 | 50 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2313-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009290 | Insulation assist Bilfinger 17465 | Dismantle Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 |  | 2024-01-08 | 2024-01-18 | 2024-01-16 | 2022-11-05 | 2022-03-10 | 60 | REL | APPR OPND | HB /D /28/HBD-2-OCS-034-2313-AD-T | 2 CRUDE OIL SOUR LINE |  | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009359 | Insulation assist Bilfinger Pack: 19298 | Insulation assist Bilfinger Pack: 19298 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-12-11 | 2023-12-27 | 2023-12-11 | 2022-11-06 | 2022-03-11 | 10 | REL | APPR OPND | HB /A /55/HBA-6-PHS-030-4018-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-PAIN | MTN-SCAF | 2200009359 | Insulation assist Bilfinger Pack: 19298 | Erect Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 52 | 0 |  | 2023-12-11 | 2023-12-27 | 2023-12-11 | 2022-11-06 | 2022-03-11 | 20 | REL | APPR OPND | HB /A /55/HBA-6-PHS-030-4018-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-PAIN | MTN-LAGG | 2200009359 | Insulation assist Bilfinger Pack: 19298 | Remove Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 |  | 2023-12-11 | 2023-12-27 | 2023-12-16 | 2022-11-06 | 2022-03-11 | 30 | REL | APPR OPND | HB /A /55/HBA-6-PHS-030-4018-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-PAIN | VEN-MECH | 2200009359 | Insulation assist Bilfinger Pack: 19298 | Bilfinger - Scan | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-12-11 | 2023-12-27 | 2023-12-18 | 2022-11-06 | 2022-03-11 | 40 | REL | APPR OPND | HB /A /55/HBA-6-PHS-030-4018-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-PAIN | MTN-LAGG | 2200009359 | Insulation assist Bilfinger Pack: 19298 | Refit Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 45 | 0 |  | 2023-12-11 | 2023-12-27 | 2023-12-18 | 2022-11-06 | 2022-03-11 | 50 | REL | APPR OPND | HB /A /55/HBA-6-PHS-030-4018-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-PAIN | MTN-SCAF | 2200009359 | Insulation assist Bilfinger Pack: 19298 | Dismantle Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 40 | 0 |  | 2023-12-11 | 2023-12-27 | 2023-12-23 | 2022-11-06 | 2022-03-11 | 60 | REL | APPR OPND | HB /A /55/HBA-6-PHS-030-4018-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000099 | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200009376 | Building and dismantling of scaffolding | Erect Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 52 | 0 |  | 2023-04-24 | 2023-05-02 | 2023-04-24 | 2022-11-05 | 2022-03-10 | 10 | REL | APPR OPND | HB /D /23/HBD-10-OCS-034-2211-BD-U | 10 CRUDE OIL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-SCAF | VEN-MECH | 2200009376 | Building and dismantling of scaffolding | Bilfinger - Scan | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-04-24 | 2023-05-02 | 2023-04-29 | 2022-11-05 | 2022-03-10 | 20 | REL | APPR OPND | HB /D /23/HBD-10-OCS-034-2211-BD-U | 10 CRUDE OIL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200009376 | Building and dismantling of scaffolding | Dismantle Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 26 | 0 |  | 2023-04-24 | 2023-05-02 | 2023-04-29 | 2022-11-05 | 2022-03-10 | 30 | REL | APPR OPND | HB /D /23/HBD-10-OCS-034-2211-BD-U | 10 CRUDE OIL SOUR LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009395 | Insulation assist Bilfinger 19299 (COMP | Insulation assist FORCE 19299 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-04-24 | 2023-05-08 | 2023-04-24 | 2022-11-05 | 2022-03-10 | 10 | REL | APPR OPND | HB /A /55/HBA-6-WI-035-4280-GFW-U | 6 INJECTION WATER LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009395 | Insulation assist Bilfinger 19299 (COMP | Erect Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 50 | 0 |  | 2023-04-24 | 2023-05-08 | 2023-04-24 | 2022-11-05 | 2022-03-10 | 20 | REL | APPR OPND | HB /A /55/HBA-6-WI-035-4280-GFW-U | 6 INJECTION WATER LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009395 | Insulation assist Bilfinger 19299 (COMP | Remove Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 18 | 0 |  | 2023-04-24 | 2023-05-08 | 2023-04-29 | 2022-11-05 | 2022-03-10 | 30 | REL | APPR OPND | HB /A /55/HBA-6-WI-035-4280-GFW-U | 6 INJECTION WATER LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | VEN-MECH | 2200009395 | Insulation assist Bilfinger 19299 (COMP | Bilfinger - Scan | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-04-24 | 2023-05-08 | 2023-05-01 | 2022-11-05 | 2022-03-10 | 40 | REL | APPR OPND | HB /A /55/HBA-6-WI-035-4280-GFW-U | 6 INJECTION WATER LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009395 | Insulation assist Bilfinger 19299 (COMP | Refit Insulation | REL MANC NMAT PRC SETC | APPR RDBL | 36 | 0 |  | 2023-04-24 | 2023-05-08 | 2023-05-01 | 2022-11-05 | 2022-03-10 | 50 | REL | APPR OPND | HB /A /55/HBA-6-WI-035-4280-GFW-U | 6 INJECTION WATER LINE | 99000099 | A |  | INP | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009395 | Insulation assist Bilfinger 19299 (COMP | Dismantle Scaffold | REL MANC NMAT PRC SETC | APPR RDBL | 30 | 0 |  | 2023-04-24 | 2023-05-08 | 2023-05-05 | 2022-11-05 | 2022-03-10 | 60 | REL | APPR OPND | HB /A /55/HBA-6-WI-035-4280-GFW-U | 6 INJECTION WATER LINE | 99000099 | A |  | INP | DK50
0 | 4 | NOSD | WGN | MTN-ELEC | PRODTECH | 2200009925 | Gemstart 4 to 5 upgrade | Isolate and remove drawer | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-02-11 | 2022-06-16 | 10 | REL | APPR OPND | HD /A /61 | POWER DISTRIBUTION (HV, LV) |  | C |  | MEL | DK60
0 | 4 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200009925 | Gemstart 4 to 5 upgrade | Isolate and remove drawer | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-02-11 | 2022-06-16 | 20 | REL | APPR OPND | HD /A /61 | POWER DISTRIBUTION (HV, LV) |  | C |  | MEL | DK60
0 | 4 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200009925 | Gemstart 4 to 5 upgrade | Insert modified drawer | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-02-11 | 2022-06-16 | 30 | REL | APPR OPND | HD /A /61 | POWER DISTRIBUTION (HV, LV) |  | C |  | MEL | DK60
0 | 4 | NOSD | WGN | MTN-ELEC | PRODTECH | 2200009925 | Gemstart 4 to 5 upgrade | De-isolate and test drawer | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-02-11 | 2022-06-16 | 40 | REL | APPR OPND | HD /A /61 | POWER DISTRIBUTION (HV, LV) |  | C |  | MEL | DK60
0 | 3 | NOSD | WGN | MTN-ELEC | PRODTECH | 2200011028 | Breaker borrowed to other switchgear | Isolate | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-07-24 | 2022-06-14 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-10-01 | HDBE- N18111001 INCOMER FR TRAFO TN-1805 |  | C |  | MEL | DK60
0 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200011028 | Breaker borrowed to other switchgear | Retract drawer | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-07-24 | 2022-06-14 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-10-01 | HDBE- N18111001 INCOMER FR TRAFO TN-1805 |  | C |  | MEL | DK60
0 | 3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200011028 | Breaker borrowed to other switchgear | Insert borrowed drawer | REL PRT MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-07-24 | 2022-06-14 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-10-01 | HDBE- N18111001 INCOMER FR TRAFO TN-1805 |  | C |  | MEL | DK60
0 | 3 | NOSD | WGN | MTN-ELEC | PRODTECH | 2200011028 | Breaker borrowed to other switchgear | De-Isolate above and test | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2022-07-24 | 2022-06-14 | 40 | REL | APPR OPND | HD /B /61/HDBE-N-1811-10-01 | HDBE- N18111001 INCOMER FR TRAFO TN-1805 |  | C |  | MEL | DK60
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200011309 | Paint of supports HBB cellar deck | Paint of supports HBB cellar deck | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2025-06-14 | 2022-12-27 | 10 | PCNF REL | APPR OPND | HB /B /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200011309 | Paint of supports HBB cellar deck | MPM permits | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 3 | 1 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2025-06-14 | 2022-12-27 | 20 | PCNF REL | APPR OPND | HB /B /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200011309 | Paint of supports HBB cellar deck | MPM surface prep | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 108 | 103 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2025-06-14 | 2022-12-27 | 30 | PCNF REL | APPR OPND | HB /B /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200011309 | Paint of supports HBB cellar deck | MPM paint | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 100 | 66 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2025-06-14 | 2022-12-27 | 40 | PCNF REL | APPR OPND | HB /B /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200011309 | Paint of supports HBB cellar deck | MPM clean up | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 60 | 3 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2025-06-14 | 2022-12-27 | 50 | PCNF REL | APPR OPND | HB /B /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS |  | A |  | MFM | DK50
2024-W45-46 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200011745 | Handheld vib meas. on rotating Eq R5 | Handheld vib meas. on rotating Eq R5 | REL MANC PRC SETC | APPR RDBL | 0 | 0 | W45-46 | 2023-11-06 | 2023-11-14 | 2023-11-06 | 2023-02-28 | 2022-10-16 | 10 | REL | APPR OPND | HB /B /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK50
2024-W45-46 | 3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200011745 | Handheld vib meas. on rotating Eq R5 | Take vib meas with handheld EX data coll | REL MANC PRC SETC | APPR RDBL | 76 | 0 | W45-46 | 2023-11-06 | 2023-11-14 | 2023-11-06 | 2023-02-28 | 2022-10-16 | 20 | REL | APPR OPND | HB /B /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-ELEC | VEN-HVAC | 2200012269 | Survey - Refurb of Cooler/ Freezer area | Survey - Refurb of Cooler/ Freezer area | REL MANC NMAT PRC SETC | APPR RDBL | 40 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2023-04-26 | 2022-12-12 | 10 | REL | APPR OPND | HB /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | A |  | MEL | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | PRODTECH | 2200013910 | Replace HBAA-PSV-35000B - PSV 2023 | Isolation of PSV | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-09 | 2026-03-05 | 2023-09-17 | 10 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000B | PRESSURE SAFETY VALVE |  | D |  | MMS | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | PRODTECH | 2200013910 | Replace HBAA-PSV-35000B - PSV 2023 | Prod Assist (breaking containment) | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-09 | 2026-03-05 | 2023-09-17 | 20 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000B | PRESSURE SAFETY VALVE |  | D |  | MMS | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | MTN-RIGG | 2200013910 | Replace HBAA-PSV-35000B - PSV 2023 | Rigging assist (install) | REL MANC NMAT PRC SETC | APPR RDBL | 24 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-09 | 2026-03-05 | 2023-09-17 | 30 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000B | PRESSURE SAFETY VALVE |  | D |  | MMS | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | MTN-MECH | 2200013910 | Replace HBAA-PSV-35000B - PSV 2023 | Remove PSV and install new PSV | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-14 | 2026-03-05 | 2023-09-17 | 40 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000B | PRESSURE SAFETY VALVE |  | D |  | MMS | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | MTN-RIGG | 2200013910 | Replace HBAA-PSV-35000B - PSV 2023 | Rigging Assist (remove) | REL MANC NMAT PRC SETC | APPR RDBL | 12 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-15 | 2026-03-05 | 2023-09-17 | 60 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000B | PRESSURE SAFETY VALVE |  | D |  | MMS | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | PRODTECH | 2200013910 | Replace HBAA-PSV-35000B - PSV 2023 | Prod Assist (breaking containment) | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-18 | 2026-03-05 | 2023-09-17 | 70 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000B | PRESSURE SAFETY VALVE |  | D |  | MMS | DK50
2024-W47-48 | 4 | HB WI SD | WGN | MTN-MECH | PRODTECH | 2200013910 | Replace HBAA-PSV-35000B - PSV 2023 | De-isolation and leak test | REL MANC NMAT PRC SETC | APPR RDBL | 4 | 0 | W47-48 | 2024-03-09 | 2024-03-19 | 2024-03-18 | 2026-03-05 | 2023-09-17 | 90 | REL | APPR OPND | HB /A /50/HBAA-PSV-35000B | PRESSURE SAFETY VALVE |  | D |  | MMS | DK50
0 | 2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200014132 | Rent of freezer for W2W campaign | Rent of freezer for W2W campaign | REL MANC PRC SETC | APPR RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-05-27 | 2023-04-12 | 10 | REL | APPR OPND | HD /B /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK60 |  | PROK
0 | 2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200014132 | Rent of freezer for W2W campaign | Rental Standalone Freezer | REL MANC PRC SETC | APPR RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-05-27 | 2023-04-12 | 30 | REL | APPR OPND | HD /B /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016006 | Assistance fur Install of Turnbed | Assistance fur Install of Turnbed | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W45-46 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-04-04 | 2023-11-21 | 10 | REL | APPR OPND | HD /B /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK60
0 | 3 | NOSD | WGN | MTN-ELEC | MTN-RIGG | 2200016006 | Assistance fur Install of Turnbed | Assistance from Rigger | REL MANC NMAT PRC SETC | APPR RDBL | 20 | 0 | W45-46 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-04-04 | 2023-11-21 | 20 | REL | APPR OPND | HD /B /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK60
2024-W49-50 | 3 | NE | WGN | MTN-TELE | MTN-TELE | 2200016035 | HBC LTE eq replacement | HBC LTE eq replacement by ATCOM | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 168 | 14 | W49-50 | 2024-09-15 | 2024-10-18 | 2024-09-15 | 2024-04-09 | 2023-11-26 | 10 | PCNF REL | APPR OPND | HB /C /08/HBCF-AS-14744 | RACK |  | A |  | MIN | DK50
2024-W45-46 | 2 | NE | WGN | MTN-TELE | MTN-TELE | 2200016077 | Troubleshoot on wavemapper server issue | Troubleshoot on wavemapper server issue | REL MANC NMAT PRC SETC | APPR RDBL | 25 | 0 | W45-46 | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2023-12-01 | 2023-10-17 | 10 | REL | APPR OPND | HB /D /08/HBDC-FP-1468 | WAVE MAPPER UNIT SERVER CABINET |  | A |  | MIN | DK50
2024-W49-50 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016304 | Uneven floor HBD office Room ass FMC/GMC | Uneven floor HBD office Room ass FMC/GMC | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W49-50 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2024-05-01 | 2023-12-18 | 10 | PCNF REL | APPR OPND | HB /D /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK50
2024-W49-50 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016304 | Uneven floor HBD office Room ass FMC/GMC | Assist relocation of equipment | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 15 | 0 | W49-50 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2024-05-01 | 2023-12-18 | 20 | PCNF REL | APPR OPND | HB /D /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK50
2024-W49-50 | 3 | NOSD | WGN | MTN-ELEC | MTN-SCAF | 2200016304 | Uneven floor HBD office Room ass FMC/GMC | Assist relocation of equipment | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 20 | 0 | W49-50 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2024-05-01 | 2023-12-18 | 40 | PCNF REL | APPR OPND | HB /D /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK50
2024-W17-18 | 2 | NE | WGN | MTN-INST | MTN-INST | 2200016541 | Wifi phone to HBC Medic | Wifi phone to HBC Medic | REL PRT MANC PRC SETC | APPR RDBL | 0 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-01-05 | 2023-11-21 | 10 | REL | APPR OPND | HB /C /08 | COMMUNICATION/TELECOM |  | A |  | MIN | DK50 |  |  | 2024-04-22
0 | 2 | NE | WGN | MTN-INST | MTN-INST | 2200016544 | Wifi phone to HAL Medic | Wifi phone to HAL Medic | REL PRT MANC PRC SETC | APPR RDBL | 0 | 0 | W13-W14 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-01-05 | 2023-11-21 | 10 | REL | APPR OPND | HD /B /08 | COMMUNICATION/TELECOM |  | A |  | MIN | DK60
2026-W13-14 | 2 | NE | WGN | MTN-TELE | MTN-TELE | 2200017475 | Replace Switch HBD. | Replace Switch HBD | REL PCNF PRT MANC PRC SETC | APPR RDBL | 4 | 10 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-22 | 2024-02-06 | 10 | PCNF REL | APPR OPND | HB /D /08 | COMMUNICATION/TELECOM |  | A |  | MIN | DK50
2026-W13-14 | 2 | NE | WGN | MTN-TELE | VEN-COMM | 2200017475 | Replace Switch HBD. | Telecom assistance Replace switch | REL PCNF PRT MANC PRC SETC | APPR RDBL | 4 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-03-22 | 2024-02-06 | 20 | PCNF REL | APPR OPND | HB /D /08 | COMMUNICATION/TELECOM |  | A |  | MIN | DK50
0 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000555 | Additional well test samples (DHRTC) | Additional well test samples (DHRTC) | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-05-29 | 10 | REL | APPR OPND | HD /A /80 | LABORATORY |  | A |  | PRD | DK60
2024-W41-42 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000683 | Materials/backload system 003 | Materials/backload system 003 | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-12-31 | 10 | REL | APPR OPND | HB | Halfdan B |  | A |  | MMS | DK50 |  |  | 2024-05-05
2024-W47-48 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000774 | DK48 MATCON, QC,TEGN MATERIAL ORDER 2019 | DK48 MATCON, QC,TEGN MATERIAL ORDER 2019 | REL MANC PRC SETC | APPR RDBL | 0 | 0 |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-01-01 | 10 | REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | CON | DK50 |  |  | 2024-05-05
2024-W25-26 | 3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300000805 | C05 Remove SCADA transmitter in SW | C05 Fjernelse af SCADA transmittere i SW | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2017-07-01 | 2017-04-02 | 10 | REL | APPR OPND | HB /A /04/HBAA-FP-2020 | SCADA PANEL |  | A |  | MIN | DK50 |  |  | 2024-04-22
2024-W35-36 | 3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300000840 | C55 Fejl i genvej på OS billede HBB08 | HMI-CCR observation | REL MANC NMAT PRC SETC | APPR RDBL | 4 | 0 | W35-36 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2016-09-23 | 2016-06-25 | 10 | REL | APPR OPND | HB /B /04/HBBA-CP-2030 | SCADA PANEL / NODE C55 |  | A |  | MIN | DK50
2024-W35-36 | 3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300000843 | C85 HBD Glycol Tank Tare Weight | C85 HBD Glycol Tank Tare Weight | REL MANC NMAT PRC SETC | APPR RDBL | 4 | 0 | W35-36 | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2016-07-21 | 2016-04-22 | 10 | REL | APPR OPND | HB /D /04/HBDC-CP-2050 | SCADA CONTROLLER CABINET |  | A |  | MIN | DK50
2024-W35-36 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000844 | E81 HMIbilleder overview ventiler HB Com | HMIbilleder overview ventiler HB Complex | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2016-10-01 | 2016-08-22 | 10 | REL | APPR OPND | HB /D /03/HBDC-CP-0250 | ESD CONTROLLER CABINET |  | A |  | MIN | DK50 |  |  | 2024-04-24
2024-W27-28 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000849 | Scada-CCR Obsertion | Scada-CCR Obsertion | REL PRT MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2030-12-31 | 2010-01-01 | 10 | REL | APPR OPND | HB /D /04/HBDC-CP-2050 | SCADA CONTROLLER CABINET |  | A |  | MEL | DK50 |  |  | 2024-04-24
2024-W15-16 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000850 | C85 HMI-CCR Observation | HMI-CCR Observation | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2016-03-27 | 2016-03-07 | 10 | REL | APPR OPND | HB /D /04/HBDC-CP-2050 | SCADA CONTROLLER CABINET |  | A |  | MIN | DK50 |  |  | 2024-04-17
2024-W31-32 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000866 | Mismatch mellem C&E og Config | Mismatch mellem C&E og Config | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2017-02-09 | 2016-12-31 | 10 | REL | APPR OPND | HB /C /03/HBCA-CPF-0101 | FIRE AND GAS CONTROLLER |  | F |  | MIN | DK50 |  |  | 2024-04-17
2024-W49-50 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000873 | SIM-E01 ESD, Enable inhibit fault. | SI-E01 ESD, Enable inhibit fault. | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W49-50 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2013-03-20 | 2013-03-13 | 10 | REL | APPR OPND | HB /A /03/HBAA-FP-0220A | ESD PANEL |  | A |  | MIN | DK50
2024-W49-50 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000874 | HBAA-ESDV-38048 traveltime ønskes ændret | HBAA-ESDV-38048 traveltime | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W49-50 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2013-03-20 | 2013-03-13 | 10 | REL | APPR OPND | HB /A /03/HBAA-FP-0220A | ESD PANEL |  | A |  | MIN | DK50
2024-W41-42 | 4 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300000885 | F84 WaterM Reset ikke ved Gen F<(>&<)>G | F84 WaterM Reset ikke ved Gen F&G Reset | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2016-02-08 | 2015-09-11 | 10 | REL | APPR OPND | HB /D /03/HBDC-CP-0150 | F&G CONTROLLER CABINET |  | A |  | MIN | DK50 |  |  | 2024-05-07
2024-W29-30 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000886 | C05 Signal HBAA-IQI-1802 ønskes fjernet. | Signal HBAA-IQI-1802 ønskes fjernet. | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2030-12-31 | 2010-01-01 | 10 | REL | APPR OPND | HB /A /04/HBAA-FP-2020 | SCADA PANEL |  | A |  | MIN | DK50 |  |  | 2024-04-24
2024-W25-26 | 4 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300000889 | C05 HBA Wells Manglende Flow Cutoff | C05 HBA Wells Manglende Flow Cutoff | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2016-07-17 | 2015-11-20 | 10 | REL | APPR OPND | HB /A /04/HBAA-FP-2020 | SCADA PANEL |  | A |  | MIN | DK50 |  |  | 2024-05-20
2024-W43-44 | 3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300000892 | F83 Sw rettelse for 4stk Fail open XCV | F83 Sw rettelse for 4stk Fail open XCV | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2015-04-06 | 2015-01-06 | 10 | REL | APPR OPND | HB /D /03/HBDC-CP-0150 | F&G CONTROLLER CABINET |  | A |  | MIN | DK50 |  |  | 2024-04-20
2025-W3-4 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000917 | SMAT:replace Faulty PC for Yokogawa HMI | replace Faulty PC for Yokogawa HMI | REL MANC PRC SETC | APPR RDBL | 0 | 0 |  | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2016-10-01 | 2016-07-03 | 10 | REL | APPR OPND | HB /C /03/HBCA-CP-0201 | ESD |  | A |  | MIN | DK50
2024-W49-50 | 4 | NE | WRO | MTN-TELE | MTN-TELE | 2300001046 | F03, Clean-up block/suppress | F03, Clean-up block/suppress | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W49-50 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2013-03-20 | 2013-03-13 | 10 | REL | APPR OPND | HB /A /03/HBAA-FP-0120A | FIRE AND GAS PANEL |  | A |  | MIN | DK50
2024-W49-50 | 4 | NE | WRO | MTN-TELE | MTN-TELE | 2300001047 | E01, Clean-up block/suppress | E01, Clean-up block/suppress | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W49-50 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2013-03-20 | 2013-03-13 | 10 | REL | APPR OPND | HB /A /03/HBAA-FP-0220A | ESD PANEL |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WRO | MTN-TELE | VEN-ELEC | 2300001102 | SIM-HMI-CCR observation | HMI-CCR observation | REL PRT MANC PRC SETC | APPR RDBL | 6 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2014-02-20 | 2014-02-20 | 10 | REL | APPR OPND | HB /D /04/HBDC-CP-2051B | SCADA SERVER CABINET 2 |  | A |  | ENG | DK50
2026-W13-14 | 4 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300001102 | SIM-HMI-CCR observation | Telecom Assistance | REL PRT MANC PRC SETC | APPR RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2014-02-20 | 2014-02-20 | 20 | REL | APPR OPND | HB /D /04/HBDC-CP-2051B | SCADA SERVER CABINET 2 |  | A |  | ENG | DK50
2024-W31-32 | 3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300001114 | C05 Exchange internals CVA-30126 | Exchange internals CVA-30126 (CJ) | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | Telecom | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2019-11-12 | 2019-08-14 | 10 | REL | APPR OPND | HB /A /04/HBAA-FP-2020 | SCADA PANEL |  | A |  | MIN | DK50 |  |  | 2024-05-07
2024-W15-16 | 3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300001115 | C05 Exchange internals CVA-30066 | Exchange internals CVA-30016 (CJ) | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | Telecom PTW 194416 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2019-11-12 | 2019-08-14 | 10 | REL | APPR OPND | HB /A /04/HBAA-FP-2020 | SCADA PANEL |  | A |  | MIN | DK50 |  |  | 2024-04-17
2024-W35-36 | 3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300001116 | C05 Exchange internals CVA-30286 | Exchange internals CVA-30286 (CJ) | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2019-11-12 | 2019-08-14 | 10 | REL | APPR OPND | HB /A /04/HBAA-FP-2020 | SCADA PANEL |  | A |  | MIN | DK50 |  |  | 2024-05-22
0 | 4 |  | WRO | VEN-ROPE | VEN-ROPE | 2300001592 | Handling of goods for Find & Fix team HD | Handling of goods for Find & Fix team HD | REL MACM PRC SETC | APPR RDBL | 0 | 0 |  | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2021-05-01 | 2020-09-03 | 10 | REL | APPR OPND | HD /C /86/FABRIC-MAINTENANCE | HDC PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
2024-W15-16 | 4 | NE | WRO | MTN-ROUS | MTN-ROUS | 2300001988 | Time registre rigging loft Halfdan B | Time registre rigging loft Halfdan B | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 200 | 479 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-01-17 | 2021-03-23 | 10 | PCNF REL | APPR OPND | HB /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMS | DK50 |  |  | 2024-04-08
0 | 4 | NE | WRO | MTN-ROUS | MTN-ROUS | 2300001989 | Time registre rigging loft Halfdan A | Time registre rigging loft Halfdan A | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 200 | 693 | W47-48 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-01-17 | 2021-03-23 | 10 | PCNF REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMS | DK60
2024-W35-36 | 3 | NE | WRO | MTN-MECH | MTN-MECH | 2300002036 | HB Fab-Main Extended Maintenance Team | HB Fab-Main Extended Maintenance Team | REL MANC PRC SETC | APPR RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-10 | 2020-11-12 | 10 | REL | APPR OPND | HB | Halfdan B |  | A |  | MFM | DK50
0 | 4 | NE | WRO | MTN-TELE | MTN-TELE | 2300002308 | Static picture changes HDA and HDB | Static picture changes HDA and HDB | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-08-19 | 2021-03-22 | 10 | REL | APPR OPND | HD /B /04/HDBE-SC-2001 | HMI SERVER RACK (SIEMENS) |  | A |  | MIN | DK60
0 | 4 |  | WRO | PRODTECH | PRODTECH | 2300002632 | DK60 - CONSUMABLE PROD - LAB | DK60 - CONSUMABLE PROD - LAB | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2022-06-06 | 2021-08-10 | 10 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | PRD | DK60
2024-W31-32 | 4 |  | WRO | PRODTECH | PRODTECH | 2300002634 | DK50 - CONSUMABLE PROD - LAB | DK50 - CONSUMABLE PROD - LAB | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2022-06-06 | 2021-08-10 | 10 | REL | APPR OPND | HB /D /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | PRD | DK50
0 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003839 | DK60 HALFDAN A ICE Team Materials | DK60 HALFDAN A SKRUMS MATRIALER | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2022-04-06 | 2022-04-06 | 2022-04-06 | 2022-05-16 | 2022-04-06 | 10 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | CON | DK60
0 | 2 |  | WRO | PRODTECH | MTN-TELE | 2300004252 | IT0098 - Telecom support | IT0098 - Notification for telecom suppor | REL PCNF MANC NMAT PRC SETC | APPR RDBL | 20 | 40 | W47-48 IOP 24/11-1/12-22 | 2022-11-24 | 2022-11-29 | 2022-11-24 | 2022-12-16 | 2022-11-01 | 10 | PCNF REL | APPR OPND | HD /B | HALFDAN DB |  | A |  | ENG | DK60
2024-W31-32 | 4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004500 | DK50 - HOURS MTN - FLM - FIRST LEVEL MTN | DK50 - HOURS MTN - FLM - FIRST LEVEL MTN | REL PCNF MANC PPRT PRC SETC | APPR RDBL | 0 | 498 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 10 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK50
2024-W31-32 | 4 | NOSD | WRO | MTN-ELEC | MTN-INST | 2300004500 | DK50 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Inst | REL PCNF MANC PPRT PRC SETC | APPR RDBL | 0 | 749.5 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 20 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK50
2024-W31-32 | 4 | NOSD | WRO | MTN-ELEC | MTN-TELE | 2300004500 | DK50 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Telecom | REL PCNF MANC PPRT PRC SETC | APPR RDBL | 0 | 1706.5 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 30 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK50
2024-W31-32 | 4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004500 | DK50 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Mech | REL PCNF MANC PPRT PRC SETC | APPR RDBL | 0 | 729.5 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 40 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK50
2024-W31-32 | 4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004500 | DK50 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Turb | REL PCNF MANC PPRT PRC SETC | APPR RDBL | 0 | 222.5 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 50 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK50
2024-W31-32 | 4 | NOSD | WRO | MTN-ELEC | MTN-ROUS | 2300004500 | DK50 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Roust | REL PCNF MANC PPRT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 60 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK50
2024-W31-32 | 4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004500 | DK50 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Scaff | REL PCNF MANC PPRT PRC SETC | APPR RDBL | 0 | 153 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 70 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK50
2024-W31-32 | 4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004500 | DK50 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Rope | REL PCNF MANC PPRT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 80 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK50
2024-W17-18 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300005485 | Halfdan Halfdan B Cybersecurity findings | Halfdan Halfdan B Cybersecurity findings | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-10-22 | 2023-06-09 | 10 | REL | APPR OPND | HB | Halfdan B |  | A |  | MIN | DK50 |  |  | 2024-04-22
2024-W19-20 | 1 | NE | WRO | MTN-TELE | MTN-TELE | 2300005723 | C05 Update of CVA-35004 choke table | C05 Update of CVA-35004 choke table | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-06-09 | 2023-05-25 | 10 | REL | APPR OPND | HB /A /04/HBAA-FP-2020 | SCADA PANEL |  | A |  | MIN | DK50 |  |  | 2024-05-07
0 | 1 |  | WRO | VEN-INST | VEN-INST | 2300006722 | Halfdan B Update Safety Monitor | Halfdan B Update Safety Monitor | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-10-06 | 2023-09-21 | 10 | REL | APPR OPND | HD /A /04 | SUBSEA/SURFACE CONTROL & SUPERVISION |  | A |  | MIN | DK60
2024-W31-32 | 3 | NOSD | WRO | MTN-INST | MTN-TELE | 2300007624 | Well profile for HBB MPFM | Well profile for HBB MPFM | REL MANC NMAT PRC SETC | APPR RDBL | 0 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-07-09 | 2024-02-25 | 10 | REL | APPR OPND | HB /B /11/HBBB-A-3745 | MULTIPHASE METER |  | A |  | MIN | DK50 |  |  | 2024-04-22
2024-W33-34 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300007845 | C05 HBA15 down hole gauge switch & HMI p | C05 HBA15 down hole gauge switch | REL MACM PRC SETC | APPR RDBL | 0 | 0 |  | 2024-03-23 | 2024-03-23 | 2024-03-23 | 2024-08-05 | 2024-03-23 | 10 | REL | APPR OPND | HB /A /04/HBAA-FP-2020 | SCADA PANEL |  | A |  | MIN | DK50 |  |  | 2024-04-24
0 | 4 | NOSD | WRO | PRODTECH | PRODTECH | 2300007983 | DK60 - CONSUMABLE PROD - WORKSHOP | DK60 - CONSUMABLE PROD - WORKSHOP | REL NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2027-02-12 | 2024-08-26 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
0 | D | NOSD | WPM | PRODTECH | PRODLABO | 2400076791 | 6M STANDARD ACID JOB HDA | OTS SCHEDULED BIMONTHLY STANDARD ACID JO | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2023-04-24 | 2023-04-25 | 2023-04-24 | 2020-08-03 | 2020-07-09 | 10 | REL | APPR OPND | HD /A /80/CHEMISTRY | CHEMISTRY |  | A | DK610077785 | PRD | DK60
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211318 | 4Y 11KV N-SWB MAINT HBDC-N-1851-K06 | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W13 DK50-M-6110 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-09-01 | 2022-06-05 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K06 | K06 BUS MEASURING |  | C | DKHB-0521 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211318 | 4Y 11KV N-SWB MAINT HBDC-N-1851-K06 | 11KV N-SWB MAINT HBDC-N-1851-K06 | REL PRT MANC NMAT PRC SETC | APPR RDBL | 3 | 0 | W13 DK50-M-6110 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-09-01 | 2022-06-05 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K06 | K06 BUS MEASURING |  | C | DKHB-0521 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211318 | 4Y 11KV N-SWB MAINT HBDC-N-1851-K06 | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W13 DK50-M-6110 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2022-09-01 | 2022-06-05 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K06 | K06 BUS MEASURING |  | C | DKHB-0521 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211373 | 4Y 400V E-DP TEST HBDD-DP-1960-AO1 | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO1 | SECTION A01 |  | C | DKHB-0438 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211373 | 4Y 400V E-DP TEST HBDD-DP-1960-AO1 | 400V E-DP TEST HBDD-DP-1960-AO1 | REL PRT MANC NMAT PRC SETC | APPR RDBL | 19 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO1 | SECTION A01 |  | C | DKHB-0438 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211373 | 4Y 400V E-DP TEST HBDD-DP-1960-AO1 | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO1 | SECTION A01 |  | C | DKHB-0438 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211374 | 4Y 400V E-DP TEST HBDD-DP-1960-AO2 | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO2 | SECTION A02 |  | C | DKHB-0439 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211374 | 4Y 400V E-DP TEST HBDD-DP-1960-AO2 | 400V E-DP TEST HBDD-DP-1960-AO2 | REL PRT MANC NMAT PRC SETC | APPR RDBL | 21 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO2 | SECTION A02 |  | C | DKHB-0439 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211374 | 4Y 400V E-DP TEST HBDD-DP-1960-AO2 | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO2 | SECTION A02 |  | C | DKHB-0439 | MEL | DK50 | EL0024
2024-W45-46 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211379 | 4Y 400V E-DP INSP HBDD-DP-1960-BO3 | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2022-12-01 | 2022-09-19 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO3 | SECTION B03 |  | C | DKHB-0444 | MEL | DK50 | EL0024
2024-W45-46 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211379 | 4Y 400V E-DP INSP HBDD-DP-1960-BO3 | 400V E-DP INSP HBDD-DP-1960-BO3 | REL PRT MANC NMAT PRC SETC | APPR RDBL | 29 | 0 | W45-46 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2022-12-01 | 2022-09-19 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO3 | SECTION B03 |  | C | DKHB-0444 | MEL | DK50 | EL0024
2024-W45-46 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211379 | 4Y 400V E-DP INSP HBDD-DP-1960-BO3 | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2022-12-01 | 2022-09-19 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO3 | SECTION B03 |  | C | DKHB-0444 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211380 | 4Y 400V E-DP TEST HBDD-DP-1960-BO4 | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W47-48 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO4 | SECTION B04 |  | C | DKHB-0445 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211380 | 4Y 400V E-DP TEST HBDD-DP-1960-BO4 | 400V E-DP TEST HBDD-DP-1960-BO4 | REL PRT MANC NMAT PRC SETC | APPR RDBL | 16 | 0 | W47-48 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO4 | SECTION B04 |  | C | DKHB-0445 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211380 | 4Y 400V E-DP TEST HBDD-DP-1960-BO4 | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W47-48 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO4 | SECTION B04 |  | C | DKHB-0445 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211382 | 4Y 400V E-DP TEST HBDD-DP-1960-CO2 | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-CO2 | SECTION C02 |  | C | DKHB-0447 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211382 | 4Y 400V E-DP TEST HBDD-DP-1960-CO2 | 400V E-DP TEST HBDD-DP-1960-CO2 | REL PRT MANC NMAT PRC SETC | APPR RDBL | 17 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-CO2 | SECTION C02 |  | C | DKHB-0447 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211382 | 4Y 400V E-DP TEST HBDD-DP-1960-CO2 | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W47-48 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-CO2 | SECTION C02 |  | C | DKHB-0447 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211438 | 4Y 400V N-DP MAINT HBC SMALL POWER | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 3 | 0 | W47-48 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /C /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | C | DKHB-0629 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211438 | 4Y 400V N-DP MAINT HBC SMALL POWER | 400V N-DP MAINT HBC SMALL POWER | REL PRT MANC NMAT PRC SETC | APPR RDBL | 24 | 0 | W47-48 | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /C /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | C | DKHB-0629 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211438 | 4Y 400V N-DP MAINT HBC SMALL POWER | 400V N-DP MAINT HBC SMALL POWER | REL PRT MANC NMAT PRC SETC | APPR RDBL | 10 | 0 | W47-48 | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /C /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | C | DKHB-0629 | MEL | DK50 | EL0024
2024-W47-48 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211438 | 4Y 400V N-DP MAINT HBC SMALL POWER | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR RDBL | 3 | 0 | W47-48 | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2022-12-01 | 2022-09-04 | 40 | REL | APPR OPND | HB /C /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | C | DKHB-0629 | MEL | DK50 | EL0024
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211445 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDA | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0401 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211445 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDA | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDA | REL MANC NMAT PRC SETC | APPR RDBL | 26 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0401 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211445 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDA | 400V N-DP HD LIGHT/SMALL POWER, HDA | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0401 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211445 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDA | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2022-12-01 | 2022-09-04 | 40 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0401 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211446 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDB | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0402 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211446 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDB | 400V N-DP HD LIGHT/SMALL POWER, HDB INSP | REL MANC NMAT PRC SETC | APPR RDBL | 42 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0402 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211446 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDB | 400V N-DP HD LIGHT/SMALL POWER, HDB INSP | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0402 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211446 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDB | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2022-12-01 | 2022-09-04 | 40 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0402 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211447 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDA | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0405 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211447 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDA | 400V N-DP HD LIGHT/SMALL POWER, HDA INSP | REL MANC NMAT PRC SETC | APPR RDBL | 14 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0405 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211447 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDA | 400V N-DP HD LIGHT/SMALL POWER, HDA INSP | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0405 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211447 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDA | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2022-12-01 | 2022-09-04 | 40 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0405 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211448 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDB | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0403 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211448 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDB | 400V N-DP HD LIGHT/SMALL POWER, HDB INSP | REL MANC NMAT PRC SETC | APPR RDBL | 26 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0403 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211448 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDB | 400V N-DP HD LIGHT/SMALL POWER, HDB INSP | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0403 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211448 | 4Y 400V N-DP HD LIGHT/SMALL POWER, HDB | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2022-12-01 | 2022-09-04 | 40 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0403 | MEL | DK60 | EL0023
0 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400219138 | 2Y 24V ES-SWBD HDAB-N-1802 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-12-12 | 2022-10-27 | 10 | REL | APPR OPND | HD /A /06/SWITCHBOARDS | SWITCHBOARDS |  | A | DKHD-0250 | MEL | DK60 | EL0023
0 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400219138 | 2Y 24V ES-SWBD HDAB-N-1802 | 24V ES-SWBD HDAB-N-1802 INSPECTION | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-12-12 | 2022-10-27 | 20 | REL | APPR OPND | HD /A /06/SWITCHBOARDS | SWITCHBOARDS |  | A | DKHD-0250 | MEL | DK60 | EL0023
0 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400219138 | 2Y 24V ES-SWBD HDAB-N-1802 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-12-12 | 2022-10-27 | 30 | REL | APPR OPND | HD /A /06/SWITCHBOARDS | SWITCHBOARDS |  | A | DKHD-0250 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | PRODLABO | PRODLABO | 2400240996 | 2M GAS SAMPLE FOR CO2 EMISSION HDA | GAS SAMPLE FOR CO2 EMISSION HDA | REL PRT NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-04-02 | 2023-04-02 | 2023-04-02 | 2023-04-13 | 2023-04-02 | 10 | REL | APPR OPND | HD /A /80 | LABORATORY |  | A | DK600003571 | PRD | DK60
2026-W13-14 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400259046 | 3Y SW LIFT PUMPS ANODES - HBCM-P-5231/2 | ISOLATION | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2023-06-08 | 2023-03-26 | 10 | REL | APPR OPND | HB /C /50/HBCM-P-5232 | SEAWATER LIFT PUMP |  | A | DKHB-2075 | MMR | DK50 | MR0084
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259046 | 3Y SW LIFT PUMPS ANODES - HBCM-P-5231/2 | SW LIFT PUMPS ANODES - HBCM-P-5231/2 | REL MANC NMAT PRC SETC | APPR RDBL | 16 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2023-06-08 | 2023-03-26 | 20 | REL | APPR OPND | HB /C /50/HBCM-P-5232 | SEAWATER LIFT PUMP |  | A | DKHB-2075 | MMR | DK50 | MR0084
2026-W13-14 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400259046 | 3Y SW LIFT PUMPS ANODES - HBCM-P-5231/2 | DE-ISOLATION | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2023-06-08 | 2023-03-26 | 30 | REL | APPR OPND | HB /C /50/HBCM-P-5232 | SEAWATER LIFT PUMP |  | A | DKHB-2075 | MMR | DK50 | MR0084
0 | C | NOSD | WPM | PRODLABO | PRODLABO | 2400259189 | 2M GAS SAMPLE FOR CO2 EMISSION HDA | GAS SAMPLE FOR CO2 EMISSION HDA | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-13 | 2023-06-02 | 10 | REL | APPR OPND | HD /A /80 | LABORATORY |  | A | DK600003571 | PRD | DK60
2026-W13-14 | D | NOSD | WPM | MTN-PAIN | MTN-SCAF | 2400263096 | 1Y TRANSPORTABLE LADDERS Halfdan B | TRANSPORTABLE LADDERS - HBA | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2023-05-18 | 2023-05-19 | 2023-05-18 | 2023-07-04 | 2023-05-18 | 10 | REL | APPR OPND | HB /A /84 | WORKSHOP/WAREHOUSE |  | A | DKHB-2041 | MFM | DK50 | FM0034
0 | B | NOSD | WPM | PRODLABO | PRODLABO | 2400272913 | 1Y HDA PW AROMATICS,PHENOLS,HEAVY METALS | HDA PW AROMATICS,PHENOLS,HEAVY METALS | REL MANC PRC SETC | APPR RDBL | 3 | 0 |  | 2023-09-11 | 2023-09-11 | 2023-09-11 | 2023-09-01 | 2023-08-02 | 10 | REL | APPR OPND | HD /A /80 | LABORATORY |  | A | DK600021079 | PRD | DK60
0 | C | NOSD | WPM | PRODLABO | PRODLABO | 2400281405 | 2M GAS SAMPLE FOR CO2 EMISSION HDA | GAS SAMPLE FOR CO2 EMISSION HDA | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-13 | 2023-10-02 | 10 | REL | APPR OPND | HD /A /80 | LABORATORY |  | A | DK600003571 | PRD | DK60
0 | C | NOSD | WPM | PRODLABO | PRODLABO | 2400291615 | 2M GAS SAMPLE FOR CO2 EMISSION HDA | GAS SAMPLE FOR CO2 EMISSION HDA | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2023-12-02 | 2023-12-02 | 2023-12-02 | 2023-12-13 | 2023-12-02 | 10 | REL | APPR OPND | HD /A /80 | LABORATORY |  | A | DK600003571 | PRD | DK60
2024-W47-48 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400293807 | 1Y PURGE WATER UNIT CLEAN-HBDD-A-1061 | PURGE WATER UNIT CLEAN-HBDD-A-1061 | REL PRT MANC NMAT PRC SETC | APPR RDBL | 4 | 0 | W47-48 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-01-01 | 2023-11-26 | 10 | REL | APPR OPND | HB /D /77/HBDD-A-1061 | MIXED BED COLUMN |  | C | DKHB-0674 | MMS | DK50 | MS0024
2024-W47-48 | C | NOSD | WPM | MTN-MECH | MTN-INST | 2400293807 | 1Y PURGE WATER UNIT CLEAN-HBDD-A-1061 | PURGE WATER UNIT SUPPORT-HBDD-A-1061 | REL PRT MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W47-48 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-01-01 | 2023-11-26 | 20 | REL | APPR OPND | HB /D /77/HBDD-A-1061 | MIXED BED COLUMN |  | C | DKHB-0674 | MMS | DK50 | MS0024
0 | B | NOSD | WPM | MTN-ELEC | MTN-INST | 2400298346 | 2Y SS-WORKSHOP EMG-SWITCH INSP HDA | SS-WORKSHOP EMG-SWITCH INSP HDA | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W19-W20 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-01-15 | 2023-11-30 | 10 | REL | APPR OPND | HD /A /61/MACHINERY-ISOLATORS | WORKSHOP EMERGENCY ISOLATORS |  | A | DKHD-0469 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302062 | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDA | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-01 | 2023-12-08 | 10 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0401 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302062 | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDA | 400V N-DP HD LIGHT/SMALL POWER, HDA | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-01 | 2023-12-08 | 20 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0401 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302062 | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDA | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-01 | 2023-12-08 | 30 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0401 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302063 | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDA | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-02-01 | 2023-12-08 | 10 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0405 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302063 | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDA | 400V N-DP HD LIGHT/SMALL POWER, HDA INSP | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-02-01 | 2023-12-08 | 20 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0405 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302063 | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDA | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-02-01 | 2023-12-08 | 30 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0405 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | PRODLABO | PRODLABO | 2400302664 | 2M GAS SAMPLE FOR CO2 EMISSION HDA | GAS SAMPLE FOR CO2 EMISSION HDA | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-13 | 2024-02-02 | 10 | REL | APPR OPND | HD /A /80 | LABORATORY |  | A | DK600003571 | PRD | DK60
0 | D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400306731 | 6M ELECTRICAL HAND TOOLS | 6M ELECTRICAL HAND TOOLS CHECK | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 | W19-W20 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-02-18 | 2024-01-24 | 10 | REL | APPR OPND | HD /A /61 | POWER DISTRIBUTION (HV, LV) |  | A | DKHD-2040 | MEL | DK60 | EL0043 | PROK
0 | D | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400306731 | 6M ELECTRICAL HAND TOOLS | 6M ELECTRICAL HAND TOOLS CHECK | REL MANC NMAT PRC SETC | APPR RDBL | 4 | 0 | W19-W20 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-02-18 | 2024-01-24 | 20 | REL | APPR OPND | HD /A /61 | POWER DISTRIBUTION (HV, LV) |  | A | DKHD-2040 | MEL | DK60 | EL0043 | PROK
0 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400307679 | 2Y 400V E-DP HD EMG. LIGHT HDB | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2024-07-30 | 2024-08-03 | 2024-07-30 | 2024-03-01 | 2024-01-15 | 10 | REL | APPR OPND | HD /B /05/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0251 | MEL | DK60 | EL0023
0 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400307679 | 2Y 400V E-DP HD EMG. LIGHT HDB | 400V E-DP HD EMG. LIGHT HDB INSPECTION | REL MANC NMAT PRC SETC | APPR RDBL | 24 | 0 |  | 2024-07-30 | 2024-08-03 | 2024-07-31 | 2024-03-01 | 2024-01-15 | 20 | REL | APPR OPND | HD /B /05/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0251 | MEL | DK60 | EL0023
0 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307679 | 2Y 400V E-DP HD EMG. LIGHT HDB | 400V E-DP HD EMG. LIGHT HDB INSPECTION | REL MANC NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2024-07-30 | 2024-08-03 | 2024-08-01 | 2024-03-01 | 2024-01-15 | 30 | REL | APPR OPND | HD /B /05/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0251 | MEL | DK60 | EL0023
0 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400307679 | 2Y 400V E-DP HD EMG. LIGHT HDB | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2024-07-30 | 2024-08-03 | 2024-08-02 | 2024-03-01 | 2024-01-15 | 40 | REL | APPR OPND | HD /B /05/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0251 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400307683 | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDB | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-03-01 | 2024-01-06 | 10 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0402 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400307683 | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDB | 400V N-DP HD LIGHT/SMALL POWER, HDB INSP | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-03-01 | 2024-01-06 | 20 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0402 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400307683 | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDB | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2024-03-01 | 2024-01-06 | 30 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0402 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400307684 | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDB | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-03-01 | 2024-01-06 | 10 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0403 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400307684 | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDB | 400V N-DP HD LIGHT/SMALL POWER, HDB INSP | REL MANC NMAT PRC SETC | APPR RDBL | 8 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-03-01 | 2024-01-06 | 20 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0403 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400307684 | 2Y 400V N-DP HD LIGHT/SMALL POWER, HDB | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2024-03-01 | 2024-01-06 | 30 | REL | APPR OPND | HD /B /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0403 | MEL | DK60 | EL0023
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307868 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M01 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M01 | SPARE MOTOR FEEDER |  | C | DKHB-0544 | MEL | DK50 | EL0024 |  | 2024-06-02
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307868 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M01 | 3KV N-SWB MAINT HBDC-N-1852-M01 | REL MANC NMAT PRC SETC | APPR RDBL | 2.5 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M01 | SPARE MOTOR FEEDER |  | C | DKHB-0544 | MEL | DK50 | EL0024 |  | 2024-06-03
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307868 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M01 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M01 | SPARE MOTOR FEEDER |  | C | DKHB-0544 | MEL | DK50 | EL0024 |  | 2024-06-05
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307869 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M02 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M02 | SPARE MOTOR FEEDER |  | C | DKHB-0545 | MEL | DK50 | EL0024 |  | 2024-05-28
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307869 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M02 | 3KV N-SWB MAINT HBDC-N-1852-M02 | REL MANC NMAT PRC SETC | APPR RDBL | 2.5 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M02 | SPARE MOTOR FEEDER |  | C | DKHB-0545 | MEL | DK50 | EL0024 |  | 2024-05-29
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307869 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M02 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M02 | SPARE MOTOR FEEDER |  | C | DKHB-0545 | MEL | DK50 | EL0024 |  | 2024-05-31
2024-W21-22 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307870 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M03 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M03 | HBDB-PM-5353 COOL MEDIUM CIRC PMP MOTOR |  | C | DKHB-0546 | MEL | DK50 | EL0024 |  | 2024-06-02
2024-W21-22 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307870 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M03 | 3KV N-SWB MAINT HBDC-N-1852-M03 | REL MANC NMAT PRC SETC | APPR RDBL | 2.5 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M03 | HBDB-PM-5353 COOL MEDIUM CIRC PMP MOTOR |  | C | DKHB-0546 | MEL | DK50 | EL0024 |  | 2024-06-03
2024-W21-22 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307870 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M03 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M03 | HBDB-PM-5353 COOL MEDIUM CIRC PMP MOTOR |  | C | DKHB-0546 | MEL | DK50 | EL0024 |  | 2024-06-05
2024-W21-22 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307871 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M04 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M04 | HBDB-PM-5361 SEA WATER LIFT PUMP MOTOR |  | C | DKHB-0547 | MEL | DK50 | EL0024 |  | 2024-06-02
2024-W21-22 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307871 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M04 | 3KV N-SWB MAINT HBDC-N-1852-M04 | REL MANC NMAT PRC SETC | APPR RDBL | 2.5 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M04 | HBDB-PM-5361 SEA WATER LIFT PUMP MOTOR |  | C | DKHB-0547 | MEL | DK50 | EL0024 |  | 2024-06-03
2024-W21-22 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307871 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M04 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M04 | HBDB-PM-5361 SEA WATER LIFT PUMP MOTOR |  | C | DKHB-0547 | MEL | DK50 | EL0024 |  | 2024-06-05
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307872 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M05 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M05 | HBDB-PM-3651 OIL EXPORT PUMP MOTOR |  | C | DKHB-0552 | MEL | DK50 | EL0024 |  | 2024-05-19
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307872 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M05 | 3KV N-SWB MAINT HBDC-N-1852-M05 | REL MANC NMAT PRC SETC | APPR RDBL | 2.5 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M05 | HBDB-PM-3651 OIL EXPORT PUMP MOTOR |  | C | DKHB-0552 | MEL | DK50 | EL0024 |  | 2024-05-20
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307872 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M05 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M05 | HBDB-PM-3651 OIL EXPORT PUMP MOTOR |  | C | DKHB-0552 | MEL | DK50 | EL0024 |  | 2024-05-22
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307873 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M06 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M06 | HBDB-PM-3652 OIL EXPORT PUMP MOTOR |  | C | DKHB-0554 | MEL | DK50 | EL0024 |  | 2024-05-19
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307873 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M06 | 3KV N-SWB MAINT HBDC-N-1852-M06 | REL MANC NMAT PRC SETC | APPR RDBL | 2.5 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M06 | HBDB-PM-3652 OIL EXPORT PUMP MOTOR |  | C | DKHB-0554 | MEL | DK50 | EL0024 |  | 2024-05-20
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307873 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M06 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M06 | HBDB-PM-3652 OIL EXPORT PUMP MOTOR |  | C | DKHB-0554 | MEL | DK50 | EL0024 |  | 2024-05-22
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307874 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M07 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M07 | HBDC-TN-1856 INCOMER FROM TRANSFORMER |  | A | DKHB-0556 | MEL | DK50 | EL0024 |  | 2024-04-20
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307874 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M07 | 3KV N-SWB MAINT HBDC-N-1852-M07 | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M07 | HBDC-TN-1856 INCOMER FROM TRANSFORMER |  | A | DKHB-0556 | MEL | DK50 | EL0024 |  | 2024-04-21
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307874 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M07 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M07 | HBDC-TN-1856 INCOMER FROM TRANSFORMER |  | A | DKHB-0556 | MEL | DK50 | EL0024 |  | 2024-04-22
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307875 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M08 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M08 | M08 |  | A | DKHB-0557 | MEL | DK50 | EL0024 |  | 2024-06-02
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307875 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M08 | 3KV N-SWB MAINT HBDC-N-1852-M08 | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M08 | M08 |  | A | DKHB-0557 | MEL | DK50 | EL0024 |  | 2024-06-04
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307875 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M08 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M08 | M08 |  | A | DKHB-0557 | MEL | DK50 | EL0024 |  | 2024-06-06
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307876 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M09 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M09 | BUS TIE BREAKER |  | A | DKHB-0558 | MEL | DK50 | EL0024 |  | 2024-06-02
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307876 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M09 | 3KV N-SWB MAINT HBDC-N-1852-M09 | REL MANC NMAT PRC SETC | APPR RDBL | 2.5 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M09 | BUS TIE BREAKER |  | A | DKHB-0558 | MEL | DK50 | EL0024 |  | 2024-06-04
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307876 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M09 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M09 | BUS TIE BREAKER |  | A | DKHB-0558 | MEL | DK50 | EL0024 |  | 2024-06-06
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307878 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M11 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M11 | HBDC-TN-1857 INCOMER FROM TRANSFORMER |  | A | DKHB-0562 | MEL | DK50 | EL0024 |  | 2024-06-02
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307878 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M11 | 3KV N-SWB MAINT HBDC-N-1852-M11 | REL MANC NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M11 | HBDC-TN-1857 INCOMER FROM TRANSFORMER |  | A | DKHB-0562 | MEL | DK50 | EL0024 |  | 2024-06-04
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307878 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M11 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M11 | HBDC-TN-1857 INCOMER FROM TRANSFORMER |  | A | DKHB-0562 | MEL | DK50 | EL0024 |  | 2024-06-06
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307879 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M12 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M12 | OIL EXPORT PUMP MOTOR HBDB-PM-3653 |  | C | DKHB-0564 | MEL | DK50 | EL0024 |  | 2024-05-17
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307879 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M12 | 3KV N-SWB MAINT HBDC-N-1852-M12 | REL MANC NMAT PRC SETC | APPR RDBL | 2.5 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M12 | OIL EXPORT PUMP MOTOR HBDB-PM-3653 |  | C | DKHB-0564 | MEL | DK50 | EL0024 |  | 2024-05-18
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307879 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M12 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M12 | OIL EXPORT PUMP MOTOR HBDB-PM-3653 |  | C | DKHB-0564 | MEL | DK50 | EL0024 |  | 2024-05-20
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307880 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M13 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M13 | COOL MEDIUM CIRC PMP MOTOR HBDB-PM-5352 |  | C | DKHB-0566 | MEL | DK50 | EL0024 |  | 2024-05-17
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307880 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M13 | 3KV N-SWB MAINT HBDC-N-1852-M13 | REL MANC NMAT PRC SETC | APPR RDBL | 2.5 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M13 | COOL MEDIUM CIRC PMP MOTOR HBDB-PM-5352 |  | C | DKHB-0566 | MEL | DK50 | EL0024 |  | 2024-05-18
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307880 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M13 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M13 | COOL MEDIUM CIRC PMP MOTOR HBDB-PM-5352 |  | C | DKHB-0566 | MEL | DK50 | EL0024 |  | 2024-05-19
2024-W27-28 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307881 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M14 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M14 | SEAWATER LIFT PUMP MOTOR HBDB-PM-5362 |  | C | DKHB-0567 | MEL | DK50 | EL0024 |  | 2024-05-03
2024-W27-28 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307881 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M14 | 3KV N-SWB MAINT HBDC-N-1852-M14 | REL MANC NMAT PRC SETC | APPR RDBL | 2.5 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M14 | SEAWATER LIFT PUMP MOTOR HBDB-PM-5362 |  | C | DKHB-0567 | MEL | DK50 | EL0024 |  | 2024-05-05
2024-W27-28 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307881 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M14 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M14 | SEAWATER LIFT PUMP MOTOR HBDB-PM-5362 |  | C | DKHB-0567 | MEL | DK50 | EL0024 |  | 2024-05-06
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307882 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M15 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M15 | SPARE MOTOR FEEDER |  | A | DKHB-0568 | MEL | DK50 | EL0024 |  | 2024-06-02
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307882 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M15 | 3KV N-SWB MAINT HBDC-N-1852-M15 | REL MANC NMAT PRC SETC | APPR RDBL | 1.5 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M15 | SPARE MOTOR FEEDER |  | A | DKHB-0568 | MEL | DK50 | EL0024 |  | 2024-06-03
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307882 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M15 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M15 | SPARE MOTOR FEEDER |  | A | DKHB-0568 | MEL | DK50 | EL0024 |  | 2024-06-05
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307883 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M16 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M16 | SPARE MOTOR FEEDER |  | A | DKHB-0569 | MEL | DK50 | EL0024 |  | 2024-05-16
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307883 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M16 | 3KV N-SWB MAINT HBDC-N-1852-M16 | REL MANC NMAT PRC SETC | APPR RDBL | 1.5 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M16 | SPARE MOTOR FEEDER |  | A | DKHB-0569 | MEL | DK50 | EL0024 |  | 2024-05-17
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307883 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M16 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M16 | SPARE MOTOR FEEDER |  | A | DKHB-0569 | MEL | DK50 | EL0024 |  | 2024-05-18
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307884 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M17 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M17 | FEEDER TO HCA VIA HBBA-JBP-75001 |  | A | DKHB-0570 | MEL | DK50 | EL0024 |  | 2024-05-16
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307884 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M17 | 3KV N-SWB MAINT HBDC-N-1852-M17 | REL MANC NMAT PRC SETC | APPR RDBL | 1.5 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M17 | FEEDER TO HCA VIA HBBA-JBP-75001 |  | A | DKHB-0570 | MEL | DK50 | EL0024 |  | 2024-05-17
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307884 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M17 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M17 | FEEDER TO HCA VIA HBBA-JBP-75001 |  | A | DKHB-0570 | MEL | DK50 | EL0024 |  | 2024-05-18
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308259 | 3M TEMP ELEC INSTALLATIONS CHECK - HD | TEMP ELEC INSTALLATIONS CHECK - HD | REL MANC NMAT PRC SETC | APPR RDBL | 3 | 0 | W19-W20 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-02-01 | 2024-01-21 | 10 | REL | APPR OPND | HD /A /84/TI | Temporary installation |  | A | DKHD-2050 | MEL | DK60 | EL0043 | PROK
0 | C | NOSD | WPM | MTN-INST | MTN-INST | 2400308627 | 6M WATER AND H2S ANALYSERS CALIBRATION | WATER AND H2S ANALYSERS CALIBRATION | REL MANC NMAT PRC SETC | APPR RDBL | 6 | 0 | W09-W10 | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-03-16 | 2024-02-26 | 10 | REL | APPR OPND | HD /A /34/INSTRUMENTS | INSTRUMENTS |  | F | DKHD-0353 | MIN | DK60 | IN0063
2026-W13-14 | D | NOSD | WPM | PRODLABO | PRODLABO | 2400309376 | 3M SAMPLING OF OiW CORRELATIONS | SAMPLING OF OiW CORRELATIONS | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-29 | 2024-03-14 | 10 | REL | APPR OPND | HB /D /80 | LABORATORY |  | A | DK600008681 | PRD | DK50
0 | C | NOSD | WPM | PRODLABO | PRODLABO | 2400315098 | 2M GAS SAMPLE FOR CO2 EMISSION HDA | GAS SAMPLE FOR CO2 EMISSION HDA | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-04-02 | 2024-04-02 | 2024-04-02 | 2024-04-13 | 2024-04-02 | 10 | REL | APPR OPND | HD /A /80 | LABORATORY |  | A | DK600003571 | PRD | DK60
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316102 | 3M TEMP ELEC INSTALLATIONS CHECK - HD | TEMP ELEC INSTALLATIONS CHECK - HD | REL NMAT PRC SETC | APPR RDBL | 3 | 0 | 24-W21-22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-01 | 2024-04-20 | 10 | REL | APPR OPND | HD /A /84/TI | Temporary installation |  | A | DKHD-2050 | MEL | DK60 | EL0043
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400321296 | 2Y 400V E-DP INSP EMG. LIGHT HBC | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-04-22 | 2024-04-25 | 2024-04-22 | 2024-05-07 | 2024-03-22 | 10 | REL | APPR OPND | HB /C /05/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHB-0411 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321296 | 2Y 400V E-DP INSP EMG. LIGHT HBC | 400V E-DP INSP EMG. LIGHT HBC | REL NMAT PRC SETC | APPR RDBL | 16 | 0 |  | 2024-04-22 | 2024-04-25 | 2024-04-22 | 2024-05-07 | 2024-03-22 | 20 | REL | APPR OPND | HB /C /05/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHB-0411 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321296 | 2Y 400V E-DP INSP EMG. LIGHT HBC | 400V E-DP INSP EMG. LIGHT HBC | REL NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-04-22 | 2024-04-25 | 2024-04-23 | 2024-05-07 | 2024-03-22 | 30 | REL | APPR OPND | HB /C /05/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHB-0411 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400321296 | 2Y 400V E-DP INSP EMG. LIGHT HBC | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-04-22 | 2024-04-25 | 2024-04-24 | 2024-05-07 | 2024-03-22 | 40 | REL | APPR OPND | HB /C /05/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHB-0411 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321312 | 2Y 400V N-DP MAINT HBC SMALL POWER | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2024-03-13 | 2024-03-17 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | C | DKHB-0629 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321312 | 2Y 400V N-DP MAINT HBC SMALL POWER | 400V N-DP MAINT HBC SMALL POWER | REL NMAT PRC SETC | APPR RDBL | 20 | 0 |  | 2024-03-13 | 2024-03-17 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | C | DKHB-0629 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321312 | 2Y 400V N-DP MAINT HBC SMALL POWER | 400V N-DP MAINT HBC SMALL POWER | REL NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2024-03-13 | 2024-03-17 | 2024-03-15 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | C | DKHB-0629 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321312 | 2Y 400V N-DP MAINT HBC SMALL POWER | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR RDBL | 5 | 0 |  | 2024-03-13 | 2024-03-17 | 2024-03-16 | 2024-05-07 | 2024-03-13 | 40 | REL | APPR OPND | HB /C /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | C | DKHB-0629 | MEL | DK50 | EL0024
2024-W17-18 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400322688 | 6M H2S SCV INJ PUMP MAINT HBDB-P-3461/2 | H2S SCV INJ PUMP MAINT HBDB-P-3461/2 | REL NMAT PRC SETC | APPR RDBL | 2 | 0 | W17-W18 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-22 | 2024-05-03 | 10 | REL | APPR OPND | HB /D /27/HBDB-P-3461 | SPENT H2S SCAV INJ PUMP - HP |  | A | DKHB-0066 | MMS | DK50 | MR0044 |  | 2024-04-22
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322712 | 3M TEMP ELEC INSTALLATIONS CHECK - HBC | TEMP ELEC INSTALLATIONS CHECK - HBC | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-05-07 | 2024-05-08 | 2024-05-07 | 2024-05-18 | 2024-05-07 | 10 | REL | APPR OPND | HB /C /84/TI | Temporary installation |  | A | DKHB-2040 | MEL | DK50 | EL0044 | PROK | 2024-05-15
2024-W15-16 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325794 | 3M SURFACE CONT PNL MAINT-HBBA-A-3103 | SURFACE CONT PNL MAINT-HBBA-A-3103 | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-05-28 | 2024-05-17 | 10 | REL | APPR OPND | HB /B /07/HBBA-A-3103 | HYDRAULIC PANEL |  | C | DKHB-0101 | MMS | DK50 | MS0064 |  | 2024-04-12
2026-W13-14 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400328745 | 1Y CHEM DIST PNL MAINT-HBBA-A-39570/80 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR RDBL | 1 | 0 | W17-W18 | 2024-05-03 | 2024-05-04 | 2024-05-03 | 2024-06-08 | 2024-05-03 | 10 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C | DKHB-0151 | MMS | DK50 | MS0114
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-INST | 2400328745 | 1Y CHEM DIST PNL MAINT-HBBA-A-39570/80 | CHEM DIST PNL MAINT-HBBA-A-39570/80 | REL NMAT PRC SETC | APPR RDBL | 8 | 0 | W17-W18 | 2024-05-03 | 2024-05-04 | 2024-05-03 | 2024-06-08 | 2024-05-03 | 20 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C | DKHB-0151 | MMS | DK50 | MS0114
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400328745 | 1Y CHEM DIST PNL MAINT-HBBA-A-39570/80 | CHEM DIST PNL MAINT-HBBA-A-39570/80 | REL NMAT PRC SETC | APPR RDBL | 2 | 0 | W17-W18 | 2024-05-03 | 2024-05-04 | 2024-05-04 | 2024-06-08 | 2024-05-03 | 30 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C | DKHB-0151 | MMS | DK50 | MS0114
2026-W13-14 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400328745 | 1Y CHEM DIST PNL MAINT-HBBA-A-39570/80 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR RDBL | 1 | 0 | W17-W18 | 2024-05-03 | 2024-05-04 | 2024-05-04 | 2024-06-08 | 2024-05-03 | 40 | REL | APPR OPND | HB /B /75/HBBA-A-39570 | CHEMICAL DISTRIBUTION PANEL |  | C | DKHB-0151 | MMS | DK50 | MS0114
0 | C | NOSD | WPM | PRODLABO | PRODLABO | 2400329445 | 2M GAS SAMPLE FOR CO2 EMISSION HDA | GAS SAMPLE FOR CO2 EMISSION HDA | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-13 | 2024-06-02 | 10 | REL | APPR OPND | HD /A /80 | LABORATORY |  | A | DK600003571 | PRD | DK60
2024-W15-16 | C | NOSD | WPM | MTN-TELE | MTN-TELE | 2400329564 | 1Y DOWNHOLE GAUGE SYSTEM MAINT - HBB | DOWNHOLE GAUGE SYSTEM MAINT - HBB | REL NMAT PRC SETC | APPR RDBL | 6 | 0 |  | 2024-05-12 | 2024-05-13 | 2024-05-12 | 2024-06-17 | 2024-05-12 | 10 | REL | APPR OPND | HB /B /10/CONTROL-PANELS | CONTROL PANELS |  | C | DKHB-0225 | MIN | DK50 | IN0084 |  | 2024-04-16
0 | D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400329585 | 1Y L-AUS TOOLS HDA/B/C | 1Y L-AUS TOOLS MAINTENANCE CHECK | REL NMAT PRC SETC | APPR RDBL | 3 | 0 |  | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-06-22 | 2024-05-06 | 10 | REL | APPR OPND | HD /B /05/EMERGENCY-POWER-GENERATORS | EMERGENCY-GENERATOR |  | A | DKHD-2035 | MEL | DK60 | EL0043 | PROK
2026-W13-14 | D | NOSD | WPM | PRODLABO | PRODLABO | 2400329956 | 3M SAMPLING OF OiW CORRELATIONS | SAMPLING OF OiW CORRELATIONS | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | 2024-06-29 | 2024-06-14 | 10 | REL | APPR OPND | HB /D /80 | LABORATORY |  | A | DK600008681 | PRD | DK50
2026-W13-14 | B | NOSD | WPM | MTN-MECH | PRODTECH | 2400333185 | 6M WELLHEAD HPU & CONT PNL MAINT-HBBB | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-06-15 | 2024-06-16 | 2024-06-15 | 2024-07-01 | 2024-06-15 | 10 | REL | APPR OPND | HB /B /07/HBBB-FP-5940 | HYDRAULIC POWER PANEL |  | C | DKHB-0104 | MMS | DK50 | MS0064
2026-W13-14 | B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400333185 | 6M WELLHEAD HPU & CONT PNL MAINT-HBBB | WELLHEAD HPU & CONT PNL MAINT-HBBB | REL NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2024-06-15 | 2024-06-16 | 2024-06-15 | 2024-07-01 | 2024-06-15 | 20 | REL | APPR OPND | HB /B /07/HBBB-FP-5940 | HYDRAULIC POWER PANEL |  | C | DKHB-0104 | MMS | DK50 | MS0064
2026-W13-14 | B | NOSD | WPM | MTN-MECH | PRODTECH | 2400333185 | 6M WELLHEAD HPU & CONT PNL MAINT-HBBB | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-06-15 | 2024-06-16 | 2024-06-16 | 2024-07-01 | 2024-06-15 | 30 | REL | APPR OPND | HB /B /07/HBBB-FP-5940 | HYDRAULIC POWER PANEL |  | C | DKHB-0104 | MMS | DK50 | MS0064
2024-W15-16 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400333190 | 6M PURGE WATER UNIT CLEAN-HBDD-A-1061 | PURGE WATER UNIT CHECK-HBDD-A-1061 | REL NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2024-07-01 | 2024-06-12 | 10 | REL | APPR OPND | HB /D /77/HBDD-A-1061 | MIXED BED COLUMN |  | C | DKHB-0674 | MMS | DK50 | MS0024 |  | 2024-04-10
2024-W15-16 | B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334356 | 3M ACCOM SPRINKLR SKID TEST-HBCR-A-0337 | ACCOM SPRINKLR SKID TEST-HBCR-A-0337 | REL NMAT PRC SETC | APPR RDBL | 4 | 0 |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2024-07-12 | 2024-07-02 | 10 | REL | APPR OPND | HB /C /01/HBCR-A-0337 | ACCOMODATION MODULE SPRINKLER SKID |  | A | DKHB-0069 | MMS | DK50 | MS0014 |  | 2024-04-10
2026-W13-14 | B | NOSD | WPM | MTN-MECH | PRODTECH | 2400334580 | 3M WELLHEAD HPU & CONT PNL MAINT-HBAA | ISOLATION BY PRODUCTION | REL PRT NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-07-18 | 2024-07-08 | 10 | REL | APPR OPND | HB /A /07/HBAA-A-5911 | HYDRAULIC POWER PACK |  | C | DKHB-0048 | MMS | DK50 | MS0064
2026-W13-14 | B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334580 | 3M WELLHEAD HPU & CONT PNL MAINT-HBAA | WELLHEAD HPU & CONT PNL MAINT-HBAA | REL PRT NMAT PRC SETC | APPR RDBL | 2 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-07-18 | 2024-07-08 | 20 | REL | APPR OPND | HB /A /07/HBAA-A-5911 | HYDRAULIC POWER PACK |  | C | DKHB-0048 | MMS | DK50 | MS0064
2026-W13-14 | B | NOSD | WPM | MTN-MECH | PRODTECH | 2400334580 | 3M WELLHEAD HPU & CONT PNL MAINT-HBAA | DE-ISOLATION BY PRODUCTION | REL PRT NMAT PRC SETC | APPR RDBL | 1 | 0 |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-07-18 | 2024-07-08 | 30 | REL | APPR OPND | HB /A /07/HBAA-A-5911 | HYDRAULIC POWER PACK |  | C | DKHB-0048 | MMS | DK50 | MS0064
2026-W13-14 | 3 |  | WSO | WELLMAIN | WELLMAIN | 2900001206 | HBB09, MFC survey, Program 19757 | HBB09, MFC survey, Program 19757 | REL MACM PRC SETC | APPR RDBL | 0 | 0 |  | 2024-01-15 | 2024-02-12 | 2024-01-15 | 2024-05-29 | 2024-01-15 | 10 | REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | PRODTECH | 2900001206 | HBB09, MFC survey, Program 19757 | Safing well/well handover (production) | REL MACM PRC SETC | APPR RDBL | 12 | 0 |  | 2024-01-15 | 2024-02-12 | 2024-01-15 | 2024-05-29 | 2024-01-15 | 20 | REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | MTN-ROUS | 2900001206 | HBB09, MFC survey, Program 19757 | Crane assist during WL R/U and RD | REL MACM PRC SETC | APPR RDBL | 48 | 0 |  | 2024-01-15 | 2024-02-12 | 2024-01-18 | 2024-05-29 | 2024-01-15 | 30 | REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | MTN-SCAF | 2900001206 | HBB09, MFC survey, Program 19757 | Scaffolder assistance for RU and RD | REL MACM PRC SETC | APPR RDBL | 48 | 0 |  | 2024-01-15 | 2024-02-12 | 2024-01-24 | 2024-05-29 | 2024-01-15 | 40 | REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | MTN-ELEC | 2900001206 | HBB09, MFC survey, Program 19757 | Electrician assistance for RU and RD | REL MACM PRC SETC | APPR RDBL | 12 | 0 |  | 2024-01-15 | 2024-02-12 | 2024-01-29 | 2024-05-29 | 2024-01-15 | 50 | REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | MTN-TELE | 2900001206 | HBB09, MFC survey, Program 19757 | Tele assist during WL RRU and RD | REL MACM PRC SETC | APPR RDBL | 24 | 0 |  | 2024-01-15 | 2024-02-12 | 2024-01-31 | 2024-05-29 | 2024-01-15 | 60 | REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLMAIN | VEN-CRAN | 2900001206 | HBB09, MFC survey, Program 19757 | Crane support assitance for days | REL MACM PRC SETC | APPR RDBL | 72 | 0 |  | 2024-01-15 | 2024-02-12 | 2024-02-05 | 2024-05-29 | 2024-01-15 | 70 | REL | APPR OPND | HB /B | HALFDAN BB |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | WELLSUPV | 2900001250 | HBB02 UMV repair/SIS job 19766 | HBB02 UMV repair/SIS job 19766 | REL PCNF NMAT PRC SETC | APPR RDBL | 0 | 0 |  | 2024-01-08 | 2024-01-25 | 2024-01-08 | 2024-02-22 | 2024-01-08 | 10 | PCNF REL | APPR OPND | HB /B /55/HBB02-WATER-INJECTION-WELLHEAD | HBB-02 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | MTN-RIGG | 2900001250 | HBB02 UMV repair/SIS job 19766 | Rigger Assistance for WHM | REL PCNF NMAT PRC SETC | APPR RDBL | 50 | 26 |  | 2024-01-08 | 2024-01-25 | 2024-01-08 | 2024-02-22 | 2024-01-08 | 20 | PCNF REL | APPR OPND | HB /B /55/HBB02-WATER-INJECTION-WELLHEAD | HBB-02 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | MTN-SCAF | 2900001250 | HBB02 UMV repair/SIS job 19766 | Scaff assistance for WHM | REL PCNF NMAT PRC SETC | APPR RDBL | 50 | 45 |  | 2024-01-08 | 2024-01-25 | 2024-01-16 | 2024-02-22 | 2024-01-08 | 30 | PCNF REL | APPR OPND | HB /B /55/HBB02-WATER-INJECTION-WELLHEAD | HBB-02 WATER INJECTION WELLHEAD |  | A |  | WLD | DK50
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001253 | HDA06, WL, MFC, CA19784 | HDA06, WL, MFC, CA19784 | REL PCNF MACM PRC SETC | APPR RDBL | 0 | 0 |  | 2024-02-24 | 2024-04-10 | 2024-02-24 | 2024-07-08 | 2024-02-24 | 10 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | PRODTECH | 2900001253 | HDA06, WL, MFC, CA19784 | Safing well/well handover (production) | REL PCNF MACM PRC SETC | APPR RDBL | 12 | 0 |  | 2024-02-24 | 2024-04-10 | 2024-02-24 | 2024-07-08 | 2024-02-24 | 20 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-ROUS | 2900001253 | HDA06, WL, MFC, CA19784 | Crane assist during WL R/U and RD | REL PCNF MACM PRC SETC | APPR RDBL | 48 | 0 |  | 2024-02-24 | 2024-04-10 | 2024-02-27 | 2024-07-08 | 2024-02-24 | 30 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-SCAF | 2900001253 | HDA06, WL, MFC, CA19784 | Scaffolder assistance for RU and RD | REL PCNF MACM PRC SETC | APPR RDBL | 50 | 30 |  | 2024-02-24 | 2024-04-10 | 2024-03-04 | 2024-07-08 | 2024-02-24 | 40 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-ELEC | 2900001253 | HDA06, WL, MFC, CA19784 | Electrician assistance for RU and RD | REL PCNF MACM PRC SETC | APPR RDBL | 12 | 0 |  | 2024-02-24 | 2024-04-10 | 2024-03-09 | 2024-07-08 | 2024-02-24 | 50 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-TELE | 2900001253 | HDA06, WL, MFC, CA19784 | Tele assist during WL RRU and RD | REL PCNF MACM PRC SETC | APPR RDBL | 24 | 0 |  | 2024-02-24 | 2024-04-10 | 2024-03-11 | 2024-07-08 | 2024-02-24 | 60 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | VEN-CRAN | 2900001253 | HDA06, WL, MFC, CA19784 | Crane support assitance for days/nights | REL PCNF MACM PRC SETC | APPR RDBL | 240 | 0 |  | 2024-02-24 | 2024-04-10 | 2024-03-16 | 2024-07-08 | 2024-02-24 | 70 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001253 | HDA06, WL, MFC, CA19784 | Oilenco tools | REL PCNF MACM PRC SETC | APPR RDBL | 0 | 0 |  | 2024-02-24 | 2024-04-10 | 2024-04-10 | 2024-07-08 | 2024-02-24 | 80 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001253 | HDA06, WL, MFC, CA19784 | Maersk H2S | REL PCNF MACM PRC SETC | APPR RDBL | 0 | 0 |  | 2024-02-24 | 2024-04-10 | 2024-04-10 | 2024-07-08 | 2024-02-24 | 90 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
2024-W37-38 | 1 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077662 | Manuel release on deluge valve leaking | Recieved mats on stock | REL PCNF PRT GMPS MANC PRC SETC | APPR PROK SMAT RDBL | 1 | 0 | W37-38 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-11-25 | 2022-11-10 | 40 | REL | APPR OPND | HB /D /01/HBDB-XCV-038051 | DELUGE VALVE |  | B |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300000845 | C85 H2S Analyser Manglende Trend Sensor | C85 H2S Analyser Manglende Trend Sensor | REL MANC NMAT PRC SETC | APPR PROK SCH RDBL | 4 | 0 | W43-44 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2016-10-31 | 2016-08-02 | 10 | REL | APPR OPND | HB /D /04/HBDC-CP-2050 | SCADA CONTROLLER CABINET |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300001126 | C05 NO HBA Biocide m3 til Liter ændring | C05 HBA Biocide m3 til Liter ændring | REL MANC NMAT PRC SETC | APPR PROK SCH RDBL | 3 | 0 | W49-50 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2016-12-04 | 2016-09-05 | 10 | REL | APPR OPND | HB /A /04/HBAA-FP-2020 | SCADA PANEL |  | A |  | MIN | DK50
2026-W1-2 | 3 | NE | WRO | MTN-TELE | CON-VEN | 2300007835 | Halfdan B HMI lifet. ext. Siemens survey | Halfdan B HMI lifet. ext. Siemens survey | REL PRT NMAT PRC SETC | APPR PROK SCH RDBL | 84 | 0 | W13-W14 | 2024-04-01 | 2024-04-16 | 2024-04-01 | 2024-08-03 | 2024-03-21 | 10 | REL | APPR OPND | HB /D /04/HBDC-CP-2051A | SCADA SERVER CABINET 1 |  | A |  | MIN | DK50
2026-W1-2 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300007835 | Halfdan B HMI lifet. ext. Siemens survey | Telecom Assistance | REL PRT NMAT PRC SETC | APPR PROK SCH RDBL | 24 | 0 | W13-W14 | 2024-04-01 | 2024-04-16 | 2024-04-10 | 2024-08-03 | 2024-03-21 | 20 | REL | APPR OPND | HB /D /04/HBDC-CP-2051A | SCADA SERVER CABINET 1 |  | A |  | MIN | DK50
2026-W1-2 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300007835 | Halfdan B HMI lifet. ext. Siemens survey | Instrument supervisor assistance | REL PRT NMAT PRC SETC | APPR PROK SCH RDBL | 6 | 0 | W13-W14 | 2024-04-01 | 2024-04-16 | 2024-04-15 | 2024-08-03 | 2024-03-21 | 30 | REL | APPR OPND | HB /D /04/HBDC-CP-2051A | SCADA SERVER CABINET 1 |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100024826 | SMAT:HPFI trips and stay f circuit no01 | Remount isolation on heattracing cable | REL PCNF CSER MANC PRC SETC | APPR PROK RDBL | 5 | 3 | LAST TASK | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2018-10-27 | 2018-10-07 | 50 | PCNF REL | APPR OPND | HB /D /61/HBDB-DP-1872 | HEAT TRACING DISTRIBUTION BOARD |  | C |  | MEL | DK50
0 | 3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300001128 | F33 HDBD_PDT_01251 Alarm HH | F33 HDBD_PDT_01251 Alarm HH | REL MANC NMAT PRC SETC | APPR PROK RDBL | 4 | 0 | Siemans scopes | 2025-01-24 | 2025-01-24 | 2025-01-24 |  | 2017-03-27 | 10 | REL | APPR OPND | HD /B /03/HDBE-CPF-0101A | F&G CONTROLLER NODE F 33 |  | A |  | MIN | DK60
2026-W13-14 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026243 | Hyd weep on 1" supply to HBB-FP-5943 to | L3 build scaff | REL MANC NMAT PRC SETC | APPR PROK AWSC RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2019-06-11 | 2019-05-02 | 10 | REL | APPR OPND | HB /B /07/HBBB-FP-5943 | VALVE CONTROL PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBBPWELL | WDF | MTN-MECH | PRODTECH | 2100026243 | Hyd weep on 1" supply to HBB-FP-5943 to | L3 Safe and depressure | REL MANC NMAT PRC SETC | APPR PROK AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2019-06-11 | 2019-05-02 | 15 | REL | APPR OPND | HB /B /07/HBBB-FP-5943 | VALVE CONTROL PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-MECH | 2100026243 | Hyd weep on 1" supply to HBB-FP-5943 to | L3 retighten or change fitting | REL MANC NMAT PRC SETC | APPR PROK AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2019-06-11 | 2019-05-02 | 20 | REL | APPR OPND | HB /B /07/HBBB-FP-5943 | VALVE CONTROL PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-MECH | 2100026243 | Hyd weep on 1" supply to HBB-FP-5943 to | L3 Test and clean after completed work | REL MANC NMAT PRC SETC | APPR PROK AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2019-06-11 | 2019-05-02 | 30 | REL | APPR OPND | HB /B /07/HBBB-FP-5943 | VALVE CONTROL PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026243 | Hyd weep on 1" supply to HBB-FP-5943 to | L3 remove scaff | REL MANC NMAT PRC SETC | APPR PROK AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2019-06-11 | 2019-05-02 | 40 | REL | APPR OPND | HB /B /07/HBBB-FP-5943 | VALVE CONTROL PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBBPWELL | WDF | MTN-MECH | PRODTECH | 2100026243 | Hyd weep on 1" supply to HBB-FP-5943 to | L3 Desafe | REL MANC NMAT PRC SETC | APPR PROK AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2019-06-11 | 2019-05-02 | 50 | REL | APPR OPND | HB /B /07/HBBB-FP-5943 | VALVE CONTROL PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBFUELG | WGN | MTN-MECH | MTN-MECH | 2200003208 | SMAT:Cavity Bleed replacement to Plug HB | Cavity Bleed replacement to Plug | REL MANC PRC SETC | APPR PROK AWSC RDBL | 0 | 0 | Martin | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 10 | REL | APPR OPND | HB /D /34/HBDC-HCV-290002-U | HCV UPSTREAM PSV-290002 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBFUELG | WGN | MTN-MECH | MTN-MECH | 2200003208 | SMAT:Cavity Bleed replacement to Plug HB | Mat are available and checked through | REL MANC PRC SETC | APPR PROK AWSC RDBL | 2 | 0 | Martin | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 20 | REL | APPR OPND | HB /D /34/HBDC-HCV-290002-U | HCV UPSTREAM PSV-290002 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBFUELG | WGN | MTN-MECH | PRODTECH | 2200003208 | SMAT:Cavity Bleed replacement to Plug HB | Safing. | REL MANC PRC SETC | APPR PROK AWSC RDBL | 2 | 0 | Prod. | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 30 | REL | APPR OPND | HB /D /34/HBDC-HCV-290002-U | HCV UPSTREAM PSV-290002 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBFUELG | WGN | MTN-MECH | MTN-MECH | 2200003208 | SMAT:Cavity Bleed replacement to Plug HB | Cavity Bleed replacement to Plugs | REL MANC PRC SETC | APPR PROK AWSC RDBL | 4 | 0 | Martin | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 40 | REL | APPR OPND | HB /D /34/HBDC-HCV-290002-U | HCV UPSTREAM PSV-290002 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBFUELG | WGN | MTN-MECH | PRODTECH | 2200003208 | SMAT:Cavity Bleed replacement to Plug HB | Desafing/leaktest | REL MANC PRC SETC | APPR PROK AWSC RDBL | 2 | 0 | Prod. | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2018-04-12 | 2018-01-12 | 50 | REL | APPR OPND | HB /D /34/HBDC-HCV-290002-U | HCV UPSTREAM PSV-290002 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB-DANLP | WGN | MTN-MECH | MTN-MECH | 2200003258 | SMAT:HBB Cavity Bleed REPLment to Plug | Cavity Bleed replacement to Plug | REL MANC PRC SETC | APPR PROK AWSC RDBL | 0 | 0 | rev. code | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 10 | REL | APPR OPND | HB /B /34/HBBA-HCV-430001 | HAND CONTROL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HB-DANLP | WGN | MTN-MECH | MTN-MECH | 2200003258 | SMAT:HBB Cavity Bleed REPLment to Plug | Mat are available and checked through | REL MANC PRC SETC | APPR PROK AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 20 | REL | APPR OPND | HB /B /34/HBBA-HCV-430001 | HAND CONTROL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HB-DANLP | WGN | MTN-MECH | PRODTECH | 2200003258 | SMAT:HBB Cavity Bleed REPLment to Plug | Safing. | REL MANC PRC SETC | APPR PROK AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 30 | REL | APPR OPND | HB /B /34/HBBA-HCV-430001 | HAND CONTROL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HB-DANLP | WGN | MTN-MECH | MTN-MECH | 2200003258 | SMAT:HBB Cavity Bleed REPLment to Plug | Cavity Bleed replacement to Plugs | REL MANC PRC SETC | APPR PROK AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 40 | REL | APPR OPND | HB /B /34/HBBA-HCV-430001 | HAND CONTROL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HB-DANLP | WGN | MTN-MECH | PRODTECH | 2200003258 | SMAT:HBB Cavity Bleed REPLment to Plug | Desafing/leaktest | REL MANC PRC SETC | APPR PROK AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2018-04-12 | 2018-01-12 | 50 | REL | APPR OPND | HB /B /34/HBBA-HCV-430001 | HAND CONTROL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HB-DANLP | WGN | MTN-TURB | MTN-MECH | 2200003259 | SMAT:NO HBB Cavity Bleed REPLment to Pl | Cavity Bleed replacement to Plug | REL MANC PRC SETC | APPR PROK AWSC RDBL | 0 | 0 | REV CODE! | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 10 | REL | APPR OPND | HB /B /34/HBBA-HCV-430000 | HAND CONTROL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HB-DANLP | WGN | MTN-TURB | MTN-MECH | 2200003259 | SMAT:NO HBB Cavity Bleed REPLment to Pl | Mat are available and checked through | REL MANC PRC SETC | APPR PROK AWSC RDBL | 2 | 0 | DFG-IPHP SD25-09 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 20 | REL | APPR OPND | HB /B /34/HBBA-HCV-430000 | HAND CONTROL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HB-DANLP | WGN | MTN-TURB | PRODTECH | 2200003259 | SMAT:NO HBB Cavity Bleed REPLment to Pl | Safing. | REL MANC PRC SETC | APPR PROK AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 30 | REL | APPR OPND | HB /B /34/HBBA-HCV-430000 | HAND CONTROL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HB-DANLP | WGN | MTN-TURB | MTN-MECH | 2200003259 | SMAT:NO HBB Cavity Bleed REPLment to Pl | Cavity Bleed replacement to Plugs | REL MANC PRC SETC | APPR PROK AWSC RDBL | 4 | 0 | Niels Chr. | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 40 | REL | APPR OPND | HB /B /34/HBBA-HCV-430000 | HAND CONTROL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HB-DANLP | WGN | MTN-TURB | PRODTECH | 2200003259 | SMAT:NO HBB Cavity Bleed REPLment to Pl | Desafing/leaktest | REL MANC PRC SETC | APPR PROK AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2018-04-12 | 2018-01-12 | 50 | REL | APPR OPND | HB /B /34/HBBA-HCV-430000 | HAND CONTROL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HB-DANLP | WGN | MTN-TURB | MTN-MECH | 2200003259 | SMAT:NO HBB Cavity Bleed REPLment to Pl | NO HBB Cavity Bleed replacement to Pl | REL MANC PRC SETC | APPR PROK AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2018-04-12 | 2018-01-12 | 60 | REL | APPR OPND | HB /B /34/HBBA-HCV-430000 | HAND CONTROL VALVE | 99000119 | D |  | MMS | DK50
0 | 3 | HB-FLARE | WRO | MTN-TELE | VEN-ELEC | 2300001590 | HBX F&G nodes - Secway punch implement | HBX F&G nodes - Secway punch implement | REL PRT MANC NMAT PRC SETC | APPR PROK AWSC RDBL | 12 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2020-09-03 | 2020-06-05 | 10 | REL | APPR OPND | HD /A /03 | ESD AND FIRE & GAS |  | A |  | MIN | DK60
0 | 3 | HB-FLARE | WRO | MTN-TELE | MTN-TELE | 2300001590 | HBX F&G nodes - Secway punch implement | Telecom Assistance | REL PRT MANC NMAT PRC SETC | APPR PROK AWSC RDBL | 5 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2020-09-03 | 2020-06-05 | 20 | REL | APPR OPND | HD /A /03 | ESD AND FIRE & GAS |  | A |  | MIN | DK60
0 | 3 | HB-FLARE | WRO | MTN-INST | VEN-ELEC | 2300001589 | HBX ESD nodes - Secway punch implement | HBX ESD nodes - Secway punch implement | REL PCNF PRT MANC NMAT PRC SETC | APPR PROK AWSC | 12 | 4 |  | 2024-08-18 | 2024-08-18 | 2024-08-18 | 2020-09-03 | 2020-06-05 | 10 | PCNF REL | APPR OPND | HD /A /03/ESD-SYSTEM | ESD SYSTEM |  | A |  | MIN | DK60
0 | 3 | HB-FLARE | WRO | MTN-INST | MTN-INST | 2300001589 | HBX ESD nodes - Secway punch implement | Telecom Assistance | REL PCNF PRT MANC NMAT PRC SETC | APPR PROK AWSC | 5 | 2 |  | 2024-08-18 | 2024-08-18 | 2024-08-18 | 2020-09-03 | 2020-06-05 | 20 | PCNF REL | APPR OPND | HD /A /03/ESD-SYSTEM | ESD SYSTEM |  | A |  | MIN | DK60
2026-W13-14 | 4 | NOSD | WDF | MTN-SCAF | MTN-SCAF | 2100025893 | HBD Removel of handrails and Hatch Scaff | HDB Removel of handrails and Hatch Scaff | REL MANC NMAT PRC SETC | APPR PROK AWDO RDBL ROUT | 40.2 | 0 |  | 2024-01-09 | 2024-01-13 | 2024-01-09 | 2021-06-02 | 2019-06-13 | 10 | REL | APPR OPND | HB /A /11/HBAB-PSV-34069 | PRESSURE SAFETY VALVE |  | A |  | MMS | DK50
2025-W1-2 | 3 | HB-FLARE | WDF | MTN-TELE | MTN-TELE | 2100025866 | LOTI:Faultfinding Power redundancy to HB | Change out of Diode | REL PCNF PRT MANC PRC SETC | APPR PROK AWDO AWSC RDBL ROUT | 2 | 0 | LOTI | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-02-16 | 2019-01-27 | 30 | REL | APPR OPND | HB /A /03/HBAB-FP-0201O | Exd RIO FIELD PANEL | 99000119 | F |  | MIN | DK50
2026-W1-2 | 3 | HBBWIWEL | WDF | MTN-MECH | PRODTECH | 2100026237 | HBBB-HCV-350201 New valve | Isolate HBBB-HCV-350201 | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RFRZ | 3 | 0 |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2019-01-27 | 2018-08-30 | 40 | REL | APPR OPND | HB /B /55/HBBB-HCV-350201 | HAND CONTROL VALVE. | 99000119 | C |  | MMS | DK50
2026-W1-2 | 3 | HBBWIWEL | WDF | MTN-MECH | MTN-RIGG | 2100026237 | HBBB-HCV-350201 New valve | Arrange rigging equipment / Rig choke | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RFRZ | 4 | 0 |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2019-01-27 | 2018-08-30 | 50 | REL | APPR OPND | HB /B /55/HBBB-HCV-350201 | HAND CONTROL VALVE. | 99000119 | C |  | MMS | DK50
2026-W1-2 | 3 | HBBWIWEL | WDF | MTN-MECH | MTN-MECH | 2100026237 | HBBB-HCV-350201 New valve | Maintenance replace HBBB-HCV-350201 | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RFRZ | 4 | 0 |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2019-01-27 | 2018-08-30 | 60 | REL | APPR OPND | HB /B /55/HBBB-HCV-350201 | HAND CONTROL VALVE. | 99000119 | C |  | MMS | DK50
2026-W1-2 | 3 | HBBWIWEL | WDF | MTN-MECH | PRODTECH | 2100026237 | HBBB-HCV-350201 New valve | De-isolate/test HBBB-HCV-350201 | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RFRZ | 3 | 0 |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2019-01-27 | 2018-08-30 | 70 | REL | APPR OPND | HB /B /55/HBBB-HCV-350201 | HAND CONTROL VALVE. | 99000119 | C |  | MMS | DK50
2026-W1-2 | 3 | HBBWIWEL | WDF | MTN-MECH | MTN-RIGG | 2100026237 | HBBB-HCV-350201 New valve | remove rigger equipment | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RFRZ | 3 | 0 |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2019-01-27 | 2018-08-30 | 80 | REL | APPR OPND | HB /B /55/HBBB-HCV-350201 | HAND CONTROL VALVE. | 99000119 | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100054254 | Replace N2 membranes | Isolate 1 ea membrane at a time | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL RFRZ ROUT | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-12-15 | 2021-09-16 | 60 | REL | APPR OPND | HB /D /74/HBDB-A-0850 | INERT GAS PACKAGE | 99000119 | A |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100054254 | Replace N2 membranes | Replace membranes | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL RFRZ ROUT | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-12-15 | 2021-09-16 | 70 | REL | APPR OPND | HB /D /74/HBDB-A-0850 | INERT GAS PACKAGE | 99000119 | A |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100054254 | Replace N2 membranes | De-isolate and check for leak | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL RFRZ ROUT | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-12-15 | 2021-09-16 | 80 | REL | APPR OPND | HB /D /74/HBDB-A-0850 | INERT GAS PACKAGE | 99000119 | A |  | MMS | DK50
0 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100026288 | HDBC-A-5402 Replacemnt of Dissicant and | L3 HDBC-A-5402 Replacement of Dissicant | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 3 | 0 | W11-W12 | 2024-03-12 | 2024-03-18 | 2024-03-12 | 2019-09-07 | 2019-04-10 | 10 | PCNF REL | APPR OPND | HD /B /07/HDBC-A-5402 | PACKAGE |  | C |  | MMR | DK60
0 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026288 | HDBC-A-5402 Replacemnt of Dissicant and | L3 Replace HDBC-A-5402 Dissicant and fil | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 12 | 4 | W11-W12 | 2024-03-12 | 2024-03-18 | 2024-03-12 | 2019-09-07 | 2019-04-10 | 20 | PCNF REL | APPR OPND | HD /B /07/HDBC-A-5402 | PACKAGE |  | C |  | MMR | DK60
0 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026288 | HDBC-A-5402 Replacemnt of Dissicant and | L3 Overhaul of div. valves | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 24 | 0 | W11-W12 | 2024-03-12 | 2024-03-18 | 2024-03-14 | 2019-09-07 | 2019-04-10 | 30 | PCNF REL | APPR OPND | HD /B /07/HDBC-A-5402 | PACKAGE |  | C |  | MMR | DK60
0 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100026288 | HDBC-A-5402 Replacemnt of Dissicant and | L3 De-isolate HDBC-A-5402 after rep. | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 3 | 0 | W11-W12 | 2024-03-12 | 2024-03-18 | 2024-03-12 | 2019-09-07 | 2019-04-10 | 40 | PCNF REL | APPR OPND | HD /B /07/HDBC-A-5402 | PACKAGE |  | C |  | MMR | DK60
0 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026288 | HDBC-A-5402 Replacemnt of Dissicant and | Multitronic base kit | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 0 | 0 | W11-W12 | 2024-03-12 | 2024-03-18 | 2024-03-12 | 2019-09-07 | 2019-04-10 | 60 | PCNF REL | APPR OPND | HD /B /07/HDBC-A-5402 | PACKAGE |  | C |  | MMR | DK60
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100075420 | WM WTR Cylinder weight False alarm | Troubleshoot periodic Alarm WT-0481504 | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 12 | 3 | W05-W06 | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2023-03-27 | 2022-11-12 | 130 | PCNF REL | APPR OPND | HB /D /01/HBDB-WT-0481504 | WATERM.CYL.BANK WEIGHT LOW RESERVE 2/3/4 |  | C |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100075420 | WM WTR Cylinder weight False alarm | Additional load cell | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 0 | 0 | W05-W06 | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2023-03-27 | 2022-11-12 | 140 | PCNF REL | APPR OPND | HB /D /01/HBDB-WT-0481504 | WATERM.CYL.BANK WEIGHT LOW RESERVE 2/3/4 |  | C |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100075420 | WM WTR Cylinder weight False alarm | Replace controller WT-0481504 | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 16 | 14 | W05-W06 | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2023-03-27 | 2022-11-12 | 150 | PCNF REL | APPR OPND | HB /D /01/HBDB-WT-0481504 | WATERM.CYL.BANK WEIGHT LOW RESERVE 2/3/4 |  | C |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100075420 | WM WTR Cylinder weight False alarm | Install new Eilersen modules | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 16 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2023-03-27 | 2022-11-12 | 160 | REL | APPR OPND | HB /D /01/HBDB-WT-0481504 | WATERM.CYL.BANK WEIGHT LOW RESERVE 2/3/4 |  | C |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088924 | LOTI: LCV-507504 is externally leaking | LCV-507504 is externally leaking | REL GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 0 | 0 | W41-42 | 2024-03-28 | 2024-04-04 | 2024-03-28 | 2023-10-01 | 2023-05-19 | 10 | REL | APPR OPND | HB /D /27/HBDB-LCV-507504 | PINCH |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100088924 | LOTI: LCV-507504 is externally leaking | Rigging Prework | REL GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 8 | 0 | W41-42 | 2024-03-28 | 2024-04-04 | 2024-03-28 | 2023-10-01 | 2023-05-19 | 20 | REL | APPR OPND | HB /D /27/HBDB-LCV-507504 | PINCH |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088924 | LOTI: LCV-507504 is externally leaking | Production isolation | REL GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 3 | 0 | W41-42 | 2024-03-28 | 2024-04-04 | 2024-03-29 | 2023-10-01 | 2023-05-19 | 30 | REL | APPR OPND | HB /D /27/HBDB-LCV-507504 | PINCH |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100088924 | LOTI: LCV-507504 is externally leaking | Rigger assistance | REL GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 8 | 0 | W41-42 | 2024-03-28 | 2024-04-04 | 2024-03-29 | 2023-10-01 | 2023-05-19 | 40 | REL | APPR OPND | HB /D /27/HBDB-LCV-507504 | PINCH |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100088924 | LOTI: LCV-507504 is externally leaking | Instrument assistance | REL GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 4 | 0 | W41-42 | 2024-03-28 | 2024-04-04 | 2024-03-31 | 2023-10-01 | 2023-05-19 | 50 | REL | APPR OPND | HB /D /27/HBDB-LCV-507504 | PINCH |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088924 | LOTI: LCV-507504 is externally leaking | Dismantle Valvebody/Actuator | REL GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 8 | 0 | W41-42 | 2024-03-28 | 2024-04-04 | 2024-04-01 | 2023-10-01 | 2023-05-19 | 60 | REL | APPR OPND | HB /D /27/HBDB-LCV-507504 | PINCH |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088924 | LOTI: LCV-507504 is externally leaking | Replace Sleeve | REL GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 4 | 0 | W41-42 | 2024-03-28 | 2024-04-04 | 2024-04-01 | 2023-10-01 | 2023-05-19 | 70 | REL | APPR OPND | HB /D /27/HBDB-LCV-507504 | PINCH |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088924 | LOTI: LCV-507504 is externally leaking | Assembly Valvebody/Actuator | REL GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 8 | 0 | W41-42 | 2024-03-28 | 2024-04-04 | 2024-04-02 | 2023-10-01 | 2023-05-19 | 80 | REL | APPR OPND | HB /D /27/HBDB-LCV-507504 | PINCH |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088924 | LOTI: LCV-507504 is externally leaking | Production deisolation | REL GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 3 | 0 | W41-42 | 2024-03-28 | 2024-04-04 | 2024-04-03 | 2023-10-01 | 2023-05-19 | 90 | REL | APPR OPND | HB /D /27/HBDB-LCV-507504 | PINCH |  | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100088924 | LOTI: LCV-507504 is externally leaking | Rigging Postwork | REL GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 6 | 0 | W41-42 | 2024-03-28 | 2024-04-04 | 2024-04-03 | 2023-10-01 | 2023-05-19 | 100 | REL | APPR OPND | HB /D /27/HBDB-LCV-507504 | PINCH |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100088925 | WPO TCV-435003 oscillates rapid | Valve set to MANUAL mode | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 0.5 | 0 | W43-44 | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2023-09-29 | 2023-05-17 | 10 | PCNF REL | APPR OPND | HB /D /34/HBDC-TCV-435003 | TEMPERATURE CONTROL VALVE |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-INST | 2100088925 | WPO TCV-435003 oscillates rapid | Isolate positioner | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 0.5 | 0 | W43-44 | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2023-09-29 | 2023-05-17 | 20 | PCNF REL | APPR OPND | HB /D /34/HBDC-TCV-435003 | TEMPERATURE CONTROL VALVE |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-INST | 2100088925 | WPO TCV-435003 oscillates rapid | Replace positioner | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 2.5 | 37 | W43-44 | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2023-09-29 | 2023-05-17 | 30 | PCNF REL | APPR OPND | HB /D /34/HBDC-TCV-435003 | TEMPERATURE CONTROL VALVE |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-INST | 2100088925 | WPO TCV-435003 oscillates rapid | De-isolate positioner/Test with CCR | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 1 | 0 | W43-44 | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2023-09-29 | 2023-05-17 | 40 | PCNF REL | APPR OPND | HB /D /34/HBDC-TCV-435003 | TEMPERATURE CONTROL VALVE |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100088925 | WPO TCV-435003 oscillates rapid | Valve set to AUTO mode | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 0.5 | 0 | W43-44 | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2023-09-29 | 2023-05-17 | 50 | PCNF REL | APPR OPND | HB /D /34/HBDC-TCV-435003 | TEMPERATURE CONTROL VALVE |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-TELE | 2100088925 | WPO TCV-435003 oscillates rapid | Ass. from Telecom | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 12 | 9 |  | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2023-09-29 | 2023-05-17 | 60 | PCNF REL | APPR OPND | HB /D /34/HBDC-TCV-435003 | TEMPERATURE CONTROL VALVE |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100088925 | WPO TCV-435003 oscillates rapid | Pre/post Rigging/Lifting Equipment | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 6 | 0 |  | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2023-09-29 | 2023-05-17 | 80 | REL | APPR OPND | HB /D /34/HBDC-TCV-435003 | TEMPERATURE CONTROL VALVE |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100088925 | WPO TCV-435003 oscillates rapid | Production isolation | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 3 | 0 |  | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2023-09-29 | 2023-05-17 | 90 | REL | APPR OPND | HB /D /34/HBDC-TCV-435003 | TEMPERATURE CONTROL VALVE |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100088925 | WPO TCV-435003 oscillates rapid | Rigger assistance | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 6 | 0 |  | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2023-09-29 | 2023-05-17 | 100 | REL | APPR OPND | HB /D /34/HBDC-TCV-435003 | TEMPERATURE CONTROL VALVE |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-INST | 2100088925 | WPO TCV-435003 oscillates rapid | Instrument assistance | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 4 | 0 |  | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2023-09-29 | 2023-05-17 | 110 | REL | APPR OPND | HB /D /34/HBDC-TCV-435003 | TEMPERATURE CONTROL VALVE |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100088925 | WPO TCV-435003 oscillates rapid | Replace TCV-435003 | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 10 | 0 |  | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2023-09-29 | 2023-05-17 | 120 | REL | APPR OPND | HB /D /34/HBDC-TCV-435003 | TEMPERATURE CONTROL VALVE |  | C |  | MMS | DK50
2026-W1-2 | 3 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100088925 | WPO TCV-435003 oscillates rapid | Production deisolation w Leak/func. test | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 3 | 0 |  | 2024-09-23 | 2024-09-24 | 2024-09-23 | 2023-09-29 | 2023-05-17 | 130 | REL | APPR OPND | HB /D /34/HBDC-TCV-435003 | TEMPERATURE CONTROL VALVE |  | C |  | MMS | DK50
2026-W1-2 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100103893 | FLM Backwash XCV-536556 internal leaking | FLM Backwash XCV-536556 internal leaking | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 0 | 0 |  | 2024-03-25 | 2024-03-28 | 2024-03-25 | 2023-11-26 | 2023-10-12 | 10 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536556 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100103893 | FLM Backwash XCV-536556 internal leaking | Production isolation | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 3 | 0 |  | 2024-03-25 | 2024-03-28 | 2024-03-25 | 2023-11-26 | 2023-10-12 | 30 | REL | APPR OPND | HB /D /51/HBDB-XCV-536556 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100103893 | FLM Backwash XCV-536556 internal leaking | Rigger assistance | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 4 | 0 |  | 2024-03-25 | 2024-03-28 | 2024-03-26 | 2023-11-26 | 2023-10-12 | 35 | REL | APPR OPND | HB /D /51/HBDB-XCV-536556 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100103893 | FLM Backwash XCV-536556 internal leaking | Replace XCV Valve/Actuator | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 12 | 0 |  | 2024-03-25 | 2024-03-28 | 2024-03-26 | 2023-11-26 | 2023-10-12 | 40 | REL | APPR OPND | HB /D /51/HBDB-XCV-536556 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100103893 | FLM Backwash XCV-536556 internal leaking | Production deisolation w function test | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 3 | 0 |  | 2024-03-25 | 2024-03-28 | 2024-03-28 | 2023-11-26 | 2023-10-12 | 50 | REL | APPR OPND | HB /D /51/HBDB-XCV-536556 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
0 | 4 | NOSD | WGN | VEN-ELEC | VEN-ELEC | 2200005810 | TMM987E - HDA Green Oil - STEP 2 | TMM987E - HDA Green Oil - STEP 2 | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 0 | 0 | W47-48 | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2022-03-04 | 2021-05-08 | 10 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | MMS | DK60
0 | 4 | NOSD | WGN | VEN-ELEC | VEN-ELEC | 2200005810 | TMM987E - HDA Green Oil - STEP 2 | Purchase Brayco Oil | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT SCH RDBL | 0 | 0 | W47-48 | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2022-03-04 | 2021-05-08 | 20 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | MMS | DK60
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012736 | Replace HBDB-PSV-085101 - PSV 2023 | Prod Assist (breaking containment) | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2025-11-19 | 2023-06-03 | 70 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085101 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012736 | Replace HBDB-PSV-085101 - PSV 2023 | De-isolation and leak test | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 4 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2025-11-19 | 2023-06-03 | 90 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085101 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-SCAF | 2200012736 | Replace HBDB-PSV-085101 - PSV 2023 | Building scaffolding | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 10 | 8 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2025-11-19 | 2023-06-03 | 100 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085101 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-SCAF | 2200012736 | Replace HBDB-PSV-085101 - PSV 2023 | Remove scaffolding | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 10 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2025-11-19 | 2023-06-03 | 110 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085101 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012736 | Replace HBDB-PSV-085101 - PSV 2023 | Install new PSV | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2025-11-19 | 2023-06-03 | 130 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085101 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012737 | Replace HBDB-PSV-085102 - PSV 2023 | Isolation of PSV | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-29 | 2024-04-22 | 2025-11-19 | 2023-06-03 | 10 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085102 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012737 | Replace HBDB-PSV-085102 - PSV 2023 | Prod Assist (breaking containment) | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-29 | 2024-04-22 | 2025-11-19 | 2023-06-03 | 20 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085102 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012737 | Replace HBDB-PSV-085102 - PSV 2023 | Rigging assist (install) | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 24 | 0 | W17-W18 | 2024-04-22 | 2024-04-29 | 2024-04-22 | 2025-11-19 | 2023-06-03 | 30 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085102 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012737 | Replace HBDB-PSV-085102 - PSV 2023 | Remove PSV and install new PSV | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 5 | 0 | W17-W18 | 2024-04-22 | 2024-04-29 | 2024-04-25 | 2025-11-19 | 2023-06-03 | 40 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085102 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012737 | Replace HBDB-PSV-085102 - PSV 2023 | Rigging Assist (remove) | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 12 | 0 | W17-W18 | 2024-04-22 | 2024-04-29 | 2024-04-25 | 2025-11-19 | 2023-06-03 | 60 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085102 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012737 | Replace HBDB-PSV-085102 - PSV 2023 | Prod Assist (breaking containment) | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 2 | 0 | W17-W18 | 2024-04-22 | 2024-04-29 | 2024-04-27 | 2025-11-19 | 2023-06-03 | 70 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085102 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012737 | Replace HBDB-PSV-085102 - PSV 2023 | De-isolation and leak test | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 4 | 0 | W17-W18 | 2024-04-22 | 2024-04-29 | 2024-04-27 | 2025-11-19 | 2023-06-03 | 90 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085102 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-SCAF | 2200012737 | Replace HBDB-PSV-085102 - PSV 2023 | Building scaffolding | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 10 | 7 | W17-W18 | 2024-04-22 | 2024-04-29 | 2024-04-27 | 2025-11-19 | 2023-06-03 | 100 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085102 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-MECH | MTN-SCAF | 2200012737 | Replace HBDB-PSV-085102 - PSV 2023 | Remove scaffolding | REL PCNF GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 10 | 0 | W17-W18 | 2024-04-22 | 2024-04-29 | 2024-04-28 | 2025-11-19 | 2023-06-03 | 110 | PCNF REL | APPR OPND | HB /D /74/HBDB-PSV-085102 | PRESSURE SAFETY RELIEF VALVE |  | A |  | MMS | DK50
2026-W1-2 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300008087 | SCALANCE SWITCH REPLACEMENT SAS B | SCALANCE SWITCH REPLACEMENT SAS B | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 10 | 36 | W13-W14 | 2024-04-01 | 2024-04-03 | 2024-04-01 | 2024-09-08 | 2024-04-26 | 10 | PCNF REL | APPR OPND | HB /A /04/HBAA-DT-202080 | SCALENCE SAS B HBA |  | A |  | MIN | DK50
2026-W1-2 | 3 | NE | WRO | MTN-TELE | MTN-TELE | 2300008087 | SCALANCE SWITCH REPLACEMENT SAS B | add. materials | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 0 | 0 | W13-W14 | 2024-04-01 | 2024-04-03 | 2024-04-03 | 2024-09-08 | 2024-04-26 | 20 | REL | APPR OPND | HB /A /04/HBAA-DT-202080 | SCALENCE SAS B HBA |  | A |  | MIN | DK50
0 | C | NOSD | WPM | MTN-MECH | VEN-MECH | 2400282127 | 1Y AIR SYSTEM INSPECTION HDBC-5401/2 | AIR SYSTEM INSPECTION HDBC-5401/2 | REL GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 24 | 0 | W11-W12 | 2024-03-13 | 2024-03-25 | 2024-03-13 | 2023-10-23 | 2023-09-17 | 10 | REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | C | DKHD-0054 | MMR | DK60 | MR0033
0 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400282127 | 1Y AIR SYSTEM INSPECTION HDBC-5401/2 | VENDOR SUPPPORT | REL GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 24 | 0 | W11-W12 | 2024-03-13 | 2024-03-25 | 2024-03-15 | 2023-10-23 | 2023-09-17 | 20 | REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | C | DKHD-0054 | MMR | DK60 | MR0033
0 | C | NOSD | WPM | MTN-MECH | MTN-INST | 2400282127 | 1Y AIR SYSTEM INSPECTION HDBC-5401/2 | VENDOR SUPPORT | REL GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 24 | 0 | W11-W12 | 2024-03-13 | 2024-03-25 | 2024-03-20 | 2023-10-23 | 2023-09-17 | 30 | REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | C | DKHD-0054 | MMR | DK60 | MR0033
0 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400282127 | 1Y AIR SYSTEM INSPECTION HDBC-5401/2 | Spare parts | REL GMPS MANC PRC SETC | APPR PMAT SCH RDBL | 0 | 0 | W11-W12 | 2024-03-13 | 2024-03-25 | 2024-03-25 | 2023-10-23 | 2023-09-17 | 40 | REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | C | DKHD-0054 | MMR | DK60 | MR0033
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100033878 | Repl leak LG SDBB DS HCV-29194 to HBA-14 | Prepare/carry out isolation w N2 purging | REL GMPS MANC PRC SETC | APPR PMAT RFRZ | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2020-08-15 | 2020-07-06 | 10 | REL | APPR OPND | HB /A /37/HBAA-HCV-29194 | LIFT GAS MANIFOLD OUTLET VALVE | 99000119 | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100033878 | Repl leak LG SDBB DS HCV-29194 to HBA-14 | Replace 2" SDBB Vlv | REL GMPS MANC PRC SETC | APPR PMAT RFRZ | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2020-08-15 | 2020-07-06 | 20 | REL | APPR OPND | HB /A /37/HBAA-HCV-29194 | LIFT GAS MANIFOLD OUTLET VALVE | 99000119 | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100033878 | Repl leak LG SDBB DS HCV-29194 to HBA-14 | Production deisolation/leak test | REL GMPS MANC PRC SETC | APPR PMAT RFRZ | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2020-08-15 | 2020-07-06 | 30 | REL | APPR OPND | HB /A /37/HBAA-HCV-29194 | LIFT GAS MANIFOLD OUTLET VALVE | 99000119 | C |  | MMS | DK50 |  | PROK
2024-W23-24 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100071505 | WPO OTI: LG-34115 on HBA test separator | Isolate Heat tracing/LED light | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL RREQ | 0.5 | 0 | 24-W23-24 | 2024-06-13 | 2024-06-15 | 2024-06-13 | 2022-08-25 | 2022-07-11 | 15 | PCNF REL | APPR OPND | HB /A /11/HBAA-LG-34115 | LEVEL GAUGE |  | C |  | MIN | DK50
2024-W23-24 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100071505 | WPO OTI: LG-34115 on HBA test separator | Rigging level glass second time | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL RREQ | 12 | 6 | 24-W23-24 | 2024-06-13 | 2024-06-15 | 2024-06-13 | 2022-08-25 | 2022-07-11 | 45 | PCNF REL | APPR OPND | HB /A /11/HBAA-LG-34115 | LEVEL GAUGE |  | C |  | MIN | DK50
2024-W23-24 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100071505 | WPO OTI: LG-34115 on HBA test separator | De-isolate Heat tracing/LED light | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL RREQ | 0.5 | 0 | 24-W23-24 | 2024-06-13 | 2024-06-15 | 2024-06-13 | 2022-08-25 | 2022-07-11 | 65 | PCNF REL | APPR OPND | HB /A /11/HBAA-LG-34115 | LEVEL GAUGE |  | C |  | MIN | DK50
2024-W23-24 | 4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100071505 | WPO OTI: LG-34115 on HBA test separator | Dimantling scaffolding | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL RREQ | 12 | 0 | 24-W23-24 | 2024-06-13 | 2024-06-15 | 2024-06-13 | 2022-08-25 | 2022-07-11 | 80 | PCNF REL | APPR OPND | HB /A /11/HBAA-LG-34115 | LEVEL GAUGE |  | C |  | MIN | DK50
2024-W23-24 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071505 | WPO OTI: LG-34115 on HBA test separator | *************************************** | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL RREQ | 0 | 0 | 24-W23-24 | 2024-06-13 | 2024-06-15 | 2024-06-13 | 2022-08-25 | 2022-07-11 | 90 | PCNF REL | APPR OPND | HB /A /11/HBAA-LG-34115 | LEVEL GAUGE |  | C |  | MIN | DK50
2024-W23-24 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100071505 | WPO OTI: LG-34115 on HBA test separator | Isolate light | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL RREQ | 0.5 | 0 | 24-W23-24 | 2024-06-13 | 2024-06-15 | 2024-06-13 | 2022-08-25 | 2022-07-11 | 100 | PCNF REL | APPR OPND | HB /A /11/HBAA-LG-34115 | LEVEL GAUGE |  | C |  | MIN | DK50
2024-W23-24 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100071505 | WPO OTI: LG-34115 on HBA test separator | Install new light | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL RREQ | 3 | 0 | 24-W23-24 | 2024-06-13 | 2024-06-15 | 2024-06-13 | 2022-08-25 | 2022-07-11 | 110 | PCNF REL | APPR OPND | HB /A /11/HBAA-LG-34115 | LEVEL GAUGE |  | C |  | MIN | DK50
2024-W23-24 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100071505 | WPO OTI: LG-34115 on HBA test separator | De-isolate Light | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL RREQ | 0.5 | 0 | 24-W23-24 | 2024-06-13 | 2024-06-15 | 2024-06-13 | 2022-08-25 | 2022-07-11 | 120 | PCNF REL | APPR OPND | HB /A /11/HBAA-LG-34115 | LEVEL GAUGE |  | C |  | MIN | DK50
2024-W23-24 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071505 | WPO OTI: LG-34115 on HBA test separator | New type level gauge | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL RREQ | 0 | 0 | 24-W23-24 | 2024-06-13 | 2024-06-15 | 2024-06-13 | 2022-08-25 | 2022-07-11 | 130 | REL | APPR OPND | HB /A /11/HBAA-LG-34115 | LEVEL GAUGE |  | C |  | MIN | DK50
2024-W23-24 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071505 | WPO OTI: LG-34115 on HBA test separator | *************************************** | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL RREQ | 0 | 0 | 24-W23-24 | 2024-06-13 | 2024-06-15 | 2024-06-13 | 2022-08-25 | 2022-07-11 | 140 | REL | APPR OPND | HB /A /11/HBAA-LG-34115 | LEVEL GAUGE |  | C |  | MIN | DK50
2024-W23-24 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100071505 | WPO OTI: LG-34115 on HBA test separator | Install Level gauge | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL RREQ | 10 | 0 | 24-W23-24 | 2024-06-13 | 2024-06-15 | 2024-06-13 | 2022-08-25 | 2022-07-11 | 150 | REL | APPR OPND | HB /A /11/HBAA-LG-34115 | LEVEL GAUGE |  | C |  | MIN | DK50
2024-W23-24 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071505 | WPO OTI: LG-34115 on HBA test separator | Install level gauge | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL RREQ | 20 | 0 | 24-W23-24 | 2024-06-13 | 2024-06-15 | 2024-06-13 | 2022-08-25 | 2022-07-11 | 160 | REL | APPR OPND | HB /A /11/HBAA-LG-34115 | LEVEL GAUGE |  | C |  | MIN | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100029619 | Replace broaken HT JB NoxMåling | Create support for JB. | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2020-04-04 | 2020-03-15 | 10 | REL | APPR OPND | HB /D /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  | PROK | 2024-06-02
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100029619 | Replace broaken HT JB NoxMåling | Isolate circuit breaker for HT | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2020-04-04 | 2020-03-15 | 20 | REL | APPR OPND | HB /D /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  | PROK | 2024-06-03
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100029619 | Replace broaken HT JB NoxMåling | Re-seal connection, install support. | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2020-04-04 | 2020-03-15 | 30 | REL | APPR OPND | HB /D /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  | PROK | 2024-06-04
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100029619 | Replace broaken HT JB NoxMåling | De-isolate the above. | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2020-04-04 | 2020-03-15 | 40 | REL | APPR OPND | HB /D /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  | PROK | 2024-06-06
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100033278 | HBAA defekt ventiler på LG | Isolate heat tracing | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 0 | W17-W18 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2021-01-29 | 2020-09-01 | 10 | REL | APPR OPND | HB /A /28/HBAA-LG-50017 | LEVEL GAUGE |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100033278 | HBAA defekt ventiler på LG | Isolate level glass | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 0 | W17-W18 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2021-01-29 | 2020-09-01 | 20 | REL | APPR OPND | HB /A /28/HBAA-LG-50017 | LEVEL GAUGE |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100033278 | HBAA defekt ventiler på LG | Remove old level glass | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 | W17-W18 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2021-01-29 | 2020-09-01 | 30 | REL | APPR OPND | HB /A /28/HBAA-LG-50017 | LEVEL GAUGE |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100033278 | HBAA defekt ventiler på LG | Install new level glass | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 | W17-W18 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2021-01-29 | 2020-09-01 | 40 | REL | APPR OPND | HB /A /28/HBAA-LG-50017 | LEVEL GAUGE |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100033278 | HBAA defekt ventiler på LG | De-isolate level glass | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 0 | W17-W18 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2021-01-29 | 2020-09-01 | 50 | REL | APPR OPND | HB /A /28/HBAA-LG-50017 | LEVEL GAUGE |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100033278 | HBAA defekt ventiler på LG | De-isolate heat tracing | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 0 | W17-W18 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2021-01-29 | 2020-09-01 | 60 | REL | APPR OPND | HB /A /28/HBAA-LG-50017 | LEVEL GAUGE |  | A |  | MIN | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100034229 | External leak upstream HCV-038072 | prep. for permit, site visit - Scaf | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2020-10-15 | 2020-07-17 | 10 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100034229 | External leak upstream HCV-038072 | prep. for permit, site visit - Mech | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2020-10-15 | 2020-07-17 | 20 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100034229 | External leak upstream HCV-038072 | prep. for job - scaf | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2020-10-15 | 2020-07-17 | 30 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100034229 | External leak upstream HCV-038072 | prep. for job - Mech | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2020-10-15 | 2020-07-17 | 40 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100034229 | External leak upstream HCV-038072 | Rig up lifting equipment - Scaf | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2020-10-15 | 2020-07-17 | 50 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100034229 | External leak upstream HCV-038072 | Isolate HCV-038072 - Prod | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2020-10-15 | 2020-07-17 | 60 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100034229 | External leak upstream HCV-038072 | Remove flange bolting - Mech | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2020-10-15 | 2020-07-17 | 70 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100034229 | External leak upstream HCV-038072 | Rig out valve - Scaf | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2020-10-15 | 2020-07-17 | 80 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100034229 | External leak upstream HCV-038072 | Rig in new valve - Scaf | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2020-10-15 | 2020-07-17 | 90 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100034229 | External leak upstream HCV-038072 | Install flange bolting - Mech | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2020-10-15 | 2020-07-17 | 100 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100034229 | External leak upstream HCV-038072 | De-isolate, leak test ETA. - Prod | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2020-10-15 | 2020-07-17 | 110 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100034229 | External leak upstream HCV-038072 | Rig down lifting equipment - Scaf | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2020-10-15 | 2020-07-17 | 120 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100034229 | External leak upstream HCV-038072 | House keeping - Mech | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-07 | 2020-10-15 | 2020-07-17 | 130 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100034229 | External leak upstream HCV-038072 | House keeping - Scaf | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-07 | 2020-10-15 | 2020-07-17 | 140 | REL | APPR OPND | HB /D /01/HBDB-HCV-038072 | BUTTERFLY VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-SCAF | 2100048521 | Pressure transmitters are missing insula | Install scaffolding | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 24 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2022-07-30 | 2021-10-03 | 10 | REL | APPR OPND | HB /B /37/HBBB-PIT-291004 | PRESSURE INDIC. TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100048521 | Pressure transmitters are missing insula | Isolate Heat tracing power supply for Tr | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2022-07-30 | 2021-10-03 | 20 | REL | APPR OPND | HB /B /37/HBBB-PIT-291004 | PRESSURE INDIC. TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100048521 | Pressure transmitters are missing insula | Install insulation for Transmitter (Scad | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 20 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2022-07-30 | 2021-10-03 | 30 | REL | APPR OPND | HB /B /37/HBBB-PIT-291004 | PRESSURE INDIC. TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100048521 | Pressure transmitters are missing insula | Deisolate Heat tracing power supply for | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-26 | 2022-07-30 | 2021-10-03 | 40 | REL | APPR OPND | HB /B /37/HBBB-PIT-291004 | PRESSURE INDIC. TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-SCAF | 2100048521 | Pressure transmitters are missing insula | Remove scaffolding | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 12 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-26 | 2022-07-30 | 2021-10-03 | 90 | REL | APPR OPND | HB /B /37/HBBB-PIT-291004 | PRESSURE INDIC. TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100055339 | Repair Pressure transmitter insulation | Isolate heat trace for Pressure transmit | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2022-01-02 | 2021-10-04 | 10 | REL | APPR OPND | HB /A /23/HBAA-PIT-34031 | PRESSURE INDICATOR TRANSMITTER (SCADA) |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100055339 | Repair Pressure transmitter insulation | Remove Insulation | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2022-01-02 | 2021-10-04 | 20 | REL | APPR OPND | HB /A /23/HBAA-PIT-34031 | PRESSURE INDICATOR TRANSMITTER (SCADA) |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100055339 | Repair Pressure transmitter insulation | Refit heat trace back | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2022-01-02 | 2021-10-04 | 30 | REL | APPR OPND | HB /A /23/HBAA-PIT-34031 | PRESSURE INDICATOR TRANSMITTER (SCADA) |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100055339 | Repair Pressure transmitter insulation | Reinstall new Insulation | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 25 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2022-01-02 | 2021-10-04 | 40 | REL | APPR OPND | HB /A /23/HBAA-PIT-34031 | PRESSURE INDICATOR TRANSMITTER (SCADA) |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100055339 | Repair Pressure transmitter insulation | Deisolate heat trace for Pressure transm | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-27 | 2022-01-02 | 2021-10-04 | 50 | REL | APPR OPND | HB /A /23/HBAA-PIT-34031 | PRESSURE INDICATOR TRANSMITTER (SCADA) |  | A |  | MIN | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055555 | Defect PI hyd.panel to XCV-38208A | Install pressure gauge | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W09-W10 | 2024-04-21 | 2024-04-21 | 2024-04-21 | 2021-11-07 | 2021-09-28 | 10 | REL | APPR OPND | HB /B /23/HBBA-XCV-38208 | UNCLASSIFIED VALVE |  | A |  | MIN | DK50 |  |  | 2024-05-25
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055556 | Defect PI hyd.panel to XCV-38408 | Install pressure gauge | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | 24-W05-06 | 2024-04-21 | 2024-04-21 | 2024-04-21 | 2021-11-07 | 2021-09-28 | 10 | REL | APPR OPND | HB /B /34/HBBA-XCV-38408 | UNCLASSIFIED VALVE |  | A |  | MIN | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | PRODTECH | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Isolate and depressurize system | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2021-11-26 | 2021-10-17 | 10 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | MTN-ELEC | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Isolate, lock out and disconnect relevan | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2021-11-26 | 2021-10-17 | 20 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | MTN-INST | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Isolate, depressurize and disconnect rel | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2021-11-26 | 2021-10-17 | 30 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | MTN-RIGG | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Prepare for rigging out hydraulic actuat | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2021-11-26 | 2021-10-17 | 40 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | MTN-MECH | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Disassemble actuator and valve from pipe | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2021-11-26 | 2021-10-17 | 50 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | MTN-RIGG | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Rig out valve and actuator from the pipe | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2021-11-26 | 2021-10-17 | 60 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | MTN-RIGG | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Rig in new valve and actuator to the pip | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2021-11-26 | 2021-10-17 | 70 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | MTN-MECH | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Assemble actuator and valve to the pipel | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2021-11-26 | 2021-10-17 | 80 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | MTN-INST | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Re-install instrumentation pressurize an | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2021-11-26 | 2021-10-17 | 90 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | MTN-ELEC | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Re-install electrical connections and pe | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2021-11-26 | 2021-10-17 | 100 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | PRODTECH | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Pressurize system and test for leakages | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2021-11-26 | 2021-10-17 | 110 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | MTN-RIGG | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Remove rigging gear etc. | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2021-11-26 | 2021-10-17 | 120 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBB03-GL | WDF | MTN-MECH | MTN-ROUS | 2100056366 | HBBB-XCV-300306 can not open, can turn 4 | Backload old Valve, bolts and gaskets | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2021-11-26 | 2021-10-17 | 130 | REL | APPR OPND | HB /B /10/HBBB-XCV-300306 | CONTROL VALVE WELL 04 |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059573 | P-5951 external leak | Isolate P-5951 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-26 | 2021-12-28 | 2021-12-08 | 20 | REL | APPR OPND | HB /B /07/HBBB-P-5951 | HYDRAULIC PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059573 | P-5951 external leak | Echange P-5951 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 20 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-26 | 2021-12-28 | 2021-12-08 | 30 | REL | APPR OPND | HB /B /07/HBBB-P-5951 | HYDRAULIC PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059573 | P-5951 external leak | De-isolate P-5951 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-05-01 | 2021-12-28 | 2021-12-08 | 40 | REL | APPR OPND | HB /B /07/HBBB-P-5951 | HYDRAULIC PUMP |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100061295 | Excessive corrosion of HBAA-FCV-39111 | Rigger assistance | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 |  | 2024-03-09 | 2024-03-14 | 2024-03-09 | 2022-09-02 | 2022-04-05 | 10 | REL | APPR OPND | HB /A /75/HBAA-FCV-39111 | FLOW CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100061295 | Excessive corrosion of HBAA-FCV-39111 | Production Isolation | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-14 | 2024-03-10 | 2022-09-02 | 2022-04-05 | 20 | REL | APPR OPND | HB /A /75/HBAA-FCV-39111 | FLOW CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100061295 | Excessive corrosion of HBAA-FCV-39111 | Instrument assistance | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 5 | 0 |  | 2024-03-09 | 2024-03-14 | 2024-03-11 | 2022-09-02 | 2022-04-05 | 30 | REL | APPR OPND | HB /A /75/HBAA-FCV-39111 | FLOW CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061295 | Excessive corrosion of HBAA-FCV-39111 | Replace FCV-39111 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 10 | 0 |  | 2024-03-09 | 2024-03-14 | 2024-03-12 | 2022-09-02 | 2022-04-05 | 40 | REL | APPR OPND | HB /A /75/HBAA-FCV-39111 | FLOW CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100061295 | Excessive corrosion of HBAA-FCV-39111 | Production De-isolation w Func. test | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-14 | 2024-03-13 | 2022-09-02 | 2022-04-05 | 50 | REL | APPR OPND | HB /A /75/HBAA-FCV-39111 | FLOW CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100062295 | New cable for TIT on wells HBA | Isolate Temperature transmitter | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 0 | BL-Team | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2022-05-24 | 2022-02-23 | 10 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062295 | New cable for TIT on wells HBA | Replace cable for TIT-30015 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 6 | 0 | BL-Team | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2022-05-24 | 2022-02-23 | 20 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100062295 | New cable for TIT on wells HBA | Deisolate and test Temperatu transmitter | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 0 | BL-Team | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2022-05-24 | 2022-02-23 | 30 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-INST | 2100062295 | New cable for TIT on wells HBA | Check the transmitter | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 | BL-Team | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2022-05-24 | 2022-02-23 | 40 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062295 | New cable for TIT on wells HBA | new mat | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2022-05-24 | 2022-02-23 | 50 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062295 | New cable for TIT on wells HBA | new mat | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2022-05-24 | 2022-02-23 | 60 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | C |  | MIN | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | PRODTECH | 2100063769 | HBAA-HCV-34132 intenal leak. | Isolate and depressurize system. | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W19-W20 | 2024-05-06 | 2024-05-07 | 2024-05-06 | 2022-10-14 | 2022-05-17 | 10 | REL | APPR OPND | HB /A /11/HBAA-HCV-34132 | DBB VALVE |  | E |  | MMS | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100063769 | HBAA-HCV-34132 intenal leak. | Dismantle defect DBB valve | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1.5 | 0 | W19-W20 | 2024-05-06 | 2024-05-07 | 2024-05-06 | 2022-10-14 | 2022-05-17 | 20 | REL | APPR OPND | HB /A /11/HBAA-HCV-34132 | DBB VALVE |  | E |  | MMS | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100063769 | HBAA-HCV-34132 intenal leak. | Install new DBB valve | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1.5 | 0 | W19-W20 | 2024-05-06 | 2024-05-07 | 2024-05-06 | 2022-10-14 | 2022-05-17 | 30 | REL | APPR OPND | HB /A /11/HBAA-HCV-34132 | DBB VALVE |  | E |  | MMS | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | PRODTECH | 2100063769 | HBAA-HCV-34132 intenal leak. | Pressurize system and test for leakages | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1.5 | 0 | W19-W20 | 2024-05-06 | 2024-05-07 | 2024-05-07 | 2022-10-14 | 2022-05-17 | 40 | REL | APPR OPND | HB /A /11/HBAA-HCV-34132 | DBB VALVE |  | E |  | MMS | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | PRODTECH | 2100063769 | HBAA-HCV-34132 intenal leak. | De-isolation | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W19-W20 | 2024-05-06 | 2024-05-07 | 2024-05-07 | 2022-10-14 | 2022-05-17 | 50 | REL | APPR OPND | HB /A /11/HBAA-HCV-34132 | DBB VALVE |  | E |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100064016 | Rensning af Flame arrestor på open drain | Production Isolation | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 | W01-02 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-06-21 | 2022-03-23 | 10 | REL | APPR OPND | HB /D /28/HBDY-FA-506032 | FLAME ARRESTOR |  | C |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100064016 | Rensning af Flame arrestor på open drain | Remove/clean/install Element | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 | W01-02 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-06-21 | 2022-03-23 | 20 | REL | APPR OPND | HB /D /28/HBDY-FA-506032 | FLAME ARRESTOR |  | C |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100064016 | Rensning af Flame arrestor på open drain | Production De-isolation w Leaktest | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 | W01-02 | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2022-06-21 | 2022-03-23 | 30 | REL | APPR OPND | HB /D /28/HBDY-FA-506032 | FLAME ARRESTOR |  | C |  | MMS | DK50
2024-W23-24 | 3 | HBA22-WI | WDF | MTN-INST | MTN-INST | 2100064017 | Outer protectiv cable broken | Isolate position switches | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-06-21 | 2022-03-23 | 10 | REL | APPR OPND | HB /A /55/HBAA-WCV-30223 | WING CONTROL VALVE (WS) |  | E |  | MIN | DK50
2024-W23-24 | 3 | HBA22-WI | WDF | MTN-INST | MTN-INST | 2100064017 | Outer protectiv cable broken | Re-install cabling for position switches | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-06-21 | 2022-03-23 | 20 | REL | APPR OPND | HB /A /55/HBAA-WCV-30223 | WING CONTROL VALVE (WS) |  | E |  | MIN | DK50
2024-W23-24 | 3 | HBA22-WI | WDF | MTN-INST | MTN-INST | 2100064017 | Outer protectiv cable broken | De-isolate position switches | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-06-21 | 2022-03-23 | 30 | REL | APPR OPND | HB /A /55/HBAA-WCV-30223 | WING CONTROL VALVE (WS) |  | E |  | MIN | DK50
2024-W23-24 | 3 | HBA22-WI | WDF | MTN-INST | MTN-INST | 2100064017 | Outer protectiv cable broken | Test WCV postion switches with CCR | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-06-21 | 2022-03-23 | 40 | REL | APPR OPND | HB /A /55/HBAA-WCV-30223 | WING CONTROL VALVE (WS) |  | E |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100064834 | Choke external leak hydraulic oil | Build scaffolding for conslagg | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 10 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-04-26 | 2022-07-05 | 2022-04-06 | 10 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100064834 | Choke external leak hydraulic oil | Remove lagging | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 3.4 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-04-27 | 2022-07-05 | 2022-04-06 | 20 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100064834 | Choke external leak hydraulic oil | Prepare rigging equipment | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-04-27 | 2022-07-05 | 2022-04-06 | 30 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100064834 | Choke external leak hydraulic oil | Isolate equipment | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-04-27 | 2022-07-05 | 2022-04-06 | 40 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064834 | Choke external leak hydraulic oil | Remove hydraulic for actuator | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-04-27 | 2022-07-05 | 2022-04-06 | 50 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100064834 | Choke external leak hydraulic oil | Remove electrical connections | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-04-27 | 2022-07-05 | 2022-04-06 | 60 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064834 | Choke external leak hydraulic oil | Demount choke valve | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 6 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-04-27 | 2022-07-05 | 2022-04-06 | 70 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100064834 | Choke external leak hydraulic oil | Rig choke | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-04-27 | 2022-07-05 | 2022-04-06 | 80 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100064834 | Choke external leak hydraulic oil | Rig choke in | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-04-27 | 2022-07-05 | 2022-04-06 | 90 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064834 | Choke external leak hydraulic oil | IMount choke | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 60 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-04-27 | 2022-07-05 | 2022-04-06 | 100 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100064834 | Choke external leak hydraulic oil | Install electrical connections | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-05-08 | 2022-07-05 | 2022-04-06 | 110 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064834 | Choke external leak hydraulic oil | Install hydraulic on actuator | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-05-08 | 2022-07-05 | 2022-04-06 | 120 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100064834 | Choke external leak hydraulic oil | Remove isolation | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-05-08 | 2022-07-05 | 2022-04-06 | 130 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100064834 | Choke external leak hydraulic oil | Remove rigging equipment | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-05-08 | 2022-07-05 | 2022-04-06 | 140 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100064834 | Choke external leak hydraulic oil | install lagging | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 3.4 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-05-08 | 2022-07-05 | 2022-04-06 | 150 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100064834 | Choke external leak hydraulic oil | Remove scaffolding | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 | W17-W18 | 2024-04-26 | 2024-05-08 | 2024-05-07 | 2022-07-05 | 2022-04-06 | 160 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | C |  | MMS | DK50
0 | 3 | HDAFLARE | WDF | MTN-MECH | PRODTECH | 2100067810 | HCV on HDAA-P-5012A cannot be closed. | Production isolation | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2022-08-27 | 2022-05-29 | 10 | REL | APPR OPND | HD /A /28/SYSTEM-28-MANUAL-VALVES | SYSTEM-28-MANUAL-VALVES |  | C |  | MMS | DK60
0 | 3 | HDAFLARE | WDF | MTN-MECH | MTN-MECH | 2100067810 | HCV on HDAA-P-5012A cannot be closed. | Replace 3" Valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-08-27 | 2022-05-29 | 20 | REL | APPR OPND | HD /A /28/SYSTEM-28-MANUAL-VALVES | SYSTEM-28-MANUAL-VALVES |  | C |  | MMS | DK60
0 | 3 | HDAFLARE | WDF | MTN-MECH | PRODTECH | 2100067810 | HCV on HDAA-P-5012A cannot be closed. | Production de-isolation w leaktest | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2022-08-27 | 2022-05-29 | 30 | REL | APPR OPND | HD /A /28/SYSTEM-28-MANUAL-VALVES | SYSTEM-28-MANUAL-VALVES |  | C |  | MMS | DK60
0 | 3 | HDAFLARE | WDF | MTN-MECH | MTN-LAGG | 2100067810 | HCV on HDAA-P-5012A cannot be closed. | Reinstate insulation | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2022-08-27 | 2022-05-29 | 40 | REL | APPR OPND | HD /A /28/SYSTEM-28-MANUAL-VALVES | SYSTEM-28-MANUAL-VALVES |  | C |  | MMS | DK60
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100069957 | HBA05 Test XCV-30059 internally leaking | Prepare & Rigging of XCV valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 20 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-05-30 | 2022-12-12 | 10 | REL | APPR OPND | HB /A /10/HBAA-XCV-30059 | 8" 2500# T PLUG VALVE FROM WELL 05 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100069957 | HBA05 Test XCV-30059 internally leaking | Production Isolation | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2025-05-30 | 2022-12-12 | 20 | REL | APPR OPND | HB /A /10/HBAA-XCV-30059 | 8" 2500# T PLUG VALVE FROM WELL 05 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100069957 | HBA05 Test XCV-30059 internally leaking | Replace XCV-30059 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 16 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2025-05-30 | 2022-12-12 | 30 | REL | APPR OPND | HB /A /10/HBAA-XCV-30059 | 8" 2500# T PLUG VALVE FROM WELL 05 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-INST | 2100069957 | HBA05 Test XCV-30059 internally leaking | Inst part of XCV replacement | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2025-05-30 | 2022-12-12 | 40 | REL | APPR OPND | HB /A /10/HBAA-XCV-30059 | 8" 2500# T PLUG VALVE FROM WELL 05 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100069957 | HBA05 Test XCV-30059 internally leaking | Production De-isolation w Leaktest | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-07 | 2025-05-30 | 2022-12-12 | 50 | REL | APPR OPND | HB /A /10/HBAA-XCV-30059 | 8" 2500# T PLUG VALVE FROM WELL 05 |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100070677 | Gear box leaking oil HBDB-P-3455 | Isolate HBDB-P-3455 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2024-03-09 | 2024-07-22 | 2024-03-09 | 2022-12-26 | 2022-08-13 | 20 | REL | APPR OPND | HB /D /27/HBDB-P-3455 | SPENT H2S SCAVENGER WATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100070677 | Gear box leaking oil HBDB-P-3455 | Remove insulation and HT | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2024-03-09 | 2024-07-22 | 2024-03-09 | 2022-12-26 | 2022-08-13 | 30 | REL | APPR OPND | HB /D /27/HBDB-P-3455 | SPENT H2S SCAVENGER WATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100070677 | Gear box leaking oil HBDB-P-3455 | Disconnect pump inkl. elmotor | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 5 | 0 |  | 2024-03-09 | 2024-07-22 | 2024-03-09 | 2022-12-26 | 2022-08-13 | 40 | REL | APPR OPND | HB /D /27/HBDB-P-3455 | SPENT H2S SCAVENGER WATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100070677 | Gear box leaking oil HBDB-P-3455 | Disconnect pump inkl. elmotor | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 20 | 0 |  | 2024-03-09 | 2024-07-22 | 2024-03-10 | 2022-12-26 | 2022-08-13 | 50 | REL | APPR OPND | HB /D /27/HBDB-P-3455 | SPENT H2S SCAVENGER WATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100070677 | Gear box leaking oil HBDB-P-3455 | Rigging HBDB-P-3455 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 20 | 0 |  | 2024-03-09 | 2024-07-22 | 2024-03-14 | 2022-12-26 | 2022-08-13 | 60 | REL | APPR OPND | HB /D /27/HBDB-P-3455 | SPENT H2S SCAVENGER WATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100070677 | Gear box leaking oil HBDB-P-3455 | Backload HBDB-P-3455 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 10 | 0 |  | 2024-03-09 | 2024-07-22 | 2024-03-16 | 2022-12-26 | 2022-08-13 | 70 | REL | APPR OPND | HB /D /27/HBDB-P-3455 | SPENT H2S SCAVENGER WATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100070677 | Gear box leaking oil HBDB-P-3455 | Rigging HBDB-P-3455 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 20 | 0 |  | 2024-03-09 | 2024-07-22 | 2024-07-16 | 2022-12-26 | 2022-08-13 | 80 | REL | APPR OPND | HB /D /27/HBDB-P-3455 | SPENT H2S SCAVENGER WATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100070677 | Gear box leaking oil HBDB-P-3455 | Install HBDB-P-3455 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 20 | 0 |  | 2024-03-09 | 2024-07-22 | 2024-07-16 | 2022-12-26 | 2022-08-13 | 90 | REL | APPR OPND | HB /D /27/HBDB-P-3455 | SPENT H2S SCAVENGER WATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100070677 | Gear box leaking oil HBDB-P-3455 | Install HBDB-P-3455 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 10 | 0 |  | 2024-03-09 | 2024-07-22 | 2024-07-20 | 2022-12-26 | 2022-08-13 | 100 | REL | APPR OPND | HB /D /27/HBDB-P-3455 | SPENT H2S SCAVENGER WATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100070677 | Gear box leaking oil HBDB-P-3455 | Reinstall insulation and HT | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2024-03-09 | 2024-07-22 | 2024-07-22 | 2022-12-26 | 2022-08-13 | 110 | REL | APPR OPND | HB /D /27/HBDB-P-3455 | SPENT H2S SCAVENGER WATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100070677 | Gear box leaking oil HBDB-P-3455 | De-isolate HBDB-P-3455 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-07-22 | 2024-07-22 | 2022-12-26 | 2022-08-13 | 120 | REL | APPR OPND | HB /D /27/HBDB-P-3455 | SPENT H2S SCAVENGER WATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100071178 | Instrumental tubing insulation well head | Isolate heat trace for Pressure transmit | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W01-02 | 2023-04-24 | 2023-04-26 | 2023-04-24 | 2022-12-29 | 2022-08-16 | 10 | REL | APPR OPND | HB /A /10/HBA10-WELLHEAD | HBA10 WELLHEAD |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100071178 | Instrumental tubing insulation well head | Remove Insulation | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 | W01-02 | 2023-04-24 | 2023-04-26 | 2023-04-24 | 2022-12-29 | 2022-08-16 | 20 | REL | APPR OPND | HB /A /10/HBA10-WELLHEAD | HBA10 WELLHEAD |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100071178 | Instrumental tubing insulation well head | Refit heat trace back | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W01-02 | 2023-04-24 | 2023-04-26 | 2023-04-25 | 2022-12-29 | 2022-08-16 | 30 | REL | APPR OPND | HB /A /10/HBA10-WELLHEAD | HBA10 WELLHEAD |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100071178 | Instrumental tubing insulation well head | Reinstall new Insulation | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 | W01-02 | 2023-04-24 | 2023-04-26 | 2023-04-25 | 2022-12-29 | 2022-08-16 | 40 | REL | APPR OPND | HB /A /10/HBA10-WELLHEAD | HBA10 WELLHEAD |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100071178 | Instrumental tubing insulation well head | Deisolate heat trace for Pressure transm | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 | W01-02 | 2023-04-24 | 2023-04-26 | 2023-04-26 | 2022-12-29 | 2022-08-16 | 50 | REL | APPR OPND | HB /A /10/HBA10-WELLHEAD | HBA10 WELLHEAD |  | A |  | MIN | DK50
0 | 3 | HDADEG A | WDF | MTN-ROPE | MTN-ROPE | 2100071370 | Valve spool blocked for PIT-50169A | Install rope access equipment | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-01-03 | 2022-08-21 | 10 | REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | E |  | MIN | DK60
0 | 3 | HDADEG A | WDF | MTN-ROPE | PRODTECH | 2100071370 | Valve spool blocked for PIT-50169A | Isolate and purge degasser ICC | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-01-03 | 2022-08-21 | 20 | REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | E |  | MIN | DK60
0 | 3 | HDADEG A | WDF | MTN-ROPE | MTN-INST | 2100071370 | Valve spool blocked for PIT-50169A | Isolate pressure transmitter | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-01-03 | 2022-08-21 | 30 | REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | E |  | MIN | DK60
0 | 3 | HDADEG A | WDF | MTN-ROPE | MTN-ROPE | 2100071370 | Valve spool blocked for PIT-50169A | Remove spool | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-01-03 | 2022-08-21 | 40 | REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | E |  | MIN | DK60
0 | 3 | HDADEG A | WDF | MTN-ROPE | MTN-ROPE | 2100071370 | Valve spool blocked for PIT-50169A | Check flange/repair it | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-01-03 | 2022-08-21 | 45 | REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | E |  | MIN | DK60
0 | 3 | HDADEG A | WDF | MTN-ROPE | MTN-ROPE | 2100071370 | Valve spool blocked for PIT-50169A | Install new SDBB valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-01-03 | 2022-08-21 | 50 | REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | E |  | MIN | DK60
0 | 3 | HDADEG A | WDF | MTN-ROPE | MTN-INST | 2100071370 | Valve spool blocked for PIT-50169A | Install instrument tubing | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-01-03 | 2022-08-21 | 60 | REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | E |  | MIN | DK60
0 | 3 | HDADEG A | WDF | MTN-ROPE | MTN-INST | 2100071370 | Valve spool blocked for PIT-50169A | Remove transmitter isolation | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-01-03 | 2022-08-21 | 65 | REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | E |  | MIN | DK60
0 | 3 | HDADEG A | WDF | MTN-ROPE | MTN-INST | 2100071370 | Valve spool blocked for PIT-50169A | Calibrate and check transmitter | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-01-03 | 2022-08-21 | 70 | REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | E |  | MIN | DK60
0 | 3 | HDADEG A | WDF | MTN-ROPE | PRODTECH | 2100071370 | Valve spool blocked for PIT-50169A | Remove isolation from degasser | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-01-03 | 2022-08-21 | 80 | REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | E |  | MIN | DK60
0 | 3 | HDADEG A | WDF | MTN-ROPE | MTN-ROPE | 2100071370 | Valve spool blocked for PIT-50169A | Remove rope access equipment | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-01-03 | 2022-08-21 | 90 | REL | APPR OPND | HD /A /27/P-G | PIPING GROUP |  | E |  | MIN | DK60
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100072389 | SDBB liftgasmanifold to HBA-14 Seep | Isolate/deisolate valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2023-01-29 | 2022-09-16 | 10 | REL | APPR OPND | HB /A /37/HBAA-HCV-29194 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100072389 | SDBB liftgasmanifold to HBA-14 Seep | Replace valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2023-01-29 | 2022-09-16 | 20 | REL | APPR OPND | HB /A /37/HBAA-HCV-29194 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072442 | Change Transducers N-1851 | Program transducers | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 6 | 1 | W37-38 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-01-31 | 2022-09-18 | 10 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | A |  | MEL | DK50
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072442 | Change Transducers N-1851 | open signals for transducer signals | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 2 | 1 | W37-38 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-01-31 | 2022-09-18 | 20 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | A |  | MEL | DK50
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072442 | Change Transducers N-1851 | Change transducers | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 12 | 10 | W37-38 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-01-31 | 2022-09-18 | 30 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | A |  | MEL | DK50
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072442 | Change Transducers N-1851 | Remove inhibit for transducer signals | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 2 | 1 | W37-38 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-01-31 | 2022-09-18 | 40 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | A |  | MEL | DK50
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072442 | Change Transducers N-1851 | PO cavion | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-01-31 | 2022-09-18 | 50 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | A |  | MEL | DK50
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072442 | Change Transducers N-1851 | Additional parts | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-01-31 | 2022-09-18 | 60 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073050 | Replace vibration dampers on HBCM-A-1236 | Recover refrigerant into receiver | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 | W05-06 IOP | 2024-04-19 | 2024-04-26 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 10 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073050 | Replace vibration dampers on HBCM-A-1236 | Isolate compressor breaker | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 | W05-06 IOP | 2024-04-19 | 2024-04-26 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 20 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100073050 | Replace vibration dampers on HBCM-A-1236 | Cover / scaf / "tent" before weld | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 24 | 0 | W05-06 IOP | 2024-04-19 | 2024-04-26 | 2024-04-20 | 2023-02-13 | 2022-10-01 | 30 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073050 | Replace vibration dampers on HBCM-A-1236 | Modify pipe ends for flex connections | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 | W05-06 IOP | 2024-04-19 | 2024-04-26 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 35 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100073050 | Replace vibration dampers on HBCM-A-1236 | Cut out / weld in flex pipes in system | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 24 | 0 | W05-06 IOP | 2024-04-19 | 2024-04-26 | 2024-04-22 | 2023-02-13 | 2022-10-01 | 40 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | CON-NDTI | 2100073050 | Replace vibration dampers on HBCM-A-1236 | X-ray (100%) of 4 welds | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 12 | 0 |  | 2024-04-19 | 2024-04-26 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 45 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073050 | Replace vibration dampers on HBCM-A-1236 | Leak test @10 bar with N2 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 12 | 0 | W05-06 IOP | 2024-04-19 | 2024-04-26 | 2024-04-23 | 2023-02-13 | 2022-10-01 | 50 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073050 | Replace vibration dampers on HBCM-A-1236 | Apply vacuum, recharge refrigerant | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 | W05-06 IOP | 2024-04-19 | 2024-04-26 | 2024-04-24 | 2023-02-13 | 2022-10-01 | 60 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073050 | Replace vibration dampers on HBCM-A-1236 | Deisolate / test / top up refrigerant | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 | W05-06 IOP | 2024-04-19 | 2024-04-26 | 2024-04-25 | 2023-02-13 | 2022-10-01 | 70 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-PAIN | 2100073050 | Replace vibration dampers on HBCM-A-1236 | Paint | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W05-06 IOP | 2024-04-19 | 2024-04-26 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 80 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073050 | Replace vibration dampers on HBCM-A-1236 | Insulate pipes | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W05-06 IOP | 2024-04-19 | 2024-04-26 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 90 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | PRODTECH | 2100074716 | HBA17 liftgas HCV external leak | Isolate and depressurize system. | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2025-08-31 | 2023-03-15 | 10 | REL | APPR OPND | HB /A /37/HBAA-HCV-29174 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-RIGG | 2100074716 | HBA17 liftgas HCV external leak | Prepare Rigging Materials | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2025-08-31 | 2023-03-15 | 20 | REL | APPR OPND | HB /A /37/HBAA-HCV-29174 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100074716 | HBA17 liftgas HCV external leak | Demount HCV Valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2025-08-31 | 2023-03-15 | 30 | REL | APPR OPND | HB /A /37/HBAA-HCV-29174 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-RIGG | 2100074716 | HBA17 liftgas HCV external leak | Rigging assist. Rig out HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2025-08-31 | 2023-03-15 | 40 | REL | APPR OPND | HB /A /37/HBAA-HCV-29174 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-RIGG | 2100074716 | HBA17 liftgas HCV external leak | Rigging assist. Rig in New HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2025-08-31 | 2023-03-15 | 50 | REL | APPR OPND | HB /A /37/HBAA-HCV-29174 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100074716 | HBA17 liftgas HCV external leak | Mount New HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2025-08-31 | 2023-03-15 | 60 | REL | APPR OPND | HB /A /37/HBAA-HCV-29174 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100074716 | HBA17 liftgas HCV external leak | Deisolate | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2025-08-31 | 2023-03-15 | 70 | REL | APPR OPND | HB /A /37/HBAA-HCV-29174 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100074994 | HCV-29104 internal leaking | Isolate and depressurize system. | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2023-03-21 | 2022-11-06 | 10 | REL | APPR OPND | HB /A /37/HBAA-HCV-29104 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100074994 | HCV-29104 internal leaking | Prepare Rigging Materials | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2023-03-21 | 2022-11-06 | 20 | REL | APPR OPND | HB /A /37/HBAA-HCV-29104 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100074994 | HCV-29104 internal leaking | Demount HCV Valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2023-03-21 | 2022-11-06 | 30 | REL | APPR OPND | HB /A /37/HBAA-HCV-29104 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100074994 | HCV-29104 internal leaking | Rigging assist. Rig out HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-24 | 2024-08-23 | 2023-03-21 | 2022-11-06 | 40 | REL | APPR OPND | HB /A /37/HBAA-HCV-29104 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100074994 | HCV-29104 internal leaking | Rigging assist. Rig in New HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-24 | 2024-08-23 | 2023-03-21 | 2022-11-06 | 50 | REL | APPR OPND | HB /A /37/HBAA-HCV-29104 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100074994 | HCV-29104 internal leaking | Mount New HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-24 | 2024-08-23 | 2023-03-21 | 2022-11-06 | 60 | REL | APPR OPND | HB /A /37/HBAA-HCV-29104 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100074994 | HCV-29104 internal leaking | Deisolate | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-24 | 2024-08-23 | 2023-03-21 | 2022-11-06 | 70 | REL | APPR OPND | HB /A /37/HBAA-HCV-29104 | LIFT GAS MANIFOLD OUTLET VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076146 | P3904 secondary stroke adjustment broken | P3904 secondary stroke adjustment broken | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2025-09-23 | 2023-04-07 | 10 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100076146 | P3904 secondary stroke adjustment broken | Prepare for rigging | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 15 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2025-09-23 | 2023-04-07 | 20 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076146 | P3904 secondary stroke adjustment broken | Isolate & safing of P-3904 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2025-09-23 | 2023-04-07 | 30 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076146 | P3904 secondary stroke adjustment broken | Remove pump mechanical | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 5 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2025-09-23 | 2023-04-07 | 40 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100076146 | P3904 secondary stroke adjustment broken | Electric demol pump | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2025-09-23 | 2023-04-07 | 50 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076146 | P3904 secondary stroke adjustment broken | Rigger out pump assistance | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2025-09-23 | 2023-04-07 | 60 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076146 | P3904 secondary stroke adjustment broken | Prepare installtion of new pump | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2025-09-23 | 2023-04-07 | 70 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100076146 | P3904 secondary stroke adjustment broken | Rigging new pump | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2025-09-23 | 2023-04-07 | 80 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076146 | P3904 secondary stroke adjustment broken | Installation of new pump mechnical | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2025-09-23 | 2023-04-07 | 90 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100076146 | P3904 secondary stroke adjustment broken | Installation of new pump electrical | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2025-09-23 | 2023-04-07 | 100 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076146 | P3904 secondary stroke adjustment broken | De-isolate DFFA-P-3904 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-11 | 2025-09-23 | 2023-04-07 | 110 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076146 | P3904 secondary stroke adjustment broken | Shipment of old pump for onshore service | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2025-09-23 | 2023-04-07 | 120 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076146 | P3904 secondary stroke adjustment broken | *** New Scope of Work 21.11.2023 *** | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2025-09-23 | 2023-04-07 | 130 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076146 | P3904 secondary stroke adjustment broken | Isolate & safing of P-3904 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2025-09-23 | 2023-04-07 | 140 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076146 | P3904 secondary stroke adjustment broken | Dismantle faulty pump stroke | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 6 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2025-09-23 | 2023-04-07 | 150 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076146 | P3904 secondary stroke adjustment broken | Install new part for pump stroke | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 6 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2025-09-23 | 2023-04-07 | 160 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076146 | P3904 secondary stroke adjustment broken | de-isolate & de-safing of P-3904 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2025-09-23 | 2023-04-07 | 170 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076146 | P3904 secondary stroke adjustment broken | Function test | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2025-09-23 | 2023-04-07 | 180 | REL | APPR OPND | HB /A /75/HBAA-P-3904 | PUMP P-3904 |  | A |  | MMR | DK50
2026-W13-14 | 3 | HD-HBOIL | WDF | MTN-MECH | PRODTECH | 2100076722 | Pig indicator not working | Isolate and puge line | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-10-08 | 2023-04-22 | 10 | REL | APPR OPND | HB /A /12/HBAA-XPI-38027 | PIG SIGNAL FOR HBAA-EP-3811 |  | A |  | MIN | DK50
2026-W13-14 | 3 | HD-HBOIL | WDF | MTN-MECH | MTN-MECH | 2100076722 | Pig indicator not working | Removee old pig signaller | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-10-08 | 2023-04-22 | 20 | REL | APPR OPND | HB /A /12/HBAA-XPI-38027 | PIG SIGNAL FOR HBAA-EP-3811 |  | A |  | MIN | DK50
2026-W13-14 | 3 | HD-HBOIL | WDF | MTN-MECH | MTN-MECH | 2100076722 | Pig indicator not working | Install blanking hub | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-10-08 | 2023-04-22 | 30 | REL | APPR OPND | HB /A /12/HBAA-XPI-38027 | PIG SIGNAL FOR HBAA-EP-3811 |  | A |  | MIN | DK50
2026-W13-14 | 3 | HD-HBOIL | WDF | MTN-MECH | MTN-INST | 2100076722 | Pig indicator not working | Install and calibrate new pig signaler | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2025-10-08 | 2023-04-22 | 40 | REL | APPR OPND | HB /A /12/HBAA-XPI-38027 | PIG SIGNAL FOR HBAA-EP-3811 |  | A |  | MIN | DK50
2026-W13-14 | 3 | HD-HBOIL | WDF | MTN-MECH | PRODTECH | 2100076722 | Pig indicator not working | Deisolate the line | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2025-10-08 | 2023-04-22 | 50 | REL | APPR OPND | HB /A /12/HBAA-XPI-38027 | PIG SIGNAL FOR HBAA-EP-3811 |  | A |  | MIN | DK50
2026-W13-14 | 3 | HD-HBOIL | WDF | MTN-MECH | QAQCELEC | 2100076722 | Pig indicator not working | Send drw to Information managment 'AS BU | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-10-08 | 2023-04-22 | 60 | REL | APPR OPND | HB /A /12/HBAA-XPI-38027 | PIG SIGNAL FOR HBAA-EP-3811 |  | A |  | MIN | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-SCAF | 2100079876 | Replace demistor for HBDC-A-4352 | Erect Scaffold | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 16 | 0 |  | 2024-04-22 | 2024-05-01 | 2024-04-22 | 2023-06-15 | 2023-01-31 | 5 | REL | APPR OPND | HB /D /31/HBDD-T-4301 | AIR / OIL SEPARATOR |  | A |  | MMR | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | PRODTECH | 2100079876 | Replace demistor for HBDC-A-4352 | Isolation & safing | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-04-22 | 2024-05-01 | 2024-04-23 | 2023-06-15 | 2023-01-31 | 10 | REL | APPR OPND | HB /D /31/HBDD-T-4301 | AIR / OIL SEPARATOR |  | A |  | MMR | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-TURB | 2100079876 | Replace demistor for HBDC-A-4352 | Disconnect oil demister | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 |  | 2024-04-22 | 2024-05-01 | 2024-04-24 | 2023-06-15 | 2023-01-31 | 20 | REL | APPR OPND | HB /D /31/HBDD-T-4301 | AIR / OIL SEPARATOR |  | A |  | MMR | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-RIGG | 2100079876 | Replace demistor for HBDC-A-4352 | Rigging Assistance | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 12 | 0 |  | 2024-04-22 | 2024-05-01 | 2024-04-25 | 2023-06-15 | 2023-01-31 | 30 | REL | APPR OPND | HB /D /31/HBDD-T-4301 | AIR / OIL SEPARATOR |  | A |  | MMR | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-TURB | 2100079876 | Replace demistor for HBDC-A-4352 | Install new oil demister | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 |  | 2024-04-22 | 2024-05-01 | 2024-04-28 | 2023-06-15 | 2023-01-31 | 40 | REL | APPR OPND | HB /D /31/HBDD-T-4301 | AIR / OIL SEPARATOR |  | A |  | MMR | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | PRODTECH | 2100079876 | Replace demistor for HBDC-A-4352 | De-Isolation and De-safing | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-04-22 | 2024-05-01 | 2024-04-29 | 2023-06-15 | 2023-01-31 | 50 | REL | APPR OPND | HB /D /31/HBDD-T-4301 | AIR / OIL SEPARATOR |  | A |  | MMR | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-SCAF | 2100079876 | Replace demistor for HBDC-A-4352 | Dismantling Scaffold | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 16 | 0 |  | 2024-04-22 | 2024-05-01 | 2024-04-30 | 2023-06-15 | 2023-01-31 | 60 | REL | APPR OPND | HB /D /31/HBDD-T-4301 | AIR / OIL SEPARATOR |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080530 | P-5035 cannot generate pressure | P-5035 cannot generate pressure | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-06-23 | 2023-02-08 | 10 | REL | APPR OPND | HB /C /28/HBCM-P-5035 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100080530 | P-5035 cannot generate pressure | Prepare for rigging | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 15 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-06-23 | 2023-02-08 | 20 | REL | APPR OPND | HB /C /28/HBCM-P-5035 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100080530 | P-5035 cannot generate pressure | Isolate P-5035 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-06-23 | 2023-02-08 | 30 | REL | APPR OPND | HB /C /28/HBCM-P-5035 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080530 | P-5035 cannot generate pressure | Remove pump mechanical | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-06-23 | 2023-02-08 | 40 | REL | APPR OPND | HB /C /28/HBCM-P-5035 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100080530 | P-5035 cannot generate pressure | Electric demol pump | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-06-23 | 2023-02-08 | 50 | REL | APPR OPND | HB /C /28/HBCM-P-5035 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080530 | P-5035 cannot generate pressure | Rigger out pump assistance | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-06-23 | 2023-02-08 | 60 | REL | APPR OPND | HB /C /28/HBCM-P-5035 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080530 | P-5035 cannot generate pressure | Prepare installtion of new pump | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-06-23 | 2023-02-08 | 70 | REL | APPR OPND | HB /C /28/HBCM-P-5035 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100080530 | P-5035 cannot generate pressure | Rigging new pump | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-06-23 | 2023-02-08 | 80 | REL | APPR OPND | HB /C /28/HBCM-P-5035 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080530 | P-5035 cannot generate pressure | Installation of new pump mechnical | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2023-06-23 | 2023-02-08 | 90 | REL | APPR OPND | HB /C /28/HBCM-P-5035 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100080530 | P-5035 cannot generate pressure | Installation of new motor | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2023-06-23 | 2023-02-08 | 100 | REL | APPR OPND | HB /C /28/HBCM-P-5035 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100080530 | P-5035 cannot generate pressure | De-isolate P-5035 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2023-06-23 | 2023-02-08 | 110 | REL | APPR OPND | HB /C /28/HBCM-P-5035 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080530 | P-5035 cannot generate pressure | Shipment of old pump for onshore service | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-10 | 2023-06-23 | 2023-02-08 | 120 | REL | APPR OPND | HB /C /28/HBCM-P-5035 | OPEN DRAIN PUMP |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100081844 | Leak from seawater filter motor 5367 | Setup rigging equipment | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2023-07-25 | 2023-03-12 | 10 | REL | APPR OPND | HB /D /51/HBDB-XM-5367 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081844 | Leak from seawater filter motor 5367 | Prepare matr/tool | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2023-07-25 | 2023-03-12 | 20 | REL | APPR OPND | HB /D /51/HBDB-XM-5367 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100081844 | Leak from seawater filter motor 5367 | Isolation of equipment | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-23 | 2023-07-25 | 2023-03-12 | 30 | REL | APPR OPND | HB /D /51/HBDB-XM-5367 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100081844 | Leak from seawater filter motor 5367 | Rigger assistance rig up/down | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-23 | 2023-07-25 | 2023-03-12 | 40 | REL | APPR OPND | HB /D /51/HBDB-XM-5367 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100081844 | Leak from seawater filter motor 5367 | Electrical assisance on cable | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2023-07-25 | 2023-03-12 | 50 | REL | APPR OPND | HB /D /51/HBDB-XM-5367 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081844 | Leak from seawater filter motor 5367 | Removal of gear/motor | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2023-07-25 | 2023-03-12 | 60 | REL | APPR OPND | HB /D /51/HBDB-XM-5367 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081844 | Leak from seawater filter motor 5367 | Replace worn out parts | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2023-07-25 | 2023-03-12 | 70 | REL | APPR OPND | HB /D /51/HBDB-XM-5367 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081844 | Leak from seawater filter motor 5367 | re-install gear/motor | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2023-07-25 | 2023-03-12 | 80 | REL | APPR OPND | HB /D /51/HBDB-XM-5367 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100081844 | Leak from seawater filter motor 5367 | Leak-test & de-isolation | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-25 | 2023-07-25 | 2023-03-12 | 90 | REL | APPR OPND | HB /D /51/HBDB-XM-5367 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081844 | Leak from seawater filter motor 5367 | Function test | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-25 | 2024-08-25 | 2023-07-25 | 2023-03-12 | 100 | REL | APPR OPND | HB /D /51/HBDB-XM-5367 | SEAWATER FILTER FILTER MOTOR |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100084832 | Pump HBDB-P-5366 Bearing defect | Prepare for rigging | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-04-30 | 2024-05-07 | 2024-04-30 | 2023-08-05 | 2023-03-23 | 10 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084832 | Pump HBDB-P-5366 Bearing defect | Isolate HBDB-P-5366 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-04-30 | 2024-05-07 | 2024-05-01 | 2023-08-05 | 2023-03-23 | 20 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100084832 | Pump HBDB-P-5366 Bearing defect | Dismount HBDB-P-5366 (Electrical) | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2024-04-30 | 2024-05-07 | 2024-05-01 | 2023-08-05 | 2023-03-23 | 30 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084832 | Pump HBDB-P-5366 Bearing defect | Dismount HBDB-P-5366 (Mechanical) | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2024-04-30 | 2024-05-07 | 2024-05-02 | 2023-08-05 | 2023-03-23 | 50 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100084832 | Pump HBDB-P-5366 Bearing defect | Rigging assistance | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-04-30 | 2024-05-07 | 2024-05-03 | 2023-08-05 | 2023-03-23 | 80 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084832 | Pump HBDB-P-5366 Bearing defect | Backloading of HBDB-P-5366 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-04-30 | 2024-05-07 | 2024-05-03 | 2023-08-05 | 2023-03-23 | 100 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084832 | Pump HBDB-P-5366 Bearing defect | Mount HBDB-P-5366 (Mechanical) | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 |  | 2024-04-30 | 2024-05-07 | 2024-05-04 | 2023-08-05 | 2023-03-23 | 110 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100084832 | Pump HBDB-P-5366 Bearing defect | Mount HBDB-P-5366 (Electrical) | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2024-04-30 | 2024-05-07 | 2024-05-05 | 2023-08-05 | 2023-03-23 | 120 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084832 | Pump HBDB-P-5366 Bearing defect | Alignment of HBDB-P-5366 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-04-30 | 2024-05-07 | 2024-05-06 | 2023-08-05 | 2023-03-23 | 130 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084832 | Pump HBDB-P-5366 Bearing defect | Deisolate and test HBDB-P-5366 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-04-30 | 2024-05-07 | 2024-05-07 | 2023-08-05 | 2023-03-23 | 140 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100084832 | Pump HBDB-P-5366 Bearing defect | Removal of rigging equipment | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-04-30 | 2024-05-07 | 2024-05-07 | 2023-08-05 | 2023-03-23 | 150 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100086077 | HBA-27 flowline 1½" drain valve blocked | HBA-27 flowline 1½" drain valve blocked | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 | W19-W20 | 2024-05-07 | 2024-05-08 | 2024-05-07 | 2023-08-17 | 2023-04-04 | 10 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100086077 | HBA-27 flowline 1½" drain valve blocked | ISOLATE XCV-30278 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W19-W20 | 2024-05-07 | 2024-05-08 | 2024-05-07 | 2023-08-17 | 2023-04-04 | 20 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100086077 | HBA-27 flowline 1½" drain valve blocked | Dismantle valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 | W19-W20 | 2024-05-07 | 2024-05-08 | 2024-05-07 | 2023-08-17 | 2023-04-04 | 30 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100086077 | HBA-27 flowline 1½" drain valve blocked | Install new valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 | W19-W20 | 2024-05-07 | 2024-05-08 | 2024-05-07 | 2023-08-17 | 2023-04-04 | 40 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100086077 | HBA-27 flowline 1½" drain valve blocked | De-isolate | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W19-W20 | 2024-05-07 | 2024-05-08 | 2024-05-08 | 2023-08-17 | 2023-04-04 | 50 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100086717 | Seep on HCV-290032-U lift gas grayloc | Isolation by Production | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2023-08-23 | 2023-04-10 | 10 | REL | APPR OPND | HB /D /34/HBDB-HCV-290032-U | HCV UPSTREAM BDV-290032 |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100086717 | Seep on HCV-290032-U lift gas grayloc | Prepare Rigging Materials | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2023-08-23 | 2023-04-10 | 20 | REL | APPR OPND | HB /D /34/HBDB-HCV-290032-U | HCV UPSTREAM BDV-290032 |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100086717 | Seep on HCV-290032-U lift gas grayloc | Demount HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2023-08-23 | 2023-04-10 | 30 | REL | APPR OPND | HB /D /34/HBDB-HCV-290032-U | HCV UPSTREAM BDV-290032 |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100086717 | Seep on HCV-290032-U lift gas grayloc | Rigging assist. Rig out HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2023-08-23 | 2023-04-10 | 40 | REL | APPR OPND | HB /D /34/HBDB-HCV-290032-U | HCV UPSTREAM BDV-290032 |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100086717 | Seep on HCV-290032-U lift gas grayloc | Rigging assist. Rig in New HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2023-08-23 | 2023-04-10 | 50 | REL | APPR OPND | HB /D /34/HBDB-HCV-290032-U | HCV UPSTREAM BDV-290032 |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100086717 | Seep on HCV-290032-U lift gas grayloc | Mount New HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2023-08-23 | 2023-04-10 | 60 | REL | APPR OPND | HB /D /34/HBDB-HCV-290032-U | HCV UPSTREAM BDV-290032 |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100086717 | Seep on HCV-290032-U lift gas grayloc | DEISOLATION | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2023-08-23 | 2023-04-10 | 70 | REL | APPR OPND | HB /D /34/HBDB-HCV-290032-U | HCV UPSTREAM BDV-290032 |  | A |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-INST | MTN-INST | 2100093144 | Position transmitter not working on dump | Isolate position transmitter | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 0 | 24-W05-06 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2023-07-27 | 2023-06-12 | 10 | REL | APPR OPND | HB /A /50/HBAA-CVA-35004 | CHOKE |  | C |  | MIN | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-INST | MTN-INST | 2100093144 | Position transmitter not working on dump | Replace position transmitter | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 | 24-W05-06 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2023-07-27 | 2023-06-12 | 20 | REL | APPR OPND | HB /A /50/HBAA-CVA-35004 | CHOKE |  | C |  | MIN | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-INST | MTN-INST | 2100093144 | Position transmitter not working on dump | De-isolate and test | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1.5 | 0 | 24-W05-06 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2023-07-27 | 2023-06-12 | 30 | REL | APPR OPND | HB /A /50/HBAA-CVA-35004 | CHOKE |  | C |  | MIN | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-INST | MTN-INST | 2100093144 | Position transmitter not working on dump | Return to stock | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 | 24-W05-06 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2023-07-27 | 2023-06-12 | 40 | REL | APPR OPND | HB /A /50/HBAA-CVA-35004 | CHOKE |  | C |  | MIN | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100094579 | New HCV for LIT-576001 | Mount Access Platform Scaffold | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-12-30 | 2023-08-17 | 10 | REL | APPR OPND | HB /D /71/HBDC-LIT-576001 | LEVEL INDICATOR TRANSMITTER (METERING) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100094579 | New HCV for LIT-576001 | Isolation of Valves | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-12-30 | 2023-08-17 | 20 | REL | APPR OPND | HB /D /71/HBDC-LIT-576001 | LEVEL INDICATOR TRANSMITTER (METERING) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100094579 | New HCV for LIT-576001 | Demount Valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-12-30 | 2023-08-17 | 30 | REL | APPR OPND | HB /D /71/HBDC-LIT-576001 | LEVEL INDICATOR TRANSMITTER (METERING) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100094579 | New HCV for LIT-576001 | Install New Valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-12-30 | 2023-08-17 | 40 | REL | APPR OPND | HB /D /71/HBDC-LIT-576001 | LEVEL INDICATOR TRANSMITTER (METERING) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100094579 | New HCV for LIT-576001 | De-isolate | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-12-30 | 2023-08-17 | 50 | REL | APPR OPND | HB /D /71/HBDC-LIT-576001 | LEVEL INDICATOR TRANSMITTER (METERING) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-INST | 2100094579 | New HCV for LIT-576001 | Calibrate HBC_LIT-576001 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-28 | 2023-12-30 | 2023-08-17 | 60 | REL | APPR OPND | HB /D /71/HBDC-LIT-576001 | LEVEL INDICATOR TRANSMITTER (METERING) |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100095365 | LG HCV for HBA29 internally leaking | Isolate and depressurize system. | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-01-25 | 2023-09-12 | 10 | REL | APPR OPND | HB /A /37/HBAA-HCV-29294 | LIFT GAS MANIFOLD OUTLET VALVE |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-RIGG | 2100095365 | LG HCV for HBA29 internally leaking | Prepare Rigging Materials | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-01-25 | 2023-09-12 | 20 | REL | APPR OPND | HB /A /37/HBAA-HCV-29294 | LIFT GAS MANIFOLD OUTLET VALVE |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100095365 | LG HCV for HBA29 internally leaking | Demount HCV Valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-01-25 | 2023-09-12 | 30 | REL | APPR OPND | HB /A /37/HBAA-HCV-29294 | LIFT GAS MANIFOLD OUTLET VALVE |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-RIGG | 2100095365 | LG HCV for HBA29 internally leaking | Rigging assist. Rig out HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-01-25 | 2023-09-12 | 40 | REL | APPR OPND | HB /A /37/HBAA-HCV-29294 | LIFT GAS MANIFOLD OUTLET VALVE |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-RIGG | 2100095365 | LG HCV for HBA29 internally leaking | Rigging assist. Rig in New HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-01-25 | 2023-09-12 | 50 | REL | APPR OPND | HB /A /37/HBAA-HCV-29294 | LIFT GAS MANIFOLD OUTLET VALVE |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100095365 | LG HCV for HBA29 internally leaking | Mount New HCV | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2024-01-25 | 2023-09-12 | 60 | REL | APPR OPND | HB /A /37/HBAA-HCV-29294 | LIFT GAS MANIFOLD OUTLET VALVE |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100095365 | LG HCV for HBA29 internally leaking | Deisolate | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2024-01-25 | 2023-09-12 | 70 | REL | APPR OPND | HB /A /37/HBAA-HCV-29294 | LIFT GAS MANIFOLD OUTLET VALVE |  | E |  | MMS | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096686 | Def. Transmitter HBCM-FIT-03002 | Isolate flow transmitter | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 6 | 24-W21-22 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-02-19 | 2023-10-07 | 20 | PCNF REL | APPR OPND | HB /C /01/HBCM-FIT-03002 | FIREWATER PUMP TEST |  | C |  | MIN | DK50 |  |  | 2024-06-02
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096686 | Def. Transmitter HBCM-FIT-03002 | Replace flow transmitter | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 2.5 | 0 | 24-W21-22 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-02-19 | 2023-10-07 | 30 | PCNF REL | APPR OPND | HB /C /01/HBCM-FIT-03002 | FIREWATER PUMP TEST |  | C |  | MIN | DK50 |  |  | 2024-06-03
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096686 | Def. Transmitter HBCM-FIT-03002 | Deisolate/calibrate transmitter | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 | 24-W21-22 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-02-19 | 2023-10-07 | 40 | PCNF REL | APPR OPND | HB /C /01/HBCM-FIT-03002 | FIREWATER PUMP TEST |  | C |  | MIN | DK50 |  |  | 2024-06-04
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096686 | Def. Transmitter HBCM-FIT-03002 | Test with CCR | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0.5 | 0 | 24-W21-22 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-02-19 | 2023-10-07 | 50 | PCNF REL | APPR OPND | HB /C /01/HBCM-FIT-03002 | FIREWATER PUMP TEST |  | C |  | MIN | DK50 |  |  | 2024-06-05
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100096686 | Def. Transmitter HBCM-FIT-03002 | Remove scaffolding | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 | 24-W21-22 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-02-19 | 2023-10-07 | 60 | PCNF REL | APPR OPND | HB /C /01/HBCM-FIT-03002 | FIREWATER PUMP TEST |  | C |  | MIN | DK50 |  |  | 2024-06-06
2024-W21-22 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100096686 | Def. Transmitter HBCM-FIT-03002 | Transmitter | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 | 24-W21-22 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-02-19 | 2023-10-07 | 70 | PCNF REL | APPR OPND | HB /C /01/HBCM-FIT-03002 | FIREWATER PUMP TEST |  | C |  | MIN | DK50 |  |  | 2024-06-08
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100101116 | HCV-575063 internal leaking | Pre Rigging of valve | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 8 | 0 | W19-W20 | 2024-05-27 | 2024-05-31 | 2024-05-27 | 2024-04-26 | 2023-12-13 | 10 | REL | APPR OPND | HB /D /70/HBDC-HCV-575063 | DBB BALL VALVE |  | F |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100101116 | HCV-575063 internal leaking | Production isolation | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 | W19-W20 | 2024-05-27 | 2024-05-31 | 2024-05-28 | 2024-04-26 | 2023-12-13 | 20 | REL | APPR OPND | HB /D /70/HBDC-HCV-575063 | DBB BALL VALVE |  | F |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100101116 | HCV-575063 internal leaking | Rigger Assistance/Lifting/Post work | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 5 | 0 | W19-W20 | 2024-05-27 | 2024-05-31 | 2024-05-28 | 2024-04-26 | 2023-12-13 | 30 | REL | APPR OPND | HB /D /70/HBDC-HCV-575063 | DBB BALL VALVE |  | F |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100101116 | HCV-575063 internal leaking | Replace HCV-575063 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 10 | 0 | W19-W20 | 2024-05-27 | 2024-05-31 | 2024-05-29 | 2024-04-26 | 2023-12-13 | 40 | REL | APPR OPND | HB /D /70/HBDC-HCV-575063 | DBB BALL VALVE |  | F |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100101116 | HCV-575063 internal leaking | Production deisolation f. leaktest | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 | W19-W20 | 2024-05-27 | 2024-05-31 | 2024-05-30 | 2024-04-26 | 2023-12-13 | 50 | REL | APPR OPND | HB /D /70/HBDC-HCV-575063 | DBB BALL VALVE |  | F |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | NE | WDF | MTN-MECH | PRODTECH | 2100107914 | Replace demistor for A-1650 | Isolation & safing of HBDC-A-1660 | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 6 | 0 |  | 2024-08-19 | 2024-08-28 | 2024-08-19 | 2027-02-04 | 2024-08-18 | 10 | REL | APPR OPND | HB /D /60/HBDD-T-1601 | AIR/OIL SEPERATOR (TG) |  | A |  | MMR | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-TURB | 2100107914 | Replace demistor for A-1650 | Disconnect oil demister | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 12 | 0 |  | 2024-08-19 | 2024-08-28 | 2024-08-20 | 2027-02-04 | 2024-08-18 | 20 | REL | APPR OPND | HB /D /60/HBDD-T-1601 | AIR/OIL SEPERATOR (TG) |  | A |  | MMR | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-RIGG | 2100107914 | Replace demistor for A-1650 | Rigging Assistance | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 12 | 0 |  | 2024-08-19 | 2024-08-28 | 2024-08-22 | 2027-02-04 | 2024-08-18 | 25 | REL | APPR OPND | HB /D /60/HBDD-T-1601 | AIR/OIL SEPERATOR (TG) |  | A |  | MMR | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | MTN-TURB | 2100107914 | Replace demistor for A-1650 | Install new oil demister | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 12 | 0 |  | 2024-08-19 | 2024-08-28 | 2024-08-24 | 2027-02-04 | 2024-08-18 | 30 | REL | APPR OPND | HB /D /60/HBDD-T-1601 | AIR/OIL SEPERATOR (TG) |  | A |  | MMR | DK50
2026-W13-14 | 4 | NE | WDF | MTN-MECH | PRODTECH | 2100107914 | Replace demistor for A-1650 | De-Isolation and De-safing of HBDC-A-166 | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 6 | 0 |  | 2024-08-19 | 2024-08-28 | 2024-08-26 | 2027-02-04 | 2024-08-18 | 40 | REL | APPR OPND | HB /D /60/HBDD-T-1601 | AIR/OIL SEPERATOR (TG) |  | A |  | MMR | DK50
2024-W25-26 | 4 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200003231 | NO_Rust i foringer HBD nøddiesel 1710 | Offshore survey, scope survey | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2025-02-09 | 2025-02-09 | 2025-02-09 | 2016-10-14 | 2016-02-17 | 11 | REL | APPR OPND | HB /D /05/HBDE-G-1710 | EMERGENCY DIESEL GENERATOR | DK0500013006 | A |  | MMR | DK50
2024-W25-26 | 4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200003231 | NO_Rust i foringer HBD nøddiesel 1710 | Offshore survey, lifting inspection | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2025-02-09 | 2025-02-09 | 2025-02-09 | 2016-10-14 | 2016-02-17 | 12 | REL | APPR OPND | HB /D /05/HBDE-G-1710 | EMERGENCY DIESEL GENERATOR | DK0500013006 | A |  | MMR | DK50
2024-W43-44 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200005975 | Contingency valves for PVI on HBDC-V-345 | Contingency valves for PVI on HBDC-V-345 | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2022-03-29 | 2021-06-02 | 10 | REL | APPR OPND | HB /D /20/SYSTEM-20-MANUAL-VALVES | SYSTEM 20 MANUAL VALVES |  | A |  | MMS | DK50 |  |  | 2024-05-28
2026-W13-14 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010108 | Contingency materials for HBAA-V-3411. | Contingency materials for HBAA-V-3411 | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-03-09 | 2024-04-10 | 2024-03-09 | 2022-07-06 | 2022-04-07 | 10 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR | 99000099 | E |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200010108 | Contingency materials for HBAA-V-3411. | Rigging preparation | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 25 | 0 | W37-38 | 2024-03-09 | 2024-04-10 | 2024-03-09 | 2022-07-06 | 2022-04-07 | 20 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR | 99000099 | E |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-MECH | MTN-SCAF | 2200010108 | Contingency materials for HBAA-V-3411. | Scaffold | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 25 | 0 | W37-38 | 2024-03-09 | 2024-04-10 | 2024-03-14 | 2022-07-06 | 2022-04-07 | 30 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR | 99000099 | E |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200010108 | Contingency materials for HBAA-V-3411. | Isolate vavles | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 6 | 0 | W37-38 | 2024-03-09 | 2024-04-10 | 2024-03-19 | 2022-07-06 | 2022-04-07 | 40 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR | 99000099 | E |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010108 | Contingency materials for HBAA-V-3411. | Changeout valves | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 30 | 0 | W37-38 | 2024-03-09 | 2024-04-10 | 2024-03-20 | 2022-07-06 | 2022-04-07 | 50 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR | 99000099 | E |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200010108 | Contingency materials for HBAA-V-3411. | Rigging assistance | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 30 | 0 | W37-38 | 2024-03-09 | 2024-04-10 | 2024-03-26 | 2022-07-06 | 2022-04-07 | 60 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR | 99000099 | E |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200010108 | Contingency materials for HBAA-V-3411. | De-isolate | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 6 | 0 | W37-38 | 2024-03-09 | 2024-04-10 | 2024-04-01 | 2022-07-06 | 2022-04-07 | 70 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR | 99000099 | E |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200010108 | Contingency materials for HBAA-V-3411. | Rigging post work | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 20 | 0 | W37-38 | 2024-03-09 | 2024-04-10 | 2024-04-02 | 2022-07-06 | 2022-04-07 | 80 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR | 99000099 | E |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-MECH | MTN-SCAF | 2200010108 | Contingency materials for HBAA-V-3411. | Scaffold demol | REL PRT GMPS MANC PRC SETC | APPR PMAT RDBL | 20 | 0 | W37-38 | 2024-03-09 | 2024-04-10 | 2024-04-06 | 2022-07-06 | 2022-04-07 | 90 | REL | APPR OPND | HB /A /11/HBAA-V-3411 | PRODUCTION/TEST SEPARATOR | 99000099 | E |  | MMS | DK50
0 | 4 | OILEXPSD | WGN | MTN-MECH | MTN-MECH | 2200010130 | Contingency valves for HDA PVI | Contingency valves for HDA PVI | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2022-11-04 | 2022-06-07 | 10 | REL | APPR OPND | HD /A /27/SYSTEM-27-MANUAL-VALVES | SYSTEM-27-MANUAL-VALVES |  | E |  | MMS | DK60
0 | 4 | OILEXPSD | WGN | MTN-MECH | MTN-MECH | 2200010130 | Contingency valves for HDA PVI | materials | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2022-11-04 | 2022-06-07 | 20 | REL | APPR OPND | HD /A /27/SYSTEM-27-MANUAL-VALVES | SYSTEM-27-MANUAL-VALVES |  | E |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-CRAN | MTN-PIPF | 2200011731 | HDB/78 New air connection to wiper | Install air pips accoring to attached | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 12 | 0 | W47-48 | 2024-07-11 | 2024-07-12 | 2024-07-11 | 2023-02-27 | 2022-10-15 | 10 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200011731 | HDB/78 New air connection to wiper | Measuring of air hose acc. attached | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 2 | 0 | W47-48 | 2024-07-11 | 2024-07-12 | 2024-07-12 | 2023-02-27 | 2022-10-15 | 20 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | Max/min bestillings GE01 Halfdan B | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 10 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-02
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | Materialer | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 30 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-03
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 40 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-04
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | Mat order 17.03 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 50 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-05
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | DECK ORDER | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 60 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-06
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | TELECOM REP/RETUR | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 70 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-07
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | BESTILLING 20.03 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 80 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-08
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | LAB ORDER 20.03 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 90 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-09
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | Bestilling 22.03 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 100 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-10
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | Bestilling 22.03 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 110 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-11
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | Bestilling 22.03 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 120 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-12
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | Bestilling 24.03 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 130 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-13
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | Bestilling 24.03 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 140 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-14
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 28.03 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 150 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-15
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 29.03 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 160 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-16
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 30.03 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 170 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-17
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 14.04 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 180 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-18
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 15.04 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 190 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-19
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 15.04 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 200 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-20
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 17.04 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 210 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-21
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 21.04 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 220 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-22
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 26.04 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 230 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-23
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 0230 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 240 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-24
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 0240 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 250 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-25
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 0250 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 260 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-26
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 0260 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 270 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-27
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 0270 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 280 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-28
2024-W29-30 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000536 | Max/min bestillings GE01 Halfdan B 2019 | MAT ORDER 29.04 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-12-31 | 2019-12-31 | 290 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-29
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | DK48 SCAFF MATERIAL ORDER 2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 10 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-02
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | STILLADS GREJ 28-02-2020 L0512152 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 11 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-03
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026099 L0512471 02-03-2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 12 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-04
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026100 L0512471 02-03-2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 13 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-05
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026107 L0512471 03.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 14 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-06
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026110 L0512471 03.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 15 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-07
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026105 L0512471 03.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 16 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-08
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100023364 L0516416 05.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 17 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-09
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026117 L0516416 05.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 18 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-10
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026112 L0512471 05.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 19 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-11
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026062 L0512471 05.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 20 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-12
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100025918 L0516416 06.06.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 21 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-13
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100024258 L0516416 09.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 31 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-14
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100029451 L0512471 10.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 32 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-15
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026033 L0512471 10.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 33 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-16
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100029452 L0512471 10.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 34 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-17
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026097 L0512471 10.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 35 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-18
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026061 L0512471 10.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 36 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-19
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100024258 L0516416 05.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 37 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-20
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100025891 L0512471 10.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 38 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-21
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026113 L0512471 10.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 39 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-22
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026059 L0512471 10.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 40 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-23
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026096 L0512471 10.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 41 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-24
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100026101 L0512471 10.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 42 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-25
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100025892 L0512471 10.03.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 43 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-26
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 3 stk. Tifor taljer | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 53 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-27
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | Udløbet grej til LSI032 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 54 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-28
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2700001338 L0512471 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 64 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-29
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2400054906 L0512471 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 66 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-30
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | 2100024258 LSI032 2 X 15 ØJEBOLTE | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 76 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-07-01
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | Urgent slings 30.05.2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 86 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-07-02
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | MATERIAL CAMPAIGN 09.06.20 HBC | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 96 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-07-03
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | Urgent Lifting Eye Theipa | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 106 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-07-04
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | Matt. best. 29/6 SCAFF 2400054908 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 116 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-07-05
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | koblings kasser bestil HBA | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 126 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-07-06
2024-W25-26 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000579 | DK48 SCAFF MATERIAL ORDER 2020 | koblings kasse + bsk bestilt HBA | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2020-01-01 | 136 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-07-07
0 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000641 | DK49 SCAFF MATERIAL ORDER 2020/21 | Muehlhan So-312 + best til V-3401 | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-01-04 | 2022-01-04 | 2022-01-04 | 2020-12-31 | 2020-01-01 | 104 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | CON | DK60
0 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000643 | DK49 PAINT MATERIAL ORDER 2020 | DK49 PAINT MATERIAL ORDER 2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2020-12-31 | 2020-01-01 | 10 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | CON | DK60
0 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000643 | DK49 PAINT MATERIAL ORDER 2020 | HDA PVI WO: 2400064217 V-3401 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2020-12-31 | 2020-01-01 | 20 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | CON | DK60
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | DK50 PAINT MATERIAL ORDER 2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 10 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | Matt bestilling 2/9-20 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 20 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | Matt bestilling 29/9-20 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 30 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | Sundstrøm Adapter Paint | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 31 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | Propan Detektor 2 stk | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 32 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | Ekstra dragter 1188580 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 33 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | GLYCOL TOG 2020 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 43 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | HBPVI20 26.01.21 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 44 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | 2300001472 27.01.21 HUB LIFTING MUEHL | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 54 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | 2800013548 28.01.21 SCAFFPADS | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 64 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | HBPVI-2021 V-3451 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 74 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | Regndragter PVI 2021 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 75 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | 2800008136 23.04.21 MAT WASH.COMP MM MUE | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 85 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | 2800008173 26.04.21 MAT BAG,HOOD,SUIT MM | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 95 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | 2800008136 27.05 TMP297 SAND | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 105 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | Mejsler | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 115 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | 2300001472 31.08 GLOVE,CLEAN SUIT V3411 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 125 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | 2300001472 31.08 BOOTS PVI3411 MUE | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 135 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | 2100047291 08.09 TOOL,NEEDLE,POT MUE | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 145 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W39-40 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001472 | DK50 PAINT MATERIAL ORDER 2020/21 | 2300001472 20.09 BOOTS,SUIT DUST MM | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-07-06 | 2020-09-09 | 155 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
0 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001495 | DK60 - CONSUMABLE PROD - CHEMICALS | DK60 - CONSUMABLE PROD - CHEMICALS | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2021-07-06 | 2020-09-09 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
0 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001495 | DK60 - CONSUMABLE PROD - CHEMICALS | rental containers from Certex | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2021-07-06 | 2020-09-09 | 20 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
0 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001495 | DK60 - CONSUMABLE PROD - CHEMICALS | Rental equipment from Ocean Team | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2021-07-06 | 2020-09-09 | 40 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
0 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001495 | DK60 - CONSUMABLE PROD - CHEMICALS | new filters | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2021-07-06 | 2020-09-09 | 70 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
0 | 4 | NE | WRO | MTN-TURB | MTN-TURB | 2300001532 | DK60 - CONSUMABLE MTN - TURB (ROTATING) | Materiels HMI | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-07-26 | 2020-09-29 | 20 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMR | DK60
2024-W23-24 | 4 |  | WRO | PRODTECH | PRODTECH | 2300002633 | DK50 - CONSUMABLE PROD - OCEAN TEAM | DK50 - CONSUMABLE PROD - CHEMICALS | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2022-06-06 | 2021-08-10 | 10 | REL | APPR OPND | HB /D /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | PRD | DK50
2024-W27-28 | 4 | NOSD | WRO | MTN-TURB | MTN-TURB | 2300002905 | DK50 - CONSUMABLE MTN - TURB (ROTATING) | DK50 - CONSUMABLE MTN - TURB (ROTATING) | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-03 | 2021-11-07 | 10 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMR | DK50 |  |  | 2024-05-25
2024-W27-28 | 4 | NOSD | WRO | MTN-TURB | MTN-TURB | 2300002905 | DK50 - CONSUMABLE MTN - TURB (ROTATING) | ekstra power supply | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-03 | 2021-11-07 | 20 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMR | DK50 |  |  | 2024-05-26
2024-W27-28 | 4 | NOSD | WRO | MTN-TURB | MTN-TURB | 2300002905 | DK50 - CONSUMABLE MTN - TURB (ROTATING) | Rental Equipment | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-03 | 2021-11-07 | 30 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMR | DK50 |  |  | 2024-05-27
2024-W27-28 | 4 | NOSD | WRO | MTN-TURB | MTN-TURB | 2300002905 | DK50 - CONSUMABLE MTN - TURB (ROTATING) | Kema Anti seize compound | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-03 | 2021-11-07 | 40 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMR | DK50 |  |  | 2024-05-28
2024-W27-28 | 4 | NOSD | WRO | MTN-TURB | MTN-TURB | 2300002905 | DK50 - CONSUMABLE MTN - TURB (ROTATING) | L303 Sov Solar | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-03 | 2021-11-07 | 50 | PCNF REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMR | DK50 |  |  | 2024-05-29
2024-W27-28 | 4 | NOSD | WRO | MTN-TURB | MTN-TURB | 2300002905 | DK50 - CONSUMABLE MTN - TURB (ROTATING) | Riste til Flasker i watermist skids | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-03 | 2021-11-07 | 60 | PCNF REL | INIT OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMR | DK50 |  |  | 2024-05-30
2024-W27-28 | 4 | NOSD | WRO | MTN-TURB | MTN-TURB | 2300002905 | DK50 - CONSUMABLE MTN - TURB (ROTATING) | ekstra power supply | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-09-03 | 2021-11-07 | 70 | PCNF REL | INIT OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MMR | DK50 |  |  | 2024-05-31
0 | 4 | NOSD | WRO | MTN-CRAN | MTN-CRAN | 2300003389 | DK60 - CONSUMABLE MTN - CRAN (CRANE) | DK60 - CONSUMABLE MTN - CRAN (CRANE) | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 6 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-05 | 2022-05-09 | 10 | PCNF REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMS | DK60
2024-W35-36 | 4 | NOSD | WRO | MTN-ROPE | MTN-ROPE | 2300003421 | Halfdan BC DO NOT USE ANY MORE | MM Survey / ISC - 3D scanning | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2023-03-26 | 2022-05-30 | 100 | REL | INIT OPND | HB /C /86/FABRIC-MAINTENANCE | HBC PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50 |  |  | 2024-06-02
0 | 4 | NOSD | WRO | MTN-MECH | MTN-MECH | 2300003808 | DK60 - Replaced by 2300005427 | DK60 - CONSUMABLE MTN - MECH | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-07-04 | 2022-09-07 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMS | DK60
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | DK50 HALFDAN B SKRUMS MATRIAL ORDER | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 10 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | DK50 HALFDAN B SKRUMS MATRIAL ORDER 2 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 20 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | DK50 HALFDAN B SKRUMS MATRIAL ORDER 3 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 30 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | DK50 HALFDAN B SKRUMS MATRIAL ORDER 4 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 40 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | DK50 HALFDAN B SKRUMS MATRIAL ORDER 5 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 50 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | ORDERING OF CAMERA 26-04-2022 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 60 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | DK50 HALFDAN B SKRUMS MATRIAL ORDER 6 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 70 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | DK50 HALFDAN B FLUSH RIG 23-05-22 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 80 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | DK50 HALFDAN B SKRUMS MATRIAL ORDER 7 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 90 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | SELE OG JOJO SKIFT 03-06-22 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 100 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | DIGITAL GAUGE BESTILLING HALFDAN B | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 110 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | OPRIGNING GREJ/STILLADS ALTRAD 08-07-22 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 120 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | SMEDE BESTILLING HALFDAN B 20-07-22 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 130 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | VÆRKTØJ BESTILLING TIL HALFDAN B TMP297 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 140 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | DK50 HALFDAN B SKRUMS MATRIAL ORDER 8 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 150 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | SORT QC BESTILLING | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 160 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | SCAFF BESTILLING 08-08-2022 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 170 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | DIVERSE VARE BESTILLING 12-08-2022 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 180 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | SCAFF BESTILLING 15-08-2022 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 190 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | SMEDE BESTILLING ICE TEAM 22.08.22 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 200 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W29-30 | 3 |  | WRO | PRODTECH | PRODTECH | 2300003838 | DK50 HALFDAN B ICE Team Materials | SMEDE BESTILLING ICE TEAM 24.08.22 | REL GMPS MANC PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-16 | 2022-04-06 | 210 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 4 | NOSD | WRO | PRODTECH | PRODTECH | 2300003904 | DK50 - CONSUMABLE PROD - SAFETY EQ | DK50 - CONSUMABLE PROD - SAFETY EQ | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-10-26 | 2022-10-26 | 2022-10-26 | 2023-08-22 | 2022-10-26 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK50 |  |  | 2024-06-02
0 | 4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004023 | DK60 - CONSUMABLE PROD - OIL | DK60 - CONSUMABLE PROD - OIL | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2022-12-31 | 2022-12-31 | 2022-12-31 | 2025-06-18 | 2022-12-31 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
0 | 4 |  | WRO | PRODTECH | PRODTECH | 2300004248 | DK60 - CONSUMABLE PROD - OFFICE | DK60 - CONSUMABLE PROD - OFFICE | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2025-10-11 | 2023-04-25 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MIN | DK60
0 | 4 |  | WRO | PRODLABO | PRODLABO | 2300005424 | DK60 - CONSUMABLE PROD - LAB | DK60 - CONSUMABLE PROD - LAB | REL GMPS MACM PPRT PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2026-04-03 | 2023-10-16 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
0 | 4 | NOSD | WRO | PRODTECH | PRODTECH | 2300005713 | DK60 - CONSUMABLE PROD - SAFETY EQ | DK60 - CONSUMABLE PROD - SAFETY EQ | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2026-05-08 | 2023-11-20 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
2024-W21-22 | 4 | NOSD | WRO | PRODTECH | PRODTECH | 2300005714 | DK50 - CONSUMABLE PROD - OIL | DK50 - CONSUMABLE PROD - OIL | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2026-05-08 | 2023-11-20 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK50 |  |  | 2024-06-02
2024-W33-34 | 4 |  | WRO | PRODTECH | PRODTECH | 2300006189 | DK50 - CONSUMABLE PROD - OFFICE | DK50 - CONSUMABLE PROD - OFFICE | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-01-14 | 2024-01-14 | 2024-01-14 | 2026-07-02 | 2024-01-14 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK50
2024-W23-24 | 4 |  | WRO | PRODTECH | PRODTECH | 2300006993 | DK50 - CONSUMABLE PROD - TOOLS | DK50 - CONSUMABLE PROD - TOOLS | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2026-10-17 | 2024-04-30 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK50
2024-W23-24 | 4 |  | WRO | PRODTECH | PRODTECH | 2300007083 | DK50 - CONSUMABLE PROD - PPE | DK50 - CONSUMABLE PROD - PPE | REL GMPS PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-05-11 | 2024-05-11 | 2024-05-11 | 2026-10-28 | 2024-05-11 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK50
2024-W23-24 | 4 | NOSD | WRO | MTN-ROUS | MTN-ROUS | 2300007127 | DK50 - CONSUMABLE PROD - DECK | DK50 - CONSUMABLE PROD - DECK | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2026-11-04 | 2024-05-18 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MIN | DK50 |  |  | 2024-05-20
2024-W39-40 | 4 | NOSD | WRO | PRODLABO | PRODLABO | 2300007130 | DK50 - CONSUMABLE PROD - LAB | DK50 - CONSUMABLE PROD - LAB | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2026-11-04 | 2024-05-18 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MIN | DK50 |  |  | 2024-06-02
0 | 4 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300007171 | DK60 - CONSUMABLE MTN - ELEC | DK60 - CONSUMABLE MTN - ELEC | REL GMPS PRC SETC | APPR PMAT RDBL | 0 | 0 | 24-W21-22 | 2024-05-22 | 2024-05-22 | 2024-05-22 | 2026-11-08 | 2024-05-22 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MIN | DK60
2024-W29-30 | 4 |  | WRO | PRODTECH | PRODTECH | 2300007174 | DK50 - CONSUMABLE PROD - CHEMICALS | DK50 - CONSUMABLE PROD - CHEMICALS | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | 2026-11-08 | 2024-05-22 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK50
0 | 4 | NE | WRO | MTN-INST | MTN-INST | 2300007445 | DK60 - CONSUMABLE MTN - INST | DK60 - CONSUMABLE MTN - INST | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2026-12-04 | 2024-06-17 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MIN | DK60
2024-W31-32 | 4 | NOSD | WRO | MTN-INST | MTN-INST | 2300007451 | DK50 - CONSUMABLE MTN - ELEC | DK50 - CONSUMABLE MTN - ELEC | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2026-12-05 | 2024-06-18 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MIN | DK50 |  |  | 2024-05-21
2024-W23-24 | 4 | NE | WRO | MTN-INST | MTN-INST | 2300007758 | DK50 - CONSUMABLE MTN - INST | DK50 - CONSUMABLE MTN - INST | REL GMPS PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-07-27 | 2024-07-27 | 2024-07-27 | 2027-01-13 | 2024-07-27 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MIN | DK50 |  |  | 2024-05-21
2024-W21-22 | 4 | NOSD | WRO | MTN-MECH | MTN-INST | 2300007839 | DK50 - CONSUMABLE MTN - MECH (Static) | DK50 - CONSUMABLE MTN - MECH (Static) | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-08-05 | 2024-08-05 | 2024-08-05 | 2027-01-22 | 2024-08-05 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MIN | DK50 |  |  | 2024-05-21
0 | 4 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300007984 | DK60 - CONSUMABLE MTN - TELE | DK60 - CONSUMABLE MTN - TELE | REL GMPS PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2027-02-12 | 2024-08-26 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MIN | DK60
0 | D | NOSD | WPM | MTN-INST | MTN-INST | 2400291822 | 6M PROCESS CALIBRATION EQUIPMENT HDA | PROCESS CALIBRATION EQUIPMENT | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2024-04-15 | 2024-04-16 | 2024-04-15 | 2023-12-15 | 2023-11-20 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A | DKHD-2026 | MIN | DK60 | IN0113
0 | D | NOSD | WPM | MTN-INST | MTN-INST | 2400291822 | 6M PROCESS CALIBRATION EQUIPMENT HDA | New items from backload ret doc 1056756 | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-04-15 | 2024-04-16 | 2024-04-16 | 2023-12-15 | 2023-11-20 | 30 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A | DKHD-2026 | MIN | DK60 | IN0113
0 | D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308632 | 1Y HV TESTERS/EARTHING EQUIPMENT HDA | HV TESTERS/EARTHING EQUIPMENT HDA | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 3 | 0 | W13-W14 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-17 | 2024-01-30 | 10 | REL | APPR OPND | HD /A /84/TEST-EQUIPMENT | TEST EQUIPMENT |  | A | DKHD-2023 | MEL | DK60 | EL0043 | PROK
2026-W13-14 | C | HBAT-SEP | WPM | MTN-INST | PRODTECH | 2400315178 | 2Y HBAA-V-3411 - METERING | ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2024-09-18 | 2024-09-25 | 2024-09-18 | 2024-04-11 | 2024-02-16 | 10 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6001 | MIN | DK50 | IN0014
2026-W13-14 | C | HBAT-SEP | WPM | MTN-INST | MTN-MECH | 2400315178 | 2Y HBAA-V-3411 - METERING | DISASSEMBLY OF METER | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 16 | 0 |  | 2024-09-18 | 2024-09-25 | 2024-09-19 | 2024-04-11 | 2024-02-16 | 20 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6001 | MIN | DK50 | IN0014
2026-W13-14 | C | HBAT-SEP | WPM | MTN-INST | MTN-RIGG | 2400315178 | 2Y HBAA-V-3411 - METERING | ASISTANCE FOR METERING MAINT | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 6 | 0 |  | 2024-09-18 | 2024-09-25 | 2024-09-20 | 2024-04-11 | 2024-02-16 | 30 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6001 | MIN | DK50 | IN0014
2026-W13-14 | C | HBAT-SEP | WPM | MTN-INST | MTN-INST | 2400315178 | 2Y HBAA-V-3411 - METERING | HBAA-V-3411 - METERING | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 6 | 0 |  | 2024-09-18 | 2024-09-25 | 2024-09-22 | 2024-04-11 | 2024-02-16 | 50 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6001 | MIN | DK50 | IN0014
2026-W13-14 | C | HBAT-SEP | WPM | MTN-INST | MTN-MECH | 2400315178 | 2Y HBAA-V-3411 - METERING | ASSEMBLY OF METER | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 16 | 0 |  | 2024-09-18 | 2024-09-25 | 2024-09-23 | 2024-04-11 | 2024-02-16 | 60 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6001 | MIN | DK50 | IN0014
2026-W13-14 | C | HBAT-SEP | WPM | MTN-INST | PRODTECH | 2400315178 | 2Y HBAA-V-3411 - METERING | DE-ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2024-09-18 | 2024-09-25 | 2024-09-24 | 2024-04-11 | 2024-02-16 | 70 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6001 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400322715 | 1Y HBDC-FE-575501 - CO2 METERING | ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2025-02-01 | 2025-02-05 | 2025-02-01 | 2024-05-19 | 2024-04-13 | 10 | REL | APPR OPND | HB /D /70/HBDC-FIT-575501 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6017 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-RIGG | 2400322715 | 1Y HBDC-FE-575501 - CO2 METERING | RIGGING CORIOLIS METER | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 8 | 0 |  | 2025-02-01 | 2025-02-05 | 2025-02-01 | 2024-05-19 | 2024-04-13 | 15 | REL | APPR OPND | HB /D /70/HBDC-FIT-575501 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6017 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400322715 | 1Y HBDC-FE-575501 - CO2 METERING | DISASSEMBLY OF METERING | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2025-02-01 | 2025-02-05 | 2025-02-02 | 2024-05-19 | 2024-04-13 | 20 | REL | APPR OPND | HB /D /70/HBDC-FIT-575501 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6017 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-INST | 2400322715 | 1Y HBDC-FE-575501 - CO2 METERING | HBDC-FE-575501 - CO2 METERING | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2025-02-01 | 2025-02-05 | 2025-02-03 | 2024-05-19 | 2024-04-13 | 30 | REL | APPR OPND | HB /D /70/HBDC-FIT-575501 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6017 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400322715 | 1Y HBDC-FE-575501 - CO2 METERING | ASSEMBLY OF METERING | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2025-02-01 | 2025-02-05 | 2025-02-04 | 2024-05-19 | 2024-04-13 | 40 | REL | APPR OPND | HB /D /70/HBDC-FIT-575501 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6017 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400322715 | 1Y HBDC-FE-575501 - CO2 METERING | DE-ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2025-02-01 | 2025-02-05 | 2025-02-05 | 2024-05-19 | 2024-04-13 | 50 | REL | APPR OPND | HB /D /70/HBDC-FIT-575501 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6017 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400329566 | 1Y ANTI-FOULING PKG TEST HBCM-A-5233 | ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-06-15 | 2024-05-10 | 10 | REL | APPR OPND | HB /C /52/HBCM-A-5233 | SEAWATER ANTI-FOULING UNIT |  |  | DKHB-0675 | MMS | DK50 | MS0134
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-INST | 2400329566 | 1Y ANTI-FOULING PKG TEST HBCM-A-5233 | ANTI-FOULING PKG TEST HBCM-A-5233 | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-06-15 | 2024-05-10 | 20 | REL | APPR OPND | HB /C /52/HBCM-A-5233 | SEAWATER ANTI-FOULING UNIT |  |  | DKHB-0675 | MMS | DK50 | MS0134
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329566 | 1Y ANTI-FOULING PKG TEST HBCM-A-5233 | ANTI-FOULING PKG TEST HBCM-A-5233 | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 8 | 0 |  | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-06-15 | 2024-05-10 | 30 | REL | APPR OPND | HB /C /52/HBCM-A-5233 | SEAWATER ANTI-FOULING UNIT |  |  | DKHB-0675 | MMS | DK50 | MS0134
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400329566 | 1Y ANTI-FOULING PKG TEST HBCM-A-5233 | ANTI-FOULING PKG TEST HBCM-A-5233 | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 8 | 0 |  | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-06-15 | 2024-05-10 | 40 | REL | APPR OPND | HB /C /52/HBCM-A-5233 | SEAWATER ANTI-FOULING UNIT |  |  | DKHB-0675 | MMS | DK50 | MS0134
2026-W13-14 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400329566 | 1Y ANTI-FOULING PKG TEST HBCM-A-5233 | DE-ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-06-15 | 2024-05-10 | 50 | REL | APPR OPND | HB /C /52/HBCM-A-5233 | SEAWATER ANTI-FOULING UNIT |  |  | DKHB-0675 | MMS | DK50 | MS0134
2026-W13-14 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400334602 | 1Y HBDC-FE-575402 - CO2 METERING | ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-06-13 | 2024-06-16 | 2024-06-13 | 2024-07-19 | 2024-06-13 | 10 | REL | APPR OPND | HB /D /70/HBDC-FIT-575402 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6021 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-INST | 2400334602 | 1Y HBDC-FE-575402 - CO2 METERING | RIGGER ASSISTANCE | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 3 | 0 |  | 2024-06-13 | 2024-06-16 | 2024-06-13 | 2024-07-19 | 2024-06-13 | 15 | REL | APPR OPND | HB /D /70/HBDC-FIT-575402 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6021 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400334602 | 1Y HBDC-FE-575402 - CO2 METERING | DISASSEMBLY OF METERING | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2024-06-13 | 2024-06-16 | 2024-06-13 | 2024-07-19 | 2024-06-13 | 20 | REL | APPR OPND | HB /D /70/HBDC-FIT-575402 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6021 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-INST | 2400334602 | 1Y HBDC-FE-575402 - CO2 METERING | HBDC-FE-575402 - CO2 METERING | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 2.5 | 0 |  | 2024-06-13 | 2024-06-16 | 2024-06-14 | 2024-07-19 | 2024-06-13 | 30 | REL | APPR OPND | HB /D /70/HBDC-FIT-575402 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6021 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400334602 | 1Y HBDC-FE-575402 - CO2 METERING | ASSEMBLY OF METERING | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 4 | 0 |  | 2024-06-13 | 2024-06-16 | 2024-06-15 | 2024-07-19 | 2024-06-13 | 40 | REL | APPR OPND | HB /D /70/HBDC-FIT-575402 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6021 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400334602 | 1Y HBDC-FE-575402 - CO2 METERING | DE-ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR PMAT RDBL | 1 | 0 |  | 2024-06-13 | 2024-06-16 | 2024-06-16 | 2024-07-19 | 2024-06-13 | 50 | REL | APPR OPND | HB /D /70/HBDC-FIT-575402 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6021 | MIN | DK50 | IN0014
2026-W13-14 | 2 |  | WSO | WELLSUPV | WELLSUPV | 2900001345 | HBA27B Stimulation | HBA27B Stimulation | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-03-25 | 2024-05-07 | 2024-03-25 | 2024-04-06 | 2024-02-21 | 10 | PCNF REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | E |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | WELLSUPV | 2900001345 | HBA27B Stimulation | HBA Dogis Rental Frac Tree | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-03-25 | 2024-05-07 | 2024-03-25 | 2024-04-06 | 2024-02-21 | 20 | PCNF REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | E |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | WELLSUPV | 2900001345 | HBA27B Stimulation | HBA Well Service XO Package | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 0 | 0 |  | 2024-03-25 | 2024-05-07 | 2024-03-25 | 2024-04-06 | 2024-02-21 | 30 | PCNF REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | E |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | PRODTECH | 2900001345 | HBA27B Stimulation | Production Support | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 24 | 0 |  | 2024-03-25 | 2024-05-07 | 2024-03-25 | 2024-04-06 | 2024-02-21 | 40 | PCNF REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | E |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | MTN-SCAF | 2900001345 | HBA27B Stimulation | Scaff Support Rig Up / Rig Down | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 72 | 25 |  | 2024-03-25 | 2024-05-07 | 2024-03-31 | 2024-04-06 | 2024-02-21 | 50 | PCNF REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | E |  | WLD | DK50
2026-W13-14 | 2 |  | WSO | WELLSUPV | MTN-ROUS | 2900001345 | HBA27B Stimulation | Crane Support Internal | REL PCNF GMPS MANC PRC SETC | APPR PMAT RDBL | 240 | 0 |  | 2024-03-25 | 2024-05-07 | 2024-04-07 | 2024-04-06 | 2024-02-21 | 60 | PCNF REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | E |  | WLD | DK50
2026-W13-14 | A | HBD-IPHP | WPM | MTN-TURB | MTN-TURB | 2400308686 | 8000H TURBINE SKID, COUNTER | OVERHAUL | REL GMPS MACM PRC SETC | APPR PMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2024-10-03 | 2024-10-12 | 2024-10-03 | 2024-03-17 | 2024-02-16 | 10 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | G | DKHB-0478 | MMR | DK50 | MR0094 | PTW MISS
2026-W13-14 | A | HBD-IPHP | WPM | MTN-TURB | VEN-MECH | 2400308686 | 8000H TURBINE SKID, COUNTER | OVERHAUL SUPPORT-VENDOR | REL GMPS MACM PRC SETC | APPR PMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2024-10-03 | 2024-10-12 | 2024-10-05 | 2024-03-17 | 2024-02-16 | 20 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | G | DKHB-0478 | MMR | DK50 | MR0094 | PTW MISS
2026-W13-14 | A | HBD-IPHP | WPM | MTN-TURB | MTN-INST | 2400308686 | 8000H TURBINE SKID, COUNTER | FUNCTION TEST & CALIBRATION | REL GMPS MACM PRC SETC | APPR PMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-03 | 2024-10-12 | 2024-10-06 | 2024-03-17 | 2024-02-16 | 30 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | G | DKHB-0478 | MMR | DK50 | MR0094 | PTW MISS
2026-W13-14 | A | HBD-IPHP | WPM | MTN-TURB | MTN-TURB | 2400308686 | 8000H TURBINE SKID, COUNTER | OEM SERVICE | REL GMPS MACM PRC SETC | APPR PMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 9 | 0 |  | 2024-10-03 | 2024-10-12 | 2024-10-09 | 2024-03-17 | 2024-02-16 | 40 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | G | DKHB-0478 | MMR | DK50 | MR0094 | PTW MISS
2026-W13-14 | A | HBD-IPHP | WPM | MTN-TURB | MTN-ELEC | 2400308686 | 8000H TURBINE SKID, COUNTER | ELECTRICAL CHECK | REL GMPS MACM PRC SETC | APPR PMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-10-03 | 2024-10-12 | 2024-10-11 | 2024-03-17 | 2024-02-16 | 50 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | G | DKHB-0478 | MMR | DK50 | MR0094 | PTW MISS
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-SCAF | 2100022373 | FMP 100631976 to be approved before rele | L3 Rig-up scaffold | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 18 | 0 |  | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2019-11-09 | 2019-08-11 | 10 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-RIGG | 2100022373 | FMP 100631976 to be approved before rele | L3 Rig-up hoist for removal | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 10 | 0 |  | 2025-01-01 | 2025-01-09 | 2025-01-02 | 2019-11-09 | 2019-08-11 | 20 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100022373 | FMP 100631976 to be approved before rele | L2 Isolate line HBA-6"-GPS-294017-FE | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-09 | 2025-01-04 | 2019-11-09 | 2019-08-11 | 30 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100022373 | FMP 100631976 to be approved before rele | L2 Remove inserted spool piece | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-09 | 2025-01-04 | 2019-11-09 | 2019-08-11 | 40 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100022373 | FMP 100631976 to be approved before rele | L2 Install new ball DBB valve HCV-29200 | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-09 | 2025-01-05 | 2019-11-09 | 2019-08-11 | 50 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | QAQCMECH | 2100022373 | FMP 100631976 to be approved before rele | L2 Leak Test HCV-29200 | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-09 | 2025-01-06 | 2019-11-09 | 2019-08-11 | 60 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100022373 | FMP 100631976 to be approved before rele | L2 De-isolate line HBA-6"-GPS-294017-FE | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-09 | 2025-01-06 | 2019-11-09 | 2019-08-11 | 70 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-RIGG | 2100022373 | FMP 100631976 to be approved before rele | L3 Rig-down hoist | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-09 | 2025-01-07 | 2019-11-09 | 2019-08-11 | 80 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-SCAF | 2100022373 | FMP 100631976 to be approved before rele | L3 Rig-down scaffold | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 14 | 0 |  | 2025-01-01 | 2025-01-09 | 2025-01-07 | 2019-11-09 | 2019-08-11 | 90 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100024716 | DGS:607240 Replace HBAA-XCV-38033 | Megger test of heat tracing | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2019-07-28 | 2019-07-08 | 115 | REL | APPR OPND | HB /A /50/HBAA-XCV-38033 | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100024716 | DGS:607240 Replace HBAA-XCV-38033 | L3 Re-install insulation | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 2 | 1 | OIM 10 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2019-07-28 | 2019-07-08 | 120 | PCNF REL | APPR OPND | HB /A /50/HBAA-XCV-38033 | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100026211 | HBAA-XCV-34008 changeout bolt and gasket | L3 buildup small scafford | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 18 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2021-01-14 | 2020-01-20 | 5 | REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100026211 | HBAA-XCV-34008 changeout bolt and gasket | L3 Isolation of HBAA-XCV-34008 hydraulic | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2021-01-14 | 2020-01-20 | 10 | REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100026211 | HBAA-XCV-34008 changeout bolt and gasket | L3 Changeout bolt and gasket on blind | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2021-01-14 | 2020-01-20 | 20 | REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100026211 | HBAA-XCV-34008 changeout bolt and gasket | L3 De-Isolation/test HBAA-XCV-34008 hydr | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-04 | 2021-01-14 | 2020-01-20 | 30 | REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100026211 | HBAA-XCV-34008 changeout bolt and gasket | L3 Build down small scafford | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 14 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2021-01-14 | 2020-01-20 | 40 | REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2024-W33-34 | 3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100026263 | Changeout complete choke CVA-300207 HBB0 | L3 install lagging | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 3.4 | 0 | W33-34 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2019-05-25 | 2019-04-15 | 160 | PCNF REL | APPR OPND | HB /B /55/HBBB-CVA-300207 | CHOKE VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Rig up for move recever | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 39 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 5 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-PIPF | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Find material, tools and brake flange | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 39 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 6 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | PRODTECH | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Isolate - flush - braking flange | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 4 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 7 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-PIPF | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Install blind hubs and flange | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 16 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 8 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Move reciever 5-10cm vest | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 18 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 9 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Rig-up hoist for change valve | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 24 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 10 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | PRODTECH | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Isolate XCV and equipment | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 5 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-20 | 2020-05-05 | 2020-02-05 | 20 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | VEN-ELEC | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Dis-connect cables | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 4 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-21 | 2020-05-05 | 2020-02-05 | 30 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-INST | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Dis-connect hydraulics | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 6 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-21 | 2020-05-05 | 2020-02-05 | 40 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-PIPF | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Replace XCV-38308 old - new | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 24 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-23 | 2020-05-05 | 2020-02-05 | 50 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-MECH | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Blinds for Isolate | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 0 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 55 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Assist in replacement | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 60 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-20 | 2020-05-05 | 2020-02-05 | 60 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-INST | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Connect hydraulics | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 6 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-24 | 2020-05-05 | 2020-02-05 | 70 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | VEN-ELEC | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Connect cables | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 4 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-25 | 2020-05-05 | 2020-02-05 | 80 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-PIPF | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Braking flange/ prepare install reciever | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 8 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 81 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | PRODTECH | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Measure - flush - braking flange | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 4 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 82 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Rig - move reciever - final position | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 39 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 83 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-PIPF | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | connect new xcv and reciever tight bolt | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 36 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 84 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | VEN-ELEC | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Functional test | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 3 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-25 | 2020-05-05 | 2020-02-05 | 90 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | PRODTECH | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | De-isolate XCV and equipment | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 5 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-26 | 2020-05-05 | 2020-02-05 | 100 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Remove hoist and clean-up | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 21 | 0 | OIM 10 | 2024-09-18 | 2024-09-28 | 2024-09-27 | 2020-05-05 | 2020-02-05 | 110 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-MECH | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Driving plates | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 0 | 0 |  | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 130 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-MECH | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Valve cradle and support column | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 0 | 0 |  | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 140 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-MECH | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Extra equipment | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 0 | 0 |  | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 170 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-MECH | 2100026517 | DGS 628396 HBBA-XCV-38308 EP-3823 repl. | Increase of PO 4300032636 | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWSC RDBL | 0 | 0 |  | 2024-09-18 | 2024-09-28 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 220 | REL | APPR OPND | HB /B /34/HBBA-XCV-38308 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Install rigging equipment | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 2 | 0 |  | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 10 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Line BOC | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 2 | 0 |  | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 20 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Inhibit ESD signals before isolation | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 0.5 | 0 | W09-10 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 30 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-INST | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Isolate instrument device | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 | W09-10 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 40 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Remove old valve | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1.5 | 0 |  | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 50 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Rig out old valve | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1.5 | 0 |  | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 60 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Rigg in new valve | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1.5 | 0 |  | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 70 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Install new valve | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1.5 | 0 |  | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 80 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-INST | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Install/Change Instrument Piping | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 2 | 0 | W09-10 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 90 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-INST | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Deisolate after repair | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 0.5 | 0 | W09-10 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 100 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-INST | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Test after completed work | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 | W09-10 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 110 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Deisolate line | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 120 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Remove inhibit Input device | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 0.5 | 0 | W09-10 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 130 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Remove rigging equipment | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 140 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100035233 | Minor seep on hyd. sup. - FCV-29143 | Additional materials | REL CSER GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 0 | 0 |  | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2020-09-07 | 2020-07-29 | 999 | REL | APPR OPND | HB /A /37/HBAA-FCV-29143 | LIFT GAS FLOW CONTROL VALVE |  | D |  | MMS | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-RIGG | 2100065968 | Hard to operate HCV-038064 | Prepare equip/carryout Lifting operation | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2022-11-23 | 2022-06-26 | 10 | REL | APPR OPND | HB /D /01/HBDB-HCV-038064 | BUTTERFLY VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100065968 | Hard to operate HCV-038064 | Production isolation | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-11-23 | 2022-06-26 | 20 | REL | APPR OPND | HB /D /01/HBDB-HCV-038064 | BUTTERFLY VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100065968 | Hard to operate HCV-038064 | Replace HCV-038064 | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 12 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2022-11-23 | 2022-06-26 | 30 | REL | APPR OPND | HB /D /01/HBDB-HCV-038064 | BUTTERFLY VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100065968 | Hard to operate HCV-038064 | Production de-isolation w leaktest | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2022-11-23 | 2022-06-26 | 40 | REL | APPR OPND | HB /D /01/HBDB-HCV-038064 | BUTTERFLY VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBA10-GL | WDF | MTN-INST | PRODTECH | 2100074858 | Seep on DBB to HBAA-PIT-301001 | Isolate and Inhibit gaslift line | REL PRT GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-03-15 | 2022-10-31 | 5 | REL | APPR OPND | HB /A /37/HBAA-PIT-301001 | C - CASING PRESSURE INDIC. TRANSMITTER | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HBA10-GL | WDF | MTN-INST | MTN-INST | 2100074858 | Seep on DBB to HBAA-PIT-301001 | Isolate Pressure transmitter | REL PRT GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-03-15 | 2022-10-31 | 10 | REL | APPR OPND | HB /A /37/HBAA-PIT-301001 | C - CASING PRESSURE INDIC. TRANSMITTER | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HBA10-GL | WDF | MTN-INST | MTN-MECH | 2100074858 | Seep on DBB to HBAA-PIT-301001 | Replace SDBB valve for Pressure transmit | REL PRT GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 2.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-03-15 | 2022-10-31 | 30 | REL | APPR OPND | HB /A /37/HBAA-PIT-301001 | C - CASING PRESSURE INDIC. TRANSMITTER | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HBA10-GL | WDF | MTN-INST | MTN-INST | 2100074858 | Seep on DBB to HBAA-PIT-301001 | Deisolate Pressure transmitter | REL PRT GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2023-03-15 | 2022-10-31 | 40 | REL | APPR OPND | HB /A /37/HBAA-PIT-301001 | C - CASING PRESSURE INDIC. TRANSMITTER | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HBA10-GL | WDF | MTN-INST | PRODTECH | 2100074858 | Seep on DBB to HBAA-PIT-301001 | Deisolate and repeal inhibits from gasli | REL PRT GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2023-03-15 | 2022-10-31 | 50 | REL | APPR OPND | HB /A /37/HBAA-PIT-301001 | C - CASING PRESSURE INDIC. TRANSMITTER | 99000119 | E |  | MIN | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078740 | DP-1960 - CB04 def. power supply | Additional parts | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-05-18 | 2023-01-03 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A04-02 | OVERCUR AND E/FAULT RELAY BUS-COUPLER AC |  | A |  | MEL | DK50 |  | PROK | 2024-05-25
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078740 | DP-1960 - CB04 def. power supply | DP-1960 - CB04 def. power supply | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-05-18 | 2023-01-03 | 35 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A04-02 | OVERCUR AND E/FAULT RELAY BUS-COUPLER AC |  | A |  | MEL | DK50 |  | PROK | 2024-05-26
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078740 | DP-1960 - CB04 def. power supply | Electrical isolate | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-05-18 | 2023-01-03 | 45 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A04-02 | OVERCUR AND E/FAULT RELAY BUS-COUPLER AC |  | A |  | MEL | DK50 |  | PROK | 2024-05-27
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078740 | DP-1960 - CB04 def. power supply | Change out relay | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-05-18 | 2023-01-03 | 55 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A04-02 | OVERCUR AND E/FAULT RELAY BUS-COUPLER AC |  | A |  | MEL | DK50 |  | PROK | 2024-05-28
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078740 | DP-1960 - CB04 def. power supply | Electriucal de isolate | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-05-18 | 2023-01-03 | 65 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A04-02 | OVERCUR AND E/FAULT RELAY BUS-COUPLER AC |  | A |  | MEL | DK50 |  | PROK | 2024-05-29
2024-W21-22 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078740 | DP-1960 - CB04 def. power supply | Additional relay | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-05-18 | 2023-01-03 | 75 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-A04-02 | OVERCUR AND E/FAULT RELAY BUS-COUPLER AC |  | A |  | MEL | DK50 |  | PROK | 2024-05-30
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400307666 | 1Y PRIME MOVER-HBDE-MD-6150 | ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 2 | 0 |  | 2024-09-12 | 2024-09-17 | 2024-09-12 | 2024-05-16 | 2024-04-16 | 10 | REL | APPR OPND | HB /D /78/HBDE-MD-6150 | POWER PACK, PEDESTAL CRANE |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400307666 | 1Y PRIME MOVER-HBDE-MD-6150 | PRIME MOVER MAINTENANCE -HBDE-MD-6150 | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 48 | 0 |  | 2024-09-12 | 2024-09-17 | 2024-09-12 | 2024-05-16 | 2024-04-16 | 20 | REL | APPR OPND | HB /D /78/HBDE-MD-6150 | POWER PACK, PEDESTAL CRANE |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400307666 | 1Y PRIME MOVER-HBDE-MD-6150 | DE-ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 2 | 0 |  | 2024-09-12 | 2024-09-17 | 2024-09-15 | 2024-05-16 | 2024-04-16 | 40 | REL | APPR OPND | HB /D /78/HBDE-MD-6150 | POWER PACK, PEDESTAL CRANE |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400307666 | 1Y PRIME MOVER-HBDE-MD-6150 | Assistance for vendor | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 12 | 0 |  | 2024-09-12 | 2024-09-17 | 2024-09-15 | 2024-05-16 | 2024-04-16 | 50 | REL | APPR OPND | HB /D /78/HBDE-MD-6150 | POWER PACK, PEDESTAL CRANE |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400307667 | 1Y HVAC COOL UNIT VENDOR HBCM-A-1235/36 | PERSONAL ISOLATION | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2024-03-05 | 2024-02-04 | 10 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | C | DKHB-2007 | MEL | DK50 | EL0014
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400307667 | 1Y HVAC COOL UNIT VENDOR HBCM-A-1235/36 | HVAC COOL UNIT VENDOR HBCM-A-1235/36 | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 8 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2024-03-05 | 2024-02-04 | 20 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | C | DKHB-2007 | MEL | DK50 | EL0014
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400307667 | 1Y HVAC COOL UNIT VENDOR HBCM-A-1235/36 | HVAC COOL UNIT VENDOR HBCM-A-1235/36 | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 4 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-02 | 2024-03-05 | 2024-02-04 | 30 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | C | DKHB-2007 | MEL | DK50 | EL0014
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400307667 | 1Y HVAC COOL UNIT VENDOR HBCM-A-1235/36 | PERSONAL DE-ISOLATION | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-02 | 2024-03-05 | 2024-02-04 | 40 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | C | DKHB-2007 | MEL | DK50 | EL0014
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400307667 | 1Y HVAC COOL UNIT VENDOR HBCM-A-1235/36 | RETURN TO OPERATION | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-02 | 2024-03-05 | 2024-02-04 | 50 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | C | DKHB-2007 | MEL | DK50 | EL0014
2026-W13-14 | D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309081 | 4Y HVAC COOL VENDOR HBCM-A-1247/48 | PERSONAL ISOLATION | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-05-01 | 2024-05-05 | 2024-05-01 | 2024-03-22 | 2023-11-26 | 10 | REL | APPR OPND | HB /C /09/AHU-2 | ACCOMMODATION AIR HANDLING UNIT |  | C | DKHB-2029 | MEL | DK50 | EL0014
2026-W13-14 | D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309081 | 4Y HVAC COOL VENDOR HBCM-A-1247/48 | HVAC COOL VENDOR HBCM-A-1247/48 | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 30 | 0 |  | 2024-05-01 | 2024-05-05 | 2024-05-01 | 2024-03-22 | 2023-11-26 | 20 | REL | APPR OPND | HB /C /09/AHU-2 | ACCOMMODATION AIR HANDLING UNIT |  | C | DKHB-2029 | MEL | DK50 | EL0014
2026-W13-14 | D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400309081 | 4Y HVAC COOL VENDOR HBCM-A-1247/48 | HVAC COOL VENDOR HBCM-A-1247/48 | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 6 | 0 |  | 2024-05-01 | 2024-05-05 | 2024-05-04 | 2024-03-22 | 2023-11-26 | 30 | REL | APPR OPND | HB /C /09/AHU-2 | ACCOMMODATION AIR HANDLING UNIT |  | C | DKHB-2029 | MEL | DK50 | EL0014
2026-W13-14 | D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309081 | 4Y HVAC COOL VENDOR HBCM-A-1247/48 | PERSONAL DE-ISOLATION | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-05-01 | 2024-05-05 | 2024-05-05 | 2024-03-22 | 2023-11-26 | 40 | REL | APPR OPND | HB /C /09/AHU-2 | ACCOMMODATION AIR HANDLING UNIT |  | C | DKHB-2029 | MEL | DK50 | EL0014
2026-W13-14 | D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309081 | 4Y HVAC COOL VENDOR HBCM-A-1247/48 | RETURN TO OPERATION | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-05-01 | 2024-05-05 | 2024-05-05 | 2024-03-22 | 2023-11-26 | 50 | REL | APPR OPND | HB /C /09/AHU-2 | ACCOMMODATION AIR HANDLING UNIT |  | C | DKHB-2029 | MEL | DK50 | EL0014
2026-W13-14 | D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309082 | 4Y HVAC COOL AHU VENDOR HBCM-A-1264/65 | PERSONAL ISOLATION | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-04-24 | 2024-04-28 | 2024-04-24 | 2024-03-22 | 2023-11-26 | 10 | REL | APPR OPND | HB /C /09/AHU-1 | UTILITY AIR HANDLING UNIT |  | C | DKHB-2030 | MEL | DK50 | EL0014
2026-W13-14 | D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309082 | 4Y HVAC COOL AHU VENDOR HBCM-A-1264/65 | HVAC COOL AHU VENDOR HBCM-A-1264/65 | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 24 | 0 |  | 2024-04-24 | 2024-04-28 | 2024-04-24 | 2024-03-22 | 2023-11-26 | 20 | REL | APPR OPND | HB /C /09/AHU-1 | UTILITY AIR HANDLING UNIT |  | C | DKHB-2030 | MEL | DK50 | EL0014
2026-W13-14 | D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400309082 | 4Y HVAC COOL AHU VENDOR HBCM-A-1264/65 | HVAC COOL AHU VENDOR HBCM-A-1264/65 | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 6 | 0 |  | 2024-04-24 | 2024-04-28 | 2024-04-26 | 2024-03-22 | 2023-11-26 | 30 | REL | APPR OPND | HB /C /09/AHU-1 | UTILITY AIR HANDLING UNIT |  | C | DKHB-2030 | MEL | DK50 | EL0014
2026-W13-14 | D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309082 | 4Y HVAC COOL AHU VENDOR HBCM-A-1264/65 | PERSONAL DE-ISOLATION | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-04-24 | 2024-04-28 | 2024-04-27 | 2024-03-22 | 2023-11-26 | 40 | REL | APPR OPND | HB /C /09/AHU-1 | UTILITY AIR HANDLING UNIT |  | C | DKHB-2030 | MEL | DK50 | EL0014
2026-W13-14 | D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309082 | 4Y HVAC COOL AHU VENDOR HBCM-A-1264/65 | RETURN TO OPERATION | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-04-24 | 2024-04-28 | 2024-04-27 | 2024-03-22 | 2023-11-26 | 50 | REL | APPR OPND | HB /C /09/AHU-1 | UTILITY AIR HANDLING UNIT |  | C | DKHB-2030 | MEL | DK50 | EL0014
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400314638 | 1Y PRIME MOVER HBAB-MD-6130 | ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 2 | 0 |  | 2024-09-12 | 2024-09-17 | 2024-09-12 | 2024-06-22 | 2024-05-23 | 10 | REL | APPR OPND | HB /A /78/HBAB-MD-6130 | POWER PACK, PEDESTAL CRANE |  | C | DKHB-0656 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400314638 | 1Y PRIME MOVER HBAB-MD-6130 | PRIME MOVER MAINTENANCE HBAB-MD-6130 | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 48 | 0 |  | 2024-09-12 | 2024-09-17 | 2024-09-12 | 2024-06-22 | 2024-05-23 | 20 | REL | APPR OPND | HB /A /78/HBAB-MD-6130 | POWER PACK, PEDESTAL CRANE |  | C | DKHB-0656 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400314638 | 1Y PRIME MOVER HBAB-MD-6130 | DE-ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 2 | 0 |  | 2024-09-12 | 2024-09-17 | 2024-09-15 | 2024-06-22 | 2024-05-23 | 40 | REL | APPR OPND | HB /A /78/HBAB-MD-6130 | POWER PACK, PEDESTAL CRANE |  | C | DKHB-0656 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400314638 | 1Y PRIME MOVER HBAB-MD-6130 | Assistance for vendor | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 12 | 0 |  | 2024-09-12 | 2024-09-17 | 2024-09-15 | 2024-06-22 | 2024-05-23 | 50 | REL | APPR OPND | HB /A /78/HBAB-MD-6130 | POWER PACK, PEDESTAL CRANE |  | C | DKHB-0656 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400314641 | 1Y HBDC-FE-575504 - CO2 METERING | ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-12-25 | 2024-12-27 | 2024-12-25 | 2024-04-01 | 2024-02-25 | 10 | REL | APPR OPND | HB /D /70/HBDC-FIT-575504 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6025 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400314641 | 1Y HBDC-FE-575504 - CO2 METERING | DISASSEMBLY OF METERING | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 4 | 0 |  | 2024-12-25 | 2024-12-27 | 2024-12-25 | 2024-04-01 | 2024-02-25 | 20 | REL | APPR OPND | HB /D /70/HBDC-FIT-575504 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6025 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-INST | 2400314641 | 1Y HBDC-FE-575504 - CO2 METERING | HBDC-FE-575504 - CO2 METERING | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 2.5 | 0 |  | 2024-12-25 | 2024-12-27 | 2024-12-26 | 2024-04-01 | 2024-02-25 | 30 | REL | APPR OPND | HB /D /70/HBDC-FIT-575504 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6025 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400314641 | 1Y HBDC-FE-575504 - CO2 METERING | ASSEMBLY OF METERING | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 4 | 0 |  | 2024-12-25 | 2024-12-27 | 2024-12-26 | 2024-04-01 | 2024-02-25 | 40 | REL | APPR OPND | HB /D /70/HBDC-FIT-575504 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6025 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400314641 | 1Y HBDC-FE-575504 - CO2 METERING | DE-ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR PMAT AWSC RDBL | 1 | 0 |  | 2024-12-25 | 2024-12-27 | 2024-12-27 | 2024-04-01 | 2024-02-25 | 50 | REL | APPR OPND | HB /D /70/HBDC-FIT-575504 | FLOW INDICATOR TRANSMITTER (METERING) |  | A | DKHB-6025 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400315173 | 3Y AVIATION FUEL SKID MAINT-HBCB-A-5601 | AVIATION FUEL SKID MAINT-HBCB-A-5601 | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 20 | 0 |  | 2024-05-06 | 2024-05-14 | 2024-05-06 | 2024-04-08 | 2024-01-25 | 10 | REL | APPR OPND | HB /C /81/HBCB-A-5601 | PUMP SKID WITH AVIATION FUEL PUMP |  | C | DKHB-0172 | MMR | DK50 | MR0124 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-INST | 2400315173 | 3Y AVIATION FUEL SKID MAINT-HBCB-A-5601 | AVIATION FUEL SKID MAINT-HBCB-A-5601 | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 4 | 0 |  | 2024-05-06 | 2024-05-14 | 2024-05-10 | 2024-04-08 | 2024-01-25 | 20 | REL | APPR OPND | HB /C /81/HBCB-A-5601 | PUMP SKID WITH AVIATION FUEL PUMP |  | C | DKHB-0172 | MMR | DK50 | MR0124 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400315173 | 3Y AVIATION FUEL SKID MAINT-HBCB-A-5601 | AVIATION FUEL SKID MAINT-HBCB-A-5601 | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 8 | 0 |  | 2024-05-06 | 2024-05-14 | 2024-05-10 | 2024-04-08 | 2024-01-25 | 30 | REL | APPR OPND | HB /C /81/HBCB-A-5601 | PUMP SKID WITH AVIATION FUEL PUMP |  | C | DKHB-0172 | MMR | DK50 | MR0124 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-MECH | VEN-MECH | 2400315173 | 3Y AVIATION FUEL SKID MAINT-HBCB-A-5601 | AVIATION FUEL SKID MAINT-HBCB-A-5601 | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 6 | 0 |  | 2024-05-06 | 2024-05-14 | 2024-05-12 | 2024-04-08 | 2024-01-25 | 40 | REL | APPR OPND | HB /C /81/HBCB-A-5601 | PUMP SKID WITH AVIATION FUEL PUMP |  | C | DKHB-0172 | MMR | DK50 | MR0124 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400315173 | 3Y AVIATION FUEL SKID MAINT-HBCB-A-5601 | ASSIST AUDIT | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 4 | 0 |  | 2024-05-06 | 2024-05-14 | 2024-05-13 | 2024-04-08 | 2024-01-25 | 50 | REL | APPR OPND | HB /C /81/HBCB-A-5601 | PUMP SKID WITH AVIATION FUEL PUMP |  | C | DKHB-0172 | MMR | DK50 | MR0124 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400315173 | 3Y AVIATION FUEL SKID MAINT-HBCB-A-5601 | additional materials | REL GMPS MANC PRC SETC | APPR PMAT AWSC RDBL | 0 | 0 |  | 2024-05-06 | 2024-05-14 | 2024-05-14 | 2024-04-08 | 2024-01-25 | 60 | REL | APPR OPND | HB /C /81/HBCB-A-5601 | PUMP SKID WITH AVIATION FUEL PUMP |  | C | DKHB-0172 | MMR | DK50 | MR0124 | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100098564 | Flame out G-1650 | Flame out G-1650 Exchange of GF Valve | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RFRZ ROUT | 16 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-03-20 | 2023-11-06 | 10 | REL | APPR OPND | HB /D /60/HBDC-GT-1650 | GAS TURBINE |  | E |  | MMR | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100098564 | Flame out G-1650 | PECC GF VALVE ASSY MAIN | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RFRZ ROUT | 0 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2024-03-20 | 2023-11-06 | 20 | REL | APPR OPND | HB /D /60/HBDC-GT-1650 | GAS TURBINE |  | E |  | MMR | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100098564 | Flame out G-1650 | PECC GF VALVE ASSY PILOT | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RFRZ ROUT | 0 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2024-03-20 | 2023-11-06 | 30 | REL | APPR OPND | HB /D /60/HBDC-GT-1650 | GAS TURBINE |  | E |  | MMR | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100059469 | HBA/78: Measure hoses engine cooling sys | Isolate crane HBAB-X-6130 | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RDBL ROUT | 1 | 0 | W15-W16 | 2024-03-13 | 2024-06-18 | 2024-03-13 | 2022-07-24 | 2022-02-24 | 10 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100059469 | HBA/78: Measure hoses engine cooling sys | Measure all cooling hoses that need to b | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RDBL ROUT | 12 | 0 | W15-W16 | 2024-03-13 | 2024-06-18 | 2024-03-13 | 2022-07-24 | 2022-02-24 | 20 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100059469 | HBA/78: Measure hoses engine cooling sys | De-isolate crane HBAB-X-6130 | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RDBL ROUT | 1 | 0 | W15-W16 | 2024-03-13 | 2024-06-18 | 2024-03-14 | 2022-07-24 | 2022-02-24 | 30 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100059469 | HBA/78: Measure hoses engine cooling sys | Check new materials | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RDBL ROUT | 1 | 0 | W15-W16 | 2024-03-13 | 2024-06-18 | 2024-06-12 | 2022-07-24 | 2022-02-24 | 40 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100059469 | HBA/78: Measure hoses engine cooling sys | Isolate crane HBAB-X-6130 | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RDBL ROUT | 1 | 0 | W15-W16 | 2024-03-13 | 2024-06-18 | 2024-06-13 | 2022-07-24 | 2022-02-24 | 50 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100059469 | HBA/78: Measure hoses engine cooling sys | Drain cooling water | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RDBL ROUT | 3 | 0 | W15-W16 | 2024-03-13 | 2024-06-18 | 2024-06-13 | 2022-07-24 | 2022-02-24 | 60 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100059469 | HBA/78: Measure hoses engine cooling sys | Replace cooling hoses | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RDBL ROUT | 24 | 0 | W15-W16 | 2024-03-13 | 2024-06-18 | 2024-06-13 | 2022-07-24 | 2022-02-24 | 70 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100059469 | HBA/78: Measure hoses engine cooling sys | Refill cooling water | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RDBL ROUT | 3 | 0 | W15-W16 | 2024-03-13 | 2024-06-18 | 2024-06-16 | 2022-07-24 | 2022-02-24 | 80 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100059469 | HBA/78: Measure hoses engine cooling sys | De-isolate crane HBAB-X-6130 | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RDBL ROUT | 1 | 0 | W15-W16 | 2024-03-13 | 2024-06-18 | 2024-06-16 | 2022-07-24 | 2022-02-24 | 90 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100059469 | HBA/78: Measure hoses engine cooling sys | Test with high engine temperature and ch | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RDBL ROUT | 2 | 0 | W15-W16 | 2024-03-13 | 2024-06-18 | 2024-06-16 | 2022-07-24 | 2022-02-24 | 100 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100059469 | HBA/78: Measure hoses engine cooling sys | Assist VEN-CRAN and operating crane | REL GMPS MANC PRC SETC | APPR PMAT AWDO SCH RDBL ROUT | 6 | 0 | W15-W16 | 2024-03-13 | 2024-06-18 | 2024-06-16 | 2022-07-24 | 2022-02-24 | 110 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100072540 | Remount new valve | Reinstate insulation | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT AWDO SCH RDBL RFRZ ROUT | 4 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-02-04 | 2022-09-22 | 50 | PCNF REL | APPR OPND | HB /B /28/HAZARDOUS-OPEN-DRAIN | HBB HAZARDOUS OPEN DRAIN |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025859 | FFSPR Replace spools with corroded flang | Check and survey new Spool/Valve. | REL GMPS MANC PRC SETC | APPR PMAT AWDO ROUT | 2 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2021-01-26 | 2020-02-01 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK | 99000087 | F |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025859 | FFSPR Replace spools with corroded flang | Production isolation. | REL GMPS MANC PRC SETC | APPR PMAT AWDO ROUT | 2 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2021-01-26 | 2020-02-01 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK | 99000087 | F |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025859 | FFSPR Replace spools with corroded flang | Replace Spool HB-1254-1 | REL GMPS MANC PRC SETC | APPR PMAT AWDO ROUT | 9 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2021-01-26 | 2020-02-01 | 80 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK | 99000087 | F |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025859 | FFSPR Replace spools with corroded flang | Replace 3 Butterfly valves. | REL GMPS MANC PRC SETC | APPR PMAT AWDO ROUT | 15 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2021-01-26 | 2020-02-01 | 90 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK | 99000087 | F |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025859 | FFSPR Replace spools with corroded flang | Rigger assistance. | REL GMPS MANC PRC SETC | APPR PMAT AWDO ROUT | 10 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2021-01-26 | 2020-02-01 | 100 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK | 99000087 | F |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025859 | FFSPR Replace spools with corroded flang | Production deisolation leak test. | REL GMPS MANC PRC SETC | APPR PMAT AWDO ROUT | 2 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2021-01-26 | 2020-02-01 | 110 | REL | APPR OPND | HB /A /01/HBAA-A-0374 | DELUGE SKID CELLAR DECK | 99000087 | F |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100058595 | HBC/78: Constant Tension not working | Check new spareparts are 1 to 1 | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWDO ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-23 | 2024-03-09 | 2022-03-06 | 2021-12-06 | 10 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100058595 | HBC/78: Constant Tension not working | Isolate crane HBCO-A-6101 | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWDO ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-23 | 2024-03-09 | 2022-03-06 | 2021-12-06 | 20 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100058595 | HBC/78: Constant Tension not working | Build scaffolding gallow | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWDO ROUT | 50 | 0 |  | 2024-03-09 | 2024-03-23 | 2024-03-09 | 2022-03-06 | 2021-12-06 | 30 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100058595 | HBC/78: Constant Tension not working | Dissasemble hyd motor and valve block | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWDO ROUT | 24 | 0 |  | 2024-03-09 | 2024-03-23 | 2024-03-12 | 2022-03-06 | 2021-12-06 | 40 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100058595 | HBC/78: Constant Tension not working | Rigging old hyd motor and valve block do | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWDO ROUT | 24 | 0 |  | 2024-03-09 | 2024-03-23 | 2024-03-12 | 2022-03-06 | 2021-12-06 | 50 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100058595 | HBC/78: Constant Tension not working | Assemble new hyd motor and valve block | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWDO ROUT | 24 | 0 |  | 2024-03-09 | 2024-03-23 | 2024-03-15 | 2022-03-06 | 2021-12-06 | 60 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100058595 | HBC/78: Constant Tension not working | Remove scaffolding gallow | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWDO ROUT | 50 | 0 |  | 2024-03-09 | 2024-03-23 | 2024-03-16 | 2022-03-06 | 2021-12-06 | 70 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100058595 | HBC/78: Constant Tension not working | Deisolate crane HBCO-A-6101 | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWDO ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-23 | 2024-03-19 | 2022-03-06 | 2021-12-06 | 80 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100058595 | HBC/78: Constant Tension not working | Function test and proof load test | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWDO ROUT | 12 | 0 |  | 2024-03-09 | 2024-03-23 | 2024-03-20 | 2022-03-06 | 2021-12-06 | 90 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100058595 | HBC/78: Constant Tension not working | Operating under test and assist MTN-CRAN | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWDO ROUT | 12 | 0 |  | 2024-03-09 | 2024-03-23 | 2024-03-20 | 2022-03-06 | 2021-12-06 | 100 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100058595 | HBC/78: Constant Tension not working | Clean-up, documentation QC, backload old | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWDO ROUT | 3 | 0 |  | 2024-03-09 | 2024-03-23 | 2024-03-23 | 2022-03-06 | 2021-12-06 | 110 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100058595 | HBC/78: Constant Tension not working | Replace backup battery on PLC according | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWDO ROUT | 0 | 0 |  | 2024-03-09 | 2024-03-23 | 2024-03-09 | 2022-03-06 | 2021-12-06 | 120 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-PIPF | CON-WELD | 2100024256 | RECAL HBAA-PSV-50121 | Isolering D2/11-2020 | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR PMAT AWDO RFRZ ROUT | 0 | 0 |  | 2021-07-05 | 2023-04-24 | 2023-04-24 | 2020-06-19 | 2019-06-25 | 11 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE | 99000074 | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-PIPF | MTN-LAGG | 2100024256 | RECAL HBAA-PSV-50121 | Re-install insulation on PSV | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR PMAT AWDO RFRZ ROUT | 6 | 0 |  | 2021-07-05 | 2023-04-24 | 2023-04-24 | 2020-06-19 | 2019-06-25 | 260 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE | 99000074 | A |  | MMS | DK50
0 | 4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100045479 | ANOC Escape Route Marking Halfdan A | Escape Route Marking All over Halfdan A | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO RDBL ROUT | 0 | 0 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-09-24 | 2021-04-27 | 10 | REL | APPR OPND | HD /A /02/ESCAPE-ROUTES | ESCAPE ROUTES AND ACCESS WAYS - E2.1 |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100045479 | ANOC Escape Route Marking Halfdan A | Vendor Materials | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO RDBL ROUT | 0 | 0 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-09-24 | 2021-04-27 | 40 | REL | APPR OPND | HD /A /02/ESCAPE-ROUTES | ESCAPE ROUTES AND ACCESS WAYS - E2.1 |  | A |  | MFM | DK60
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100066013 | Bleed is internal leak HBDB-PIT-365305 | Isolate and Inhibit Pressure transmitter | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2022-11-17 | 2022-06-20 | 10 | REL | APPR OPND | HB /D /23/HBDB-PIT-365305 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066013 | Bleed is internal leak HBDB-PIT-365305 | Replace SDBB valve | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2022-11-17 | 2022-06-20 | 20 | REL | APPR OPND | HB /D /23/HBDB-PIT-365305 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100066013 | Bleed is internal leak HBDB-PIT-365305 | Test Pressure transmitter | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2022-11-17 | 2022-06-20 | 30 | REL | APPR OPND | HB /D /23/HBDB-PIT-365305 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100066013 | Bleed is internal leak HBDB-PIT-365305 | Deisolate and repeal inhibits Pressure t | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL ROUT | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2022-11-17 | 2022-06-20 | 40 | REL | APPR OPND | HB /D /23/HBDB-PIT-365305 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023666 | Loadtest of winch LB2 (X-0702) | Loadtest (later by Verhoef) | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W38-39 DK50-M-6220 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2018-09-26 | 2018-04-29 | 190 | PCNF REL | APPR OPND | HB /C /02/HBCA-X-0702 | LIFEBOAT 2 - 45 PERS. |  | A |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | MTN-SCAF | 2100025860 | FFSPR Replace spools corroded flanges A- | L3 Prepare scaffold (overboard work) | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 20 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2021-01-26 | 2020-02-01 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | PRODTECH | 2100025860 | FFSPR Replace spools corroded flanges A- | L3 Isolate equipment | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2021-01-26 | 2020-02-01 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | MTN-MECH | 2100025860 | FFSPR Replace spools corroded flanges A- | L3 Dismantle spools & valves | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2021-01-26 | 2020-02-01 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | MTN-SCAF | 2100025860 | FFSPR Replace spools corroded flanges A- | L3 Rig out & in of spools & valves | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 16 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2021-01-26 | 2020-02-01 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | MTN-MECH | 2100025860 | FFSPR Replace spools corroded flanges A- | L2 Install spools & valves | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2021-01-26 | 2020-02-01 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | PRODTECH | 2100025860 | FFSPR Replace spools corroded flanges A- | L3 Remove isolation | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2021-01-26 | 2020-02-01 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | MTN-SCAF | 2100025860 | FFSPR Replace spools corroded flanges A- | L3 Remove Scaffold (overboard work) | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 15 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2021-01-26 | 2020-02-01 | 70 | REL | APPR OPND | HB /A /01/HBAA-A-0376 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | CON-INPF | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Temp Repair on Line: 3"-IW-35-4004-GFW | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-01 | 2021-09-23 | 2021-04-26 | 1 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-ROPE | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | 2100045792-0002-COATING | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-01 | 2021-09-23 | 2021-04-26 | 2 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-ROPE | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | 2100045792-0003-CONSUMER-GOODS | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-01 | 2021-09-23 | 2021-04-26 | 3 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-ROPE | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | 2100045792-004-RENT-ALTRAD | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-01 | 2021-09-23 | 2021-04-26 | 4 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-ROPE | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | 2100045792-0005-RENT-MOURITSEN (DRAFT) | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-01 | 2021-09-23 | 2021-04-26 | 5 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-ROPE | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Paint; Prep/Scaf/Rope/Gear/Net+Post | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 36 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-01 | 2021-09-23 | 2021-04-26 | 10 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-ROPE | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Paint; Clean-Off, Inspect, QC.Log, Waste | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-02 | 2021-09-23 | 2021-04-26 | 20 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-ROPE | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Paint; QC-Log, Wrap+Recoat to Spec | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-02 | 2021-09-23 | 2021-04-26 | 30 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-ROPE | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Paint; Clean-Up+Color-Cote+Backload | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-03 | 2021-09-23 | 2021-04-26 | 40 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-RIGG | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | secure spool/ Lifting gear | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 20 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-04 | 2021-09-23 | 2021-04-26 | 80 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-LAGG | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Remove insulation | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-05 | 2021-09-23 | 2021-04-26 | 100 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-ELEC | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Demount heattracing | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-06 | 2021-09-23 | 2021-04-26 | 110 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | PRODTECH | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Isolation (Prod) | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-06 | 2021-09-23 | 2021-04-26 | 120 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-PIPF | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Install BL Flanges | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-06 | 2021-09-23 | 2021-04-26 | 130 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-PIPF | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Dismantling BL Flanges | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-06 | 2021-09-23 | 2021-04-26 | 140 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | PRODTECH | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Leak test and deisolation(prod) | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-07 | 2021-09-23 | 2021-04-26 | 150 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-ELEC | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Mount. heat tracing | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-08 | 2021-09-23 | 2021-04-26 | 160 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-LAGG | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Re-install insulation. | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-08 | 2021-09-23 | 2021-04-26 | 170 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-RIGG | 2100045792 | FFSPR On Line: 3"-IW-35-4004-GFW TMP270 | Remove lifting gear | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 20 | 0 |  | 2025-01-01 | 2025-01-10 | 2025-01-08 | 2021-09-23 | 2021-04-26 | 180 | REL | APPR OPND | HB /A /50/HBA-3-WI-035-4004-GFW-T | 3 INJECTION WATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-SCAF | 2100048522 | Pressure transmitters are missing insula | Install scaffolding | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2022-07-30 | 2021-10-03 | 10 | REL | APPR OPND | HB /B /37/HBBB-PIT-291005 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | PRODTECH | 2100048522 | Pressure transmitters are missing insula | Isolate/Inhibit Pressure Indic. Transmit | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-26 | 2022-07-30 | 2021-10-03 | 20 | REL | APPR OPND | HB /B /37/HBBB-PIT-291005 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100048522 | Pressure transmitters are missing insula | Isolate Heat tracing power supply for Tr | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-25 | 2022-07-30 | 2021-10-03 | 30 | REL | APPR OPND | HB /B /37/HBBB-PIT-291005 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100048522 | Pressure transmitters are missing insula | Install insulation for Transmitter (ESD) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 20 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2022-07-30 | 2021-10-03 | 50 | REL | APPR OPND | HB /B /37/HBBB-PIT-291005 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100048522 | Pressure transmitters are missing insula | Deisolate Heat tracing power supply for | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-26 | 2022-07-30 | 2021-10-03 | 60 | REL | APPR OPND | HB /B /37/HBBB-PIT-291005 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | PRODTECH | 2100048522 | Pressure transmitters are missing insula | Deisolate/ Remove inhibit Pressure Indic | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-26 | 2022-07-30 | 2021-10-03 | 70 | REL | APPR OPND | HB /B /37/HBBB-PIT-291005 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-SCAF | 2100048522 | Pressure transmitters are missing insula | Remove scaffolding | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-26 | 2022-07-30 | 2021-10-03 | 80 | REL | APPR OPND | HB /B /37/HBBB-PIT-291005 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100062586 | FLMPR Loose Ubolt & fretting of pipe | 2100062586-0002~COATING | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-03-28 | 2022-03-30 | 2022-03-28 | 2022-09-25 | 2022-04-28 | 2 | REL | APPR OPND | HB /A /28/HBA-1.5-DPS-050-4051-FC-U | 1.5 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100062586 | FLMPR Loose Ubolt & fretting of pipe | 2100062586-0003~CONSUMABLES | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-03-28 | 2022-03-30 | 2022-03-28 | 2022-09-25 | 2022-04-28 | 3 | REL | APPR OPND | HB /A /28/HBA-1.5-DPS-050-4051-FC-U | 1.5 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100062586 | FLMPR Loose Ubolt & fretting of pipe | 2100062586-0004~ALTRAD | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-03-28 | 2022-03-30 | 2022-03-28 | 2022-09-25 | 2022-04-28 | 4 | REL | APPR OPND | HB /A /28/HBA-1.5-DPS-050-4051-FC-U | 1.5 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100062586 | FLMPR Loose Ubolt & fretting of pipe | Loose Ubolt & fretting of pipe | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-03-28 | 2022-03-30 | 2022-03-28 | 2022-09-25 | 2022-04-28 | 10 | REL | APPR OPND | HB /A /28/HBA-1.5-DPS-050-4051-FC-U | 1.5 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100062586 | FLMPR Loose Ubolt & fretting of pipe | Ordering materials. | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-03-28 | 2022-03-30 | 2022-03-28 | 2022-09-25 | 2022-04-28 | 20 | REL | APPR OPND | HB /A /28/HBA-1.5-DPS-050-4051-FC-U | 1.5 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100062586 | FLMPR Loose Ubolt & fretting of pipe | Dismantling existing U-Bolt | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2022-03-28 | 2022-03-30 | 2022-03-28 | 2022-09-25 | 2022-04-28 | 40 | REL | APPR OPND | HB /A /28/HBA-1.5-DPS-050-4051-FC-U | 1.5 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100062586 | FLMPR Loose Ubolt & fretting of pipe | Paint 1 | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-03-28 | 2022-03-30 | 2022-03-28 | 2022-09-25 | 2022-04-28 | 50 | REL | APPR OPND | HB /A /28/HBA-1.5-DPS-050-4051-FC-U | 1.5 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100062586 | FLMPR Loose Ubolt & fretting of pipe | Install new U-Bolt | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2022-03-28 | 2022-03-30 | 2022-03-28 | 2022-09-25 | 2022-04-28 | 60 | REL | APPR OPND | HB /A /28/HBA-1.5-DPS-050-4051-FC-U | 1.5 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100062586 | FLMPR Loose Ubolt & fretting of pipe | Paint; Prep/Team/Gear/Barrier+POST | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2022-03-28 | 2022-03-30 | 2022-03-28 | 2022-09-25 | 2022-04-28 | 90 | REL | APPR OPND | HB /A /28/HBA-1.5-DPS-050-4051-FC-U | 1.5 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100062586 | FLMPR Loose Ubolt & fretting of pipe | Paint; Clean-Off, QC, Prime Surface | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 18 | 0 |  | 2022-03-28 | 2022-03-30 | 2022-03-29 | 2022-09-25 | 2022-04-28 | 100 | REL | APPR OPND | HB /A /28/HBA-1.5-DPS-050-4051-FC-U | 1.5 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100062586 | FLMPR Loose Ubolt & fretting of pipe | Paint; Clean, QC, Paint to Spec. | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 18 | 0 |  | 2022-03-28 | 2022-03-30 | 2022-03-29 | 2022-09-25 | 2022-04-28 | 110 | REL | APPR OPND | HB /A /28/HBA-1.5-DPS-050-4051-FC-U | 1.5 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100062586 | FLMPR Loose Ubolt & fretting of pipe | Paint; Clean-Up | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2022-03-28 | 2022-03-30 | 2022-03-30 | 2022-09-25 | 2022-04-28 | 120 | REL | APPR OPND | HB /A /28/HBA-1.5-DPS-050-4051-FC-U | 1.5 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-INST | PRODTECH | 2100069364 | Internal leak on HCV for LIT-416104 | Production Isolation | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2023-01-27 | 2022-08-30 | 10 | REL | APPR OPND | HB /D /30/HBDB-LIT-416104 | DIFF. PRESS. TX. WITH REMOTE DISP. (ESD) |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-INST | MTN-MECH | 2100069364 | Internal leak on HCV for LIT-416104 | Replace 2" Ball Vlv | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2023-01-27 | 2022-08-30 | 20 | REL | APPR OPND | HB /D /30/HBDB-LIT-416104 | DIFF. PRESS. TX. WITH REMOTE DISP. (ESD) |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-INST | MTN-INST | 2100069364 | Internal leak on HCV for LIT-416104 | Recalibrate LIT-416104 | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2023-01-27 | 2022-08-30 | 30 | REL | APPR OPND | HB /D /30/HBDB-LIT-416104 | DIFF. PRESS. TX. WITH REMOTE DISP. (ESD) |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-INST | PRODTECH | 2100069364 | Internal leak on HCV for LIT-416104 | Production De-isolation w Leaktest | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2023-01-27 | 2022-08-30 | 40 | REL | APPR OPND | HB /D /30/HBDB-LIT-416104 | DIFF. PRESS. TX. WITH REMOTE DISP. (ESD) |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100071674 | HBA/78: Man-riding brake leaking | Isolate/de-isolate of crane HBAB-X-6130 | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-20 | 2024-06-26 | 2024-06-20 | 2023-01-11 | 2022-08-29 | 10 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100071674 | HBA/78: Man-riding brake leaking | Build/demol of gallows | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 30 | 0 |  | 2024-06-20 | 2024-06-26 | 2024-06-20 | 2023-01-11 | 2022-08-29 | 20 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100071674 | HBA/78: Man-riding brake leaking | Replace AUX Secondary brake, complete | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2024-06-20 | 2024-06-26 | 2024-06-23 | 2023-01-11 | 2022-08-29 | 30 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100071674 | HBA/78: Man-riding brake leaking | Handling/rigging of brake | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 20 | 0 |  | 2024-06-20 | 2024-06-26 | 2024-06-23 | 2023-01-11 | 2022-08-29 | 40 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100071674 | HBA/78: Man-riding brake leaking | Perform stall brake test | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-20 | 2024-06-26 | 2024-06-24 | 2023-01-11 | 2022-08-29 | 50 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100071674 | HBA/78: Man-riding brake leaking | Perform proof load test of Secondary bra | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-06-20 | 2024-06-26 | 2024-06-25 | 2023-01-11 | 2022-08-29 | 60 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100071674 | HBA/78: Man-riding brake leaking | Operation of crane | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-06-20 | 2024-06-26 | 2024-06-25 | 2023-01-11 | 2022-08-29 | 70 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50 |  | PROK
2024-W23-24 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080208 | Dampers for PI's are defect. | Isolate presure gauges | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 | W13-W14 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2025-12-13 | 2023-06-27 | 10 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | A |  | MIN | DK50 |  |  | 2024-05-28
2024-W23-24 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080208 | Dampers for PI's are defect. | Replace pressure gauges | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W13-W14 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2025-12-13 | 2023-06-27 | 20 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | A |  | MIN | DK50 |  |  | 2024-05-29
2024-W23-24 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080208 | Dampers for PI's are defect. | De-isolate pressure gauges | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 | W13-W14 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2025-12-13 | 2023-06-27 | 30 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID |  | A |  | MIN | DK50 |  |  | 2024-05-30
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100094580 | New HCV for LIT-576002 | Mount Access Platform Scaffold | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-12-30 | 2023-08-17 | 2 | REL | APPR OPND | HB /D /71/HBDC-LIT-576002 | LEVEL INDICATOR TRANSMITTER (ESD) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100094580 | New HCV for LIT-576002 | Isolation of Valves | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2023-12-30 | 2023-08-17 | 20 | REL | APPR OPND | HB /D /71/HBDC-LIT-576002 | LEVEL INDICATOR TRANSMITTER (ESD) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100094580 | New HCV for LIT-576002 | Demount Valve | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-12-30 | 2023-08-17 | 30 | REL | APPR OPND | HB /D /71/HBDC-LIT-576002 | LEVEL INDICATOR TRANSMITTER (ESD) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100094580 | New HCV for LIT-576002 | Install New Valve | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-12-30 | 2023-08-17 | 40 | REL | APPR OPND | HB /D /71/HBDC-LIT-576002 | LEVEL INDICATOR TRANSMITTER (ESD) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100094580 | New HCV for LIT-576002 | De-isolate | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2023-12-30 | 2023-08-17 | 50 | REL | APPR OPND | HB /D /71/HBDC-LIT-576002 | LEVEL INDICATOR TRANSMITTER (ESD) |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100097879 | Replace noisy fan motor 11M7-E-1702 | Isolate Equipment. | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-03-06 | 2023-10-23 | 20 | REL | APPR OPND | HB /C /05/HBCA-E-1702 | AIR COOLER EMG GEN. HBCM-E-1760/1761) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097879 | Replace noisy fan motor 11M7-E-1702 | Replace motor & Accessories | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-03-06 | 2023-10-23 | 30 | REL | APPR OPND | HB /C /05/HBCA-E-1702 | AIR COOLER EMG GEN. HBCM-E-1760/1761) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100097879 | Replace noisy fan motor 11M7-E-1702 | De-isolate Equipment | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-03-06 | 2023-10-23 | 40 | REL | APPR OPND | HB /C /05/HBCA-E-1702 | AIR COOLER EMG GEN. HBCM-E-1760/1761) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097879 | Replace noisy fan motor 11M7-E-1702 | Test & put back in service | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2024-03-06 | 2023-10-23 | 50 | REL | APPR OPND | HB /C /05/HBCA-E-1702 | AIR COOLER EMG GEN. HBCM-E-1760/1761) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097879 | Replace noisy fan motor 11M7-E-1702 | Rigging assistance | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-07-30 | 2024-07-31 | 2024-07-31 | 2024-03-06 | 2023-10-23 | 60 | REL | APPR OPND | HB /C /05/HBCA-E-1702 | AIR COOLER EMG GEN. HBCM-E-1760/1761) |  | A |  | MEL | DK50 |  | PROK
2024-W23-24 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098346 | LOTI Fan motor 12M3-E-1701 is stuck. | Isolate Equipment. | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-10-30 | 2023-09-15 | 10 | REL | APPR OPND | HB /C /05/HBCA-E-1701 | AIR COOLER EMG. GEN. HBCM-E-1750/1751) |  | A |  | MEL | DK50 |  | PROK | 2024-05-28
2024-W23-24 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098346 | LOTI Fan motor 12M3-E-1701 is stuck. | Replace motor & Accessories | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2023-10-30 | 2023-09-15 | 20 | REL | APPR OPND | HB /C /05/HBCA-E-1701 | AIR COOLER EMG. GEN. HBCM-E-1750/1751) |  | A |  | MEL | DK50 |  | PROK | 2024-05-29
2024-W23-24 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098346 | LOTI Fan motor 12M3-E-1701 is stuck. | Rigging assistance | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2023-10-30 | 2023-09-15 | 21 | REL | APPR OPND | HB /C /05/HBCA-E-1701 | AIR COOLER EMG. GEN. HBCM-E-1750/1751) |  | A |  | MEL | DK50 |  | PROK | 2024-05-30
2024-W23-24 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098346 | LOTI Fan motor 12M3-E-1701 is stuck. | De-isolate Equipment | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2023-10-30 | 2023-09-15 | 30 | REL | APPR OPND | HB /C /05/HBCA-E-1701 | AIR COOLER EMG. GEN. HBCM-E-1750/1751) |  | A |  | MEL | DK50 |  | PROK | 2024-05-31
2024-W23-24 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098346 | LOTI Fan motor 12M3-E-1701 is stuck. | Test & put back in service | REL GMPS MANC PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2023-10-30 | 2023-09-15 | 40 | REL | APPR OPND | HB /C /05/HBCA-E-1701 | AIR COOLER EMG. GEN. HBCM-E-1750/1751) |  | A |  | MEL | DK50 |  | PROK | 2024-06-01
2024-W29-30 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100099094 | Inst. air Brass valve leaking HBD Lev3 | Inst. air Brass valve leaking HBD Lev3 | REL GMPS MACM PRC SETC | APPR PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-03-29 | 2023-11-15 | 10 | REL | APPR OPND | HB /D /09/HBDD-FD-12344 | FIRE DAMPER |  | A |  | MIN | DK50
2026-W13-14 | 3 | HBAT-SEP | WDF | MTN-MECH | MTN-RIGG | 2100104215 | Intenal leak at HCV for LIT-34140 | Install rigging equipment | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT RREQ | 3 | 0 |  | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-06-19 | 2024-02-05 | 10 | REL | APPR OPND | HB /A /11/HBAA-LIT-34140 | LEVEL INDICATOR TRANSMITTER (ESD) |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBAT-SEP | WDF | MTN-MECH | PRODTECH | 2100104215 | Intenal leak at HCV for LIT-34140 | Isolate Seperator | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT RREQ | 1 | 0 |  | 2024-05-05 | 2024-05-06 | 2024-05-06 | 2024-06-19 | 2024-02-05 | 20 | REL | APPR OPND | HB /A /11/HBAA-LIT-34140 | LEVEL INDICATOR TRANSMITTER (ESD) |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBAT-SEP | WDF | MTN-MECH | MTN-INST | 2100104215 | Intenal leak at HCV for LIT-34140 | Isolate transmitter | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT RREQ | 1 | 0 |  | 2024-05-05 | 2024-05-06 | 2024-05-06 | 2024-06-19 | 2024-02-05 | 30 | REL | APPR OPND | HB /A /11/HBAA-LIT-34140 | LEVEL INDICATOR TRANSMITTER (ESD) |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBAT-SEP | WDF | MTN-MECH | MTN-MECH | 2100104215 | Intenal leak at HCV for LIT-34140 | Remove old HCV valve | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT RREQ | 2 | 0 |  | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-06-19 | 2024-02-05 | 40 | REL | APPR OPND | HB /A /11/HBAA-LIT-34140 | LEVEL INDICATOR TRANSMITTER (ESD) |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBAT-SEP | WDF | MTN-MECH | MTN-RIGG | 2100104215 | Intenal leak at HCV for LIT-34140 | Remove old HCV valve | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT RREQ | 2 | 0 |  | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-06-19 | 2024-02-05 | 50 | REL | APPR OPND | HB /A /11/HBAA-LIT-34140 | LEVEL INDICATOR TRANSMITTER (ESD) |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBAT-SEP | WDF | MTN-MECH | MTN-MECH | 2100104215 | Intenal leak at HCV for LIT-34140 | Install new HCV valve | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT RREQ | 2 | 0 |  | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-06-19 | 2024-02-05 | 60 | REL | APPR OPND | HB /A /11/HBAA-LIT-34140 | LEVEL INDICATOR TRANSMITTER (ESD) |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBAT-SEP | WDF | MTN-MECH | MTN-RIGG | 2100104215 | Intenal leak at HCV for LIT-34140 | Install new HCV valve | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT RREQ | 2 | 0 |  | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-06-19 | 2024-02-05 | 70 | REL | APPR OPND | HB /A /11/HBAA-LIT-34140 | LEVEL INDICATOR TRANSMITTER (ESD) |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBAT-SEP | WDF | MTN-MECH | MTN-INST | 2100104215 | Intenal leak at HCV for LIT-34140 | Deisolate transmitter/Test with CCR | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT RREQ | 2 | 0 |  | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-06-19 | 2024-02-05 | 80 | REL | APPR OPND | HB /A /11/HBAA-LIT-34140 | LEVEL INDICATOR TRANSMITTER (ESD) |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBAT-SEP | WDF | MTN-MECH | PRODTECH | 2100104215 | Intenal leak at HCV for LIT-34140 | Deisolate Seperator | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT RREQ | 0.5 | 0 |  | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-06-19 | 2024-02-05 | 90 | REL | APPR OPND | HB /A /11/HBAA-LIT-34140 | LEVEL INDICATOR TRANSMITTER (ESD) |  | E |  | MMS | DK50
2026-W13-14 | 3 | HBAT-SEP | WDF | MTN-MECH | MTN-RIGG | 2100104215 | Intenal leak at HCV for LIT-34140 | Remove rigging equipment | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT RREQ | 1 | 0 |  | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-06-19 | 2024-02-05 | 100 | REL | APPR OPND | HB /A /11/HBAA-LIT-34140 | LEVEL INDICATOR TRANSMITTER (ESD) |  | E |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | MTN-PIPF | 2100025902 | FFSPR Replace spools with corroded flang | L3 Prepare scaffold (overboard work) | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 20 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2021-01-26 | 2020-02-01 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | PRODTECH | 2100025902 | FFSPR Replace spools with corroded flang | L3 Isolate equipment | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2021-01-26 | 2020-02-01 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | MTN-PIPF | 2100025902 | FFSPR Replace spools with corroded flang | L3 Dismantle spools & valves | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2021-01-26 | 2020-02-01 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | MTN-SCAF | 2100025902 | FFSPR Replace spools with corroded flang | L3 Rig out & in of spools & valves | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 16 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2021-01-26 | 2020-02-01 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | MTN-PIPF | 2100025902 | FFSPR Replace spools with corroded flang | L2 Install spools & valves | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-04 | 2021-01-26 | 2020-02-01 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | PRODTECH | 2100025902 | FFSPR Replace spools with corroded flang | L3 Remove isolation | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2021-01-26 | 2020-02-01 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-ROPE | MTN-SCAF | 2100025902 | FFSPR Replace spools with corroded flang | L3 Remove Scaffold (overboard work) | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 15 | 0 |  | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2021-01-26 | 2020-02-01 | 70 | REL | APPR OPND | HB /A /01/HBAA-A-0375 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | MTN-PIPF | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Prepare permits weld. | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | MATS ETA 2/10 | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 2 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | MTN-SCAF | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Prepare permits scaf | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | MATS ETA 2/10 | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 3 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | MTN-SCAF | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Build scaffolding and prepare rigging | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 78 | 0 | MATS ETA 2/10 | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 11 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | MTN-PIPF | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Tools, tjek materials and spools | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 13 | 0 | MATS ETA 2/10 | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 15 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | PRODTECH | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Safing. | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | MATS ETA 2/10 | 2025-01-01 | 2025-01-23 | 2025-01-09 | 2017-08-22 | 2017-05-24 | 20 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | MTN-PIPF | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Loose bolts at clamps | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | MATS ETA 2/10 | 2025-01-01 | 2025-01-23 | 2025-01-10 | 2017-08-22 | 2017-05-24 | 25 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | MTN-SCAF | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Rig af gammelt spool/Rig out spool | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 39 | 0 | MATS ETA 2/10 | 2025-01-01 | 2025-01-23 | 2025-01-10 | 2017-08-22 | 2017-05-24 | 30 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | MTN-SCAF | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Rig af nyt Spool/Rig in new spool | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 52 | 0 | MATS ETA 2/10 | 2025-01-01 | 2025-01-23 | 2025-01-14 | 2017-08-22 | 2017-05-24 | 40 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | MTN-PIPF | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Fastgørelse/spænding spool.Bolt/Tension | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 26 | 0 | MATS ETA 2/10 | 2025-01-01 | 2025-01-23 | 2025-01-14 | 2017-08-22 | 2017-05-24 | 50 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | MTN-PIPF | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Oprydning.Cleanup | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 8 | 0 | MATS ETA 2/10 | 2025-01-01 | 2025-01-23 | 2025-01-16 | 2017-08-22 | 2017-05-24 | 60 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | MTN-SCAF | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Oprydning.Cleanup | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 71 | 0 | MATS ETA 2/10 | 2025-01-01 | 2025-01-23 | 2025-01-16 | 2017-08-22 | 2017-05-24 | 70 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | PRODTECH | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Desafing | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | MATS ETA 2/10 | 2025-01-01 | 2025-01-23 | 2025-01-15 | 2017-08-22 | 2017-05-24 | 80 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Additional materials 2 | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 110 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 | Genbestilling af: 6" SPOOL NO. HB-1134-0 | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 120 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 |  | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 130 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 |  | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 140 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 |  | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 150 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 |  | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 160 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 |  | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 170 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 |  | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 180 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 |  | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 190 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 |  | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 200 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 |  | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 210 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 |  | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 220 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 |  | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 230 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 3 | HBB01-GL | WDF | MTN-MECH | CON-WELD | 2100027613 | FFSPR Repl. HBB01 well -HBB-6-PHS-030-01 |  | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-23 | 2025-01-01 | 2017-08-22 | 2017-05-24 | 240 | REL | APPR OPND | HB /B /10/HBB-6-PHS-030-0101-GFW-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | C |  | MFM | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-INST | PRODTECH | 2100069365 | New HCV for LIT-416503 | Production Isolation | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2023-01-27 | 2022-08-30 | 10 | REL | APPR OPND | HB /D /30/HBDB-LIT-416503 | DIFF. PRESSURE INDIC. TRANSMITTER (ESD) |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-INST | MTN-MECH | 2100069365 | New HCV for LIT-416503 | Replace HCV valve | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2023-01-27 | 2022-08-30 | 20 | REL | APPR OPND | HB /D /30/HBDB-LIT-416503 | DIFF. PRESSURE INDIC. TRANSMITTER (ESD) |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-INST | MTN-INST | 2100069365 | New HCV for LIT-416503 | Transmitter recalibration | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2023-01-27 | 2022-08-30 | 30 | REL | APPR OPND | HB /D /30/HBDB-LIT-416503 | DIFF. PRESSURE INDIC. TRANSMITTER (ESD) |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBD-GLY | WDF | MTN-INST | PRODTECH | 2100069365 | New HCV for LIT-416503 | Production Deisolation w leak test | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2023-01-27 | 2022-08-30 | 40 | REL | APPR OPND | HB /D /30/HBDB-LIT-416503 | DIFF. PRESSURE INDIC. TRANSMITTER (ESD) |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | VEN-ELEC | MTN-ELEC | 2100071675 | Faulty PCB FU 620 | Faulty PCB FU 620 | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-01-01 | 2024-01-02 | 2024-01-01 | 2023-01-05 | 2022-08-23 | 10 | REL | APPR OPND | HB /C /06/HBCA-AE-1921 | UPS B - MAIN SUPPLY |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | VEN-ELEC | MTN-ELEC | 2100071675 | Faulty PCB FU 620 | Socomec Spareparts | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-01-01 | 2024-01-02 | 2024-01-01 | 2023-01-05 | 2022-08-23 | 20 | REL | APPR OPND | HB /C /06/HBCA-AE-1921 | UPS B - MAIN SUPPLY |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | VEN-ELEC | VEN-ELEC | 2100071675 | Faulty PCB FU 620 | Sitevisit - TBT. | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-01-01 | 2024-01-02 | 2024-01-01 | 2023-01-05 | 2022-08-23 | 30 | REL | APPR OPND | HB /C /06/HBCA-AE-1921 | UPS B - MAIN SUPPLY |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | VEN-ELEC | PRODTECH | 2100071675 | Faulty PCB FU 620 | Isolate - HBCA-AE-1921 | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-01-01 | 2024-01-02 | 2024-01-01 | 2023-01-05 | 2022-08-23 | 40 | REL | APPR OPND | HB /C /06/HBCA-AE-1921 | UPS B - MAIN SUPPLY |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | VEN-ELEC | VEN-ELEC | 2100071675 | Faulty PCB FU 620 | Replace Card. | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-01-01 | 2024-01-02 | 2024-01-01 | 2023-01-05 | 2022-08-23 | 50 | REL | APPR OPND | HB /C /06/HBCA-AE-1921 | UPS B - MAIN SUPPLY |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | VEN-ELEC | VEN-ELEC | 2100071675 | Faulty PCB FU 620 | Santion to test. | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0.5 | 0 |  | 2024-01-01 | 2024-01-02 | 2024-01-01 | 2023-01-05 | 2022-08-23 | 60 | REL | APPR OPND | HB /C /06/HBCA-AE-1921 | UPS B - MAIN SUPPLY |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | VEN-ELEC | VEN-ELEC | 2100071675 | Faulty PCB FU 620 | Test and check up. | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-01-01 | 2024-01-02 | 2024-01-01 | 2023-01-05 | 2022-08-23 | 70 | REL | APPR OPND | HB /C /06/HBCA-AE-1921 | UPS B - MAIN SUPPLY |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | VEN-ELEC | PRODTECH | 2100071675 | Faulty PCB FU 620 | Remove Isolation | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0.5 | 0 |  | 2024-01-01 | 2024-01-02 | 2024-01-02 | 2023-01-05 | 2022-08-23 | 80 | REL | APPR OPND | HB /C /06/HBCA-AE-1921 | UPS B - MAIN SUPPLY |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | VEN-ELEC | VEN-ELEC | 2100071675 | Faulty PCB FU 620 | Clean up site / Documentation. | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0.5 | 0 |  | 2024-01-01 | 2024-01-02 | 2024-01-02 | 2023-01-05 | 2022-08-23 | 90 | REL | APPR OPND | HB /C /06/HBCA-AE-1921 | UPS B - MAIN SUPPLY |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | VEN-ELEC | MTN-ELEC | 2100071675 | Faulty PCB FU 620 | PO Coromatic | REL GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-01-01 | 2024-01-02 | 2024-01-02 | 2023-01-05 | 2022-08-23 | 100 | REL | APPR OPND | HB /C /06/HBCA-AE-1921 | UPS B - MAIN SUPPLY |  | C |  | MEL | DK50 |  | PROK
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400241241 | 8Y FWP ANODE REPLACEMENT - HDBC-P-0301 | ISOLATION | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-08-22 | 2024-11-14 | 2024-08-22 | 2023-04-10 | 2023-01-09 | 10 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | A | DKHD-2046 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400241241 | 8Y FWP ANODE REPLACEMENT - HDBC-P-0301 | FIREWATER PUMP HDBC-P-0301 | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 120 | 0 |  | 2024-08-22 | 2024-11-14 | 2024-08-22 | 2023-04-10 | 2023-01-09 | 20 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | A | DKHD-2046 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241241 | 8Y FWP ANODE REPLACEMENT - HDBC-P-0301 | FIREWATER PUMP HDBC-P-0301 | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 120 | 0 |  | 2024-08-22 | 2024-11-14 | 2024-09-04 | 2023-04-10 | 2023-01-09 | 30 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | A | DKHD-2046 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400241241 | 8Y FWP ANODE REPLACEMENT - HDBC-P-0301 | DE-ISOLATION | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-08-22 | 2024-11-14 | 2024-09-28 | 2023-04-10 | 2023-01-09 | 40 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | A | DKHD-2046 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241241 | 8Y FWP ANODE REPLACEMENT - HDBC-P-0301 | Yearly capacity test | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-08-22 | 2024-11-14 | 2024-09-28 | 2023-04-10 | 2023-01-09 | 50 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | A | DKHD-2046 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400241241 | 8Y FWP ANODE REPLACEMENT - HDBC-P-0301 | Rigging assistance | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 120 | 0 |  | 2024-08-22 | 2024-11-14 | 2024-09-29 | 2023-04-10 | 2023-01-09 | 60 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | A | DKHD-2046 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | MTN-ROPE | 2400241241 | 8Y FWP ANODE REPLACEMENT - HDBC-P-0301 | Rope aasistance | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 36 | 0 |  | 2024-08-22 | 2024-11-14 | 2024-10-23 | 2023-04-10 | 2023-01-09 | 70 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | A | DKHD-2046 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400241241 | 8Y FWP ANODE REPLACEMENT - HDBC-P-0301 | Crane assisstance | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 80 | 0 |  | 2024-08-22 | 2024-11-14 | 2024-10-24 | 2023-04-10 | 2023-01-09 | 80 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | A | DKHD-2046 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | INP-SITE | 2400241241 | 8Y FWP ANODE REPLACEMENT - HDBC-P-0301 | Inspection of pad eyes / lifting points | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-08-22 | 2024-11-14 | 2024-11-13 | 2023-04-10 | 2023-01-09 | 90 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | A | DKHD-2046 | MMS | DK60 | MS0013
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241241 | 8Y FWP ANODE REPLACEMENT - HDBC-P-0301 | Materials | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-08-22 | 2024-11-14 | 2024-11-14 | 2023-04-10 | 2023-01-09 | 100 | REL | APPR OPND | HD /B /01/HDBD-A-0301 | FIREWATER PUMP PACKAGE |  | A | DKHD-2046 | MMS | DK60 | MS0013
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284408 | PSV Exchange - HBAA-PSV-50121 | Isolation of PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 10 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV021 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284408 | PSV Exchange - HBAA-PSV-50121 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 20 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV021 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284408 | PSV Exchange - HBAA-PSV-50121 | Rigging assist (remove) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 30 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV021 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284408 | PSV Exchange - HBAA-PSV-50121 | Remove PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-22 | 2024-12-31 | 2024-10-19 | 40 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV021 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284408 | PSV Exchange - HBAA-PSV-50121 | Install blinds | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-23 | 2024-12-31 | 2024-10-19 | 50 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV021 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284408 | PSV Exchange - HBAA-PSV-50121 | Re-certify PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-23 | 2024-12-31 | 2024-10-19 | 60 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV021 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284408 | PSV Exchange - HBAA-PSV-50121 | Rigging Assist (Install) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-24 | 2024-12-31 | 2024-10-19 | 70 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV021 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284408 | PSV Exchange - HBAA-PSV-50121 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-25 | 2024-12-31 | 2024-10-19 | 80 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV021 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284408 | PSV Exchange - HBAA-PSV-50121 | Install re-certified PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-26 | 2024-12-31 | 2024-10-19 | 90 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV021 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284408 | PSV Exchange - HBAA-PSV-50121 | De-isolation and leak test | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-27 | 2024-12-31 | 2024-10-19 | 100 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV021 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284408 | PSV Exchange - HBAA-PSV-50121 | Documentation & CNF WO | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-27 | 2024-12-31 | 2024-10-19 | 110 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV021 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284408 | PSV Exchange - HBAA-PSV-50121 | Check PSV flanges & alignment | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W09-W10 | 2024-10-19 | 2024-10-28 | 2024-10-28 | 2024-12-31 | 2024-10-19 | 120 | REL | APPR OPND | HB /A /20/HBAA-PSV-50121 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV021 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284409 | PSV Exchange - HBAA-PSV-50026 | Isolation of PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /A /28/HBAA-PSV-50026 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV022 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284409 | PSV Exchange - HBAA-PSV-50026 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /A /28/HBAA-PSV-50026 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV022 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284409 | PSV Exchange - HBAA-PSV-50026 | Install re-certified PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /A /28/HBAA-PSV-50026 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV022 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284409 | PSV Exchange - HBAA-PSV-50026 | De-isolation and leak test | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /A /28/HBAA-PSV-50026 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV022 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284409 | PSV Exchange - HBAA-PSV-50026 | Documentation & CNF WO | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /A /28/HBAA-PSV-50026 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV022 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284409 | PSV Exchange - HBAA-PSV-50026 | Check PSV flanges & alignment | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /A /28/HBAA-PSV-50026 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV022 | MMS | DK50
2026-W13-14 | A | HB WI SD | WPM | MTN-MECH | PRODTECH | 2400284410 | PSV Exchange - HBAA-PSV-38112 | Isolation of PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 10 | REL | APPR OPND | HB /A /50/HBAA-PSV-38112 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV030 | MMS | DK50
2026-W13-14 | A | HB WI SD | WPM | MTN-MECH | PRODTECH | 2400284410 | PSV Exchange - HBAA-PSV-38112 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 20 | REL | APPR OPND | HB /A /50/HBAA-PSV-38112 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV030 | MMS | DK50
2026-W13-14 | A | HB WI SD | WPM | MTN-MECH | MTN-RIGG | 2400284410 | PSV Exchange - HBAA-PSV-38112 | Rigging assist (remove) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 30 | REL | APPR OPND | HB /A /50/HBAA-PSV-38112 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV030 | MMS | DK50
2026-W13-14 | A | HB WI SD | WPM | MTN-MECH | MTN-MECH | 2400284410 | PSV Exchange - HBAA-PSV-38112 | Remove PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-22 | 2024-12-31 | 2024-10-19 | 40 | REL | APPR OPND | HB /A /50/HBAA-PSV-38112 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV030 | MMS | DK50
2026-W13-14 | A | HB WI SD | WPM | MTN-MECH | MTN-MECH | 2400284410 | PSV Exchange - HBAA-PSV-38112 | Install blinds | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-23 | 2024-12-31 | 2024-10-19 | 50 | REL | APPR OPND | HB /A /50/HBAA-PSV-38112 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV030 | MMS | DK50
2026-W13-14 | A | HB WI SD | WPM | MTN-MECH | MTN-MECH | 2400284410 | PSV Exchange - HBAA-PSV-38112 | Re-certify PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-23 | 2024-12-31 | 2024-10-19 | 60 | REL | APPR OPND | HB /A /50/HBAA-PSV-38112 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV030 | MMS | DK50
2026-W13-14 | A | HB WI SD | WPM | MTN-MECH | MTN-RIGG | 2400284410 | PSV Exchange - HBAA-PSV-38112 | Rigging Assist (Install) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-24 | 2024-12-31 | 2024-10-19 | 70 | REL | APPR OPND | HB /A /50/HBAA-PSV-38112 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV030 | MMS | DK50
2026-W13-14 | A | HB WI SD | WPM | MTN-MECH | PRODTECH | 2400284410 | PSV Exchange - HBAA-PSV-38112 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-25 | 2024-12-31 | 2024-10-19 | 80 | REL | APPR OPND | HB /A /50/HBAA-PSV-38112 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV030 | MMS | DK50
2026-W13-14 | A | HB WI SD | WPM | MTN-MECH | MTN-MECH | 2400284410 | PSV Exchange - HBAA-PSV-38112 | Install re-certified PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-26 | 2024-12-31 | 2024-10-19 | 90 | REL | APPR OPND | HB /A /50/HBAA-PSV-38112 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV030 | MMS | DK50
2026-W13-14 | A | HB WI SD | WPM | MTN-MECH | PRODTECH | 2400284410 | PSV Exchange - HBAA-PSV-38112 | De-isolation and leak test | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-27 | 2024-12-31 | 2024-10-19 | 100 | REL | APPR OPND | HB /A /50/HBAA-PSV-38112 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV030 | MMS | DK50
2026-W13-14 | A | HB WI SD | WPM | MTN-MECH | MTN-MECH | 2400284410 | PSV Exchange - HBAA-PSV-38112 | Documentation & CNF WO | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-27 | 2024-12-31 | 2024-10-19 | 110 | REL | APPR OPND | HB /A /50/HBAA-PSV-38112 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV030 | MMS | DK50
2026-W13-14 | A | HB WI SD | WPM | MTN-MECH | VEN-INSP | 2400284410 | PSV Exchange - HBAA-PSV-38112 | Check PSV flanges & alignment | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-28 | 2024-10-28 | 2024-12-31 | 2024-10-19 | 120 | REL | APPR OPND | HB /A /50/HBAA-PSV-38112 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV030 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284417 | PSV Exchange - HBDB-PSV-346111 | Isolation of PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /27/HBDB-PSV-346111 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV104 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284417 | PSV Exchange - HBDB-PSV-346111 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /27/HBDB-PSV-346111 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV104 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284417 | PSV Exchange - HBDB-PSV-346111 | Install re-certified PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /27/HBDB-PSV-346111 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV104 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284417 | PSV Exchange - HBDB-PSV-346111 | De-isolation and leak test | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /27/HBDB-PSV-346111 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV104 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284417 | PSV Exchange - HBDB-PSV-346111 | Documentation & CNF WO | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /27/HBDB-PSV-346111 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV104 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284417 | PSV Exchange - HBDB-PSV-346111 | Check PSV flanges & alignment | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /27/HBDB-PSV-346111 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV104 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284421 | PSV Exchange - HBDB-PSV-417101 | Isolation of PSV | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-20 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /30/HBDB-PSV-417101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV128 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284421 | PSV Exchange - HBDB-PSV-417101 | Prod Assist (breaking containment) | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-20 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /30/HBDB-PSV-417101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV128 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284421 | PSV Exchange - HBDB-PSV-417101 | Rigging assist (remove) | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2024-10-12 | 2024-10-20 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /30/HBDB-PSV-417101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV128 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284421 | PSV Exchange - HBDB-PSV-417101 | Remove PSV and install blinds | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-20 | 2024-10-15 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /30/HBDB-PSV-417101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV128 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284421 | PSV Exchange - HBDB-PSV-417101 | Re-certify PSV | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-20 | 2024-10-16 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /30/HBDB-PSV-417101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV128 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284421 | PSV Exchange - HBDB-PSV-417101 | Rigging Assist (Install) | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-12 | 2024-10-20 | 2024-10-16 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /30/HBDB-PSV-417101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV128 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284421 | PSV Exchange - HBDB-PSV-417101 | Prod Assist (breaking containment) | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-20 | 2024-10-18 | 2024-12-31 | 2024-10-12 | 70 | REL | APPR OPND | HB /D /30/HBDB-PSV-417101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV128 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284421 | PSV Exchange - HBDB-PSV-417101 | Install re-certified PSV | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-20 | 2024-10-18 | 2024-12-31 | 2024-10-12 | 80 | REL | APPR OPND | HB /D /30/HBDB-PSV-417101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV128 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284421 | PSV Exchange - HBDB-PSV-417101 | De-isolation and leak test | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-20 | 2024-10-19 | 2024-12-31 | 2024-10-12 | 90 | REL | APPR OPND | HB /D /30/HBDB-PSV-417101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV128 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284421 | PSV Exchange - HBDB-PSV-417101 | Documentation & CNF WO | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-20 | 2024-10-20 | 2024-12-31 | 2024-10-12 | 100 | REL | APPR OPND | HB /D /30/HBDB-PSV-417101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV128 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284421 | PSV Exchange - HBDB-PSV-417101 | Check PSV flanges & alignment | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-20 | 2024-10-20 | 2024-12-31 | 2024-10-12 | 110 | REL | APPR OPND | HB /D /30/HBDB-PSV-417101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV128 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284422 | PSV Exchange - HBDB-PSV-417301 | Isolation of PSV | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /30/HBDB-PSV-417301 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV130 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284422 | PSV Exchange - HBDB-PSV-417301 | Prod Assist (breaking containment) | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /30/HBDB-PSV-417301 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV130 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284422 | PSV Exchange - HBDB-PSV-417301 | Install re-certified PSV | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /30/HBDB-PSV-417301 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV130 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284422 | PSV Exchange - HBDB-PSV-417301 | De-isolation and leak test | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /30/HBDB-PSV-417301 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV130 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284422 | PSV Exchange - HBDB-PSV-417301 | Documentation & CNF WO | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /30/HBDB-PSV-417301 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV130 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284422 | PSV Exchange - HBDB-PSV-417301 | Check PSV flanges & alignment | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /30/HBDB-PSV-417301 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV130 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284423 | PSV Exchange - HBDB-PSV-417401 | Isolation of PSV | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /30/HBDB-PSV-417401 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV131 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284423 | PSV Exchange - HBDB-PSV-417401 | Prod Assist (breaking containment) | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /30/HBDB-PSV-417401 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV131 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284423 | PSV Exchange - HBDB-PSV-417401 | Install re-certified PSV | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /30/HBDB-PSV-417401 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV131 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284423 | PSV Exchange - HBDB-PSV-417401 | De-isolation and leak test | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /30/HBDB-PSV-417401 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV131 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284423 | PSV Exchange - HBDB-PSV-417401 | Documentation & CNF WO | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /30/HBDB-PSV-417401 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV131 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284423 | PSV Exchange - HBDB-PSV-417401 | Check PSV flanges & alignment | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /30/HBDB-PSV-417401 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV131 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284424 | PSV Exchange - HBDB-PSV-417502 | Isolation of PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /30/HBDB-PSV-417502 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV134 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284424 | PSV Exchange - HBDB-PSV-417502 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /30/HBDB-PSV-417502 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV134 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284424 | PSV Exchange - HBDB-PSV-417502 | Install re-certified PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /30/HBDB-PSV-417502 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV134 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284424 | PSV Exchange - HBDB-PSV-417502 | De-isolation and leak test | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /30/HBDB-PSV-417502 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV134 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284424 | PSV Exchange - HBDB-PSV-417502 | Documentation & CNF WO | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /30/HBDB-PSV-417502 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV134 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284424 | PSV Exchange - HBDB-PSV-417502 | Check PSV flanges & alignment | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /30/HBDB-PSV-417502 | PRESSURE SAFETY VALVE |  | C | DKHB-PSV134 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284425 | PSV Exchange - HBDB-PSV-418101 | Isolation of PSV | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /30/HBDB-PSV-418101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV136 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284425 | PSV Exchange - HBDB-PSV-418101 | Prod Assist (breaking containment) | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /30/HBDB-PSV-418101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV136 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284425 | PSV Exchange - HBDB-PSV-418101 | Install re-certified PSV | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /30/HBDB-PSV-418101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV136 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284425 | PSV Exchange - HBDB-PSV-418101 | De-isolation and leak test | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /30/HBDB-PSV-418101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV136 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284425 | PSV Exchange - HBDB-PSV-418101 | Documentation & CNF WO | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /30/HBDB-PSV-418101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV136 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284425 | PSV Exchange - HBDB-PSV-418101 | Check PSV flanges & alignment | REL CSER GMPS MACM PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /30/HBDB-PSV-418101 | PRESSURE SAFETY VALVE |  | A | DKHB-PSV136 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284426 | PSV Calibration - HBDC-PSV-415201 | Isolation of PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-11-15 | 2025-01-19 | 2024-11-15 | 2024-12-31 | 2024-11-15 | 10 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284426 | PSV Calibration - HBDC-PSV-415201 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-11-15 | 2025-01-19 | 2024-11-15 | 2024-12-31 | 2024-11-15 | 20 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284426 | PSV Calibration - HBDC-PSV-415201 | Rigging assist (remove) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2024-11-15 | 2025-01-19 | 2024-11-15 | 2024-12-31 | 2024-11-15 | 30 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284426 | PSV Calibration - HBDC-PSV-415201 | Remove PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-11-15 | 2025-01-19 | 2024-11-17 | 2024-12-31 | 2024-11-15 | 40 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284426 | PSV Calibration - HBDC-PSV-415201 | Install blinds | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-11-15 | 2025-01-19 | 2024-11-18 | 2024-12-31 | 2024-11-15 | 50 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284426 | PSV Calibration - HBDC-PSV-415201 | Backload PSV to Norspie Workshop | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-11-15 | 2025-01-19 | 2024-11-18 | 2024-12-31 | 2024-11-15 | 51 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284426 | PSV Calibration - HBDC-PSV-415201 | Re-certify PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-11-15 | 2025-01-19 | 2024-11-18 | 2024-12-31 | 2024-11-15 | 60 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284426 | PSV Calibration - HBDC-PSV-415201 | Rigging Assist (Install) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-11-15 | 2025-01-19 | 2025-01-17 | 2024-12-31 | 2024-11-15 | 70 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284426 | PSV Calibration - HBDC-PSV-415201 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-11-15 | 2025-01-19 | 2025-01-18 | 2024-12-31 | 2024-11-15 | 80 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284426 | PSV Calibration - HBDC-PSV-415201 | Install re-certified PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-11-15 | 2025-01-19 | 2025-01-18 | 2024-12-31 | 2024-11-15 | 90 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284426 | PSV Calibration - HBDC-PSV-415201 | De-isolation and leak test | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-11-15 | 2025-01-19 | 2025-01-17 | 2024-12-31 | 2024-11-15 | 100 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284426 | PSV Calibration - HBDC-PSV-415201 | Documentation & CNF WO | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-11-15 | 2025-01-19 | 2025-01-17 | 2024-12-31 | 2024-11-15 | 110 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284426 | PSV Calibration - HBDC-PSV-415201 | Check PSV flanges & alignment | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W09-W10 | 2024-11-15 | 2025-01-19 | 2025-01-17 | 2024-12-31 | 2024-11-15 | 120 | REL | APPR OPND | HB /D /30/HBDC-PSV-415201 | PRESSURE SAFETY RELIEF VALVE |  | A | DKHB-PSV137 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284427 | PSV Calibration - HBDD-PSV-415301 | Isolation of PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 10 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284427 | PSV Calibration - HBDD-PSV-415301 | Prod Assist (breaking containment) | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 20 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284427 | PSV Calibration - HBDD-PSV-415301 | Rigging assist (remove) | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 7 |  | 2024-10-19 | 2024-12-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 30 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284427 | PSV Calibration - HBDD-PSV-415301 | Remove PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 40 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284427 | PSV Calibration - HBDD-PSV-415301 | Install blinds | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-20 | 2024-12-31 | 2024-10-19 | 50 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284427 | PSV Calibration - HBDD-PSV-415301 | Backload PSV to Norspie Workshop | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-20 | 2024-12-31 | 2024-10-19 | 51 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284427 | PSV Calibration - HBDD-PSV-415301 | Re-certify PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-10-20 | 2024-12-31 | 2024-10-19 | 60 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284427 | PSV Calibration - HBDD-PSV-415301 | Rigging Assist (Install) | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-19 | 2024-12-31 | 2024-10-19 | 70 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284427 | PSV Calibration - HBDD-PSV-415301 | Prod Assist (breaking containment) | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-20 | 2024-12-31 | 2024-10-19 | 80 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284427 | PSV Calibration - HBDD-PSV-415301 | Install re-certified PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-19 | 2024-12-31 | 2024-10-19 | 90 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284427 | PSV Calibration - HBDD-PSV-415301 | De-isolation and leak test | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-20 | 2024-12-31 | 2024-10-19 | 100 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284427 | PSV Calibration - HBDD-PSV-415301 | Documentation & CNF WO | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-12-21 | 2024-12-20 | 2024-12-31 | 2024-10-19 | 110 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284427 | PSV Calibration - HBDD-PSV-415301 | Check PSV flanges & alignment | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W09-W10 | 2024-10-19 | 2024-12-21 | 2024-12-20 | 2024-12-31 | 2024-10-19 | 120 | PCNF REL | APPR OPND | HB /D /30/HBDD-PSV-415301 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV139 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284428 | PSV Exchange - HBDC-PSV-535508 | Isolation of PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /31/HBDC-PSV-535508 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV142 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284428 | PSV Exchange - HBDC-PSV-535508 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /31/HBDC-PSV-535508 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV142 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284428 | PSV Exchange - HBDC-PSV-535508 | Install re-certified PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /31/HBDC-PSV-535508 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV142 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284428 | PSV Exchange - HBDC-PSV-535508 | De-isolation and leak test | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /31/HBDC-PSV-535508 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV142 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284428 | PSV Exchange - HBDC-PSV-535508 | Documentation & CNF WO | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /31/HBDC-PSV-535508 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV142 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284428 | PSV Exchange - HBDC-PSV-535508 | Check PSV flanges & alignment | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /31/HBDC-PSV-535508 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV142 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284430 | PSV Calibration - HBDD-PSV-445201 | Isolation of PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 10 | PCNF REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284430 | PSV Calibration - HBDD-PSV-445201 | Prod Assist (breaking containment) | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 20 | PCNF REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284430 | PSV Calibration - HBDD-PSV-445201 | Rigging assist (remove) | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 4 |  | 2024-10-30 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 30 | PCNF REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284430 | PSV Calibration - HBDD-PSV-445201 | Remove PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-30 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 40 | PCNF REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284430 | PSV Calibration - HBDD-PSV-445201 | Install blinds | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 50 | PCNF REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284430 | PSV Calibration - HBDD-PSV-445201 | Backload PSV to Norspie Workshop | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-10-30 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 51 | REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284430 | PSV Calibration - HBDD-PSV-445201 | Re-certify PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-30 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 2024-10-30 | 60 | PCNF REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284430 | PSV Calibration - HBDD-PSV-445201 | Rigging Assist (Install) | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-30 | 2024-12-29 | 2024-12-29 | 2024-12-31 | 2024-10-30 | 70 | PCNF REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284430 | PSV Calibration - HBDD-PSV-445201 | Prod Assist (breaking containment) | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2024-12-29 | 2024-12-29 | 2024-12-31 | 2024-10-30 | 80 | PCNF REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284430 | PSV Calibration - HBDD-PSV-445201 | Install re-certified PSV | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-30 | 2024-12-29 | 2024-12-29 | 2024-12-31 | 2024-10-30 | 90 | PCNF REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284430 | PSV Calibration - HBDD-PSV-445201 | De-isolation and leak test | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-30 | 2024-12-29 | 2024-12-29 | 2024-12-31 | 2024-10-30 | 100 | PCNF REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284430 | PSV Calibration - HBDD-PSV-445201 | Documentation & CNF WO | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-30 | 2024-12-29 | 2024-12-29 | 2024-12-31 | 2024-10-30 | 110 | PCNF REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284430 | PSV Calibration - HBDD-PSV-445201 | Check PSV flanges & alignment | REL PCNF CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W09-W10 | 2024-10-30 | 2024-12-29 | 2024-12-29 | 2024-12-31 | 2024-10-30 | 120 | PCNF REL | APPR OPND | HB /D /31/HBDD-PSV-445201 | PRESSURE SAFETY RELIEF VALVE |  | D | DKHB-PSV146 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284432 | PSV Exchange - HBDC-PSV-535503 | Isolation of PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /34/HBDC-PSV-535503 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV158 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284432 | PSV Exchange - HBDC-PSV-535503 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /34/HBDC-PSV-535503 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV158 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284432 | PSV Exchange - HBDC-PSV-535503 | Install re-certified PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /34/HBDC-PSV-535503 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV158 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284432 | PSV Exchange - HBDC-PSV-535503 | De-isolation and leak test | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /34/HBDC-PSV-535503 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV158 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284432 | PSV Exchange - HBDC-PSV-535503 | Documentation & CNF WO | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /34/HBDC-PSV-535503 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV158 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284432 | PSV Exchange - HBDC-PSV-535503 | Check PSV flanges & alignment | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /34/HBDC-PSV-535503 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV158 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284436 | PSV Exchange - HBDC-PSV-575301 | Isolation of PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 10 | REL | APPR OPND | HB /D /70/HBDC-PSV-575301 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV175 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284436 | PSV Exchange - HBDC-PSV-575301 | Prod Assist (breaking containment) | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 20 | REL | APPR OPND | HB /D /70/HBDC-PSV-575301 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV175 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284436 | PSV Exchange - HBDC-PSV-575301 | Install re-certified PSV | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 30 | REL | APPR OPND | HB /D /70/HBDC-PSV-575301 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV175 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284436 | PSV Exchange - HBDC-PSV-575301 | De-isolation and leak test | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 40 | REL | APPR OPND | HB /D /70/HBDC-PSV-575301 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV175 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284436 | PSV Exchange - HBDC-PSV-575301 | Documentation & CNF WO | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 50 | REL | APPR OPND | HB /D /70/HBDC-PSV-575301 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV175 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284436 | PSV Exchange - HBDC-PSV-575301 | Check PSV flanges & alignment | REL CSER GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 60 | REL | APPR OPND | HB /D /70/HBDC-PSV-575301 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV175 | MMS | DK50
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400307664 | 1Y PED. CRANE CHECK VENDOR-HBCO-A-6101 | ISOLATION BY PRODUCTION | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-19 | 2024-04-08 | 2024-05-16 | 2024-04-16 | 10 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKHB-0658 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400307664 | 1Y PED. CRANE CHECK VENDOR-HBCO-A-6101 | PED. CRANE CHECK VENDOR-HBCO-A-6101 | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 5 | 0 | W15-W16 | 2024-04-08 | 2024-04-19 | 2024-04-08 | 2024-05-16 | 2024-04-16 | 20 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKHB-0658 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | VEN-CRAN | 2400307664 | 1Y PED. CRANE CHECK VENDOR-HBCO-A-6101 | PED. CRANE CHECK VENDOR-HBCO-A-6101 | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 92 | 0 | W15-W16 | 2024-04-08 | 2024-04-19 | 2024-04-09 | 2024-05-16 | 2024-04-16 | 30 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKHB-0658 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400307664 | 1Y PED. CRANE CHECK VENDOR-HBCO-A-6101 | PED. CRANE CHECK VENDOR-HBCO-A-6101 | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 | W15-W16 | 2024-04-08 | 2024-04-19 | 2024-04-14 | 2024-05-16 | 2024-04-16 | 40 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKHB-0658 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400307664 | 1Y PED. CRANE CHECK VENDOR-HBCO-A-6101 | DE-ISOLATION BY PRODUCTION | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-19 | 2024-04-15 | 2024-05-16 | 2024-04-16 | 50 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKHB-0658 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-SCAF | 2400307664 | 1Y PED. CRANE CHECK VENDOR-HBCO-A-6101 | Minor Scaffold for access to slew bolts | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 | W15-W16 | 2024-04-08 | 2024-04-19 | 2024-04-16 | 2024-05-16 | 2024-04-16 | 60 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKHB-0658 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400307664 | 1Y PED. CRANE CHECK VENDOR-HBCO-A-6101 | General assistance | REL PRT GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 | W15-W16 | 2024-04-08 | 2024-04-19 | 2024-04-17 | 2024-05-16 | 2024-04-16 | 70 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | C | DKHB-0658 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400314637 | 1Y PED. CRANE CHECK VENDOR-HBAB-X-6130 | ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-20 | 2024-07-05 | 2024-06-20 | 2024-06-22 | 2024-05-23 | 10 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | C | DKHB-0656 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400314637 | 1Y PED. CRANE CHECK VENDOR-HBAB-X-6130 | PED. CRANE VENDOR-HBAB-X-6130 | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 48 | 0 |  | 2024-06-20 | 2024-07-05 | 2024-06-20 | 2024-06-22 | 2024-05-23 | 20 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | C | DKHB-0656 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400314637 | 1Y PED. CRANE CHECK VENDOR-HBAB-X-6130 | PED. CRANE VENDOR-HBAB-X-6130 | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 20 | 0 |  | 2024-06-20 | 2024-07-05 | 2024-06-22 | 2024-06-22 | 2024-05-23 | 30 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | C | DKHB-0656 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400314637 | 1Y PED. CRANE CHECK VENDOR-HBAB-X-6130 | DE-ISOLATION BY PRODUCTION | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-20 | 2024-07-05 | 2024-06-25 | 2024-06-22 | 2024-05-23 | 40 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | C | DKHB-0656 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400314637 | 1Y PED. CRANE CHECK VENDOR-HBAB-X-6130 | Check of slip ring & electric checks | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2024-06-20 | 2024-07-05 | 2024-06-25 | 2024-06-22 | 2024-05-23 | 50 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | C | DKHB-0656 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-ROUS | 2400314637 | 1Y PED. CRANE CHECK VENDOR-HBAB-X-6130 | Assist with crane operation | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-06-20 | 2024-07-05 | 2024-06-30 | 2024-06-22 | 2024-05-23 | 60 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | C | DKHB-0656 | MMS | DK50 | MS0154 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400314637 | 1Y PED. CRANE CHECK VENDOR-HBAB-X-6130 | General assistance | REL GMPS MANC PRC SETC | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-06-20 | 2024-07-05 | 2024-07-03 | 2024-06-22 | 2024-05-23 | 70 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | C | DKHB-0656 | MMS | DK50 | MS0154 | PROK
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Vibration with Well Instrument Tubing | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 0 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-07-12 | 2020-06-22 | 10 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-SCAF | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Built scaffold near by: WELL HDA-11 | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 6 | 0 | ? W44-45 | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-07-12 | 2020-06-22 | 20 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Isolate inst. pipe to tag: HDAB-PI-30112 | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 2 | 0 | ? W44-45 | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2020-07-12 | 2020-06-22 | 30 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Disassenble and refit Instrument to std. | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 2 | 0 | ? W44-45 | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2020-07-12 | 2020-06-22 | 40 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | De-Isolate Tubing for PI | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2020-07-12 | 2020-06-22 | 50 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Test tag: PI | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2020-07-12 | 2020-06-22 | 60 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Finish job and cleanup work area | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 1 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2020-07-12 | 2020-06-22 | 70 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-SCAF | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Remove scaffold | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2020-07-12 | 2020-06-22 | 80 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-SCAF | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Built scaffold near by: WELL HDA-13 | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-07-12 | 2020-06-22 | 90 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Isolate inst. pipe to tag: HDAB-ESDV-291 | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-07-12 | 2020-06-22 | 100 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Disassenble and refit Instrument to std. | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2020-07-12 | 2020-06-22 | 110 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | De-Isolate Tubing for ESDV | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-07-12 | 2020-06-22 | 120 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Test tag: ESDV | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-07-12 | 2020-06-22 | 130 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Finish job and cleanup work area | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 1 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2020-07-12 | 2020-06-22 | 140 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-SCAF | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Remove scaffold | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2020-07-12 | 2020-06-22 | 150 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Isolate inst. pipe to tag: HDAB-WCV-3027 | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-07-12 | 2020-06-22 | 190 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Disassenble and refit Instrument to std. | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-07-12 | 2020-06-22 | 200 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | De-Isolate Tubing for WCV | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-07-12 | 2020-06-22 | 210 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Test tag: WCV | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-07-12 | 2020-06-22 | 220 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Finish job and cleanup work area | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 1 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-07-12 | 2020-06-22 | 230 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
0 | 3 | HDAPWELL | WDF | MTN-INST | CON-INST | 2100033887 | CAMP. Install Well Instr. Tubing(INST-TU | Materials | REL GMPS MANC PPRT PRC SETC | APPR PMAT AWCA RDBL SREQ | 0 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-07-12 | 2020-06-22 | 240 | REL | APPR OPND | HD /A /07/HYDRAULICS-SYSTEM | HYDRAULICS SYSTEM | 99000120 | E |  | MIN | DK60
2024-W31-32 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100036153 | ANOS Missing Angle Support for 3"-WF Lin | 2100036153-0002~COATING | REL PCNF GMPS MANC PRC SETC | APPR PMAT | 0 | 0 |  | 2020-10-27 | 2020-10-28 | 2020-10-27 | 2021-03-26 | 2020-10-27 | 2 | REL | APPR OPND | HB /D /01/P-G | PIPING GROUP |  | A |  | MFM | DK50
2024-W31-32 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100036153 | ANOS Missing Angle Support for 3"-WF Lin | 2100036153-0003~CONSUMABLES | REL PCNF GMPS MANC PRC SETC | APPR PMAT | 0 | 0 |  | 2020-10-27 | 2020-10-28 | 2020-10-27 | 2021-03-26 | 2020-10-27 | 3 | REL | APPR OPND | HB /D /01/P-G | PIPING GROUP |  | A |  | MFM | DK50
2024-W31-32 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100036153 | ANOS Missing Angle Support for 3"-WF Lin | 2100036153-0004~ALTRAD | REL PCNF GMPS MANC PRC SETC | APPR PMAT | 0 | 0 |  | 2020-10-27 | 2020-10-28 | 2020-10-27 | 2021-03-26 | 2020-10-27 | 4 | REL | APPR OPND | HB /D /01/P-G | PIPING GROUP |  | A |  | MFM | DK50
2024-W31-32 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100036153 | ANOS Missing Angle Support for 3"-WF Lin | 2100036153-0005~DRAFT-MOURITSEN | REL PCNF GMPS MANC PRC SETC | APPR PMAT | 0 | 0 |  | 2020-10-27 | 2020-10-28 | 2020-10-27 | 2021-03-26 | 2020-10-27 | 5 | REL | APPR OPND | HB /D /01/P-G | PIPING GROUP |  | A |  | MFM | DK50
2024-W31-32 | 4 |  | WDF | MTN-ROPE | MTN-MECH | 2100036153 | ANOS Missing Angle Support for 3"-WF Lin | Missing Angle Support for 3"-WF Line | REL PCNF GMPS MANC PRC SETC | APPR PMAT | 0 | 0 |  | 2020-10-27 | 2020-10-28 | 2020-10-27 | 2021-03-26 | 2020-10-27 | 10 | REL | APPR OPND | HB /D /01/P-G | PIPING GROUP |  | A |  | MFM | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-PIPF | 2100037399 | Replace HBDB-XCV-536456 | prep. for permit, site visit, job - Weld | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-12-24 | 2020-09-25 | 10 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-MECH | 2100037399 | Replace HBDB-XCV-536456 | prep. for permit, site visit, job - Mech | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 2 | 4 | Opertunity | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-12-24 | 2020-09-25 | 20 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-RIGG | 2100037399 | Replace HBDB-XCV-536456 | prep. for permit, site visit, job - Rigg | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-12-24 | 2020-09-25 | 30 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-RIGG | 2100037399 | Replace HBDB-XCV-536456 | rig up lifting equipment - Rigg | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2020-12-24 | 2020-09-25 | 40 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | PRODTECH | 2100037399 | Replace HBDB-XCV-536456 | Isolate valve & act - Prod | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2020-12-24 | 2020-09-25 | 50 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-PIPF | 2100037399 | Replace HBDB-XCV-536456 | Remove valve and Act - Weld | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-12-24 | 2020-09-25 | 60 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-MECH | 2100037399 | Replace HBDB-XCV-536456 | Install old act on new valve - Mech | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-12-24 | 2020-09-25 | 70 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-PIPF | 2100037399 | Replace HBDB-XCV-536456 | Install new valve & act. - Weld | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2020-12-24 | 2020-09-25 | 80 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | PRODTECH | 2100037399 | Replace HBDB-XCV-536456 | De-isolate, leak test etc - Prod | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2020-12-24 | 2020-09-25 | 110 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-RIGG | 2100037399 | Replace HBDB-XCV-536456 | remove lifting equipment - Rigg | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2020-12-24 | 2020-09-25 | 120 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-PIPF | 2100037399 | Replace HBDB-XCV-536456 | house keeping - Weld | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2020-12-24 | 2020-09-25 | 130 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-MECH | 2100037399 | Replace HBDB-XCV-536456 | house keeping - Mech | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2020-12-24 | 2020-09-25 | 140 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-RIGG | 2100037399 | Replace HBDB-XCV-536456 | house keeping - Rigg | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2020-12-24 | 2020-09-25 | 150 | PCNF REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | PRODTECH | 2100037399 | Replace HBDB-XCV-536456 | Production assistance safing hydraulic | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-12-24 | 2020-09-25 | 160 | REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-RIGG | 2100037399 | Replace HBDB-XCV-536456 | rig up lifting equipment - Rigg | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-12-24 | 2020-09-25 | 170 | REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-MECH | 2100037399 | Replace HBDB-XCV-536456 | Replace actuator | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-12-24 | 2020-09-25 | 180 | REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-RIGG | 2100037399 | Replace HBDB-XCV-536456 | remove lifting equipment - Rigg | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-12-24 | 2020-09-25 | 190 | REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | PRODTECH | 2100037399 | Replace HBDB-XCV-536456 | De-isolate, leak test etc - Prod | REL PCNF GMPS MANC PPRT PRC SETC | APPR PMAT | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2020-12-24 | 2020-09-25 | 200 | REL | APPR OPND | HB /D /51/HBDB-XCV-536456 | ON OFF VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100055025 | Cabinet sign and deluge hose | Isolation of system | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT | 1 | 0 | W49 IOP IR-HB3970 | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2022-04-27 | 2021-11-28 | 10 | PCNF REL | APPR OPND | HB /A /01/HBAA-XCV-03720 | 8" DELUGE VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | VEN-ROPE | 2100055025 | Cabinet sign and deluge hose | Mount new cabinet sign | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT | 1 | 0 |  | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2022-04-27 | 2021-11-28 | 30 | PCNF REL | APPR OPND | HB /A /01/HBAA-XCV-03720 | 8" DELUGE VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100055025 | Cabinet sign and deluge hose | De-isolation | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT | 1 | 0 |  | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2022-04-27 | 2021-11-28 | 40 | PCNF REL | APPR OPND | HB /A /01/HBAA-XCV-03720 | 8" DELUGE VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | VEN-ROPE | 2100055025 | Cabinet sign and deluge hose | Additional materials. | REL PCNF PRT GMPS MANC PRC SETC | APPR PMAT | 0 | 0 |  | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2022-04-27 | 2021-11-28 | 50 | PCNF REL | APPR OPND | HB /A /01/HBAA-XCV-03720 | 8" DELUGE VALVE |  | A |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100070043 | XCV-30109 is internally leaking | Prepare & Rigging of XCV valve | REL PRT GMPS MANC PRC SETC | APPR PMAT | 20 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2023-02-05 | 2022-09-08 | 10 | REL | APPR OPND | HB /A /10/HBAA-XCV-30109 | 8" 2500# T PLUG VALVE FROM WELL 10 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100070043 | XCV-30109 is internally leaking | Production Isolation | REL PRT GMPS MANC PRC SETC | APPR PMAT | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2023-02-05 | 2022-09-08 | 20 | REL | APPR OPND | HB /A /10/HBAA-XCV-30109 | 8" 2500# T PLUG VALVE FROM WELL 10 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100070043 | XCV-30109 is internally leaking | Replace XCV-30109 | REL PRT GMPS MANC PRC SETC | APPR PMAT | 16 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2023-02-05 | 2022-09-08 | 30 | REL | APPR OPND | HB /A /10/HBAA-XCV-30109 | 8" 2500# T PLUG VALVE FROM WELL 10 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-INST | 2100070043 | XCV-30109 is internally leaking | Inst part of XCV replacement | REL PRT GMPS MANC PRC SETC | APPR PMAT | 6 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2023-02-05 | 2022-09-08 | 40 | REL | APPR OPND | HB /A /10/HBAA-XCV-30109 | 8" 2500# T PLUG VALVE FROM WELL 10 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100070043 | XCV-30109 is internally leaking | Production De-isolation w Leaktest | REL PRT GMPS MANC PRC SETC | APPR PMAT | 3 | 0 |  | 2025-01-01 | 2025-01-07 | 2025-01-07 | 2023-02-05 | 2022-09-08 | 50 | REL | APPR OPND | HB /A /10/HBAA-XCV-30109 | 8" 2500# T PLUG VALVE FROM WELL 10 |  | F |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100076963 | LOTI: HBAA-FCV-29193 Many Faults | Rigging Pre Work | REL GMPS MANC PRC SETC | APPR PMAT | 8 | 0 | W19-W20 | 2024-04-26 | 2024-04-30 | 2024-04-26 | 2023-04-26 | 2022-12-12 | 10 | REL | APPR OPND | HB /A /37/HBAA-FCV-29193 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100076963 | LOTI: HBAA-FCV-29193 Many Faults | Production isolation | REL GMPS MANC PRC SETC | APPR PMAT | 3 | 0 | W19-W20 | 2024-04-26 | 2024-04-30 | 2024-04-27 | 2023-04-26 | 2022-12-12 | 20 | REL | APPR OPND | HB /A /37/HBAA-FCV-29193 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-INST | 2100076963 | LOTI: HBAA-FCV-29193 Many Faults | Cable/Tubing removal | REL GMPS MANC PRC SETC | APPR PMAT | 4 | 0 | W19-W20 | 2024-04-26 | 2024-04-30 | 2024-04-27 | 2023-04-26 | 2022-12-12 | 30 | REL | APPR OPND | HB /A /37/HBAA-FCV-29193 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100076963 | LOTI: HBAA-FCV-29193 Many Faults | Rigger Assistance/Lifting/Post work | REL GMPS MANC PRC SETC | APPR PMAT | 4 | 0 | W19-W20 | 2024-04-26 | 2024-04-30 | 2024-04-28 | 2023-04-26 | 2022-12-12 | 40 | REL | APPR OPND | HB /A /37/HBAA-FCV-29193 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100076963 | LOTI: HBAA-FCV-29193 Many Faults | Replace FCV-29193 | REL GMPS MANC PRC SETC | APPR PMAT | 8 | 0 | W19-W20 | 2024-04-26 | 2024-04-30 | 2024-04-29 | 2023-04-26 | 2022-12-12 | 50 | REL | APPR OPND | HB /A /37/HBAA-FCV-29193 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100076963 | LOTI: HBAA-FCV-29193 Many Faults | Production deisolation w. function test | REL GMPS MANC PRC SETC | APPR PMAT | 3 | 0 | W19-W20 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2023-04-26 | 2022-12-12 | 60 | REL | APPR OPND | HB /A /37/HBAA-FCV-29193 | LIFT GAS FLOW CONTROL VALVE |  | C |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-TURB | MTN-RIGG | 2100107683 | Liquid fuel leak from filterhouse A-1660 | Prepare for rigging | REL GMPS MANC PRC SETC | APPR PMAT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-08-12 | 2024-03-30 | 10 | REL | APPR OPND | HB /D /60/HBDC-FIL-16060 | LIQUID FUEL FILTERS ASSY |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-TURB | PRODTECH | 2100107683 | Liquid fuel leak from filterhouse A-1660 | Isolate Liquid Fuel Filters Assy | REL GMPS MANC PRC SETC | APPR PMAT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2024-08-12 | 2024-03-30 | 20 | REL | APPR OPND | HB /D /60/HBDC-FIL-16060 | LIQUID FUEL FILTERS ASSY |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-TURB | MTN-TURB | 2100107683 | Liquid fuel leak from filterhouse A-1660 | Replace Filterhousing | REL GMPS MANC PRC SETC | APPR PMAT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-27 | 2024-08-12 | 2024-03-30 | 30 | REL | APPR OPND | HB /D /60/HBDC-FIL-16060 | LIQUID FUEL FILTERS ASSY |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-TURB | MTN-RIGG | 2100107683 | Liquid fuel leak from filterhouse A-1660 | Rigging assistance | REL GMPS MANC PRC SETC | APPR PMAT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-27 | 2024-08-12 | 2024-03-30 | 40 | REL | APPR OPND | HB /D /60/HBDC-FIL-16060 | LIQUID FUEL FILTERS ASSY |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-TURB | PRODTECH | 2100107683 | Liquid fuel leak from filterhouse A-1660 | Deisolate Liquid Fuel Filters Assy | REL GMPS MANC PRC SETC | APPR PMAT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-28 | 2024-08-12 | 2024-03-30 | 50 | REL | APPR OPND | HB /D /60/HBDC-FIL-16060 | LIQUID FUEL FILTERS ASSY |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-TURB | MTN-RIGG | 2100107683 | Liquid fuel leak from filterhouse A-1660 | Removal of rigging equipment | REL GMPS MANC PRC SETC | APPR PMAT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-28 | 2024-08-12 | 2024-03-30 | 60 | REL | APPR OPND | HB /D /60/HBDC-FIL-16060 | LIQUID FUEL FILTERS ASSY |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-TURB | MTN-TURB | 2100107683 | Liquid fuel leak from filterhouse A-1660 | Backload old filter assy to SR for rep. | REL GMPS MANC PRC SETC | APPR PMAT | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-29 | 2024-08-12 | 2024-03-30 | 70 | REL | APPR OPND | HB /D /60/HBDC-FIL-16060 | LIQUID FUEL FILTERS ASSY |  | A |  | MMR | DK50
2026-W13-14 | 3 | NE | WDF | MTN-TURB | MTN-TURB | 2100107683 | Liquid fuel leak from filterhouse A-1660 | Extra spares | REL GMPS MANC PRC SETC | APPR PMAT | 0 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-29 | 2024-08-12 | 2024-03-30 | 80 | REL | APPR OPND | HB /D /60/HBDC-FIL-16060 | LIQUID FUEL FILTERS ASSY |  | A |  | MMR | DK50
0 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001421 | DK60 - CONSUMABLE PROD - TOOLS | DK60 - CONSUMABLE PROD - TOOLS | REL GMPS MANC PRC SETC | APPR PMAT | 0 | 0 |  | 2021-10-07 | 2021-10-07 | 2021-10-07 | 2021-07-06 | 2020-09-09 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
0 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001421 | DK60 - CONSUMABLE PROD - TOOLS | 2300001421 15.12.20 MAT CALIBRATOR MUEHL | REL GMPS MANC PRC SETC | APPR PMAT | 0 | 0 |  | 2021-10-07 | 2021-10-07 | 2021-10-07 | 2021-07-06 | 2020-09-09 | 20 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
0 | 4 |  | WRO | PRODTECH | PRODTECH | 2300001421 | DK60 - CONSUMABLE PROD - TOOLS | LADDERS 06.10.2021 | REL GMPS MANC PRC SETC | APPR PMAT | 0 | 0 |  | 2021-10-07 | 2021-10-07 | 2021-10-07 | 2021-07-06 | 2020-09-09 | 30 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
0 | 4 |  | WRO | PRODTECH | PRODTECH | 2300004344 | DK60 - CONSUMABLE PROD - PPE | DK60 - CONSUMABLE PROD - PPE | REL GMPS MANC PRC SETC | APPR PMAT | 0 | 0 |  | 2023-06-18 | 2023-06-18 | 2023-06-18 | 2025-12-04 | 2023-06-18 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059898 | HDAM-A-1060 Replacemt/overhauling | Prepare matr/tool | REL PCNF GMPS MANC PRC SETC | APPR CMAT SCH RDBL | 1 | 27 | W51-52 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-02-04 | 2021-12-26 | 10 | PCNF REL | APPR OPND | HD /B /85/HDBM-A-1060 | FRESH WATER PLANT |  | C |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059898 | HDAM-A-1060 Replacemt/overhauling | Additional materials | REL PCNF GMPS MANC PRC SETC | APPR CMAT SCH RDBL | 0 | 9 | W51-52 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-02-04 | 2021-12-26 | 60 | PCNF REL | APPR OPND | HD /B /85/HDBM-A-1060 | FRESH WATER PLANT |  | C |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059898 | HDAM-A-1060 Replacemt/overhauling | New Ctrl Valve VS160 | REL PCNF GMPS MANC PRC SETC | APPR CMAT SCH RDBL | 0 | 30 | W51-52 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-02-04 | 2021-12-26 | 70 | PCNF REL | APPR OPND | HD /B /85/HDBM-A-1060 | FRESH WATER PLANT |  | C |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059898 | HDAM-A-1060 Replacemt/overhauling | Add matr. Booster Pump | REL PCNF GMPS MANC PRC SETC | APPR CMAT SCH RDBL | 0 | 20 | W51-52 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-02-04 | 2021-12-26 | 80 | PCNF REL | APPR OPND | HD /B /85/HDBM-A-1060 | FRESH WATER PLANT |  | C |  | MMS | DK60
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100089387 | HBB05 test manifold can't open | Isolate the line to Test Separator | REL GMPS MANC PRC SETC | APPR CMAT SCH RDBL | 1 | 0 | 24-W05-06 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-09 | 2023-05-27 | 10 | REL | APPR OPND | HB /B /10/HBBB-XCV-300506 | CONTROL VALVE WELL 06 |  | C |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100089387 | HBB05 test manifold can't open | Isolate solenoid valve | REL GMPS MANC PRC SETC | APPR CMAT SCH RDBL | 0.5 | 0 | 24-W05-06 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-09 | 2023-05-27 | 20 | REL | APPR OPND | HB /B /10/HBBB-XCV-300506 | CONTROL VALVE WELL 06 |  | C |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100089387 | HBB05 test manifold can't open | Replace solenoid valve | REL GMPS MANC PRC SETC | APPR CMAT SCH RDBL | 3 | 0 | 24-W05-06 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-09 | 2023-05-27 | 30 | REL | APPR OPND | HB /B /10/HBBB-XCV-300506 | CONTROL VALVE WELL 06 |  | C |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100089387 | HBB05 test manifold can't open | De-isolate sol. valve /Test with CCR | REL GMPS MANC PRC SETC | APPR CMAT SCH RDBL | 1 | 0 | 24-W05-06 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-09 | 2023-05-27 | 40 | REL | APPR OPND | HB /B /10/HBBB-XCV-300506 | CONTROL VALVE WELL 06 |  | C |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100089387 | HBB05 test manifold can't open | De-isolate line to Test Separator | REL GMPS MANC PRC SETC | APPR CMAT SCH RDBL | 1 | 0 | 24-W05-06 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-09 | 2023-05-27 | 50 | REL | APPR OPND | HB /B /10/HBBB-XCV-300506 | CONTROL VALVE WELL 06 |  | C |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100089387 | HBB05 test manifold can't open | New solenoid | REL GMPS MANC PRC SETC | APPR CMAT SCH RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-09 | 2023-05-27 | 60 | REL | APPR OPND | HB /B /10/HBBB-XCV-300506 | CONTROL VALVE WELL 06 |  | C |  | MIN | DK50
0 | C | NOSD | WPM | MTN-MECH | VEN-MECH | 2400213694 | 1Y AIR SYSTEM INSPECTION HDBC-5402/2 | AIR SYSTEM INSPECTION HDBC-5401/2 | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT SCH RDBL | 12 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2022-10-23 | 2022-09-17 | 10 | PCNF REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | C | DKHD-0054 | MMR | DK60 | MR0033 | PROK
0 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400213694 | 1Y AIR SYSTEM INSPECTION HDBC-5402/2 | VENDOR SUPPPORT | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT SCH RDBL | 6 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2022-10-23 | 2022-09-17 | 20 | PCNF REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | C | DKHD-0054 | MMR | DK60 | MR0033 | PROK
0 | C | NOSD | WPM | MTN-MECH | MTN-INST | 2400213694 | 1Y AIR SYSTEM INSPECTION HDBC-5402/2 | VENDOR SUPPORT | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT SCH RDBL | 6 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2022-10-23 | 2022-09-17 | 30 | PCNF REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | C | DKHD-0054 | MMR | DK60 | MR0033 | PROK
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100026120 | + HBAA-HCV-290065 internally leak. | L3 Isolate equipment | REL PRT GMPS MANC PRC SETC | APPR CMAT RFRZ | 6 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2019-08-26 | 2019-05-28 | 10 | REL | APPR OPND | HB /A /34/HBAA-HCV-290065 | LC - HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100026120 | + HBAA-HCV-290065 internally leak. | L2 Exchange valve | REL PRT GMPS MANC PRC SETC | APPR CMAT RFRZ | 4 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2019-08-26 | 2019-05-28 | 20 | REL | APPR OPND | HB /A /34/HBAA-HCV-290065 | LC - HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100026120 | + HBAA-HCV-290065 internally leak. | L3 Remove isolation | REL PRT GMPS MANC PRC SETC | APPR CMAT RFRZ | 6 | 0 |  | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2019-08-26 | 2019-05-28 | 30 | REL | APPR OPND | HB /A /34/HBAA-HCV-290065 | LC - HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-SCAF | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | Erect scaffold | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 30 | 0 |  | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 9 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-RIGG | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L3 Rig-up rigging equipment for removal | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 30 | 0 | campaign scope 18/08-30/0 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 10 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-RIGG | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | Mounting deckplates | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 10 | 0 |  | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 11 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-RIGG | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | Rigging out Stair case | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 10 | 0 |  | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 14 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L1 Isolate HBAA-XCV38033/34 | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 3 | 0 | OIM 10 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 20 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-ELEC | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L1 Disconnect power cable | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 3 | 0 | OIM 10 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 40 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L1 Disconnect hydraulic pipe | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 3 | 0 | OIM 10 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 50 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L1 Remove old valve/actuator | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 10 | 0 | OIM 10 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 60 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-RIGG | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L1 Rigging out of old Valve/actuator | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 24 | 0 | OIM 10 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 70 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L1 Install new valve/actuator | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 10 | 0 | OIM 10 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 80 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-RIGG | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L1 Rigging in new Valve/actuator | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 24 | 0 | OIM 10 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 90 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L1 Re-connect hydraulic pipe | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 3 | 0 | OIM 10 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 100 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-ELEC | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L1 Re-connect power cable | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 3 | 0 | OIM 10 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 110 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | QAQCMECH | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L1 Functional test & QC | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 2 | 0 | OIM 10 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 120 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L3 De-isolate HBAA-XCV38033/34 | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 3 | 0 | OIM 10 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 140 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-RIGG | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | Rigging in Stair Case | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 10 | 0 |  | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 145 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-RIGG | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | removal of deckplates | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 10 | 0 |  | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 146 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-RIGG | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | L3 Rig-down hoist and clean area | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 16 | 0 | OIM 10 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 150 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB WI SD | WDF | MTN-MECH | MTN-RIGG | 2100026217 | DGS:607240 Replace HBAA-XCV-38031A. | dismantling of Scaffold | REL GMPS MANC PPRT PRC SETC | APPR CMAT RFRZ | 16 | 0 |  | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2019-07-28 | 2019-07-08 | 160 | REL | APPR OPND | HB /A /50/HBAA-XCV-38031A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBDHPSEP | WDF | MTN-MECH | PRODTECH | 2100043145 | HBDB-HCV-507024 V-5071 O/L HCV is intern | Isolate and depressurize reject water sy | REL PRT GMPS MANC PRC SETC | APPR CMAT RFRZ | 3 | 0 | W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2021-04-13 | 2021-01-13 | 10 | REL | APPR OPND | HB /D /27/HBDB-HCV-507024 | BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBDHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100043145 | HBDB-HCV-507024 V-5071 O/L HCV is intern | Prepare for rigging out and in of valve. | REL PRT GMPS MANC PRC SETC | APPR CMAT RFRZ | 3 | 0 | W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2021-04-13 | 2021-01-13 | 20 | REL | APPR OPND | HB /D /27/HBDB-HCV-507024 | BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBDHPSEP | WDF | MTN-MECH | MTN-MECH | 2100043145 | HBDB-HCV-507024 V-5071 O/L HCV is intern | Dismantle valve | REL PRT GMPS MANC PRC SETC | APPR CMAT RFRZ | 2 | 0 | W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2021-04-13 | 2021-01-13 | 30 | REL | APPR OPND | HB /D /27/HBDB-HCV-507024 | BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBDHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100043145 | HBDB-HCV-507024 V-5071 O/L HCV is intern | Rigg out the valve | REL PRT GMPS MANC PRC SETC | APPR CMAT RFRZ | 1.5 | 0 | W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2021-04-13 | 2021-01-13 | 40 | REL | APPR OPND | HB /D /27/HBDB-HCV-507024 | BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBDHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100043145 | HBDB-HCV-507024 V-5071 O/L HCV is intern | Rigg in the new valve | REL PRT GMPS MANC PRC SETC | APPR CMAT RFRZ | 1.5 | 0 | W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2021-04-13 | 2021-01-13 | 50 | REL | APPR OPND | HB /D /27/HBDB-HCV-507024 | BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBDHPSEP | WDF | MTN-MECH | MTN-MECH | 2100043145 | HBDB-HCV-507024 V-5071 O/L HCV is intern | Installation of valve | REL PRT GMPS MANC PRC SETC | APPR CMAT RFRZ | 2 | 0 | W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2021-04-13 | 2021-01-13 | 60 | REL | APPR OPND | HB /D /27/HBDB-HCV-507024 | BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBDHPSEP | WDF | MTN-MECH | PRODTECH | 2100043145 | HBDB-HCV-507024 V-5071 O/L HCV is intern | De-isolate and perform leak test of unit | REL PRT GMPS MANC PRC SETC | APPR CMAT RFRZ | 2 | 0 | W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2021-04-13 | 2021-01-13 | 70 | REL | APPR OPND | HB /D /27/HBDB-HCV-507024 | BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBDHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100043145 | HBDB-HCV-507024 V-5071 O/L HCV is intern | De-rigging of equipment | REL PRT GMPS MANC PRC SETC | APPR CMAT RFRZ | 2 | 0 | W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2021-04-13 | 2021-01-13 | 80 | REL | APPR OPND | HB /D /27/HBDB-HCV-507024 | BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-SCAF | 2100050468 | HCV-35012-U internally leaking | Scaffold Assistance/Erection | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 24 | 0 |  | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2022-01-10 | 2021-08-13 | 10 | REL | APPR OPND | HB /A /50/HBAA-HCV-35012-U | LO - HCV UPSTREAM PSV-35012 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100050468 | HCV-35012-U internally leaking | Insulation removal | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 3 | 0 |  | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2022-01-10 | 2021-08-13 | 20 | REL | APPR OPND | HB /A /50/HBAA-HCV-35012-U | LO - HCV UPSTREAM PSV-35012 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100050468 | HCV-35012-U internally leaking | Production isolation | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 3 | 0 |  | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2022-01-10 | 2021-08-13 | 30 | REL | APPR OPND | HB /A /50/HBAA-HCV-35012-U | LO - HCV UPSTREAM PSV-35012 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100050468 | HCV-35012-U internally leaking | Replace 2" Ball Valve | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 8 | 0 |  | 2024-09-15 | 2024-09-21 | 2024-09-18 | 2022-01-10 | 2021-08-13 | 40 | REL | APPR OPND | HB /A /50/HBAA-HCV-35012-U | LO - HCV UPSTREAM PSV-35012 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100050468 | HCV-35012-U internally leaking | Production deisolation w leak test | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 3 | 0 |  | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2022-01-10 | 2021-08-13 | 50 | REL | APPR OPND | HB /A /50/HBAA-HCV-35012-U | LO - HCV UPSTREAM PSV-35012 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-LAGG | 2100050468 | HCV-35012-U internally leaking | Insulation reassembly | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 6 | 0 |  | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2022-01-10 | 2021-08-13 | 60 | REL | APPR OPND | HB /A /50/HBAA-HCV-35012-U | LO - HCV UPSTREAM PSV-35012 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-SCAF | 2100050468 | HCV-35012-U internally leaking | Scaffold removal | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 18 | 0 |  | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2022-01-10 | 2021-08-13 | 70 | REL | APPR OPND | HB /A /50/HBAA-HCV-35012-U | LO - HCV UPSTREAM PSV-35012 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-RIGG | 2100050662 | HBA22 manifold HCV-35220 intern leak | Prepare Lifting equipment | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 6 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2022-01-16 | 2021-08-19 | 10 | REL | APPR OPND | HB /A /55/HBAA-HCV-35220 | W.I. MANIFOLD OUTLET VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100050662 | HBA22 manifold HCV-35220 intern leak | Prepare permit/tools/matr | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 4 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2022-01-16 | 2021-08-19 | 20 | REL | APPR OPND | HB /A /55/HBAA-HCV-35220 | W.I. MANIFOLD OUTLET VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100050662 | HBA22 manifold HCV-35220 intern leak | Prod prepare permit/isolation | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 3 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2022-01-16 | 2021-08-19 | 30 | REL | APPR OPND | HB /A /55/HBAA-HCV-35220 | W.I. MANIFOLD OUTLET VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-RIGG | 2100050662 | HBA22 manifold HCV-35220 intern leak | Rigger assistance | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 12 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2022-01-16 | 2021-08-19 | 35 | REL | APPR OPND | HB /A /55/HBAA-HCV-35220 | W.I. MANIFOLD OUTLET VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-ELEC | 2100050662 | HBA22 manifold HCV-35220 intern leak | Electrical Assistance | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 3 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2022-01-16 | 2021-08-19 | 40 | REL | APPR OPND | HB /A /55/HBAA-HCV-35220 | W.I. MANIFOLD OUTLET VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100050662 | HBA22 manifold HCV-35220 intern leak | Valve removal | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 6 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2022-01-16 | 2021-08-19 | 45 | REL | APPR OPND | HB /A /55/HBAA-HCV-35220 | W.I. MANIFOLD OUTLET VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100050662 | HBA22 manifold HCV-35220 intern leak | New Valve installation | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 6 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2022-01-16 | 2021-08-19 | 50 | REL | APPR OPND | HB /A /55/HBAA-HCV-35220 | W.I. MANIFOLD OUTLET VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-INST | 2100050662 | HBA22 manifold HCV-35220 intern leak | Instrument Assistance | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 3 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2022-01-16 | 2021-08-19 | 70 | REL | APPR OPND | HB /A /55/HBAA-HCV-35220 | W.I. MANIFOLD OUTLET VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100050662 | HBA22 manifold HCV-35220 intern leak | Prod deisolate w function/leak test | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 3 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2022-01-16 | 2021-08-19 | 80 | REL | APPR OPND | HB /A /55/HBAA-HCV-35220 | W.I. MANIFOLD OUTLET VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-RIGG | 2100050662 | HBA22 manifold HCV-35220 intern leak | Rigging equipment removal | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 3 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2022-01-16 | 2021-08-19 | 90 | REL | APPR OPND | HB /A /55/HBAA-HCV-35220 | W.I. MANIFOLD OUTLET VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100050662 | HBA22 manifold HCV-35220 intern leak | Housekeeping with backload off Vlv | REL GMPS MANC PRC SETC | APPR CMAT RFRZ | 3 | 0 |  | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2022-01-16 | 2021-08-19 | 100 | REL | APPR OPND | HB /A /55/HBAA-HCV-35220 | W.I. MANIFOLD OUTLET VALVE | 99000119 | F |  | MMS | DK50
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023293 | FLM Secure alu plates on walkway | Secure alu plates on walkway | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2020-02-13 | 2019-11-15 | 10 | REL | APPR OPND | HD /A /86/GRATING-STAIRS | GRATING AND STAIRS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100023293 | FLM Secure alu plates on walkway | Barrier of work area | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2020-02-13 | 2019-11-15 | 30 | REL | APPR OPND | HD /A /86/GRATING-STAIRS | GRATING AND STAIRS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100023293 | FLM Secure alu plates on walkway | Transport of plates to site | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 12 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2020-02-13 | 2019-11-15 | 40 | REL | APPR OPND | HD /A /86/GRATING-STAIRS | GRATING AND STAIRS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100023293 | FLM Secure alu plates on walkway | Remove - install plates one by one | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 31.5 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2020-02-13 | 2019-11-15 | 50 | REL | APPR OPND | HD /A /86/GRATING-STAIRS | GRATING AND STAIRS |  | A |  | MFM | DK60
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-MECH | 2100026216 | Investigation on Load cell | Investigation on Loadcell | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 20 | 12 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 10 | PCNF REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | Inhibit before isolation | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 0.5 | 0 | W09-10 | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 107 | PCNF REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | Isolate input device NON EX | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W09-10 | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 108 | PCNF REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-TELE | 2100026216 | Investigation on Load cell | Calibrate all loadcells | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 8 | 0 | W09-10 | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 110 | PCNF REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | Deisolate after repair of Load cell | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W09-10 | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 209 | PCNF REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | Test after completed work | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W09-10 | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 410 | PCNF REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | Remove inhibit Input device | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 0.5 | 0 | W09-10 | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 412 | PCNF REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | New Mats | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 422 | PCNF REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | Repair/alignment of the frame for tank | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 5 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 432 | PCNF REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | new mats | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 452 | PCNF REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | new mats according to offshore we need 8 | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 462 | PCNF REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | New load cells | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 472 | PCNF REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-TELE | 2100026216 | Investigation on Load cell | Bench testing of the new amplifiers | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 8 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 492 | REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-TELE | 2100026216 | Investigation on Load cell | Install new amplifiers | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 8 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 502 | REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | Install new load cells | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 8 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 512 | REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | Calibrate the system | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-08-01 | 2020-03-02 | 2019-10-04 | 522 | REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100026216 | Investigation on Load cell | Assist with lifting | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 12 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 532 | REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | PRODTECH | 2100026216 | Investigation on Load cell | Assist with installation | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 12 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 542 | REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026216 | Investigation on Load cell | Load cell | REL PCNF PRT CSER GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2020-03-02 | 2019-10-04 | 552 | REL | APPR OPND | HB /A /75/HBAA-WY-39021 | LOAD CELL |  | C |  | MIN | DK50
2026-W13-14 | 4 | HBB08-WI | WDF | MTN-INST | PRODTECH | 2100054256 | HBB-08 WH-Panel PI-300803 is stuck. | Production isolation | REL GMPS MANC PPRT PRC SETC | APPR CMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-04-10 | 2021-11-11 | 10 | REL | APPR OPND | HB /B /07/HBBB-FP-3140 | FIELD PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBB08-WI | WDF | MTN-INST | MTN-INST | 2100054256 | HBB-08 WH-Panel PI-300803 is stuck. | Replace PI-300803/Wing | REL GMPS MANC PPRT PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2022-04-10 | 2021-11-11 | 20 | REL | APPR OPND | HB /B /07/HBBB-FP-3140 | FIELD PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBB08-WI | WDF | MTN-INST | PRODTECH | 2100054256 | HBB-08 WH-Panel PI-300803 is stuck. | Production deisolation w leak test | REL GMPS MANC PPRT PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2022-04-10 | 2021-11-11 | 30 | REL | APPR OPND | HB /B /07/HBBB-FP-3140 | FIELD PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBOIL-SD | WDF | MTN-MECH | MTN-RIGG | 2100056369 | HCV-365161 internal leak outlet P-3651 | Prepare Rigging Equipment | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 36 | 0 | W09-10 | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2022-01-24 | 2021-10-26 | 10 | REL | APPR OPND | HB /D /23/HBDB-HCV-365161 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBOIL-SD | WDF | MTN-MECH | MTN-MECH | 2100056369 | HCV-365161 internal leak outlet P-3651 | Prepare matr/tool | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 10 | 0 | W09-10 | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2022-01-24 | 2021-10-26 | 20 | REL | APPR OPND | HB /D /23/HBDB-HCV-365161 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBOIL-SD | WDF | MTN-MECH | PRODTECH | 2100056369 | HCV-365161 internal leak outlet P-3651 | Production isolation | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 | W09-10 | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2022-01-24 | 2021-10-26 | 30 | REL | APPR OPND | HB /D /23/HBDB-HCV-365161 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBOIL-SD | WDF | MTN-MECH | MTN-RIGG | 2100056369 | HCV-365161 internal leak outlet P-3651 | Rigger assistance | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 30 | 0 | W09-10 | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2022-01-24 | 2021-10-26 | 40 | REL | APPR OPND | HB /D /23/HBDB-HCV-365161 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBOIL-SD | WDF | MTN-MECH | MTN-SCAF | 2100056369 | HCV-365161 internal leak outlet P-3651 | Scaffold assistance | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 18 | 0 | W09-10 | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2022-01-24 | 2021-10-26 | 50 | REL | APPR OPND | HB /D /23/HBDB-HCV-365161 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBOIL-SD | WDF | MTN-MECH | MTN-MECH | 2100056369 | HCV-365161 internal leak outlet P-3651 | Removal old HCV-365161 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 8 | 0 | W09-10 | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2022-01-24 | 2021-10-26 | 60 | REL | APPR OPND | HB /D /23/HBDB-HCV-365161 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBOIL-SD | WDF | MTN-MECH | MTN-MECH | 2100056369 | HCV-365161 internal leak outlet P-3651 | Install new HCV-365161 w torqueing | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 12 | 0 | W09-10 | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2022-01-24 | 2021-10-26 | 70 | REL | APPR OPND | HB /D /23/HBDB-HCV-365161 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBOIL-SD | WDF | MTN-MECH | PRODTECH | 2100056369 | HCV-365161 internal leak outlet P-3651 | Production deisolation w leaktest | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 | W09-10 | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2022-01-24 | 2021-10-26 | 80 | REL | APPR OPND | HB /D /23/HBDB-HCV-365161 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HBOIL-SD | WDF | MTN-MECH | MTN-RIGG | 2100056369 | HCV-365161 internal leak outlet P-3651 | Rigging equipment removal | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 18 | 0 | W09-10 | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2022-01-24 | 2021-10-26 | 90 | REL | APPR OPND | HB /D /23/HBDB-HCV-365161 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100056370 | HCV-365162 Internal leak inlet P-3651 | Prepare Rigging Equipment | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 40 | 0 | W19-W20 | 2024-04-26 | 2024-05-05 | 2024-04-26 | 2022-01-24 | 2021-10-26 | 10 | REL | APPR OPND | HB /D /23/HBDB-HCV-365162 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100056370 | HCV-365162 Internal leak inlet P-3651 | Prepare matr/tools | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 16 | 0 | W19-W20 | 2024-04-26 | 2024-05-05 | 2024-04-26 | 2022-01-24 | 2021-10-26 | 20 | REL | APPR OPND | HB /D /23/HBDB-HCV-365162 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100056370 | HCV-365162 Internal leak inlet P-3651 | Production isolation | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 | W19-W20 | 2024-04-26 | 2024-05-05 | 2024-04-28 | 2022-01-24 | 2021-10-26 | 30 | REL | APPR OPND | HB /D /23/HBDB-HCV-365162 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100056370 | HCV-365162 Internal leak inlet P-3651 | Rigger assistance | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 36 | 0 | W19-W20 | 2024-04-26 | 2024-05-05 | 2024-04-29 | 2022-01-24 | 2021-10-26 | 40 | REL | APPR OPND | HB /D /23/HBDB-HCV-365162 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100056370 | HCV-365162 Internal leak inlet P-3651 | Scaffold assistance | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 18 | 0 | W19-W20 | 2024-04-26 | 2024-05-05 | 2024-04-29 | 2022-01-24 | 2021-10-26 | 50 | REL | APPR OPND | HB /D /23/HBDB-HCV-365162 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100056370 | HCV-365162 Internal leak inlet P-3651 | Remove old HCV-365162 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 18 | 0 | W19-W20 | 2024-04-26 | 2024-05-05 | 2024-04-29 | 2022-01-24 | 2021-10-26 | 60 | REL | APPR OPND | HB /D /23/HBDB-HCV-365162 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100056370 | HCV-365162 Internal leak inlet P-3651 | Install new HCV-365162 w torquing | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 18 | 0 | W19-W20 | 2024-04-26 | 2024-05-05 | 2024-05-02 | 2022-01-24 | 2021-10-26 | 70 | REL | APPR OPND | HB /D /23/HBDB-HCV-365162 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100056370 | HCV-365162 Internal leak inlet P-3651 | Production de-isolation w leaktest | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 | W19-W20 | 2024-04-26 | 2024-05-05 | 2024-05-03 | 2022-01-24 | 2021-10-26 | 80 | REL | APPR OPND | HB /D /23/HBDB-HCV-365162 | DBB BALL VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100056370 | HCV-365162 Internal leak inlet P-3651 | Rigger equipment removal | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 24 | 0 | W19-W20 | 2024-04-26 | 2024-05-05 | 2024-05-04 | 2022-01-24 | 2021-10-26 | 90 | REL | APPR OPND | HB /D /23/HBDB-HCV-365162 | DBB BALL VALVE |  | F |  | MMS | DK50
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100056502 | HDBR-HCV-030137 Internal leakage. | Insulation Off/On | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2022-09-24 | 2022-01-27 | 10 | REL | APPR OPND | HD /B /01/HDBR-HCV-030137 | LO - HAND CONTROL VALVE |  | C |  | MMS | DK60 |  | PROK
0 | 4 | NE | WDF | MTN-MECH | PRODTECH | 2100056502 | HDBR-HCV-030137 Internal leakage. | Production isolation | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2022-09-24 | 2022-01-27 | 20 | REL | APPR OPND | HD /B /01/HDBR-HCV-030137 | LO - HAND CONTROL VALVE |  | C |  | MMS | DK60 |  | PROK
0 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100056502 | HDBR-HCV-030137 Internal leakage. | Replace HCV-030137 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 6 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2022-09-24 | 2022-01-27 | 30 | REL | APPR OPND | HD /B /01/HDBR-HCV-030137 | LO - HAND CONTROL VALVE |  | C |  | MMS | DK60 |  | PROK
0 | 4 | NE | WDF | MTN-MECH | PRODTECH | 2100056502 | HDBR-HCV-030137 Internal leakage. | Production deisolation w. function test | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2022-09-24 | 2022-01-27 | 40 | REL | APPR OPND | HD /B /01/HDBR-HCV-030137 | LO - HAND CONTROL VALVE |  | C |  | MMS | DK60 |  | PROK
2024-W33-34 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100060629 | Replace N2 bottle for water dew point | Replace N2 bottle for water dew point | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W33-34 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2022-02-18 | 2022-01-09 | 10 | REL | APPR OPND | HB /D /34/HBDC-AT-290001 | ANALYZER TRANSMITTER - WATER DEW POINT |  | A |  | MIN | DK50
2024-W33-34 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100060629 | Replace N2 bottle for water dew point | Materials | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W33-34 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2022-02-18 | 2022-01-09 | 20 | REL | APPR OPND | HB /D /34/HBDC-AT-290001 | ANALYZER TRANSMITTER - WATER DEW POINT |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100061839 | ANOP HUB on HBA test manifold west. | HUB on HBA test manifold west. | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-25 | 2023-04-24 | 2022-05-17 | 2022-02-16 | 10 | REL | APPR OPND | HB /A /11/P-G | PIPING GROUP |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061839 | ANOP HUB on HBA test manifold west. | Additional materials | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-25 | 2023-04-24 | 2022-05-17 | 2022-02-16 | 20 | REL | APPR OPND | HB /A /11/P-G | PIPING GROUP |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100061839 | ANOP HUB on HBA test manifold west. | Isolation | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2023-04-24 | 2023-04-25 | 2023-04-24 | 2022-05-17 | 2022-02-16 | 40 | REL | APPR OPND | HB /A /11/P-G | PIPING GROUP |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061839 | ANOP HUB on HBA test manifold west. | Dismantling existing HUB | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2023-04-24 | 2023-04-25 | 2023-04-24 | 2022-05-17 | 2022-02-16 | 50 | REL | APPR OPND | HB /A /11/P-G | PIPING GROUP |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061839 | ANOP HUB on HBA test manifold west. | Clean sealing surfaces | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2023-04-24 | 2023-04-25 | 2023-04-24 | 2022-05-17 | 2022-02-16 | 60 | REL | APPR OPND | HB /A /11/P-G | PIPING GROUP |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | INP-SITE | 2100061839 | ANOP HUB on HBA test manifold west. | Inspect sealing surfaces | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2023-04-24 | 2023-04-25 | 2023-04-24 | 2022-05-17 | 2022-02-16 | 70 | REL | APPR OPND | HB /A /11/P-G | PIPING GROUP |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061839 | ANOP HUB on HBA test manifold west. | Install new HUB | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 |  | 2023-04-24 | 2023-04-25 | 2023-04-24 | 2022-05-17 | 2022-02-16 | 80 | REL | APPR OPND | HB /A /11/P-G | PIPING GROUP |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100061839 | ANOP HUB on HBA test manifold west. | Leak test and deisolation | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2023-04-24 | 2023-04-25 | 2023-04-25 | 2022-05-17 | 2022-02-16 | 85 | REL | APPR OPND | HB /A /11/P-G | PIPING GROUP |  | C |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | PRODTECH | 2100061895 | New isolation for PIT-300612 | Isolate Pressure Indic. Transmitter (Sca | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0.5 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-01-09 | 2022-05-14 | 10 | REL | APPR OPND | HB /B /55/HBBB-PIT-300612 | PRESSURE INDIC. TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100061895 | New isolation for PIT-300612 | Isolate Heat tracing power supply for Tr | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0.5 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-01-09 | 2022-05-14 | 20 | REL | APPR OPND | HB /B /55/HBBB-PIT-300612 | PRESSURE INDIC. TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100061895 | New isolation for PIT-300612 | Install insulation for Transmitter (Scad | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-01-09 | 2022-05-14 | 40 | REL | APPR OPND | HB /B /55/HBBB-PIT-300612 | PRESSURE INDIC. TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100061895 | New isolation for PIT-300612 | Deisolate Heat tracing power supply for | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0.5 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-01-09 | 2022-05-14 | 50 | REL | APPR OPND | HB /B /55/HBBB-PIT-300612 | PRESSURE INDIC. TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | PRODTECH | 2100061895 | New isolation for PIT-300612 | Deisolate Pressure Indic. Transmitter (S | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0.5 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-01-09 | 2022-05-14 | 60 | REL | APPR OPND | HB /B /55/HBBB-PIT-300612 | PRESSURE INDIC. TRANSMITTER (SCADA) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100071506 | LG-34121 on HBA test separator V-3411 | Isolation of the level glass | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1.5 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-08-27 | 2022-07-13 | 10 | REL | APPR OPND | HB /A /11/HBAA-LG-34121 | LEVEL GAUGE |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100071506 | LG-34121 on HBA test separator V-3411 | Isolation of light and heat tracing | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-08-27 | 2022-07-13 | 20 | REL | APPR OPND | HB /A /11/HBAA-LG-34121 | LEVEL GAUGE |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071506 | LG-34121 on HBA test separator V-3411 | Removal of old level glass | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-08-27 | 2022-07-13 | 30 | REL | APPR OPND | HB /A /11/HBAA-LG-34121 | LEVEL GAUGE |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071506 | LG-34121 on HBA test separator V-3411 | Inspection of flanges and fix | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-08-27 | 2022-07-13 | 40 | REL | APPR OPND | HB /A /11/HBAA-LG-34121 | LEVEL GAUGE |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071506 | LG-34121 on HBA test separator V-3411 | Installation of the new level glass | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-08-27 | 2022-07-13 | 50 | REL | APPR OPND | HB /A /11/HBAA-LG-34121 | LEVEL GAUGE |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100071506 | LG-34121 on HBA test separator V-3411 | Deisolation of the level glass | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-08-27 | 2022-07-13 | 60 | REL | APPR OPND | HB /A /11/HBAA-LG-34121 | LEVEL GAUGE |  | A |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100071506 | LG-34121 on HBA test separator V-3411 | Deisolation of light and heat tracing | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2022-08-27 | 2022-07-13 | 70 | REL | APPR OPND | HB /A /11/HBAA-LG-34121 | LEVEL GAUGE |  | A |  | MIN | DK50
2024-W27-28 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100075419 | WM WTR Cylinder weight False alarm | Spare load cells | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-27 | 2022-11-12 | 170 | REL | APPR OPND | HB /D /01/HBDB-WT-0481501 | WATERM.CYL.BANK WEIGHT LOW MAIN 1/2/3 |  | C |  | MIN | DK50 |  |  | 2024-05-06
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100075621 | HCV-435202-U int. leaking (psv IP comp.) | Isolation of valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2023-03-31 | 2022-11-16 | 10 | REL | APPR OPND | HB /D /31/HBDC-HCV-435202-U | HCV UPSTREAM PSV-435202 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100075621 | HCV-435202-U int. leaking (psv IP comp.) | Removal of insulation | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2023-03-31 | 2022-11-16 | 20 | REL | APPR OPND | HB /D /31/HBDC-HCV-435202-U | HCV UPSTREAM PSV-435202 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100075621 | HCV-435202-U int. leaking (psv IP comp.) | setup of rigging gear / scaf | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2023-03-31 | 2022-11-16 | 30 | REL | APPR OPND | HB /D /31/HBDC-HCV-435202-U | HCV UPSTREAM PSV-435202 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100075621 | HCV-435202-U int. leaking (psv IP comp.) | Dismantle of valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2023-03-31 | 2022-11-16 | 40 | REL | APPR OPND | HB /D /31/HBDC-HCV-435202-U | HCV UPSTREAM PSV-435202 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100075621 | HCV-435202-U int. leaking (psv IP comp.) | Rigging assist removal of valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2023-03-31 | 2022-11-16 | 50 | REL | APPR OPND | HB /D /31/HBDC-HCV-435202-U | HCV UPSTREAM PSV-435202 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100075621 | HCV-435202-U int. leaking (psv IP comp.) | Rigging assist install new valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2023-03-31 | 2022-11-16 | 60 | REL | APPR OPND | HB /D /31/HBDC-HCV-435202-U | HCV UPSTREAM PSV-435202 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100075621 | HCV-435202-U int. leaking (psv IP comp.) | Install new valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2023-03-31 | 2022-11-16 | 70 | REL | APPR OPND | HB /D /31/HBDC-HCV-435202-U | HCV UPSTREAM PSV-435202 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100075621 | HCV-435202-U int. leaking (psv IP comp.) | de-isolation and leak test | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2023-03-31 | 2022-11-16 | 80 | REL | APPR OPND | HB /D /31/HBDC-HCV-435202-U | HCV UPSTREAM PSV-435202 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100075621 | HCV-435202-U int. leaking (psv IP comp.) | Install insulation on valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2023-03-31 | 2022-11-16 | 90 | REL | APPR OPND | HB /D /31/HBDC-HCV-435202-U | HCV UPSTREAM PSV-435202 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100075621 | HCV-435202-U int. leaking (psv IP comp.) | Removal of rigging gear / scaf | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2023-03-31 | 2022-11-16 | 100 | REL | APPR OPND | HB /D /31/HBDC-HCV-435202-U | HCV UPSTREAM PSV-435202 |  | A |  | MMS | DK50
2026-W13-14 | 3 | HBA09-GL | WDF | MTN-INST | PRODTECH | 2100077732 | Possible intern leak on SOV-30098 | Isolate Other Valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-05-08 | 2022-12-24 | 5 | REL | APPR OPND | HB /A /10/HBAA-XCV-30098 | 8" 2500# T PLUG VALVE FROM WELL 09 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA09-GL | WDF | MTN-INST | MTN-INST | 2100077732 | Possible intern leak on SOV-30098 | Replace Solenoid valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-05-08 | 2022-12-24 | 20 | REL | APPR OPND | HB /A /10/HBAA-XCV-30098 | 8" 2500# T PLUG VALVE FROM WELL 09 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA09-GL | WDF | MTN-INST | PRODTECH | 2100077732 | Possible intern leak on SOV-30098 | Deisolate and test Other Valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2023-05-08 | 2022-12-24 | 40 | REL | APPR OPND | HB /A /10/HBAA-XCV-30098 | 8" 2500# T PLUG VALVE FROM WELL 09 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA09-GL | WDF | MTN-INST | MTN-INST | 2100077732 | Possible intern leak on SOV-30098 | Sov valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2023-05-08 | 2022-12-24 | 50 | REL | APPR OPND | HB /A /10/HBAA-XCV-30098 | 8" 2500# T PLUG VALVE FROM WELL 09 |  | E |  | MIN | DK50
2026-W13-14 | 2 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100078394 | Upstream flange on HCV-35000A-U are weep | Upstream flange on HCV-35000A-U are weep | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2023-01-07 | 2022-11-23 | 10 | REL | APPR OPND | HB /A /50/HBAA-HCV-35000A-U | LO - HCV UPSTREAM PSV-35000A |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100078394 | Upstream flange on HCV-35000A-U are weep | Production isolate, verify isolation | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2023-01-07 | 2022-11-23 | 20 | REL | APPR OPND | HB /A /50/HBAA-HCV-35000A-U | LO - HCV UPSTREAM PSV-35000A |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100078394 | Upstream flange on HCV-35000A-U are weep | Dismount bolt and gasket, inspect seats. | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2023-01-07 | 2022-11-23 | 30 | REL | APPR OPND | HB /A /50/HBAA-HCV-35000A-U | LO - HCV UPSTREAM PSV-35000A |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | HB WI SD | WDF | MTN-MECH | MTN-MECH | 2100078394 | Upstream flange on HCV-35000A-U are weep | If ok, mount new seal. | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2023-01-07 | 2022-11-23 | 40 | REL | APPR OPND | HB /A /50/HBAA-HCV-35000A-U | LO - HCV UPSTREAM PSV-35000A |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 2 | HB WI SD | WDF | MTN-MECH | PRODTECH | 2100078394 | Upstream flange on HCV-35000A-U are weep | Production to de-isolate, check for leak | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-10 | 2023-01-07 | 2022-11-23 | 50 | REL | APPR OPND | HB /A /50/HBAA-HCV-35000A-U | LO - HCV UPSTREAM PSV-35000A |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080529 | Cracks in HT cable HBDC-DP-1870-24 | Cracks in HT cable | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-25 | 2023-07-03 | 2023-02-18 | 10 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-24 | HEAT TRACING (HTJB-1870-0024) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100080529 | Cracks in HT cable HBDC-DP-1870-24 | Remove insulation | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 9 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-25 | 2023-07-03 | 2023-02-18 | 15 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-24 | HEAT TRACING (HTJB-1870-0024) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100080529 | Cracks in HT cable HBDC-DP-1870-24 | Isolate Equipment. | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-26 | 2023-07-03 | 2023-02-18 | 20 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-24 | HEAT TRACING (HTJB-1870-0024) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080529 | Cracks in HT cable HBDC-DP-1870-24 | Replace HT Cable | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-26 | 2023-07-03 | 2023-02-18 | 30 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-24 | HEAT TRACING (HTJB-1870-0024) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100080529 | Cracks in HT cable HBDC-DP-1870-24 | De-isolate Equipment | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-26 | 2023-07-03 | 2023-02-18 | 40 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-24 | HEAT TRACING (HTJB-1870-0024) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080529 | Cracks in HT cable HBDC-DP-1870-24 | Test & put back in service | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-27 | 2023-07-03 | 2023-02-18 | 50 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-24 | HEAT TRACING (HTJB-1870-0024) |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100080529 | Cracks in HT cable HBDC-DP-1870-24 | Install insulation | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 63 | 0 | W13-W14 | 2024-03-25 | 2024-04-02 | 2024-03-27 | 2023-07-03 | 2023-02-18 | 70 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-24 | HEAT TRACING (HTJB-1870-0024) |  | C |  | MEL | DK50
2024-W31-32 | 4 | NE | WDF | MTN-MECH | MTN-MECH | 2100084870 | Sheared valve handle on HBA CI skid | FLM Sheared valve handle on HBA CI skid | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2025-11-18 | 2023-06-02 | 10 | REL | APPR OPND | HB /A /75/HBAA-P-39441 | CORROSION INHIBITOR PUMP |  | A |  | MMR | DK50 |  | PROK | 2024-05-29
2026-W13-14 | 2 | HBD-PW | WDF | MTN-RIGG | PRODTECH | 2100090334 | HCV-507031 is internally leaking | Isolation of valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2023-06-18 | 2023-05-04 | 10 | REL | APPR OPND | HB /D /20/HBDB-HCV-507031 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 2 | HBD-PW | WDF | MTN-RIGG | MTN-RIGG | 2100090334 | HCV-507031 is internally leaking | setup of rigging gear / scaf | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 10 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2023-06-18 | 2023-05-04 | 20 | REL | APPR OPND | HB /D /20/HBDB-HCV-507031 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 2 | HBD-PW | WDF | MTN-RIGG | MTN-MECH | 2100090334 | HCV-507031 is internally leaking | Dismantle of valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2023-06-18 | 2023-05-04 | 30 | REL | APPR OPND | HB /D /20/HBDB-HCV-507031 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 2 | HBD-PW | WDF | MTN-RIGG | MTN-RIGG | 2100090334 | HCV-507031 is internally leaking | Rigging assist removal of valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2023-06-18 | 2023-05-04 | 40 | REL | APPR OPND | HB /D /20/HBDB-HCV-507031 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 2 | HBD-PW | WDF | MTN-RIGG | MTN-RIGG | 2100090334 | HCV-507031 is internally leaking | Rigging assist install new valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2023-06-18 | 2023-05-04 | 50 | REL | APPR OPND | HB /D /20/HBDB-HCV-507031 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 2 | HBD-PW | WDF | MTN-RIGG | MTN-MECH | 2100090334 | HCV-507031 is internally leaking | Install new valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2023-06-18 | 2023-05-04 | 60 | REL | APPR OPND | HB /D /20/HBDB-HCV-507031 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 2 | HBD-PW | WDF | MTN-RIGG | PRODTECH | 2100090334 | HCV-507031 is internally leaking | de-isolation and leak test | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2023-06-18 | 2023-05-04 | 70 | REL | APPR OPND | HB /D /20/HBDB-HCV-507031 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 2 | HBD-PW | WDF | MTN-RIGG | MTN-RIGG | 2100090334 | HCV-507031 is internally leaking | Removal of rigging gear / scaf | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2023-06-18 | 2023-05-04 | 80 | REL | APPR OPND | HB /D /20/HBDB-HCV-507031 | HAND CONTROL VALVE |  | A |  | MMS | DK50
2024-W23-24 | 4 | HBB05-GL | WDF | MTN-MECH | MTN-MECH | 2100090339 | HBB05 MCV control PI gauge defective | Install pressure gauge | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2026-04-21 | 2023-11-03 | 10 | REL | APPR OPND | HB /B /07/HBBB-FP-3140 | FIELD PANEL |  | E |  | MIN | DK50
2024-W23-24 | 3 | HBB08-WI | WDF | MTN-MECH | MTN-MECH | 2100091593 | Gauges in WH panel defect | Replace pressure gauges | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-11-25 | 2023-07-13 | 10 | REL | APPR OPND | HB /B /07/HBBB-FP-3140 | FIELD PANEL |  | E |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100091595 | HBDB-A-1285 actuator evap. defect | Remove Bumpers | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2023-11-22 | 2023-07-10 | 9 | REL | APPR OPND | HB /D /51/HBDB-A-1285 | NH3 CHILLER PACKAGE (STANDBY) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100091595 | HBDB-A-1285 actuator evap. defect | Personal isolation of LCP | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2023-11-22 | 2023-07-10 | 10 | REL | APPR OPND | HB /D /51/HBDB-A-1285 | NH3 CHILLER PACKAGE (STANDBY) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100091595 | HBDB-A-1285 actuator evap. defect | Dismantle old actuator from valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-27 | 2023-11-22 | 2023-07-10 | 20 | REL | APPR OPND | HB /D /51/HBDB-A-1285 | NH3 CHILLER PACKAGE (STANDBY) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100091595 | HBDB-A-1285 actuator evap. defect | Mount new actuator | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-27 | 2023-11-22 | 2023-07-10 | 30 | REL | APPR OPND | HB /D /51/HBDB-A-1285 | NH3 CHILLER PACKAGE (STANDBY) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100091595 | HBDB-A-1285 actuator evap. defect | De isolate and test function of actuator | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-28 | 2023-11-22 | 2023-07-10 | 40 | REL | APPR OPND | HB /D /51/HBDB-A-1285 | NH3 CHILLER PACKAGE (STANDBY) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100091595 | HBDB-A-1285 actuator evap. defect | Mount Bumper | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-28 | 2023-11-22 | 2023-07-10 | 60 | REL | APPR OPND | HB /D /51/HBDB-A-1285 | NH3 CHILLER PACKAGE (STANDBY) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100094572 | HP hydr. isol. valves internal leaking | Production isolation | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-01-03 | 2023-08-21 | 10 | REL | APPR OPND | HB /B /07/HBBB-FP-5940 | HYDRAULIC POWER PANEL |  | C |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100094572 | HP hydr. isol. valves internal leaking | Repcae Isolation valves | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-01-03 | 2023-08-21 | 20 | REL | APPR OPND | HB /B /07/HBBB-FP-5940 | HYDRAULIC POWER PANEL |  | C |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100094572 | HP hydr. isol. valves internal leaking | Production deisolation w leak test | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 | W19-W20 | 2024-04-26 | 2024-04-28 | 2024-04-27 | 2024-01-03 | 2023-08-21 | 30 | REL | APPR OPND | HB /B /07/HBBB-FP-5940 | HYDRAULIC POWER PANEL |  | C |  | MMS | DK50
2024-W19-20 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096324 | Co² regulator for rehard filter defect | Replace Co² regulator for rehard filter | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-02-09 | 2023-09-27 | 10 | REL | APPR OPND | HB /D /85/HBDB-FIL-1064 | REHARD. FILTER |  | A |  | MMS | DK50 |  |  | 2024-05-06
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098348 | LOTI HBCM-A-1236 leak PSV adaptor | HBCM-A-1236 leak PSV adaptor | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-09 | 2023-10-26 | 10 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098348 | LOTI HBCM-A-1236 leak PSV adaptor | Add matr. | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-09 | 2023-10-26 | 20 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098348 | LOTI HBCM-A-1236 leak PSV adaptor | Isolate compressor | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-09 | 2023-10-26 | 30 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100098348 | LOTI HBCM-A-1236 leak PSV adaptor | Recover refrigerant | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 3 | 0 |  | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-09 | 2023-10-26 | 40 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100098348 | LOTI HBCM-A-1236 leak PSV adaptor | Replace adapter | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-09 | 2023-10-26 | 50 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100098348 | LOTI HBCM-A-1236 leak PSV adaptor | Vacuum suction | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-09 | 2023-10-26 | 60 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100098348 | LOTI HBCM-A-1236 leak PSV adaptor | Put system back in service mode | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-09 | 2023-10-26 | 70 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098348 | LOTI HBCM-A-1236 leak PSV adaptor | De-isolate | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-03-18 | 2024-03-19 | 2024-03-19 | 2024-03-09 | 2023-10-26 | 80 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100098348 | LOTI HBCM-A-1236 leak PSV adaptor | Startup & leaktest | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-03-18 | 2024-03-19 | 2024-03-19 | 2024-03-09 | 2023-10-26 | 90 | REL | APPR OPND | HB /C /09/HBCM-A-1236 | AHU-1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2024-W19-20 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098350 | PDI-536732 is broken (P-5367) | Isolate PDI-536732 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W19-W20 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2026-08-08 | 2024-02-20 | 10 | REL | APPR OPND | HB /D /51/HBDB-P-5367 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50 |  |  | 2024-05-06
2024-W19-20 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098350 | PDI-536732 is broken (P-5367) | Replace PDI-536732 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 | W19-W20 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2026-08-08 | 2024-02-20 | 20 | REL | APPR OPND | HB /D /51/HBDB-P-5367 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50 |  |  | 2024-05-07
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100098351 | PDI-536632 is broken (P-5366) | Isolae PDI | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W17-W18 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2026-08-08 | 2024-02-20 | 10 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098351 | PDI-536632 is broken (P-5366) | Replace PDI | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 | W17-W18 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2026-08-08 | 2024-02-20 | 20 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) |  | A |  | MMR | DK50
2026-W13-14 | 3 | HBA19-PW | WDF | MTN-INST | WELLMAIN | 2100100019 | HBA19 Return line chv is internally leak | Close weel/Isolate line | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2023-11-24 | 10 | REL | APPR OPND | HB /A /37/LIFT-GAS-WELL-HBA19 | LIFT GAS WELL HBA-19 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA19-PW | WDF | MTN-INST | MTN-INST | 2100100019 | HBA19 Return line chv is internally leak | Isolate check valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2023-11-24 | 20 | REL | APPR OPND | HB /A /37/LIFT-GAS-WELL-HBA19 | LIFT GAS WELL HBA-19 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA19-PW | WDF | MTN-INST | MTN-INST | 2100100019 | HBA19 Return line chv is internally leak | Replace check valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1.5 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2023-11-24 | 30 | REL | APPR OPND | HB /A /37/LIFT-GAS-WELL-HBA19 | LIFT GAS WELL HBA-19 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA19-PW | WDF | MTN-INST | MTN-INST | 2100100019 | HBA19 Return line chv is internally leak | Deisolate check valve | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2023-11-24 | 40 | REL | APPR OPND | HB /A /37/LIFT-GAS-WELL-HBA19 | LIFT GAS WELL HBA-19 |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA19-PW | WDF | MTN-INST | WELLMAIN | 2100100019 | HBA19 Return line chv is internally leak | Open well/Deisolate hydraulic | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2023-11-24 | 50 | REL | APPR OPND | HB /A /37/LIFT-GAS-WELL-HBA19 | LIFT GAS WELL HBA-19 |  | E |  | MIN | DK50
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100100222 | Light for motor running glass broken | Light for motor running glass broken | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 | W19-W20 | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-04-15 | 2023-12-02 | 10 | REL | APPR OPND | HB /D /76/HBDD-PM-5350 | PUMP MOTOR |  | A |  | MEL | DK50 |  | PROK | 2024-05-15
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100100222 | Light for motor running glass broken | Take off old glass | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W19-W20 | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-04-15 | 2023-12-02 | 20 | REL | APPR OPND | HB /D /76/HBDD-PM-5350 | PUMP MOTOR |  | A |  | MEL | DK50 |  | PROK | 2024-05-16
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100100222 | Light for motor running glass broken | mount new glass | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W19-W20 | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-04-15 | 2023-12-02 | 30 | REL | APPR OPND | HB /D /76/HBDD-PM-5350 | PUMP MOTOR |  | A |  | MEL | DK50 |  | PROK | 2024-05-17
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100100222 | Light for motor running glass broken | test equipment | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W19-W20 | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-04-15 | 2023-12-02 | 40 | REL | APPR OPND | HB /D /76/HBDD-PM-5350 | PUMP MOTOR |  | A |  | MEL | DK50 |  | PROK | 2024-05-18
2026-W13-14 | 2 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100100870 | Scada LIT-445101 replacement | Build scaffolding | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 12 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-26 | 2023-12-11 | 2023-10-27 | 10 | REL | APPR OPND | HB /D /32/HBDB-LIT-445101 | LEVEL INDICATOR TRANSMITTER |  | A |  | MIN | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-INST | PRODTECH | 2100100870 | Scada LIT-445101 replacement | Isolate level transmitter | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-27 | 2023-12-11 | 2023-10-27 | 20 | REL | APPR OPND | HB /D /32/HBDB-LIT-445101 | LEVEL INDICATOR TRANSMITTER |  | A |  | MIN | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-INST | MTN-INST | 2100100870 | Scada LIT-445101 replacement | Replace LT & calibrate | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 6 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-27 | 2023-12-11 | 2023-10-27 | 30 | REL | APPR OPND | HB /D /32/HBDB-LIT-445101 | LEVEL INDICATOR TRANSMITTER |  | A |  | MIN | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-INST | PRODTECH | 2100100870 | Scada LIT-445101 replacement | De-isolate LT | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-28 | 2023-12-11 | 2023-10-27 | 40 | REL | APPR OPND | HB /D /32/HBDB-LIT-445101 | LEVEL INDICATOR TRANSMITTER |  | A |  | MIN | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100100870 | Scada LIT-445101 replacement | Remove scaffolding | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 8 | 0 | W17-W18 | 2024-04-26 | 2024-04-29 | 2024-04-28 | 2023-12-11 | 2023-10-27 | 50 | REL | APPR OPND | HB /D /32/HBDB-LIT-445101 | LEVEL INDICATOR TRANSMITTER |  | A |  | MIN | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104213 | ELECTRICAL WATER HEATER FOR V-1140 | ELECTRICAL WATER HEATER FOR V-1140 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-02-09 | 2023-12-26 | 10 | REL | APPR OPND | HB /C /72/HBCM-HE-1140 | ELECTRICAL WATER HEATER |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100104213 | ELECTRICAL WATER HEATER FOR V-1140 | Isolate and prove dead | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-02-09 | 2023-12-26 | 20 | REL | APPR OPND | HB /C /72/HBCM-HE-1140 | ELECTRICAL WATER HEATER |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104213 | ELECTRICAL WATER HEATER FOR V-1140 | Replace old heater with new one. | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 6 | 0 |  | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-02-09 | 2023-12-26 | 30 | REL | APPR OPND | HB /C /72/HBCM-HE-1140 | ELECTRICAL WATER HEATER |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100104213 | ELECTRICAL WATER HEATER FOR V-1140 | Deisolate and put back in service | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-02-09 | 2023-12-26 | 40 | REL | APPR OPND | HB /C /72/HBCM-HE-1140 | ELECTRICAL WATER HEATER |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104213 | ELECTRICAL WATER HEATER FOR V-1140 | test equipment | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-07-01 | 2024-07-03 | 2024-07-03 | 2024-02-09 | 2023-12-26 | 50 | REL | APPR OPND | HB /C /72/HBCM-HE-1140 | ELECTRICAL WATER HEATER |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104213 | ELECTRICAL WATER HEATER FOR V-1140 | Added spareparts | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-02-09 | 2023-12-26 | 70 | REL | APPR OPND | HB /C /72/HBCM-HE-1140 | ELECTRICAL WATER HEATER |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104213 | ELECTRICAL WATER HEATER FOR V-1140 | New Heater | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-02-09 | 2023-12-26 | 90 | REL | APPR OPND | HB /C /72/HBCM-HE-1140 | ELECTRICAL WATER HEATER |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 2 |  | WDF | VEN-ELEC | MTN-ELEC | 2100105036 | Defect Temp. Control for TN-1801 | Defect Temp. Control for TN-1801 | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-01-09 | 2024-01-10 | 2024-01-09 | 2024-02-23 | 2024-01-09 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-1-1 | INCOMING FROM HBCA-TN-1801 |  | A |  | MEL | DK50 |  | AW-INFO
2026-W13-14 | 2 |  | WDF | VEN-ELEC | PRODTECH | 2100105036 | Defect Temp. Control for TN-1801 | Isolate Equipment. | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-01-09 | 2024-01-10 | 2024-01-09 | 2024-02-23 | 2024-01-09 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-1-1 | INCOMING FROM HBCA-TN-1801 |  | A |  | MEL | DK50 |  | AW-INFO
2026-W13-14 | 2 |  | WDF | VEN-ELEC | VEN-ELEC | 2100105036 | Defect Temp. Control for TN-1801 | Replace defective parts | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 3 | 0 |  | 2024-01-09 | 2024-01-10 | 2024-01-10 | 2024-02-23 | 2024-01-09 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-1-1 | INCOMING FROM HBCA-TN-1801 |  | A |  | MEL | DK50 |  | AW-INFO
2026-W13-14 | 2 |  | WDF | VEN-ELEC | PRODTECH | 2100105036 | Defect Temp. Control for TN-1801 | De-isolate Equipment | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-01-09 | 2024-01-10 | 2024-01-10 | 2024-02-23 | 2024-01-09 | 40 | REL | APPR OPND | HB /C /61/HBCA-N-1810-1-1 | INCOMING FROM HBCA-TN-1801 |  | A |  | MEL | DK50 |  | AW-INFO
2026-W13-14 | 2 |  | WDF | VEN-ELEC | VEN-ELEC | 2100105036 | Defect Temp. Control for TN-1801 | Test & put back in service | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-01-09 | 2024-01-10 | 2024-01-10 | 2024-02-23 | 2024-01-09 | 50 | REL | APPR OPND | HB /C /61/HBCA-N-1810-1-1 | INCOMING FROM HBCA-TN-1801 |  | A |  | MEL | DK50 |  | AW-INFO
2024-W19-20 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100106044 | CCTV camera AS-141008 failed | Install new CCTV camera | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 10 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2024-07-16 | 2024-03-03 | 10 | REL | APPR OPND | HB /D /08/HBDE-AS-141008 | PTZ CAMERA WITH SUN SHIELD |  | A |  | MIN | DK50 |  |  | 2024-05-06
2026-W13-14 | 3 | NOSD | WGN | MTN-CRAN | VEN-CRAN | 2200007986 | HBD/78 Mount handrail crane boom tip | Find and check new materials | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-14 | 2024-03-09 | 2022-01-05 | 2021-10-07 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-CRAN | PRODTECH | 2200007986 | HBD/78 Mount handrail crane boom tip | Isolate crane HBDE-A-6150 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-14 | 2024-03-09 | 2022-01-05 | 2021-10-07 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-CRAN | MTN-RIGG | 2200007986 | HBD/78 Mount handrail crane boom tip | Rigg new railing up in boomtip and assis | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 50 | 0 |  | 2024-03-09 | 2024-03-14 | 2024-03-09 | 2022-01-05 | 2021-10-07 | 30 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-CRAN | VEN-CRAN | 2200007986 | HBD/78 Mount handrail crane boom tip | Mount new railing in boom tip | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 12 | 0 |  | 2024-03-09 | 2024-03-14 | 2024-03-12 | 2022-01-05 | 2021-10-07 | 40 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-CRAN | PRODTECH | 2200007986 | HBD/78 Mount handrail crane boom tip | Deisolate crane HBDE-A-6150 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-14 | 2024-03-14 | 2022-01-05 | 2021-10-07 | 50 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-CRAN | VEN-CRAN | 2200007986 | HBD/78 Mount handrail crane boom tip | Clean-up, documentation and QC | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2024-03-09 | 2024-03-14 | 2024-03-14 | 2022-01-05 | 2021-10-07 | 60 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-CRAN | VEN-CRAN | 2200009525 | HBD/78: New boom protections | Check spareparts recived | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W44 DK50-M-6880 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2022-08-30 | 2022-04-02 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-CRAN | PRODTECH | 2200009525 | HBD/78: New boom protections | Isolate crane HBDE-A-6150 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W44 DK50-M-6880 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2022-08-30 | 2022-04-02 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-CRAN | VEN-ROPE | 2200009525 | HBD/78: New boom protections | Install new boom protection | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 72 | 0 | W44 DK50-M-6880 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2022-08-30 | 2022-04-02 | 30 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-CRAN | VEN-CRAN | 2200009525 | HBD/78: New boom protections | Assist with installing boom protection | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 24 | 0 | W44 DK50-M-6880 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2022-08-30 | 2022-04-02 | 40 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-CRAN | PRODTECH | 2200009525 | HBD/78: New boom protections | Deisolate crane HBDE-A-6150 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W44 DK50-M-6880 | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2022-08-30 | 2022-04-02 | 50 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-CRAN | VEN-CRAN | 2200009525 | HBD/78: New boom protections | Function test after installation | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W44 DK50-M-6880 | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2022-08-30 | 2022-04-02 | 60 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-CRAN | MTN-ROUS | 2200009525 | HBD/78: New boom protections | Assist with function test | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W44 DK50-M-6880 | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2022-08-30 | 2022-04-02 | 70 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-CRAN | VEN-CRAN | 2200009525 | HBD/78: New boom protections | Clean-up, documentation QC | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W44 DK50-M-6880 | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2022-08-30 | 2022-04-02 | 80 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
0 | 3 | NOSD | WGN | MTN-ROPE | PRODTECH | 2200012955 | Replace hydraulic limit switch FFLB1 | Isolate lifeboat accordingly | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 |  | 2024-10-03 | 2024-10-04 | 2024-10-03 | 2023-07-03 | 2023-02-18 | 10 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200012955 | Replace hydraulic limit switch FFLB1 | Replace hydraulic limitswitch | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 9 | 0 |  | 2024-10-03 | 2024-10-04 | 2024-10-03 | 2023-07-03 | 2023-02-18 | 20 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-ROPE | PRODTECH | 2200012955 | Replace hydraulic limit switch FFLB1 | De-isolate above | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-10-03 | 2024-10-04 | 2024-10-03 | 2023-07-03 | 2023-02-18 | 30 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A |  | MMS | DK60
0 | 2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200014276 | Install lifesaving means for campaign | install scaffold for liferaft cradle | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 12 | 0 |  | 2023-05-03 | 2023-05-06 | 2023-05-03 | 2023-06-17 | 2023-05-03 | 20 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | MMS | DK60
0 | 2 | NOSD | WGN | MTN-SCAF | MTN-RIGG | 2200014276 | Install lifesaving means for campaign | rig in & install liferaft | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 6 | 0 |  | 2023-05-03 | 2023-05-06 | 2023-05-04 | 2023-06-17 | 2023-05-03 | 30 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | MMS | DK60
0 | 2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200014276 | Install lifesaving means for campaign | prepare temporary storage for survivalsu | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 12 | 0 |  | 2023-05-03 | 2023-05-06 | 2023-05-04 | 2023-06-17 | 2023-05-03 | 40 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | MMS | DK60
0 | 2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200014276 | Install lifesaving means for campaign | align lifevests and suits in tempstorage | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 6 | 0 |  | 2023-05-03 | 2023-05-06 | 2023-05-05 | 2023-06-17 | 2023-05-03 | 50 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015389 | Replace FFLB2 coolant with GlysantinG30 | Isolate lifeboat | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-02-13 | 2023-10-01 | 10 | REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | C |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015389 | Replace FFLB2 coolant with GlysantinG30 | Flush coolant system with Glysantin G30 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-02-13 | 2023-10-01 | 20 | REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | C |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015389 | Replace FFLB2 coolant with GlysantinG30 | De-isolate accordingly | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-02-13 | 2023-10-01 | 30 | REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | C |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015390 | Replace FFLB1 coolant with GlysantinG30 | Isolate lifeboat | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-02-13 | 2023-10-01 | 10 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | C |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015390 | Replace FFLB1 coolant with GlysantinG30 | Flush coolant system with Glysantin G30 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 3 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-02-13 | 2023-10-01 | 20 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | C |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015390 | Replace FFLB1 coolant with GlysantinG30 | De-isolate accordingly | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-02-13 | 2023-10-01 | 30 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | C |  | MMS | DK60
0 | 4 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300001438 | DK60 - CONSUMABLE-GALLEY | DK60 - CONSUMABLE-GALLEY | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT RDBL | 0 | 6 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-07-06 | 2020-09-09 | 10 | PCNF REL | APPR OPND | HD /A /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK60
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | DK50 SMEDE MATERIAL ORDER | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 10 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | TMP297 UAN | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 11 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | TMP297 UAN | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 12 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | 2300002680 26.04 TMP-297 HOSE,COUPLING | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 22 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | TMP297 UAN 2 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 23 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | 2300002680 21.05 MAT SMERGEL,KLINGE MM | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 33 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | TMP297 UAN 3 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 43 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | TMP297 UAN 4 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 53 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | TMP297 UAN 5 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 63 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | TMP297 UAN 6 Argon reg | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 73 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | TMP297 UAN 7 TIG KIT | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 83 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | TMP297 UAN 8 RØRTRÅDS KIT MM | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 93 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | TMP297 UAN 9 WIRE OG LÅSE | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 103 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | 2300002680 10.06 MAT JET EL PUMP MM MUEH | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 113 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | HBACOR UAN WO 2800013547 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 123 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | Muehlhan So-308 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 133 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | KÆDESPÆNDER TIL WO 2700001308 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 143 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | Muehlhan So: 313 for wo 2400116224 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 153 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | HBA-V-3411 wo: 2400116224 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 155 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | 3 mm Svejseelektroder wo 2800008079 MM | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 160 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | 2300002680 20.07 MAT DRILL,BIT,TAP TOT | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 170 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | Muehlhan mat. 1206007 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 180 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | ARGON TIL TMP297 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 190 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W23-24 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002680 | DK50 SMEDE MATERIAL ORDER | 2300002680 01.09 GASDECT | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-04-25 | 2021-03-16 | 200 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | COW | DK50
2024-W33-34 | 3 | NOSD | WRO | PRODTECH | PRODTECH | 2300003332 | Purchase of new Safemaster Ladders | Purchase of new Safemaster Ladders | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-12-11 | 2021-11-01 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | PRD | DK50 |  |  | 2024-05-19
2024-W31-32 | 4 |  | WRO | PRODTECH | PRODTECH | 2300004268 | DK50 - CONSUMABLE PROD - WORKSHOP | DK50 - CONSUMABLE PROD - WORKSHOP | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2023-05-10 | 2023-05-10 | 2023-05-10 | 2025-10-26 | 2023-05-10 | 10 | REL | APPR OPND | HB /D /84 | WORKSHOP/WAREHOUSE |  | A |  | MIN | DK50
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400245919 | 1Y HVAC EXT. HDBD-FAN-1210A/B - 1217A/B | PERSONAL ISOLATION | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-05-23 | 2023-04-17 | 10 | REL | APPR OPND | HD /B /09/TOILET-EXTRACT | FANS 1210A/B |  | A | DKHD-2015 | MEL | DK60 | EL0013
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400245919 | 1Y HVAC EXT. HDBD-FAN-1210A/B - 1217A/B | EXHAUST CHECK, DUTY & STBY, BELT DRIVEN | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-05-23 | 2023-04-17 | 20 | REL | APPR OPND | HD /B /09/TOILET-EXTRACT | FANS 1210A/B |  | A | DKHD-2015 | MEL | DK60 | EL0013
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400245919 | 1Y HVAC EXT. HDBD-FAN-1210A/B - 1217A/B | PERSONAL DE-ISOLATION | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2023-05-23 | 2023-04-17 | 30 | REL | APPR OPND | HD /B /09/TOILET-EXTRACT | FANS 1210A/B |  | A | DKHD-2015 | MEL | DK60 | EL0013
2024-W19-20 | C | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400302377 | 1Y CRANE HOIST EQUIP, HB | CRANE HOIST EQUIP, HB | REL PRT GMPS MANC PRC SETC | APPR CMAT RDBL | 10 | 0 | W17-W18 | 2024-04-26 | 2024-04-28 | 2024-04-26 | 2024-05-01 | 2024-03-26 | 10 | REL | APPR OPND | HB /C /78 | LIFTING EQUIPMENT |  | A | DKHB-2065 | MMS | DK50 | MS0154 |  | 2024-05-06
0 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400307678 | 1Y ANTI FOULING INSPECTION HDBC-A-5500 | ISOLATION | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 | W17-W18 | 2024-04-24 | 2024-04-30 | 2024-04-24 | 2024-02-27 | 2024-01-22 | 10 | REL | APPR OPND | HD /B /52/HDBC-A-5500 | ANTI-FOULING PACKAGE |  | A | DKHD-0130 | MMS | DK60 | MS0133
0 | C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400307678 | 1Y ANTI FOULING INSPECTION HDBC-A-5500 | ANTI FOULING INSPECTION HDBC-A-5500 | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 12 | 0 | W17-W18 | 2024-04-24 | 2024-04-30 | 2024-04-24 | 2024-02-27 | 2024-01-22 | 20 | REL | APPR OPND | HD /B /52/HDBC-A-5500 | ANTI-FOULING PACKAGE |  | A | DKHD-0130 | MMS | DK60 | MS0133
0 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400307678 | 1Y ANTI FOULING INSPECTION HDBC-A-5500 | MECHANICAL ASSISTANCE | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 10 | 0 | W17-W18 | 2024-04-24 | 2024-04-30 | 2024-04-26 | 2024-02-27 | 2024-01-22 | 30 | REL | APPR OPND | HD /B /52/HDBC-A-5500 | ANTI-FOULING PACKAGE |  | A | DKHD-0130 | MMS | DK60 | MS0133
0 | C | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400307678 | 1Y ANTI FOULING INSPECTION HDBC-A-5500 | RIGGER ASSISTANCE | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 4 | 0 | W17-W18 | 2024-04-24 | 2024-04-30 | 2024-04-28 | 2024-02-27 | 2024-01-22 | 40 | REL | APPR OPND | HD /B /52/HDBC-A-5500 | ANTI-FOULING PACKAGE |  | A | DKHD-0130 | MMS | DK60 | MS0133
0 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400307678 | 1Y ANTI FOULING INSPECTION HDBC-A-5500 | DE-ISOLATION | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 2 | 0 | W17-W18 | 2024-04-24 | 2024-04-30 | 2024-04-29 | 2024-02-27 | 2024-01-22 | 50 | REL | APPR OPND | HD /B /52/HDBC-A-5500 | ANTI-FOULING PACKAGE |  | A | DKHD-0130 | MMS | DK60 | MS0133
2024-W19-20 | D | NOSD | WPM | MTN-INST | MTN-INST | 2400325378 | 1Y BUMPTEST STATION MAINT-HBCY-X-80003 | BUMPTEST STATION MAINT-HBCY-X-80003 | REL GMPS MACM PRC SETC | APPR CMAT RDBL | 1 | 0 |  | 2024-04-09 | 2024-04-09 | 2024-04-09 | 2024-05-26 | 2024-04-09 | 10 | REL | APPR OPND | HB /C /84/HBCY-X-80003 | BUMP TEST STATION |  | C | DKHB-2054 | MIN | DK50 | IN0114 |  | 2024-05-06
0 | D | NOSD | WPM | MTN-INST | MTN-INST | 2400329584 | 6M PROCESS CALIBRATION EQUIPMENT HDA | PROCESS CALIBRATION EQUIPMENT | REL GMPS MANC PRC SETC | APPR CMAT RDBL | 0 | 0 |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-06-15 | 2024-05-21 | 10 | REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A | DKHD-2026 | MIN | DK60 | IN0113
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-INST | MTN-ROPE | 2100076145 | TIT for the HP flare ignition panel | Prepare rope access | REL GMPS MANC PRC SETC | APPR CMAT AWSD RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-09-26 | 2023-04-10 | 10 | REL | APPR OPND | HB /D /36/HBDC-TE-405301 | TEMPERATURE ELEMENT |  | G |  | MIN | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-INST | MTN-ROPE | 2100076145 | TIT for the HP flare ignition panel | Isolate Temperature element (Sensor) | REL GMPS MANC PRC SETC | APPR CMAT AWSD RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-09-26 | 2023-04-10 | 20 | REL | APPR OPND | HB /D /36/HBDC-TE-405301 | TEMPERATURE ELEMENT |  | G |  | MIN | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-INST | MTN-ROPE | 2100076145 | TIT for the HP flare ignition panel | Replace Temperature element (Sensor) | REL GMPS MANC PRC SETC | APPR CMAT AWSD RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-09-26 | 2023-04-10 | 30 | REL | APPR OPND | HB /D /36/HBDC-TE-405301 | TEMPERATURE ELEMENT |  | G |  | MIN | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-INST | MTN-ROPE | 2100076145 | TIT for the HP flare ignition panel | Deisolate Temperature element (Sensor) | REL GMPS MANC PRC SETC | APPR CMAT AWSD RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-09-26 | 2023-04-10 | 40 | REL | APPR OPND | HB /D /36/HBDC-TE-405301 | TEMPERATURE ELEMENT |  | G |  | MIN | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-INST | MTN-ROPE | 2100076145 | TIT for the HP flare ignition panel | Remove rope access | REL GMPS MANC PRC SETC | APPR CMAT AWSD RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-09-26 | 2023-04-10 | 50 | REL | APPR OPND | HB /D /36/HBDC-TE-405301 | TEMPERATURE ELEMENT |  | G |  | MIN | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-INST | MTN-INST | 2100076145 | TIT for the HP flare ignition panel | Assistance | REL GMPS MANC PRC SETC | APPR CMAT AWSD RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-09-26 | 2023-04-10 | 60 | REL | APPR OPND | HB /D /36/HBDC-TE-405301 | TEMPERATURE ELEMENT |  | G |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100091590 | pig launcher XCV - no remote operate | Replace closing Solenoid | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWSD RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-11-14 | 2023-07-02 | 50 | PCNF REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE |  | G |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100091590 | pig launcher XCV - no remote operate | ************************************** | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWSD RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-11-14 | 2023-07-02 | 60 | REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE |  | G |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100091590 | pig launcher XCV - no remote operate | Work prep./valve isolation | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWSD RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-11-14 | 2023-07-02 | 70 | REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE |  | G |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100091590 | pig launcher XCV - no remote operate | Isolate solenoid valve | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWSD RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-11-14 | 2023-07-02 | 80 | REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE |  | G |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100091590 | pig launcher XCV - no remote operate | Replace solenoid valve | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWSD RDBL | 3.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-11-14 | 2023-07-02 | 90 | REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE |  | G |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100091590 | pig launcher XCV - no remote operate | De-isolate solenoid valve / test with CC | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWSD RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-11-14 | 2023-07-02 | 100 | REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE |  | G |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | MTN-TELE | 2100091590 | pig launcher XCV - no remote operate | Change settings in SCADA | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWSD RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-11-14 | 2023-07-02 | 110 | REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE |  | G |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100091590 | pig launcher XCV - no remote operate | Valve is back in service | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWSD RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-11-14 | 2023-07-02 | 120 | REL | APPR OPND | HB /A /12/HBAA-XCV-34008 | PRODUCTION MANIFOLD INLET VALVE |  | G |  | MIN | DK50
0 | 3 | HBOIL-SD | WGN | MTN-TELE | MTN-TELE | 2200006512 | ESD2 shutdown test ref EXP-407 HDA | ESD2 shutdown test ref EXP-407 HDA | REL GMPS MANC PRC SETC | APPR CMAT AWSD AWSC | 0 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-06-24 | 2021-03-26 | 10 | REL | APPR OPND | HD /B /08/HDBE-CP-0201 | ESD CONTROLLER, IESD RACK |  | G |  | MIN | DK60
0 | 3 | HBOIL-SD | WGN | MTN-TELE | MTN-TELE | 2200006512 | ESD2 shutdown test ref EXP-407 HDA | Resitors | REL GMPS MANC PRC SETC | APPR CMAT AWSD AWSC | 0 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-06-24 | 2021-03-26 | 20 | REL | APPR OPND | HD /B /08/HDBE-CP-0201 | ESD CONTROLLER, IESD RACK |  | G |  | MIN | DK60
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-INST | MTN-SCAF | 2100057878 | Possitioner on ESDV in bad shape | Place ladder | REL GMPS MANC PRC SETC | APPR CMAT AWSD AWDO RDBL ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-12-23 | 2021-11-13 | 9 | REL | APPR OPND | HB /D /20/HBDC-ESDV-345102 | EMERGENCY SHUTDOWN VALVE | 99000119 | G |  | MIN | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-INST | PRODTECH | 2100057878 | Possitioner on ESDV in bad shape | Isolate ShutDown Valve (SDV) | REL GMPS MANC PRC SETC | APPR CMAT AWSD AWDO RDBL ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-12-23 | 2021-11-13 | 10 | REL | APPR OPND | HB /D /20/HBDC-ESDV-345102 | EMERGENCY SHUTDOWN VALVE | 99000119 | G |  | MIN | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-INST | MTN-INST | 2100057878 | Possitioner on ESDV in bad shape | Replace and adjust position switch | REL GMPS MANC PRC SETC | APPR CMAT AWSD AWDO RDBL ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-12-23 | 2021-11-13 | 20 | REL | APPR OPND | HB /D /20/HBDC-ESDV-345102 | EMERGENCY SHUTDOWN VALVE | 99000119 | G |  | MIN | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-INST | PRODTECH | 2100057878 | Possitioner on ESDV in bad shape | Deisolate and test ShutDown Valve (SDV) | REL GMPS MANC PRC SETC | APPR CMAT AWSD AWDO RDBL ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-12-23 | 2021-11-13 | 30 | REL | APPR OPND | HB /D /20/HBDC-ESDV-345102 | EMERGENCY SHUTDOWN VALVE | 99000119 | G |  | MIN | DK50
2026-W13-14 | 3 | HBDHPSEP | WDF | MTN-INST | MTN-SCAF | 2100057878 | Possitioner on ESDV in bad shape | Remove ladder | REL GMPS MANC PRC SETC | APPR CMAT AWSD AWDO RDBL ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-12-23 | 2021-11-13 | 40 | REL | APPR OPND | HB /D /20/HBDC-ESDV-345102 | EMERGENCY SHUTDOWN VALVE | 99000119 | G |  | MIN | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-PIPF | PRODTECH | 2100066284 | FFS Replace 1" VAG6S cracked valve | Production Isolation | REL GMPS MANC PRC SETC | APPR CMAT AWSD AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-12-31 | 2022-05-01 | 10 | REL | APPR OPND | HB /D /07/HBD-2-AI-054-8551-AG-U | 2 INSTRUMENT AIR LINE |  | G |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-PIPF | MTN-MECH | 2100066284 | FFS Replace 1" VAG6S cracked valve | Replace cracked valve | REL GMPS MANC PRC SETC | APPR CMAT AWSD AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2023-12-31 | 2022-05-01 | 20 | REL | APPR OPND | HB /D /07/HBD-2-AI-054-8551-AG-U | 2 INSTRUMENT AIR LINE |  | G |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-PIPF | PRODTECH | 2100066284 | FFS Replace 1" VAG6S cracked valve | Production Deisolation w leak test | REL GMPS MANC PRC SETC | APPR CMAT AWSD AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2023-12-31 | 2022-05-01 | 30 | REL | APPR OPND | HB /D /07/HBD-2-AI-054-8551-AG-U | 2 INSTRUMENT AIR LINE |  | G |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | VEN-MECH | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | PR for vendor for machining 14" flange | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-01 | 2022-03-31 | 2021-12-24 | 20 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | PRODTECH | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Safing / SD | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-01 | 2022-03-31 | 2021-12-24 | 30 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-SCAF | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Prepare scaffold / equipment | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 18 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-01 | 2022-03-31 | 2021-12-24 | 40 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-SCAF | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Build scaffold | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-02 | 2022-03-31 | 2021-12-24 | 50 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-RIGG | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Install rigging gear | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-04 | 2022-03-31 | 2021-12-24 | 60 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-PIPF | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Dismantle spool PTW 2082390 | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-04 | 2022-03-31 | 2021-12-24 | 70 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | INP-SITE | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Check of flanges on valve / Adj. spool | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-05 | 2022-03-31 | 2021-12-24 | 71 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-SCAF | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Dismantle scaffold for rig down spool | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 18 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-05 | 2022-03-31 | 2021-12-24 | 80 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-RIGG | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Rig down old spool | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-06 | 2022-03-31 | 2021-12-24 | 90 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-RIGG | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Rig up new spool | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-07 | 2022-03-31 | 2021-12-24 | 100 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-SCAF | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Re build scaffold for install new spool | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-08 | 2022-03-31 | 2021-12-24 | 110 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | VEN-MECH | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Machining of flanges if required | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-09 | 2022-03-31 | 2021-12-24 | 111 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-PIPF | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Install spool and torque up | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 16 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-09 | 2022-03-31 | 2021-12-24 | 120 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | PRODTECH | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Leak test | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-11 | 2022-03-31 | 2021-12-24 | 130 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-SCAF | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Dismantle rigging gear/ scaffold | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-11 | 2022-03-31 | 2021-12-24 | 140 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-PIPF | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Clean work site | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-13 | 2022-03-31 | 2021-12-24 | 150 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-PIPF | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Erection materials for spool | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-13 | 2022-03-31 | 2021-12-24 | 160 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-PIPF | MTN-RIGG | 2100061196 | DGSPR: HBA-14"-PHS-033-4033 Grayloc hub | Riggerudstyr MDKW | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSD AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-13 | 2022-03-31 | 2021-12-24 | 170 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4033-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | G |  | MFM | DK50
2026-W13-14 | 4 | HBA03-GL | WDF | MTN-INST | MTN-INST | 2100026224 | Replace cables HBAA-FCV-29033 | Isolate HBAA-FCV-29033 | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL SREQ | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-30 | 2018-04-28 | 10 | REL | APPR OPND | HB /A /37/HBAA-FCV-29033 | LIFT GAS FLOW CONTROL VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBA03-GL | WDF | MTN-INST | MTN-INST | 2100026224 | Replace cables HBAA-FCV-29033 | Investigate oil leak | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL SREQ | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-30 | 2018-04-28 | 20 | REL | APPR OPND | HB /A /37/HBAA-FCV-29033 | LIFT GAS FLOW CONTROL VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBA03-GL | WDF | MTN-INST | MTN-INST | 2100026224 | Replace cables HBAA-FCV-29033 | Clean up for hydraulic oil in JB. | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL SREQ | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-30 | 2018-04-28 | 30 | REL | APPR OPND | HB /A /37/HBAA-FCV-29033 | LIFT GAS FLOW CONTROL VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBA03-GL | WDF | MTN-INST | MTN-INST | 2100026224 | Replace cables HBAA-FCV-29033 | Replace cables between JB and FCV | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL SREQ | 18 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-30 | 2018-04-28 | 40 | REL | APPR OPND | HB /A /37/HBAA-FCV-29033 | LIFT GAS FLOW CONTROL VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBA03-GL | WDF | MTN-INST | MTN-INST | 2100026224 | Replace cables HBAA-FCV-29033 | De-Isolate/test HBAA-FCV-29033 | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL SREQ | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-30 | 2018-04-28 | 50 | REL | APPR OPND | HB /A /37/HBAA-FCV-29033 | LIFT GAS FLOW CONTROL VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBA03-GL | WDF | MTN-INST | MTN-SCAF | 2100026224 | Replace cables HBAA-FCV-29033 | Build mobile platform | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL SREQ | 12 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-30 | 2018-04-28 | 60 | REL | APPR OPND | HB /A /37/HBAA-FCV-29033 | LIFT GAS FLOW CONTROL VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBA03-GL | WDF | MTN-INST | MTN-INST | 2100026224 | Replace cables HBAA-FCV-29033 | Materials | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL SREQ | 0 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-30 | 2018-04-28 | 70 | REL | APPR OPND | HB /A /37/HBAA-FCV-29033 | LIFT GAS FLOW CONTROL VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100022712 | DGS: 628862 Replace HBBA-XCV-38208 | Rigg up for lifting. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 4 | 0 | OIM 10 | 2024-04-25 | 2024-04-26 | 2024-04-25 | 2019-06-16 | 2019-03-18 | 9 | REL | APPR OPND | HB /B /23/HBBA-XCV-38208 | UNCLASSIFIED VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | PRODTECH | 2100022712 | DGS: 628862 Replace HBBA-XCV-38208 | Isolation of HBBA-XCV-38208 | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | OIM 10 | 2024-04-25 | 2024-04-26 | 2024-04-25 | 2019-06-16 | 2019-03-18 | 10 | REL | APPR OPND | HB /B /23/HBBA-XCV-38208 | UNCLASSIFIED VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-MECH | 2100022712 | DGS: 628862 Replace HBBA-XCV-38208 | Replace HBBA-XCV-38208 | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 6 | 0 | OIM 10 | 2024-04-25 | 2024-04-26 | 2024-04-25 | 2019-06-16 | 2019-03-18 | 20 | REL | APPR OPND | HB /B /23/HBBA-XCV-38208 | UNCLASSIFIED VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100022712 | DGS: 628862 Replace HBBA-XCV-38208 | Help replace valve | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 | OIM 10 | 2024-04-25 | 2024-04-26 | 2024-04-25 | 2019-06-16 | 2019-03-18 | 29 | REL | APPR OPND | HB /B /23/HBBA-XCV-38208 | UNCLASSIFIED VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | PRODTECH | 2100022712 | DGS: 628862 Replace HBBA-XCV-38208 | De-Isolation / test HBBA-XCV-38208 | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | OIM 10 | 2024-04-25 | 2024-04-26 | 2024-04-26 | 2019-06-16 | 2019-03-18 | 30 | REL | APPR OPND | HB /B /23/HBBA-XCV-38208 | UNCLASSIFIED VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100022712 | DGS: 628862 Replace HBBA-XCV-38208 | Remove rigging | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 | OIM 10 | 2024-04-25 | 2024-04-26 | 2024-04-26 | 2019-06-16 | 2019-03-18 | 40 | REL | APPR OPND | HB /B /23/HBBA-XCV-38208 | UNCLASSIFIED VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-MECH | 2100022712 | DGS: 628862 Replace HBBA-XCV-38208 | New Valve | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 |  | 2024-04-25 | 2024-04-26 | 2024-04-25 | 2019-06-16 | 2019-03-18 | 50 | REL | APPR OPND | HB /B /23/HBBA-XCV-38208 | UNCLASSIFIED VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100022949 | Replace 2 pcs 3/4" valves (HBD 100 bar h | L3 Isolation of HBDC-P-5963 | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-05-04 | 2019-03-25 | 10 | REL | APPR OPND | HB /D /07/HBDC-P-5963 | HYDRAULIC OIL PUMP | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100022949 | Replace 2 pcs 3/4" valves (HBD 100 bar h | L2 Replace 2 pcs 3/4" valves | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-05-04 | 2019-03-25 | 20 | REL | APPR OPND | HB /D /07/HBDC-P-5963 | HYDRAULIC OIL PUMP | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100022949 | Replace 2 pcs 3/4" valves (HBD 100 bar h | L3 De-Isolation / test HBDC-P-5963 | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-05-04 | 2019-03-25 | 30 | REL | APPR OPND | HB /D /07/HBDC-P-5963 | HYDRAULIC OIL PUMP | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-RIGG | 2100023465 | DGS:607240 Replace HBAA-XCV-35001 | L3 Lift the waist up to the XCV-35001 | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 17.4 | 0 | OIM 10 | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2018-12-21 | 2018-07-24 | 10 | REL | APPR OPND | HB /A /50/HBAA-XCV-35001 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | PRODTECH | 2100023465 | DGS:607240 Replace HBAA-XCV-35001 | L3 Safing Injection manifold and Valve | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | OIM 10 | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2018-12-21 | 2018-07-24 | 20 | REL | APPR OPND | HB /A /50/HBAA-XCV-35001 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-PIPF | 2100023465 | DGS:607240 Replace HBAA-XCV-35001 | L3 Remove the Actuator from XCV | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 8 | 0 | OIM 10 | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2018-12-21 | 2018-07-24 | 21 | REL | APPR OPND | HB /A /50/HBAA-XCV-35001 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-PIPF | 2100023465 | DGS:607240 Replace HBAA-XCV-35001 | L3 Remove the XCV-35001 | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 8 | 0 | OIM 10 | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2018-12-21 | 2018-07-24 | 30 | REL | APPR OPND | HB /A /50/HBAA-XCV-35001 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | PRODTECH | 2100023465 | DGS:607240 Replace HBAA-XCV-35001 | L2 Mount XCV-35001 | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 12 | 0 | OIM 10 | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2018-12-21 | 2018-07-24 | 40 | REL | APPR OPND | HB /A /50/HBAA-XCV-35001 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-PIPF | 2100023465 | DGS:607240 Replace HBAA-XCV-35001 | L2 Mount the Actuator | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 8 | 0 | OIM 10 | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2018-12-21 | 2018-07-24 | 41 | REL | APPR OPND | HB /A /50/HBAA-XCV-35001 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | PRODTECH | 2100023465 | DGS:607240 Replace HBAA-XCV-35001 | L3 Desafing Injection manifold and Valve | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | OIM 10 | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2018-12-21 | 2018-07-24 | 50 | REL | APPR OPND | HB /A /50/HBAA-XCV-35001 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HB WI SD | WDF | MTN-PIPF | MTN-RIGG | 2100023465 | DGS:607240 Replace HBAA-XCV-35001 | L3 Remove waist after use | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 17.4 | 0 | OIM 10 | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2018-12-21 | 2018-07-24 | 60 | REL | APPR OPND | HB /A /50/HBAA-XCV-35001 | PRODUCTION MANIFOLD INLET VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | MTN-PIPF | 2100024718 | DGS #657382 +Exchange DB&B XCV valve inc | L3 Site visit | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-01 | 2019-05-28 | 2019-02-27 | 5 | REL | APPR OPND | HB /A /34/HBAA-XCV-38012A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | MTN-SCAF | 2100024718 | DGS #657382 +Exchange DB&B XCV valve inc | L3 Prepare rigging equipment | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 17.4 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-01 | 2019-05-28 | 2019-02-27 | 10 | REL | APPR OPND | HB /A /34/HBAA-XCV-38012A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | PRODTECH | 2100024718 | DGS #657382 +Exchange DB&B XCV valve inc | L3 Isolate equipment | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 12 | 0 | RCE | 2025-01-01 | 2025-01-12 | 2025-01-03 | 2019-05-28 | 2019-02-27 | 20 | REL | APPR OPND | HB /A /34/HBAA-XCV-38012A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | MTN-PIPF | 2100024718 | DGS #657382 +Exchange DB&B XCV valve inc | L3 Dismantle Hydraulic & hubs | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 13.4 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-05 | 2019-05-28 | 2019-02-27 | 30 | REL | APPR OPND | HB /A /34/HBAA-XCV-38012A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | VEN-ELEC | 2100024718 | DGS #657382 +Exchange DB&B XCV valve inc | L3 Disconnect cables | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-05 | 2019-05-28 | 2019-02-27 | 40 | REL | APPR OPND | HB /A /34/HBAA-XCV-38012A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | MTN-SCAF | 2100024718 | DGS #657382 +Exchange DB&B XCV valve inc | L3 Rig in & out of valve | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 17.4 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-06 | 2019-05-28 | 2019-02-27 | 50 | REL | APPR OPND | HB /A /34/HBAA-XCV-38012A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | MTN-MECH | 2100024718 | DGS #657382 +Exchange DB&B XCV valve inc | L2 Connect hubs & hydraulic | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 20 | 0 | RCE | 2025-01-01 | 2025-01-12 | 2025-01-07 | 2019-05-28 | 2019-02-27 | 60 | REL | APPR OPND | HB /A /34/HBAA-XCV-38012A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | MTN-ELEC | 2100024718 | DGS #657382 +Exchange DB&B XCV valve inc | L2 Connect cables | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | RCE | 2025-01-01 | 2025-01-12 | 2025-01-07 | 2019-05-28 | 2019-02-27 | 70 | REL | APPR OPND | HB /A /34/HBAA-XCV-38012A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | PRODTECH | 2100024718 | DGS #657382 +Exchange DB&B XCV valve inc | L3 Remove isolation | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 12 | 0 | RCE | 2025-01-01 | 2025-01-12 | 2025-01-09 | 2019-05-28 | 2019-02-27 | 80 | REL | APPR OPND | HB /A /34/HBAA-XCV-38012A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-PIPF | MTN-SCAF | 2100024718 | DGS #657382 +Exchange DB&B XCV valve inc | L3 Remove rigging equipment | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 13.4 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-11 | 2019-05-28 | 2019-02-27 | 90 | REL | APPR OPND | HB /A /34/HBAA-XCV-38012A | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | D |  | MMS | DK50
2026-W13-14 | 4 | HBA05-GL | WDF | MTN-MECH | PRODTECH | 2100026239 | LOTI:HBB05 Liftgas Flowelement re-Mount. | Safing | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 | LOTI | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-08-31 | 2019-08-26 | 10 | REL | APPR OPND | HB /B /37/HBBB-FCV-290502 | GAS LIFT CONTROL VALVE, HBB-05 | 99000119 | E |  | MMS | DK50
2026-W13-14 | 4 | HBA05-GL | WDF | MTN-MECH | MTN-MECH | 2100026239 | LOTI:HBB05 Liftgas Flowelement re-Mount. | Dismantel 2"Blind hub | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-08-31 | 2019-08-26 | 20 | REL | APPR OPND | HB /B /37/HBBB-FCV-290502 | GAS LIFT CONTROL VALVE, HBB-05 | 99000119 | E |  | MMS | DK50
2026-W13-14 | 4 | HBA05-GL | WDF | MTN-MECH | MTN-RIGG | 2100026239 | LOTI:HBB05 Liftgas Flowelement re-Mount. | Rig of flowelement | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2019-08-31 | 2019-08-26 | 30 | REL | APPR OPND | HB /B /37/HBBB-FCV-290502 | GAS LIFT CONTROL VALVE, HBB-05 | 99000119 | E |  | MMS | DK50
2026-W13-14 | 4 | HBA05-GL | WDF | MTN-MECH | MTN-MECH | 2100026239 | LOTI:HBB05 Liftgas Flowelement re-Mount. | Mount of flowelement | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2019-08-31 | 2019-08-26 | 40 | REL | APPR OPND | HB /B /37/HBBB-FCV-290502 | GAS LIFT CONTROL VALVE, HBB-05 | 99000119 | E |  | MMS | DK50
2026-W13-14 | 4 | HBA05-GL | WDF | MTN-MECH | MTN-INST | 2100026239 | LOTI:HBB05 Liftgas Flowelement re-Mount. | Mount of tubing | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 3.4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-08-31 | 2019-08-26 | 50 | REL | APPR OPND | HB /B /37/HBBB-FCV-290502 | GAS LIFT CONTROL VALVE, HBB-05 | 99000119 | E |  | MMS | DK50
2026-W13-14 | 4 | HBA05-GL | WDF | MTN-MECH | PRODTECH | 2100026239 | LOTI:HBB05 Liftgas Flowelement re-Mount. | Desafing | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2019-08-31 | 2019-08-26 | 55 | REL | APPR OPND | HB /B /37/HBBB-FCV-290502 | GAS LIFT CONTROL VALVE, HBB-05 | 99000119 | E |  | MMS | DK50
2026-W13-14 | 4 | HBA05-GL | WDF | MTN-MECH | MTN-MECH | 2100026239 | LOTI:HBB05 Liftgas Flowelement re-Mount. | Asbuilt Welder | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2019-08-31 | 2019-08-26 | 60 | REL | APPR OPND | HB /B /37/HBBB-FCV-290502 | GAS LIFT CONTROL VALVE, HBB-05 | 99000119 | E |  | MMS | DK50
2026-W13-14 | 4 | HBA05-GL | WDF | MTN-MECH | MTN-INST | 2100026239 | LOTI:HBB05 Liftgas Flowelement re-Mount. | Asbuilt Elec | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2019-08-31 | 2019-08-26 | 70 | REL | APPR OPND | HB /B /37/HBBB-FCV-290502 | GAS LIFT CONTROL VALVE, HBB-05 | 99000119 | E |  | MMS | DK50
2026-W13-14 | 4 | HBA05-GL | WDF | MTN-MECH | MTN-TELE | 2100026239 | LOTI:HBB05 Liftgas Flowelement re-Mount. | Update V-cone Calculation in C05 | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | Tele Frank PtW 197288 | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-08-31 | 2019-08-26 | 80 | REL | APPR OPND | HB /B /37/HBBB-FCV-290502 | GAS LIFT CONTROL VALVE, HBB-05 | 99000119 | E |  | MMS | DK50
2026-W13-14 | 4 | HBA05-GL | WDF | MTN-MECH | MTN-MECH | 2100026239 | LOTI:HBB05 Liftgas Flowelement re-Mount. | Order new V-cone | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-08-31 | 2019-08-26 | 90 | REL | APPR OPND | HB /B /37/HBBB-FCV-290502 | GAS LIFT CONTROL VALVE, HBB-05 | 99000119 | E |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026252 | DGS: 628396 Replace XCV-38310.(COMP - 20 | Rip-up hoist for removal | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 12 | 0 | OIM 10 | 2024-09-18 | 2024-09-25 | 2024-09-18 | 2020-05-05 | 2020-02-05 | 10 | REL | APPR OPND | HB /B /34/HBBA-XCV-38310 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | PRODTECH | 2100026252 | DGS: 628396 Replace XCV-38310.(COMP - 20 | Isolate XCV and equipment | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | OIM 10 | 2024-09-18 | 2024-09-25 | 2024-09-19 | 2020-05-05 | 2020-02-05 | 20 | REL | APPR OPND | HB /B /34/HBBA-XCV-38310 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | VEN-ELEC | 2100026252 | DGS: 628396 Replace XCV-38310.(COMP - 20 | Dis-connect cables | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 | OIM 10 | 2024-09-18 | 2024-09-25 | 2024-09-20 | 2020-05-05 | 2020-02-05 | 30 | REL | APPR OPND | HB /B /34/HBBA-XCV-38310 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-INST | 2100026252 | DGS: 628396 Replace XCV-38310.(COMP - 20 | Dis-connect hydraulics | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | OIM 10 | 2024-09-18 | 2024-09-25 | 2024-09-20 | 2020-05-05 | 2020-02-05 | 40 | REL | APPR OPND | HB /B /34/HBBA-XCV-38310 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-PIPF | 2100026252 | DGS: 628396 Replace XCV-38310.(COMP - 20 | Replace XCV-38310 | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 10 | 0 | OIM 10 | 2024-09-18 | 2024-09-25 | 2024-09-21 | 2020-05-05 | 2020-02-05 | 50 | REL | APPR OPND | HB /B /34/HBBA-XCV-38310 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026252 | DGS: 628396 Replace XCV-38310.(COMP - 20 | Assist in replacement | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 5 | 0 | OIM 10 | 2024-09-18 | 2024-09-25 | 2024-09-20 | 2020-05-05 | 2020-02-05 | 60 | REL | APPR OPND | HB /B /34/HBBA-XCV-38310 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-INST | 2100026252 | DGS: 628396 Replace XCV-38310.(COMP - 20 | Connect hydraulics | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | OIM 10 | 2024-09-18 | 2024-09-25 | 2024-09-21 | 2020-05-05 | 2020-02-05 | 70 | REL | APPR OPND | HB /B /34/HBBA-XCV-38310 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | VEN-ELEC | 2100026252 | DGS: 628396 Replace XCV-38310.(COMP - 20 | Connect cables | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 | OIM 10 | 2024-09-18 | 2024-09-25 | 2024-09-22 | 2020-05-05 | 2020-02-05 | 80 | REL | APPR OPND | HB /B /34/HBBA-XCV-38310 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | PRODTECH | 2100026252 | DGS: 628396 Replace XCV-38310.(COMP - 20 | Functional test | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | OIM 10 | 2024-09-18 | 2024-09-25 | 2024-09-22 | 2020-05-05 | 2020-02-05 | 90 | REL | APPR OPND | HB /B /34/HBBA-XCV-38310 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | PRODTECH | 2100026252 | DGS: 628396 Replace XCV-38310.(COMP - 20 | De-isolate XCV and equipment | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | OIM 10 | 2024-09-18 | 2024-09-25 | 2024-09-23 | 2020-05-05 | 2020-02-05 | 100 | REL | APPR OPND | HB /B /34/HBBA-XCV-38310 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100026252 | DGS: 628396 Replace XCV-38310.(COMP - 20 | Remove hoist and clean-up | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 8 | 0 |  | 2024-09-18 | 2024-09-25 | 2024-09-24 | 2020-05-05 | 2020-02-05 | 110 | REL | APPR OPND | HB /B /34/HBBA-XCV-38310 | UNCLASSIFIED VALVE | 99000099 | C |  | MMS | DK50
0 | 3 | HDASW | WDF | MTN-MECH | PRODTECH | 2100029439 | Change HDAD-TI-53052A | Inhibit before isolation | REL PRT CSER GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 2.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-04-27 | 2020-03-18 | 97 | REL | APPR OPND | HD /A /76/INSTRUMENTS | INSTRUMENTS | 99000120 | E |  | MIN | DK60
0 | 3 | HDASW | WDF | MTN-MECH | MTN-MECH | 2100029439 | Change HDAD-TI-53052A | Isolate input device NON EX | REL PRT CSER GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-04-27 | 2020-03-18 | 98 | REL | APPR OPND | HD /A /76/INSTRUMENTS | INSTRUMENTS | 99000120 | E |  | MIN | DK60
0 | 3 | HDASW | WDF | MTN-MECH | MTN-MECH | 2100029439 | Change HDAD-TI-53052A | Replace the thermowell and gauge | REL PRT CSER GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 | W50 Frank | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-04-27 | 2020-03-18 | 100 | REL | APPR OPND | HD /A /76/INSTRUMENTS | INSTRUMENTS | 99000120 | E |  | MIN | DK60
0 | 3 | HDASW | WDF | MTN-MECH | MTN-MECH | 2100029439 | Change HDAD-TI-53052A | Deisolate after repair | REL PRT CSER GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-04-27 | 2020-03-18 | 199 | REL | APPR OPND | HD /A /76/INSTRUMENTS | INSTRUMENTS | 99000120 | E |  | MIN | DK60
0 | 3 | HDASW | WDF | MTN-MECH | MTN-INST | 2100029439 | Change HDAD-TI-53052A | Test after completed work | REL PRT CSER GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-04-27 | 2020-03-18 | 400 | REL | APPR OPND | HD /A /76/INSTRUMENTS | INSTRUMENTS | 99000120 | E |  | MIN | DK60
0 | 3 | HDASW | WDF | MTN-MECH | PRODTECH | 2100029439 | Change HDAD-TI-53052A | Remove inhibit Input device | REL PRT CSER GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2020-04-27 | 2020-03-18 | 402 | REL | APPR OPND | HD /A /76/INSTRUMENTS | INSTRUMENTS | 99000120 | E |  | MIN | DK60
2026-W13-14 | 4 | HBBPWELL | WDF | MTN-MECH | PRODTECH | 2100061655 | Grease nipples is leaking | Production isolation | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-09-08 | 2022-04-11 | 10 | REL | APPR OPND | HB /B /10/HBBA-HCV-34047 | LO - HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBBPWELL | WDF | MTN-MECH | MTN-MECH | 2100061655 | Grease nipples is leaking | Replace grease nipples/+greasing Vlv | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-09-08 | 2022-04-11 | 20 | REL | APPR OPND | HB /B /10/HBBA-HCV-34047 | LO - HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBBPWELL | WDF | MTN-MECH | PRODTECH | 2100061655 | Grease nipples is leaking | Production de-isolation w leaktest | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-09-08 | 2022-04-11 | 30 | REL | APPR OPND | HB /B /10/HBBA-HCV-34047 | LO - HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBA13-GL | WDF | MTN-INST | PRODTECH | 2100063368 | Seep in SOV Cabinet. LG FCV HBA13 | Isolate and manual mode for Control Valv | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-09-27 | 2022-04-30 | 5 | REL | APPR OPND | HB /A /37/HBAA-FCV-29133 | LIFT GAS FLOW CONTROL VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBA13-GL | WDF | MTN-INST | MTN-INST | 2100063368 | Seep in SOV Cabinet. LG FCV HBA13 | Isolate Control Valve | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-09-27 | 2022-04-30 | 10 | REL | APPR OPND | HB /A /37/HBAA-FCV-29133 | LIFT GAS FLOW CONTROL VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBA13-GL | WDF | MTN-INST | MTN-INST | 2100063368 | Seep in SOV Cabinet. LG FCV HBA13 | Troubleshoot Control Valve | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-09-27 | 2022-04-30 | 30 | REL | APPR OPND | HB /A /37/HBAA-FCV-29133 | LIFT GAS FLOW CONTROL VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBA13-GL | WDF | MTN-INST | MTN-INST | 2100063368 | Seep in SOV Cabinet. LG FCV HBA13 | Deisolate Control Valve | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-09-27 | 2022-04-30 | 40 | REL | APPR OPND | HB /A /37/HBAA-FCV-29133 | LIFT GAS FLOW CONTROL VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 4 | HBA13-GL | WDF | MTN-INST | PRODTECH | 2100063368 | Seep in SOV Cabinet. LG FCV HBA13 | Deisolate and remove manual mode for Con | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2022-09-27 | 2022-04-30 | 50 | REL | APPR OPND | HB /A /37/HBAA-FCV-29133 | LIFT GAS FLOW CONTROL VALVE | 99000119 | E |  | MIN | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-INST | PRODTECH | 2100066137 | Hydr. weep from SOV to LG FCV-29203 | Well SD prep for work | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 2 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-05-30 | 2022-04-20 | 10 | PCNF REL | APPR OPND | HB /A /37/HBAA-FCV-29203 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-INST | MTN-INST | 2100066137 | Hydr. weep from SOV to LG FCV-29203 | Isolate solenoid valve | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-05-30 | 2022-04-20 | 20 | PCNF REL | APPR OPND | HB /A /37/HBAA-FCV-29203 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-INST | MTN-INST | 2100066137 | Hydr. weep from SOV to LG FCV-29203 | Retighten solenoid valve | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-05-30 | 2022-04-20 | 30 | PCNF REL | APPR OPND | HB /A /37/HBAA-FCV-29203 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-INST | MTN-INST | 2100066137 | Hydr. weep from SOV to LG FCV-29203 | De-isolate solenoid valve / test with CC | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-05-30 | 2022-04-20 | 40 | PCNF REL | APPR OPND | HB /A /37/HBAA-FCV-29203 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-INST | PRODTECH | 2100066137 | Hydr. weep from SOV to LG FCV-29203 | Well back in service | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1.5 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-05-30 | 2022-04-20 | 50 | PCNF REL | APPR OPND | HB /A /37/HBAA-FCV-29203 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-INST | MTN-INST | 2100066137 | Hydr. weep from SOV to LG FCV-29203 | Solenoid | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-05-30 | 2022-04-20 | 60 | PCNF REL | APPR OPND | HB /A /37/HBAA-FCV-29203 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-INST | MTN-INST | 2100066137 | Hydr. weep from SOV to LG FCV-29203 | ************************************** | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-05-30 | 2022-04-20 | 70 | REL | APPR OPND | HB /A /37/HBAA-FCV-29203 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-INST | PRODTECH | 2100066137 | Hydr. weep from SOV to LG FCV-29203 | Well SD prep for work | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-05-30 | 2022-04-20 | 80 | REL | APPR OPND | HB /A /37/HBAA-FCV-29203 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-INST | MTN-INST | 2100066137 | Hydr. weep from SOV to LG FCV-29203 | Isolate solenoid valve | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0.5 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-05-30 | 2022-04-20 | 90 | REL | APPR OPND | HB /A /37/HBAA-FCV-29203 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-INST | MTN-INST | 2100066137 | Hydr. weep from SOV to LG FCV-29203 | Replace solenoid valve | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-05-30 | 2022-04-20 | 100 | REL | APPR OPND | HB /A /37/HBAA-FCV-29203 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-INST | MTN-INST | 2100066137 | Hydr. weep from SOV to LG FCV-29203 | De-isolate solenoid valve/Test with CCR | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-05-30 | 2022-04-20 | 110 | REL | APPR OPND | HB /A /37/HBAA-FCV-29203 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-INST | PRODTECH | 2100066137 | Hydr. weep from SOV to LG FCV-29203 | Well back in service | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-05-30 | 2022-04-20 | 120 | REL | APPR OPND | HB /A /37/HBAA-FCV-29203 | LIFT GAS FLOW CONTROL VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-RIGG | 2100079875 | Ringmain valve HCV 030179. Loss of integ | Rigging prework | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 6 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-28 | 2023-06-17 | 2023-02-02 | 10 | REL | APPR OPND | HB /D /01/HBDB-HCV-030179 | BUTTERFLY VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100079875 | Ringmain valve HCV 030179. Loss of integ | Isolate valve | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-28 | 2023-06-17 | 2023-02-02 | 20 | REL | APPR OPND | HB /D /01/HBDB-HCV-030179 | BUTTERFLY VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100079875 | Ringmain valve HCV 030179. Loss of integ | changeout valve | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 6 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-29 | 2023-06-17 | 2023-02-02 | 30 | REL | APPR OPND | HB /D /01/HBDB-HCV-030179 | BUTTERFLY VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-RIGG | 2100079875 | Ringmain valve HCV 030179. Loss of integ | rigging assistance | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 12 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-29 | 2023-06-17 | 2023-02-02 | 40 | REL | APPR OPND | HB /D /01/HBDB-HCV-030179 | BUTTERFLY VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100079875 | Ringmain valve HCV 030179. Loss of integ | deisolate | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-30 | 2023-06-17 | 2023-02-02 | 50 | REL | APPR OPND | HB /D /01/HBDB-HCV-030179 | BUTTERFLY VALVE |  | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-RIGG | 2100079875 | Ringmain valve HCV 030179. Loss of integ | Rigging postwork | REL PRT GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 6 | 0 |  | 2024-03-28 | 2024-03-31 | 2024-03-31 | 2023-06-17 | 2023-02-02 | 60 | REL | APPR OPND | HB /D /01/HBDB-HCV-030179 | BUTTERFLY VALVE |  | F |  | MMS | DK50
2024-W21-22 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100079924 | HBC temp rep of roof for coolers |  | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 |  | 2023-03-13 | 2023-03-15 | 2023-03-13 | 2023-06-19 | 2023-02-04 | 50 | PCNF REL | APPR OPND | HB /C /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK50 |  |  | 2024-06-01
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087424 | FWP-0332/ Expired cooling hoses | FWP-0331/ Expired cooling hoses | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 |  | 2024-04-11 | 2024-04-14 | 2024-04-11 | 2023-04-25 | 2023-03-11 | 10 | REL | APPR OPND | HB /C /01/HBCM-P-0363 | JACKET WATER CIRC PUMP INCL MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100087424 | FWP-0332/ Expired cooling hoses | Isolate FWP | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 | W37-38 | 2024-04-11 | 2024-04-14 | 2024-04-11 | 2023-04-25 | 2023-03-11 | 20 | REL | APPR OPND | HB /C /01/HBCM-P-0363 | JACKET WATER CIRC PUMP INCL MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087424 | FWP-0332/ Expired cooling hoses | Drain coolant - shall be re-used | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 | W37-38 | 2024-04-11 | 2024-04-14 | 2024-04-11 | 2023-04-25 | 2023-03-11 | 30 | REL | APPR OPND | HB /C /01/HBCM-P-0363 | JACKET WATER CIRC PUMP INCL MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087424 | FWP-0332/ Expired cooling hoses | Replace hoses | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 6 | 0 | W37-38 | 2024-04-11 | 2024-04-14 | 2024-04-12 | 2023-04-25 | 2023-03-11 | 40 | REL | APPR OPND | HB /C /01/HBCM-P-0363 | JACKET WATER CIRC PUMP INCL MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087424 | FWP-0332/ Expired cooling hoses | Re-fill coolant. Top up power cool | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 | W37-38 | 2024-04-11 | 2024-04-14 | 2024-04-13 | 2023-04-25 | 2023-03-11 | 50 | REL | APPR OPND | HB /C /01/HBCM-P-0363 | JACKET WATER CIRC PUMP INCL MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100087424 | FWP-0332/ Expired cooling hoses | De-isolate | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 2 | 0 | W37-38 | 2024-04-11 | 2024-04-14 | 2024-04-13 | 2023-04-25 | 2023-03-11 | 60 | REL | APPR OPND | HB /C /01/HBCM-P-0363 | JACKET WATER CIRC PUMP INCL MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087424 | FWP-0332/ Expired cooling hoses | Additional materials | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 |  | 2024-04-11 | 2024-04-14 | 2024-04-11 | 2023-04-25 | 2023-03-11 | 70 | REL | APPR OPND | HB /C /01/HBCM-P-0363 | JACKET WATER CIRC PUMP INCL MOTOR |  | A |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087424 | FWP-0332/ Expired cooling hoses | Additional materials | REL GMPS MANC PPRT PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 |  | 2024-04-11 | 2024-04-14 | 2024-04-11 | 2023-04-25 | 2023-03-11 | 80 | REL | APPR OPND | HB /C /01/HBCM-P-0363 | JACKET WATER CIRC PUMP INCL MOTOR |  | A |  | MMS | DK50
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098078 | Damaged HT cable on HBB-02 WI Manifold. | Damaged HT cable on HBB-02 WI Manifold | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-26 | 2024-03-10 | 2023-10-27 | 10 | REL | APPR OPND | HB /B /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  |  | 2024-05-06
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098078 | Damaged HT cable on HBB-02 WI Manifold. | Sitevisit - TBT. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-26 | 2024-03-10 | 2023-10-27 | 20 | REL | APPR OPND | HB /B /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  |  | 2024-05-07
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098078 | Damaged HT cable on HBB-02 WI Manifold. | Isolate - prove dead. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-26 | 2024-03-10 | 2023-10-27 | 30 | REL | APPR OPND | HB /B /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  |  | 2024-05-08
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098078 | Damaged HT cable on HBB-02 WI Manifold. | Build Scarfold if required. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 6 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-26 | 2024-03-10 | 2023-10-27 | 40 | REL | APPR OPND | HB /B /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  |  | 2024-05-09
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098078 | Damaged HT cable on HBB-02 WI Manifold. | Remove Insulation. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 6 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-27 | 2024-03-10 | 2023-10-27 | 50 | REL | APPR OPND | HB /B /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  |  | 2024-05-10
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098078 | Damaged HT cable on HBB-02 WI Manifold. | Remove HT-cable. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-28 | 2024-03-10 | 2023-10-27 | 60 | REL | APPR OPND | HB /B /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  |  | 2024-05-11
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098078 | Damaged HT cable on HBB-02 WI Manifold. | Install new HT Cable and Kit. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-29 | 2024-03-10 | 2023-10-27 | 70 | REL | APPR OPND | HB /B /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  |  | 2024-05-12
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098078 | Damaged HT cable on HBB-02 WI Manifold. | Cunduct a B.test. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-30 | 2024-03-10 | 2023-10-27 | 80 | REL | APPR OPND | HB /B /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  |  | 2024-05-13
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098078 | Damaged HT cable on HBB-02 WI Manifold. | Reaply insulation. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 6 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-30 | 2024-03-10 | 2023-10-27 | 90 | REL | APPR OPND | HB /B /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  |  | 2024-05-14
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098078 | Damaged HT cable on HBB-02 WI Manifold. | Cunduct a A.test. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-05-01 | 2024-03-10 | 2023-10-27 | 100 | REL | APPR OPND | HB /B /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  |  | 2024-05-15
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098078 | Damaged HT cable on HBB-02 WI Manifold. | De-Isolate - test - check up. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-05-01 | 2024-03-10 | 2023-10-27 | 110 | REL | APPR OPND | HB /B /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  |  | 2024-05-16
2024-W19-20 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098078 | Damaged HT cable on HBB-02 WI Manifold. | Documentation. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0.5 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-05-01 | 2024-03-10 | 2023-10-27 | 120 | REL | APPR OPND | HB /B /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50 |  |  | 2024-05-17
2024-W51-52 | 4 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200012785 | HBC Installation of mess furniture | Replace worn out furniture in mess hall. | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 | 23-W51-52 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2025-11-22 | 2023-06-06 | 10 | REL | APPR OPND | HB /C /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK50
2024-W51-52 | 4 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200012785 | HBC Installation of mess furniture | add. materials | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2025-11-22 | 2023-06-06 | 30 | REL | APPR OPND | HB /C /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK50
2024-W19-20 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015442 | Replace handles for HVAC HBB-A-1213 | Replace handles for HVAC HBB-A-1213 | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-02-21 | 2023-10-09 | 10 | REL | APPR OPND | HB /B /09/HBBB-A-1213 | HVAC UNIT |  | A |  | MEL | DK50 |  |  | 2024-05-12
2024-W19-20 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015442 | Replace handles for HVAC HBB-A-1213 | Replace handles | REL GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 4 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-02-21 | 2023-10-09 | 20 | REL | APPR OPND | HB /B /09/HBBB-A-1213 | HVAC UNIT |  | A |  | MEL | DK50 |  |  | 2024-05-13
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211470 | 4Y 400V N-SWB MAINT HBDD-N-1854-A08 | ISOLATION BY PRODUCTION | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 1 | W02 Caverion | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-11-01 | 2022-08-05 | 10 | PCNF REL | APPR OPND | HB /D /61/HBDD-N-1854-A08 | CUBICLE A08 |  | C | DKHB-0590 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211470 | 4Y 400V N-SWB MAINT HBDD-N-1854-A08 | 400V N-SWB MAINT HBDD-N-1854-A08 | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 4 | 32 | W02 Caverion | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-11-01 | 2022-08-05 | 20 | PCNF REL | APPR OPND | HB /D /61/HBDD-N-1854-A08 | CUBICLE A08 |  | C | DKHB-0590 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211470 | 4Y 400V N-SWB MAINT HBDD-N-1854-A08 | DE-ISOLATION BY PRODUCTION | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 1 | 1 | W02 Caverion | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-11-01 | 2022-08-05 | 30 | PCNF REL | APPR OPND | HB /D /61/HBDD-N-1854-A08 | CUBICLE A08 |  | C | DKHB-0590 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400211470 | 4Y 400V N-SWB MAINT HBDD-N-1854-A08 | Test equipment | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWSC RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-11-01 | 2022-08-05 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A08 | CUBICLE A08 |  | C | DKHB-0590 | MEL | DK50 | EL0024
0 | D | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400315194 | 1Y HVAC REFRIG PROVISIONS HDBF-A-1212A/B | 1Y HVAC REFRIG PROVISIONS CHECK | REL GMPS MACM PRC SETC | APPR CMAT AWSC RDBL | 24 | 0 | W17-W18 | 2024-04-25 | 2024-04-28 | 2024-04-25 | 2024-04-16 | 2024-02-29 | 10 | REL | APPR OPND | HD /B /09/HDBF-A-1212A | AIR COOLED CONDENSER |  | A | DKHD-2017 | MEL | DK60 | EL0013
0 | D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315194 | 1Y HVAC REFRIG PROVISIONS HDBF-A-1212A/B | SUPPORT TO VENDOR | REL GMPS MACM PRC SETC | APPR CMAT AWSC RDBL | 6 | 0 | W17-W18 | 2024-04-25 | 2024-04-28 | 2024-04-27 | 2024-04-16 | 2024-02-29 | 20 | REL | APPR OPND | HD /B /09/HDBF-A-1212A | AIR COOLED CONDENSER |  | A | DKHD-2017 | MEL | DK60 | EL0013
2026-W13-14 | B | NOSD | WPM | MTN-INST | PRODTECH | 2400329572 | 2Y HBAA-V-3421 - METERING | ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-04 | 2024-05-02 | 2024-06-17 | 2024-05-02 | 10 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6000 | MIN | DK50 | IN0014
2026-W13-14 | B | NOSD | WPM | MTN-INST | MTN-MECH | 2400329572 | 2Y HBAA-V-3421 - METERING | DISASSEMBLY OF METERING | REL GMPS MACM PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | W17-W18 | 2024-05-02 | 2024-05-04 | 2024-05-02 | 2024-06-17 | 2024-05-02 | 20 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6000 | MIN | DK50 | IN0014
2026-W13-14 | B | NOSD | WPM | MTN-INST | MTN-RIGG | 2400329572 | 2Y HBAA-V-3421 - METERING | RIGGING SUPPORT | REL GMPS MACM PRC SETC | APPR CMAT AWSC RDBL | 1.5 | 0 | W17-W18 | 2024-05-02 | 2024-05-04 | 2024-05-02 | 2024-06-17 | 2024-05-02 | 30 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6000 | MIN | DK50 | IN0014
2026-W13-14 | B | NOSD | WPM | MTN-INST | MTN-INST | 2400329572 | 2Y HBAA-V-3421 - METERING | HBAA-V-3421 - METERING | REL GMPS MACM PRC SETC | APPR CMAT AWSC RDBL | 4 | 0 | W17-W18 | 2024-05-02 | 2024-05-04 | 2024-05-03 | 2024-06-17 | 2024-05-02 | 40 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6000 | MIN | DK50 | IN0014
2026-W13-14 | B | NOSD | WPM | MTN-INST | MTN-RIGG | 2400329572 | 2Y HBAA-V-3421 - METERING | DE-RIGGING SUPPORT | REL GMPS MACM PRC SETC | APPR CMAT AWSC RDBL | 1.5 | 0 | W17-W18 | 2024-05-02 | 2024-05-04 | 2024-05-03 | 2024-06-17 | 2024-05-02 | 50 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6000 | MIN | DK50 | IN0014
2026-W13-14 | B | NOSD | WPM | MTN-INST | MTN-MECH | 2400329572 | 2Y HBAA-V-3421 - METERING | ASSEMBLY OF METERING | REL GMPS MACM PRC SETC | APPR CMAT AWSC RDBL | 3 | 0 | W17-W18 | 2024-05-02 | 2024-05-04 | 2024-05-04 | 2024-06-17 | 2024-05-02 | 60 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6000 | MIN | DK50 | IN0014
2026-W13-14 | B | NOSD | WPM | MTN-INST | PRODTECH | 2400329572 | 2Y HBAA-V-3421 - METERING | DE-ISOLATION BY PRODUCTION | REL GMPS MACM PRC SETC | APPR CMAT AWSC RDBL | 1 | 0 | W17-W18 | 2024-05-02 | 2024-05-04 | 2024-05-04 | 2024-06-17 | 2024-05-02 | 70 | REL | APPR OPND | HB /A /20/METERING | SEPARATION METERING |  | A | DKHB-6000 | MIN | DK50 | IN0014
2026-W1-2 | B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400307665 | 1Y PED. CRANE CHECK VENDOR-HBDE-A-6150 | ISOLATION BY PRODUCTION | REL PCNF PRT GMPS MANC PRC SETC | APPR CMAT AWDO SCH ROUT | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-24 | 2024-04-08 | 2024-05-16 | 2024-04-16 | 10 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W1-2 | B | NOSD | WPM | MTN-CRAN | VEN-CRAN | 2400307665 | 1Y PED. CRANE CHECK VENDOR-HBDE-A-6150 | PED. CRANE CHECK VENDOR-HBDE-A-6150 | REL PCNF PRT GMPS MANC PRC SETC | APPR CMAT AWDO SCH ROUT | 72 | 0 | W15-W16 | 2024-04-08 | 2024-04-24 | 2024-04-08 | 2024-05-16 | 2024-04-16 | 20 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W1-2 | B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400307665 | 1Y PED. CRANE CHECK VENDOR-HBDE-A-6150 | PED. CRANE CHECK VENDOR-HBDE-A-6150 | REL PCNF PRT GMPS MANC PRC SETC | APPR CMAT AWDO SCH ROUT | 12 | 9 | W15-W16 | 2024-04-08 | 2024-04-24 | 2024-04-12 | 2024-05-16 | 2024-04-16 | 30 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W1-2 | B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400307665 | 1Y PED. CRANE CHECK VENDOR-HBDE-A-6150 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT GMPS MANC PRC SETC | APPR CMAT AWDO SCH ROUT | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-24 | 2024-04-13 | 2024-05-16 | 2024-04-16 | 40 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W1-2 | B | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400307665 | 1Y PED. CRANE CHECK VENDOR-HBDE-A-6150 | Check of slip ring & electric checks | REL PCNF PRT GMPS MANC PRC SETC | APPR CMAT AWDO SCH ROUT | 24 | 0 | W15-W16 | 2024-04-08 | 2024-04-24 | 2024-04-14 | 2024-05-16 | 2024-04-16 | 50 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W1-2 | B | NOSD | WPM | MTN-CRAN | MTN-ROUS | 2400307665 | 1Y PED. CRANE CHECK VENDOR-HBDE-A-6150 | Assist with crane operation | REL PCNF PRT GMPS MANC PRC SETC | APPR CMAT AWDO SCH ROUT | 12 | 0 | W15-W16 | 2024-04-08 | 2024-04-24 | 2024-04-19 | 2024-05-16 | 2024-04-16 | 60 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W1-2 | B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400307665 | 1Y PED. CRANE CHECK VENDOR-HBDE-A-6150 | General assistance | REL PCNF PRT GMPS MANC PRC SETC | APPR CMAT AWDO SCH ROUT | 12 | 0 | W15-W16 | 2024-04-08 | 2024-04-24 | 2024-04-22 | 2024-05-16 | 2024-04-16 | 70 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W1-2 | B | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400307665 | 1Y PED. CRANE CHECK VENDOR-HBDE-A-6150 | ISOLATION BY MTN-elec | REL PCNF PRT GMPS MANC PRC SETC | APPR CMAT AWDO SCH ROUT | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-24 | 2024-04-24 | 2024-05-16 | 2024-04-16 | 80 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W1-2 | B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400307665 | 1Y PED. CRANE CHECK VENDOR-HBDE-A-6150 | DE-ISOLATION MTN-ELEC | REL PCNF PRT GMPS MANC PRC SETC | APPR CMAT AWDO SCH ROUT | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-24 | 2024-04-24 | 2024-05-16 | 2024-04-16 | 90 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | C | DKHB-0659 | MMS | DK50 | MS0154 | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100087570 | HBA/78 Camera/Screen dosent work | Replace monitor | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO SCH RDBL RFRZ ROUT | 2 | 10 | 23-W51-52 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2023-09-09 | 2023-04-27 | 70 | PCNF REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024390 | ANOS HBA R4311 change out bolts, ROPE | Install new bolt/nordlock/ Nuts | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 12 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2019-05-19 | 2018-05-24 | 30 | REL | APPR OPND | HB /A /34/HBAA-RI-664311 | R4311 - 16" HALFDAN BA TO P4306 | DK0500014746 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100035892 | HBC/78: Replace Corroded valves | Find and check material/tools | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-15 | 2024-03-09 | 2020-11-20 | 2020-08-22 | 60 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100035892 | HBC/78: Replace Corroded valves | Record and perform slewing speed test | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-15 | 2024-03-09 | 2020-11-20 | 2020-08-22 | 70 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100035892 | HBC/78: Replace Corroded valves | Operation of crane | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-15 | 2024-03-09 | 2020-11-20 | 2020-08-22 | 80 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100035892 | HBC/78: Replace Corroded valves | Isolate/de-isolate of crane HBCO-A-6101 | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL ROUT | 4 | 0 |  | 2024-03-09 | 2024-03-15 | 2024-03-09 | 2020-11-20 | 2020-08-22 | 90 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100035892 | HBC/78: Replace Corroded valves | Build/demol of scaffold for acces | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL ROUT | 30 | 0 |  | 2024-03-09 | 2024-03-15 | 2024-03-10 | 2020-11-20 | 2020-08-22 | 100 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100035892 | HBC/78: Replace Corroded valves | Bleed pressure off and replace component | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL ROUT | 20 | 0 |  | 2024-03-09 | 2024-03-15 | 2024-03-13 | 2020-11-20 | 2020-08-22 | 110 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100035892 | HBC/78: Replace Corroded valves | Assist with handling/lift of motor | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL ROUT | 5 | 0 |  | 2024-03-09 | 2024-03-15 | 2024-03-13 | 2020-11-20 | 2020-08-22 | 120 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
0 | 4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100039625 | HDB/78: Replacement of hoist winch | Isolate crane HDBR-A-6102 | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 1 | 0 |  | 2024-07-11 | 2024-07-28 | 2024-07-11 | 2021-06-04 | 2021-01-05 | 10 | REL | APPR OPND | HD /B /78/HDBR-A-6102-0201 | MAIN HOIST |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100039625 | HDB/78: Replacement of hoist winch | Build scaffolding to lift hoist winch | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 70 | 0 |  | 2024-07-11 | 2024-07-28 | 2024-07-11 | 2021-06-04 | 2021-01-05 | 20 | REL | APPR OPND | HD /B /78/HDBR-A-6102-0201 | MAIN HOIST |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100039625 | HDB/78: Replacement of hoist winch | Disconnect and secure wire | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 12 | 0 |  | 2024-07-11 | 2024-07-28 | 2024-07-15 | 2021-06-04 | 2021-01-05 | 25 | REL | APPR OPND | HD /B /78/HDBR-A-6102-0201 | MAIN HOIST |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100039625 | HDB/78: Replacement of hoist winch | Lift old winch down | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 30 | 0 |  | 2024-07-11 | 2024-07-28 | 2024-07-16 | 2021-06-04 | 2021-01-05 | 30 | REL | APPR OPND | HD /B /78/HDBR-A-6102-0201 | MAIN HOIST |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100039625 | HDB/78: Replacement of hoist winch | Move part from old winch to new winch | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 4 | 0 |  | 2024-07-11 | 2024-07-28 | 2024-07-19 | 2021-06-04 | 2021-01-05 | 35 | REL | APPR OPND | HD /B /78/HDBR-A-6102-0201 | MAIN HOIST |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100039625 | HDB/78: Replacement of hoist winch | Rigg new winch up | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 30 | 0 |  | 2024-07-11 | 2024-07-28 | 2024-07-19 | 2021-06-04 | 2021-01-05 | 40 | REL | APPR OPND | HD /B /78/HDBR-A-6102-0201 | MAIN HOIST |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100039625 | HDB/78: Replacement of hoist winch | Assemble new hoist winch | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 24 | 0 |  | 2024-07-11 | 2024-07-28 | 2024-07-21 | 2021-06-04 | 2021-01-05 | 50 | REL | APPR OPND | HD /B /78/HDBR-A-6102-0201 | MAIN HOIST |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100039625 | HDB/78: Replacement of hoist winch | Remove scaffolding | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 50 | 0 |  | 2024-07-11 | 2024-07-28 | 2024-07-22 | 2021-06-04 | 2021-01-05 | 55 | REL | APPR OPND | HD /B /78/HDBR-A-6102-0201 | MAIN HOIST |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100039625 | HDB/78: Replacement of hoist winch | De-isolate crane HDBR-A-6102 | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 1 | 0 |  | 2024-07-11 | 2024-07-28 | 2024-07-26 | 2021-06-04 | 2021-01-05 | 60 | REL | APPR OPND | HD /B /78/HDBR-A-6102-0201 | MAIN HOIST |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100039625 | HDB/78: Replacement of hoist winch | Function test and proff load test | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 12 | 0 |  | 2024-07-11 | 2024-07-28 | 2024-07-26 | 2021-06-04 | 2021-01-05 | 70 | REL | APPR OPND | HD /B /78/HDBR-A-6102-0201 | MAIN HOIST |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100039625 | HDB/78: Replacement of hoist winch | Operating under test and assist MTN-CRAN | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 12 | 0 |  | 2024-07-11 | 2024-07-28 | 2024-07-27 | 2021-06-04 | 2021-01-05 | 80 | REL | APPR OPND | HD /B /78/HDBR-A-6102-0201 | MAIN HOIST |  | A |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100039625 | HDB/78: Replacement of hoist winch | Clean-up, documentation QC, backload win | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 3 | 0 |  | 2024-07-11 | 2024-07-28 | 2024-07-28 | 2021-06-04 | 2021-01-05 | 90 | REL | APPR OPND | HD /B /78/HDBR-A-6102-0201 | MAIN HOIST |  | A |  | MMS | DK60
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | PRODTECH | 2100061894 | New isolation for PIT-301010 | Inhibit/Isolate Pressure Indic. Transmit | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 0.5 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-01-09 | 2022-05-14 | 10 | REL | APPR OPND | HB /B /10/HBBB-PIT-301010 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100061894 | New isolation for PIT-301010 | Isolate Heat tracing power supply for Tr | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 0.5 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-01-09 | 2022-05-14 | 20 | REL | APPR OPND | HB /B /10/HBBB-PIT-301010 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100061894 | New isolation for PIT-301010 | Install insulation for Transmitter (ESD) | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 4 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-01-09 | 2022-05-14 | 30 | REL | APPR OPND | HB /B /10/HBBB-PIT-301010 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100061894 | New isolation for PIT-301010 | Deisolate Heat tracing power supply for | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 0.5 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-01-09 | 2022-05-14 | 40 | REL | APPR OPND | HB /B /10/HBBB-PIT-301010 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-LAGG | PRODTECH | 2100061894 | New isolation for PIT-301010 | Deisolate Pressure Indic. Transmitter (E | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL ROUT | 0.5 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-01-09 | 2022-05-14 | 50 | REL | APPR OPND | HB /B /10/HBBB-PIT-301010 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L3 Permit ELEC | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 8.7 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-15 | 2019-04-06 | 2019-02-25 | 10 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L3 Permit INST | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 8.7 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-15 | 2019-04-06 | 2019-02-25 | 20 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-PIPF | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L3 Permit WELD | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 8.7 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-15 | 2019-04-06 | 2019-02-25 | 30 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L3 Permit SCAF | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 8.7 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-15 | 2019-04-06 | 2019-02-25 | 40 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-PIPF | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L3 Check materials | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-17 | 2019-04-06 | 2019-02-25 | 50 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L3 Isolate Pig Launcher | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 3 | 0 | W01-02 OIM 10 | 2024-09-15 | 2024-10-05 | 2024-09-17 | 2019-04-06 | 2019-02-25 | 60 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L1 Disconnect electrical | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6.7 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-17 | 2019-04-06 | 2019-02-25 | 70 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L1 Disconnect instrumentation | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 8 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-18 | 2019-04-06 | 2019-02-25 | 80 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L3 Rig-up hoist for moving EP-3822 | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 16.1 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-20 | 2019-04-06 | 2019-02-25 | 90 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L3 Rig-up temp. support for pipelines | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 17.4 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-21 | 2019-04-06 | 2019-02-25 | 100 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-PIPF | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L1 Disconnect pipelines attached | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 16.1 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-23 | 2019-04-06 | 2019-02-25 | 110 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-PIPF | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L1 Install Blind on all connections | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 16.1 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-24 | 2019-04-06 | 2019-02-25 | 120 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | CON-WELD | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | Add material | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-09-15 | 2024-10-05 | 2024-09-15 | 2019-04-06 | 2019-02-25 | 121 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ROUS | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L1 Prepare EP-3822 for shipping | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 30 | 0 | W01-02 OIM 10 | 2024-09-15 | 2024-10-05 | 2024-09-25 | 2019-04-06 | 2019-02-25 | 130 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-PIPF | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L1 Re-install EP-3822 after overhaul | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 18.1 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-27 | 2019-04-06 | 2019-02-25 | 140 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-PIPF | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L1 Remove all blinds | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 12.1 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-28 | 2019-04-06 | 2019-02-25 | 150 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-PIPF | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L1 Re-connect all pipe connections | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 12.1 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-28 | 2019-04-06 | 2019-02-25 | 160 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L1 Re-connect instrumentation | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 8 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-09-29 | 2019-04-06 | 2019-02-25 | 170 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L1 Re-connect electrical | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6.7 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-10-01 | 2019-04-06 | 2019-02-25 | 180 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | QAQCELEC | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L1 Test and Documentation | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-09-15 | 2024-10-05 | 2024-10-01 | 2019-04-06 | 2019-02-25 | 190 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L3 Rig-down temp. support | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 12.1 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-10-02 | 2019-04-06 | 2019-02-25 | 200 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L3 Rig-down hoist for lifting | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 12.1 | 0 | W01-02 | 2024-09-15 | 2024-10-05 | 2024-10-03 | 2019-04-06 | 2019-02-25 | 210 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100026521 | Halfdan B, Minor Oil leak 1" valve-EP | L3 Desafe Pig Launcher | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 3 | 0 | W01-02 OIM 10 | 2024-09-15 | 2024-10-05 | 2024-10-04 | 2019-04-06 | 2019-02-25 | 220 | REL | APPR OPND | HB /B /23/HBBA-EP-3822 | LIQUID PIG RECIEVER |  | C |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100040109 | Two independent drain valves are interna | Prepare matr/tools | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2020-12-15 | 2020-11-05 | 10 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100040109 | Two independent drain valves are interna | Production isolation w Flushing | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2020-12-15 | 2020-11-05 | 20 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100040109 | Two independent drain valves are interna | Replace 3" Globe Valve | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 5 | 0 |  | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2020-12-15 | 2020-11-05 | 40 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100040109 | Two independent drain valves are interna | Production de-isolation w leaktest | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2020-12-15 | 2020-11-05 | 50 | PCNF REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | F |  | MMS | DK50
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044608 | Glycol seep from aftercooler HDBC-E-1751 | Glycol seep from aftercooler HDBC-E-1751 | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 3 | W19-W20 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2021-05-14 | 2021-02-13 | 10 | PCNF REL | APPR OPND | HD /B /05/HDBD-E-1751 | HEAT EXCHANGER (RADIATOR) |  | A |  | MMR | DK60
2024-W21-22 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100045848 | FLMPR Install of shims on HBA flowlines | Installation of shims on HBA flowlines. | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 12 | 6 | MPM Team W21-22 | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2021-03-11 | 2021-02-19 | 10 | PCNF REL | APPR OPND | HB /A /10/HBA-PHS-CS-N-1001 | P-G SOUR HP WELLHEAD CS NON INSULATED | 99000087 | A |  | MFM | DK50 |  |  | 2024-06-02
2024-W21-22 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100045848 | FLMPR Install of shims on HBA flowlines | Materials for FLM | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2021-03-11 | 2021-02-19 | 20 | REL | APPR OPND | HB /A /10/HBA-PHS-CS-N-1001 | P-G SOUR HP WELLHEAD CS NON INSULATED | 99000087 | A |  | MFM | DK50 |  |  | 2024-06-05
2024-W23-24 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100050153 | Cracked Ball VAG6S1 - 3"-AI-054-8550-AG | Cracked Ball VAG6S1 - 3"-AI-054-8550-AG | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2021-11-02 | 2021-06-05 | 10 | REL | APPR OPND | HB /D /07/HBD-3-AI-054-8550-AG-U | 3 INSTRUMENT AIR LINE |  | A |  | MMS | DK50
2024-W23-24 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100050153 | Cracked Ball VAG6S1 - 3"-AI-054-8550-AG | replace valve | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2021-11-02 | 2021-06-05 | 20 | REL | APPR OPND | HB /D /07/HBD-3-AI-054-8550-AG-U | 3 INSTRUMENT AIR LINE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-RIGG | MTN-MECH | 2100050746 | HBD/78: Mount RFK ramming guard in boom | Find and check new materials | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-19 | 2024-03-09 | 2022-01-22 | 2021-08-25 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150-11 | CRANE STRUCTURE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-RIGG | PRODTECH | 2100050746 | HBD/78: Mount RFK ramming guard in boom | Isolate crane HBDE-A-6150 | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-19 | 2024-03-09 | 2022-01-22 | 2021-08-25 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150-11 | CRANE STRUCTURE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-RIGG | MTN-ROPE | 2100050746 | HBD/78: Mount RFK ramming guard in boom | Dismount boom wood protections | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 36 | 0 |  | 2024-03-09 | 2024-03-19 | 2024-03-09 | 2022-01-22 | 2021-08-25 | 40 | REL | APPR OPND | HB /D /78/HBDE-A-6150-11 | CRANE STRUCTURE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-RIGG | MTN-ROUS | 2100050746 | HBD/78: Mount RFK ramming guard in boom | Rigging down boom wood protections | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 36 | 0 |  | 2024-03-09 | 2024-03-19 | 2024-03-10 | 2022-01-22 | 2021-08-25 | 50 | REL | APPR OPND | HB /D /78/HBDE-A-6150-11 | CRANE STRUCTURE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-RIGG | MTN-ROUS | 2100050746 | HBD/78: Mount RFK ramming guard in boom | Rigging up new Ramming guard protection | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 36 | 0 |  | 2024-03-09 | 2024-03-19 | 2024-03-13 | 2022-01-22 | 2021-08-25 | 60 | REL | APPR OPND | HB /D /78/HBDE-A-6150-11 | CRANE STRUCTURE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-RIGG | MTN-ROPE | 2100050746 | HBD/78: Mount RFK ramming guard in boom | Mount new Ramming guard protection | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 36 | 0 |  | 2024-03-09 | 2024-03-19 | 2024-03-16 | 2022-01-22 | 2021-08-25 | 70 | REL | APPR OPND | HB /D /78/HBDE-A-6150-11 | CRANE STRUCTURE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-RIGG | MTN-MECH | 2100050746 | HBD/78: Mount RFK ramming guard in boom | Assist MTN-ROPE and MTN-RIGG | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-03-09 | 2024-03-19 | 2024-03-16 | 2022-01-22 | 2021-08-25 | 80 | REL | APPR OPND | HB /D /78/HBDE-A-6150-11 | CRANE STRUCTURE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-RIGG | PRODTECH | 2100050746 | HBD/78: Mount RFK ramming guard in boom | Deisolate crane HBDE-A-6150 | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-19 | 2024-03-18 | 2022-01-22 | 2021-08-25 | 100 | REL | APPR OPND | HB /D /78/HBDE-A-6150-11 | CRANE STRUCTURE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-RIGG | MTN-MECH | 2100050746 | HBD/78: Mount RFK ramming guard in boom | Clean-up, documentation and QC | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-03-09 | 2024-03-19 | 2024-03-18 | 2022-01-22 | 2021-08-25 | 110 | REL | APPR OPND | HB /D /78/HBDE-A-6150-11 | CRANE STRUCTURE |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | CON-ROPE | 2100064422 | ANOP Remove/Add Support on 12" WI Line H | Remove/Add Support on 12" WI Line HBA | REL GMPS MACM PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-05-19 | 2022-05-19 | 2022-05-19 | 2022-10-23 | 2022-05-26 | 10 | REL | APPR OPND | HB /A /01/HBA-12-WF-003-4160-AN-U | 12 FIREWATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064422 | ANOP Remove/Add Support on 12" WI Line H | Additional materials | REL GMPS MACM PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-05-19 | 2022-05-19 | 2022-05-19 | 2022-10-23 | 2022-05-26 | 20 | REL | APPR OPND | HB /A /01/HBA-12-WF-003-4160-AN-U | 12 FIREWATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064422 | ANOP Remove/Add Support on 12" WI Line H | Dismantling exist wood/Support | REL GMPS MACM PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2022-05-19 | 2022-05-19 | 2022-05-19 | 2022-10-23 | 2022-05-26 | 60 | REL | APPR OPND | HB /A /01/HBA-12-WF-003-4160-AN-U | 12 FIREWATER LINE | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064422 | ANOP Remove/Add Support on 12" WI Line H | Install new Support | REL GMPS MACM PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 9 | 0 |  | 2022-05-19 | 2022-05-19 | 2022-05-19 | 2022-10-23 | 2022-05-26 | 70 | REL | APPR OPND | HB /A /01/HBA-12-WF-003-4160-AN-U | 12 FIREWATER LINE | 99000087 | A |  | MFM | DK50
2024-W51-52 | 4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100066015 | Loadtest of Winch LB1 (X-0701) | Loadtest and tunning of winch | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 10 | 0 | W51-52 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-11-13 | 2022-06-16 | 70 | PCNF REL | APPR OPND | HB /C /02/HBCA-X-0701 | LIFEBOAT 1 - 45 PERS. |  | A |  | MMS | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100070044 | DB Block internal leak for LIT-415102 | Isolate and Inhibit Contact Level transm | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W02 IPHPSD | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-01-28 | 2022-08-31 | 10 | REL | APPR OPND | HB /D /32/HBDB-LIT-415102 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-ELEC | 2100070044 | DB Block internal leak for LIT-415102 | Isolate heat tracing | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 | W02 IPHPSD | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-01-28 | 2022-08-31 | 20 | REL | APPR OPND | HB /D /32/HBDB-LIT-415102 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100070044 | DB Block internal leak for LIT-415102 | Remove insulation | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W02 IPHPSD | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-01-28 | 2022-08-31 | 30 | REL | APPR OPND | HB /D /32/HBDB-LIT-415102 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100070044 | DB Block internal leak for LIT-415102 | Remove Valve f, proces isolation | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W02 IPHPSD | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-01-28 | 2022-08-31 | 40 | REL | APPR OPND | HB /D /32/HBDB-LIT-415102 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100070044 | DB Block internal leak for LIT-415102 | Reinstall Valve f, proces isolation | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 1.5 | 0 | W02 IPHPSD | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-01-28 | 2022-08-31 | 50 | REL | APPR OPND | HB /D /32/HBDB-LIT-415102 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-INST | 2100070044 | DB Block internal leak for LIT-415102 | Calibrate Contact Level transmitter (flo | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W02 IPHPSD | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-01-28 | 2022-08-31 | 60 | REL | APPR OPND | HB /D /32/HBDB-LIT-415102 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100070044 | DB Block internal leak for LIT-415102 | Deisolate and repeal inhibits Contact Le | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W02 IPHPSD | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2023-01-28 | 2022-08-31 | 70 | REL | APPR OPND | HB /D /32/HBDB-LIT-415102 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100070044 | DB Block internal leak for LIT-415102 | Restore insulation | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W02 IPHPSD | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2023-01-28 | 2022-08-31 | 90 | REL | APPR OPND | HB /D /32/HBDB-LIT-415102 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-ELEC | 2100070044 | DB Block internal leak for LIT-415102 | Remove isolation from heat tracing | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 | W02 IPHPSD | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2023-01-28 | 2022-08-31 | 100 | REL | APPR OPND | HB /D /32/HBDB-LIT-415102 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100070044 | DB Block internal leak for LIT-415102 | Rigger Services | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2023-01-28 | 2022-08-31 | 120 | REL | APPR OPND | HB /D /32/HBDB-LIT-415102 | LEVEL INDICATOR TRANSMITTER (ESD) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100070624 | HBD/78: Replace priming pump and gaskets | Isolation/deisolation of crane | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2022-12-26 | 2022-08-13 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100070624 | HBD/78: Replace priming pump and gaskets | Replace priming pump + gaskets on engine | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2022-12-26 | 2022-08-13 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100070624 | HBD/78: Replace priming pump and gaskets | Assist and operating crane at leaktest | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2022-12-26 | 2022-08-13 | 30 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100071364 | HBC/78: Replace luffing cylinders and pa | Isolate/de-isolate of crane HBCO-A-6101 | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-03-09 | 2024-03-31 | 2024-03-09 | 2023-01-04 | 2022-08-22 | 10 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100071364 | HBC/78: Replace luffing cylinders and pa | Build/remove of scaffold/gallows | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 60 | 0 |  | 2024-03-09 | 2024-03-31 | 2024-03-09 | 2023-01-04 | 2022-08-22 | 20 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100071364 | HBC/78: Replace luffing cylinders and pa | Dismatle luffing cylinders | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 48 | 0 |  | 2024-03-09 | 2024-03-31 | 2024-03-15 | 2023-01-04 | 2022-08-22 | 30 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100071364 | HBC/78: Replace luffing cylinders and pa | Assist with rigging | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 60 | 0 |  | 2024-03-09 | 2024-03-31 | 2024-03-18 | 2023-01-04 | 2022-08-22 | 40 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-PAIN | 2100071364 | HBC/78: Replace luffing cylinders and pa | Repair corroded area behind cylinder att | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 15 | 0 |  | 2024-03-09 | 2024-03-31 | 2024-03-24 | 2023-01-04 | 2022-08-22 | 50 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100071364 | HBC/78: Replace luffing cylinders and pa | Install new luffing cylinders | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 30 | 0 |  | 2024-03-09 | 2024-03-31 | 2024-03-25 | 2023-01-04 | 2022-08-22 | 60 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100071364 | HBC/78: Replace luffing cylinders and pa | Perform proof load test | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2024-03-09 | 2024-03-31 | 2024-03-27 | 2023-01-04 | 2022-08-22 | 70 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100071364 | HBC/78: Replace luffing cylinders and pa | Assist with proof loadtest | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2024-03-09 | 2024-03-31 | 2024-03-28 | 2023-01-04 | 2022-08-22 | 80 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100073422 | HBCM-P-0383 assembly cycling | HBCM-P-0383 assembly cycling | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-02-17 | 2022-10-05 | 10 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100073422 | HBCM-P-0383 assembly cycling | Isolation, HBCM-A-0331 | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 2 | 2 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-02-17 | 2022-10-05 | 20 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100073422 | HBCM-P-0383 assembly cycling | Trouble shoot Air start system | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6 | 29 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-02-17 | 2022-10-05 | 30 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100073422 | HBCM-P-0383 assembly cycling | De-Isolate B-section | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 2 | 2 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-02-17 | 2022-10-05 | 40 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100073422 | HBCM-P-0383 assembly cycling | Isolation, HBCM-A-0331 | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-02-17 | 2022-10-05 | 60 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100073422 | HBCM-P-0383 assembly cycling | Install pilot switch. recal. 190 Barg | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-02-17 | 2022-10-05 | 70 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100073422 | HBCM-P-0383 assembly cycling | De-isolate | REL PCNF GMPS MANC PPRT PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2023-02-17 | 2022-10-05 | 80 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-SCAF | 2100076237 | Replace exhaust compensator on 4352 | Prep. Build scaffold, prep rigging gear | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 20 | 55 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-03 | 2023-04-04 | 2022-11-20 | 10 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | VEN-MECH | 2100076237 | Replace exhaust compensator on 4352 | Prepare site, spot materials etc. | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 8 | 0 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-03 | 2023-04-04 | 2022-11-20 | 20 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-TURB | 2100076237 | Replace exhaust compensator on 4352 | Assist vendor whole period | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 30 | 0 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-03 | 2023-04-04 | 2022-11-20 | 30 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | PRODTECH | 2100076237 | Replace exhaust compensator on 4352 | Isolation | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-04 | 2023-04-04 | 2022-11-20 | 40 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-SCAF | 2100076237 | Replace exhaust compensator on 4352 | Finish scaffolding and barriers | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 8 | 5 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-04 | 2023-04-04 | 2022-11-20 | 50 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | VEN-MECH | 2100076237 | Replace exhaust compensator on 4352 | Remove and install soft-goods | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 24 | 0 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-04 | 2023-04-04 | 2022-11-20 | 60 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-MECH | 2100076237 | Replace exhaust compensator on 4352 | Assist vendor, cut bolts etc. | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 15 | 0 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-04 | 2023-04-04 | 2022-11-20 | 70 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-RIGG | 2100076237 | Replace exhaust compensator on 4352 | Assist vendor, rigging soft-goods | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 10 | 0 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-04 | 2023-04-04 | 2022-11-20 | 80 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | INP-SITE | 2100076237 | Replace exhaust compensator on 4352 | Assess installation | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 2 | 0 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-06 | 2023-04-04 | 2022-11-20 | 90 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-SCAF | 2100076237 | Replace exhaust compensator on 4352 | Remove scaffold | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6 | 0 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-06 | 2023-04-04 | 2022-11-20 | 100 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | PRODTECH | 2100076237 | Replace exhaust compensator on 4352 | Remove isolation | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 1 | 0 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-06 | 2023-04-04 | 2022-11-20 | 110 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-SCAF | 2100076237 | Replace exhaust compensator on 4352 | Remove remaining scaffold | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 10 | 18 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-06 | 2023-04-04 | 2022-11-20 | 120 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBD-IPHP | WDF | MTN-TURB | MTN-TURB | 2100076237 | Replace exhaust compensator on 4352 | Insulation on Stock, Altrad Warehouse | REL PCNF GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W27 DK50-M-5630 | 2025-10-03 | 2025-10-08 | 2025-10-03 | 2023-04-04 | 2022-11-20 | 130 | PCNF REL | APPR OPND | HB /D /31/HBDC-A-4352-EXH | IP/HP COMPRESSOR EXHAUST |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | HBB09-GL | WDF | MTN-INST | PRODTECH | 2100082307 | New block for HBBB-PIT-300910. | Inhibit Pressure transmitter | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-07-29 | 2023-03-16 | 10 | REL | APPR OPND | HB /B /10/HBBB-PIT-300910 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBB09-GL | WDF | MTN-INST | MTN-INST | 2100082307 | New block for HBBB-PIT-300910. | Isolate Pressure transmitter | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-07-29 | 2023-03-16 | 20 | REL | APPR OPND | HB /B /10/HBBB-PIT-300910 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBB09-GL | WDF | MTN-INST | MTN-INST | 2100082307 | New block for HBBB-PIT-300910. | Replace Pressure transmitter | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 2.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-07-29 | 2023-03-16 | 30 | REL | APPR OPND | HB /B /10/HBBB-PIT-300910 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBB09-GL | WDF | MTN-INST | MTN-INST | 2100082307 | New block for HBBB-PIT-300910. | Deisolate and test Pressure transmitter | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-07-29 | 2023-03-16 | 40 | REL | APPR OPND | HB /B /10/HBBB-PIT-300910 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2026-W13-14 | 3 | HBB09-GL | WDF | MTN-INST | PRODTECH | 2100082307 | New block for HBBB-PIT-300910. | Repeal inhibit Pressure transmitter | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0.5 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-07-29 | 2023-03-16 | 90 | REL | APPR OPND | HB /B /10/HBBB-PIT-300910 | PRESSURE INDICATOR TRANSMITTER (ESD) |  | E |  | MIN | DK50
2024-W23-24 | 4 | HBA14-GL | WDF | MTN-MECH | MTN-MECH | 2100090338 | Gauge for sssv HBA14 defective | Replace pressure gauge | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2026-04-21 | 2023-11-03 | 10 | REL | APPR OPND | HB /A /07/HBAA-A-3111 | WELLHEAD CONTROL PANEL |  | E |  | MIN | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | QAQCELEC | 2400086613 | HBDB-V-4161 - NII | PVI INTERNAL INSPECTION | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-07-15 | 2021-12-31 | 2021-09-26 | 1 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-ELEC | 2400086613 | HBDB-V-4161 - NII | Line walks for permit / ICC / Materials | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-07-15 | 2021-12-31 | 2021-09-26 | 10 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-PAIN | 2400086613 | HBDB-V-4161 - NII | Line walks for permit / Materials | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-07-15 | 2021-12-31 | 2021-09-26 | 20 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-LAGG | 2400086613 | HBDB-V-4161 - NII | Line walks for permit / Materials | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-07-17 | 2021-12-31 | 2021-09-26 | 30 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-SCAF | 2400086613 | HBDB-V-4161 - NII | Line walks for permit / Materials | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-07-18 | 2021-12-31 | 2021-09-26 | 40 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-LAGG | 2400086613 | HBDB-V-4161 - NII | Remove insulation | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 20 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-07-18 | 2021-12-31 | 2021-09-26 | 50 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-ELEC | 2400086613 | HBDB-V-4161 - NII | Remove heat tracing | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 16 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-07-20 | 2021-12-31 | 2021-09-26 | 60 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-PAIN | 2400086613 | HBDB-V-4161 - NII | Blasting of flanges | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 150 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-07-21 | 2021-12-31 | 2021-09-26 | 70 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-WELD | 2400086613 | HBDB-V-4161 - NII | Cut bolts if necessary | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-07-30 | 2021-12-31 | 2021-09-26 | 80 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-PAIN | 2400086613 | HBDB-V-4161 - NII | Prime Flanges | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 50 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-07-31 | 2021-12-31 | 2021-09-26 | 90 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-PAIN | 2400086613 | HBDB-V-4161 - NII | Paint up to spec | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 30 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-08-03 | 2021-12-31 | 2021-09-26 | 100 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | QAQCMECH | 2400086613 | HBDB-V-4161 - NII | Carry out inspection (QC) | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 120 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-08-05 | 2021-12-31 | 2021-09-26 | 110 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-SCAF | 2400086613 | HBDB-V-4161 - NII | Fireguard (Any Trade ) | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 60 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-08-12 | 2021-12-31 | 2021-09-26 | 120 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-ELEC | 2400086613 | HBDB-V-4161 - NII | Reinstall heat tracing | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 30 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-08-20 | 2021-12-31 | 2021-09-26 | 130 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-LAGG | 2400086613 | HBDB-V-4161 - NII | Reinstall insulation | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 120 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-08-22 | 2021-12-31 | 2021-09-26 | 140 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-SCAF | 2400086613 | HBDB-V-4161 - NII | Remove Scaffolding and clean up | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 20 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-08-29 | 2021-12-31 | 2021-09-26 | 160 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-LAGG | 2400086613 | HBDB-V-4161 - NII | Cleaning of work site | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-08-30 | 2021-12-31 | 2021-09-26 | 170 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-ELEC | 2400086613 | HBDB-V-4161 - NII | Cleaning of work site | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-08-31 | 2021-12-31 | 2021-09-26 | 180 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-PAIN | 2400086613 | HBDB-V-4161 - NII | Cleaning of work site | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-01 | 2021-12-31 | 2021-09-26 | 190 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | QAQCMECH | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 200 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-PAIN | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 210 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-PAIN | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 220 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-SCAF | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 230 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | QAQCMECH | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 310 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-ELEC | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 390 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-ELEC | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 400 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | QAQCELEC | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 410 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | PRODTECH | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 420 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | QAQCELEC | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 430 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-WELD | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 440 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-SCAF | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 450 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-WELD | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 460 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-SCAF | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 470 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | PRODTECH | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 480 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-LAGG | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 490 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-WELD | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 500 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-SCAF | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 510 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-SCAF | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 520 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-LAGG | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 530 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | MTN-PAIN | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 540 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | MTN-PAIN | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 550 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | MTN-PAIN | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 560 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | MTN-PAIN | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 570 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | MTN-PAIN | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 580 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | CON-SCAF | 2400086613 | HBDB-V-4161 - NII | Cancel | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 582 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2026-W13-14 | C | HBD-GLY | WPM | MTN-PAIN | MTN-PAIN | 2400086613 | HBDB-V-4161 - NII |  | REL GMPS MANC PRC SETC | APPR CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-07-15 | 2023-09-02 | 2023-09-02 | 2021-12-31 | 2021-09-26 | 590 | REL | APPR OPND | HB /D /30/HBDB-V-4161 | GLYCOL FLASH VESSEL |  | C | DK600037005 | INP | DK50
2024-W19-20 | 2 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100084669 | Flexible hoses are past expired date | Prep for permit Mech | REL GMPS MANC PRC SETC | APPR CMAT AWDO AWSC RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2023-03-17 | 2023-01-31 | 10 | REL | APPR OPND | HB /D /01/HBDC-A-0453 | WATER MIST FOR A-4352 |  | A |  | MMS | DK50 |  | PROK | 2024-05-09
2024-W19-20 | 2 | NOSD | WDF | MTN-TURB | MTN-ELEC | 2100084669 | Flexible hoses are past expired date | Prep for permit Elec | REL GMPS MANC PRC SETC | APPR CMAT AWDO AWSC RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2023-03-17 | 2023-01-31 | 20 | REL | APPR OPND | HB /D /01/HBDC-A-0453 | WATER MIST FOR A-4352 |  | A |  | MMS | DK50 |  | PROK | 2024-05-10
2024-W19-20 | 2 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100084669 | Flexible hoses are past expired date | Isolate HBDC-A-0453 | REL GMPS MANC PRC SETC | APPR CMAT AWDO AWSC RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2023-03-17 | 2023-01-31 | 30 | REL | APPR OPND | HB /D /01/HBDC-A-0453 | WATER MIST FOR A-4352 |  | A |  | MMS | DK50 |  | PROK | 2024-05-11
2024-W19-20 | 2 | NOSD | WDF | MTN-TURB | MTN-ELEC | 2100084669 | Flexible hoses are past expired date | Isolate Electrical | REL GMPS MANC PRC SETC | APPR CMAT AWDO AWSC RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2023-03-17 | 2023-01-31 | 40 | REL | APPR OPND | HB /D /01/HBDC-A-0453 | WATER MIST FOR A-4352 |  | A |  | MMS | DK50 |  | PROK | 2024-05-12
2024-W19-20 | 2 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100084669 | Flexible hoses are past expired date | De-pressurize | REL GMPS MANC PRC SETC | APPR CMAT AWDO AWSC RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2023-03-17 | 2023-01-31 | 50 | REL | APPR OPND | HB /D /01/HBDC-A-0453 | WATER MIST FOR A-4352 |  | A |  | MMS | DK50 |  | PROK | 2024-05-13
2024-W19-20 | 2 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100084669 | Flexible hoses are past expired date | Replace hoses, move tag signs | REL GMPS MANC PRC SETC | APPR CMAT AWDO AWSC RFRZ ROUT | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2023-03-17 | 2023-01-31 | 60 | REL | APPR OPND | HB /D /01/HBDC-A-0453 | WATER MIST FOR A-4352 |  | A |  | MMS | DK50 |  | PROK | 2024-05-14
2024-W19-20 | 2 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100084669 | Flexible hoses are past expired date | Pressurize, chech for leakages | REL GMPS MANC PRC SETC | APPR CMAT AWDO AWSC RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-10 | 2023-03-17 | 2023-01-31 | 70 | REL | APPR OPND | HB /D /01/HBDC-A-0453 | WATER MIST FOR A-4352 |  | A |  | MMS | DK50 |  | PROK | 2024-05-15
2024-W19-20 | 2 | NOSD | WDF | MTN-TURB | MTN-ELEC | 2100084669 | Flexible hoses are past expired date | De-isolate Electrical | REL GMPS MANC PRC SETC | APPR CMAT AWDO AWSC RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-10 | 2023-03-17 | 2023-01-31 | 80 | REL | APPR OPND | HB /D /01/HBDC-A-0453 | WATER MIST FOR A-4352 |  | A |  | MMS | DK50 |  | PROK | 2024-05-16
2024-W19-20 | 2 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100084669 | Flexible hoses are past expired date | De-isolate HBDC-A-0453 | REL GMPS MANC PRC SETC | APPR CMAT AWDO AWSC RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-10 | 2023-03-17 | 2023-01-31 | 90 | REL | APPR OPND | HB /D /01/HBDC-A-0453 | WATER MIST FOR A-4352 |  | A |  | MMS | DK50 |  | PROK | 2024-05-17
2024-W23-24 | 2 | HBA07-GL | WDF | MTN-MECH | MTN-MECH | 2100069750 | ANOP Flange Face Corr lift gas HBA-07 | Flange Face Corrosion HBA-2"-GPS-0294918 | REL GMPS MANC PRC SETC | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2022-06-14 | 2022-06-09 | 10 | REL | APPR OPND | HB /A /37/HBA-2-GPS-029-4918-GF-U | 2 PROCESS GAS SOUR LINE |  | C |  | MFM | DK50
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100108536 | Replacement of 2 ea MCB in DP-1920 | Replacement of 2 ea MCB in DP-1920 | REL GMPS MACM PRC SETC | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-05-23 | 2024-05-24 | 2024-05-23 | 2024-08-27 | 2024-04-14 | 10 | REL | APPR OPND | HB /C /06/HBCA-DP-1920 | UPS A - DISTRIBUTION PANEL |  | C |  | MEL | DK50 |  | PROK | 2024-05-11
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100108536 | Replacement of 2 ea MCB in DP-1920 | Site Visit - TBT. Coordinate with CCR | REL GMPS MACM PRC SETC | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-23 | 2024-05-24 | 2024-05-23 | 2024-08-27 | 2024-04-14 | 15 | REL | APPR OPND | HB /C /06/HBCA-DP-1920 | UPS A - DISTRIBUTION PANEL |  | C |  | MEL | DK50 |  | PROK | 2024-05-12
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100108536 | Replacement of 2 ea MCB in DP-1920 | Isolate accordingly ICC. | REL GMPS MACM PRC SETC | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-23 | 2024-05-24 | 2024-05-23 | 2024-08-27 | 2024-04-14 | 20 | REL | APPR OPND | HB /C /06/HBCA-DP-1920 | UPS A - DISTRIBUTION PANEL |  | C |  | MEL | DK50 |  | PROK | 2024-05-13
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100108536 | Replacement of 2 ea MCB in DP-1920 | Replace Faulty MCB's | REL GMPS MACM PRC SETC | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-05-23 | 2024-05-24 | 2024-05-23 | 2024-08-27 | 2024-04-14 | 30 | REL | APPR OPND | HB /C /06/HBCA-DP-1920 | UPS A - DISTRIBUTION PANEL |  | C |  | MEL | DK50 |  | PROK | 2024-05-14
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100108536 | Replacement of 2 ea MCB in DP-1920 | De-isolate for test and Check up. | REL GMPS MACM PRC SETC | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-23 | 2024-05-24 | 2024-05-24 | 2024-08-27 | 2024-04-14 | 40 | REL | APPR OPND | HB /C /06/HBCA-DP-1920 | UPS A - DISTRIBUTION PANEL |  | C |  | MEL | DK50 |  | PROK | 2024-05-16
2024-W27-28 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100108536 | Replacement of 2 ea MCB in DP-1920 | clean up site / documentation | REL GMPS MACM PRC SETC | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-05-23 | 2024-05-24 | 2024-05-24 | 2024-08-27 | 2024-04-14 | 50 | REL | APPR OPND | HB /C /06/HBCA-DP-1920 | UPS A - DISTRIBUTION PANEL |  | C |  | MEL | DK50 |  | PROK | 2024-05-17
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100024767 | Change IT-SWITCH HBDC-N-1852-M08-A | Isolate switch. See attached description | REL GMPS MANC PPRT PRC SETC | APPR CMAT | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2019-08-16 | 2019-07-07 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M08-A | IT-SWITCH |  | C |  | MEL | DK50
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100024767 | Change IT-SWITCH HBDC-N-1852-M08-A | Assist PRODTECH with Isolating | REL GMPS MANC PPRT PRC SETC | APPR CMAT | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2019-08-16 | 2019-07-07 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M08-A | IT-SWITCH |  | C |  | MEL | DK50
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100024767 | Change IT-SWITCH HBDC-N-1852-M08-A | Replace broken switch, test | REL GMPS MANC PPRT PRC SETC | APPR CMAT | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2019-08-16 | 2019-07-07 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M08-A | IT-SWITCH |  | C |  | MEL | DK50
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100024767 | Change IT-SWITCH HBDC-N-1852-M08-A | De-Isolate above | REL GMPS MANC PPRT PRC SETC | APPR CMAT | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2019-08-16 | 2019-07-07 | 40 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M08-A | IT-SWITCH |  | C |  | MEL | DK50
2024-W49-50 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100024767 | Change IT-SWITCH HBDC-N-1852-M08-A | L3 backload old switch to NJ Forsom | REL GMPS MANC PPRT PRC SETC | APPR CMAT | 1 | 0 | W49-50 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2019-08-16 | 2019-07-07 | 50 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M08-A | IT-SWITCH |  | C |  | MEL | DK50
2026-W13-14 | 2 | HBB06-WI | WDF | MTN-INST | MTN-INST | 2100091892 | Failure on HBB06 choke | install New sov on valve block | REL PCNF GMPS MANC PRC SETC | APPR CMAT | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-06-19 | 2023-06-04 | 60 | REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | E |  | MIN | DK50
2026-W13-14 | 2 | HBB06-WI | WDF | MTN-INST | PRODTECH | 2100091892 | Failure on HBB06 choke | Hydraulic line isolation | REL PCNF GMPS MANC PRC SETC | APPR CMAT | 1 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-06-19 | 2023-06-04 | 80 | REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | E |  | MIN | DK50
2026-W13-14 | 2 | HBB06-WI | WDF | MTN-INST | MTN-INST | 2100091892 | Failure on HBB06 choke | Replace solenoid valve | REL PCNF GMPS MANC PRC SETC | APPR CMAT | 3 | 0 | W17-W18 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2023-06-19 | 2023-06-04 | 90 | REL | APPR OPND | HB /B /55/HBBB-CVA-300607 | CHOKE VALVE |  | E |  | MIN | DK50
2026-W13-14 | 3 | HDAFLARE | WDF | MTN-INST | MTN-ROPE | 2100076142 | TIT for LP flare ignition panel | Prepare rope access | REL MANC NMAT PRC SETC | APPR AWSD RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-04-07 | 2022-11-23 | 10 | REL | APPR OPND | HB /D /36/HBDC-TE-406301 | TEMPERATURE ELEMENT |  | G |  | MIN | DK50
2026-W13-14 | 3 | HDAFLARE | WDF | MTN-INST | MTN-ROPE | 2100076142 | TIT for LP flare ignition panel | Isolate Temperature element (Sensor) | REL MANC NMAT PRC SETC | APPR AWSD RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-04-07 | 2022-11-23 | 20 | REL | APPR OPND | HB /D /36/HBDC-TE-406301 | TEMPERATURE ELEMENT |  | G |  | MIN | DK50
2026-W13-14 | 3 | HDAFLARE | WDF | MTN-INST | MTN-ROPE | 2100076142 | TIT for LP flare ignition panel | Replace Temperature element (Sensor) | REL MANC NMAT PRC SETC | APPR AWSD RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-04-07 | 2022-11-23 | 30 | REL | APPR OPND | HB /D /36/HBDC-TE-406301 | TEMPERATURE ELEMENT |  | G |  | MIN | DK50
2026-W13-14 | 3 | HDAFLARE | WDF | MTN-INST | MTN-ROPE | 2100076142 | TIT for LP flare ignition panel | Deisolate Temperature element (Sensor) | REL MANC NMAT PRC SETC | APPR AWSD RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-04-07 | 2022-11-23 | 40 | REL | APPR OPND | HB /D /36/HBDC-TE-406301 | TEMPERATURE ELEMENT |  | G |  | MIN | DK50
2026-W13-14 | 3 | HDAFLARE | WDF | MTN-INST | MTN-ROPE | 2100076142 | TIT for LP flare ignition panel | Remove rope access | REL MANC NMAT PRC SETC | APPR AWSD RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-04-07 | 2022-11-23 | 50 | REL | APPR OPND | HB /D /36/HBDC-TE-406301 | TEMPERATURE ELEMENT |  | G |  | MIN | DK50
2026-W13-14 | 3 | HDAFLARE | WDF | MTN-INST | MTN-INST | 2100076142 | TIT for LP flare ignition panel | Assistance | REL MANC NMAT PRC SETC | APPR AWSD RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2023-04-07 | 2022-11-23 | 60 | REL | APPR OPND | HB /D /36/HBDC-TE-406301 | TEMPERATURE ELEMENT |  | G |  | MIN | DK50
2024-W23-24 | 3 | HBOIL-SD | WGN | MTN-TELE | MTN-TELE | 2200006513 | ESD2 shutdown test ref EXP-407 HBD | ESD2 shutdown test ref EXP-407 HBD | REL MANC NMAT PRC SETC | APPR AWSD AWSC | 0.5 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-06-24 | 2021-03-26 | 10 | REL | APPR OPND | HB /A /03/HBAA-FP-0220A | ESD PANEL | 99000119 | G |  | MIN | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100025903 | FFSPR CMAT:Replace spool with corroded f | Corr. found on upstream spool flange | REL MANC PRC SETC | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | 0 | 0 | 200650915+676325+650842 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2021-04-26 | 2019-05-07 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | G |  | MFM | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100025903 | FFSPR CMAT:Replace spool with corroded f | Prepare the work site, and place rigger | REL MANC PRC SETC | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | 200650915+676325+650842 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2021-04-26 | 2019-05-07 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | G |  | MFM | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100025903 | FFSPR CMAT:Replace spool with corroded f | Isolate Deluge skid HBAA-A-0371 - Prod | REL MANC PRC SETC | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | 200650915+676325+650842 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2021-04-26 | 2019-05-07 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | G |  | MFM | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100025903 | FFSPR CMAT:Replace spool with corroded f | Replace spool | REL MANC PRC SETC | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | 8 | 0 | 200650915+676325+650842 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2021-04-26 | 2019-05-07 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | G |  | MFM | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | PRODTECH | 2100025903 | FFSPR CMAT:Replace spool with corroded f | de-Isolate Deluge skid HBAA-A-0371 - Pro | REL MANC PRC SETC | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | 200650915+676325+650842 | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2021-04-26 | 2019-05-07 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | G |  | MFM | DK50
2026-W13-14 | 4 | HB-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100025903 | FFSPR CMAT:Replace spool with corroded f | cleaning work site | REL MANC PRC SETC | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | 200650915+676325+650842 | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2021-04-26 | 2019-05-07 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | G |  | MFM | DK50
2026-W13-14 | A | HBD-IPHP | WPM | MTN-TURB | MTN-TURB | 2400308687 | 8000H COMPRESSOR SKID, COUNTER | OVERHAUL | REL NMAT PRC SETC | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2024-10-03 | 2024-10-10 | 2024-10-03 | 2024-03-17 | 2024-02-16 | 10 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | G | DKHB-0478 | MMR | DK50 | MR0094 | PTW MISS
2026-W13-14 | A | HBD-IPHP | WPM | MTN-TURB | VEN-MECH | 2400308687 | 8000H COMPRESSOR SKID, COUNTER | OVERHAUL SUPPORT-VENDOR | REL NMAT PRC SETC | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2024-10-03 | 2024-10-10 | 2024-10-05 | 2024-03-17 | 2024-02-16 | 20 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | G | DKHB-0478 | MMR | DK50 | MR0094 | PTW MISS
2026-W13-14 | A | HBD-IPHP | WPM | MTN-TURB | MTN-INST | 2400308687 | 8000H COMPRESSOR SKID, COUNTER | FUNCTION TEST & CALIBRATION | REL NMAT PRC SETC | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-03 | 2024-10-10 | 2024-10-06 | 2024-03-17 | 2024-02-16 | 30 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | G | DKHB-0478 | MMR | DK50 | MR0094 | PTW MISS
2026-W13-14 | A | HBD-IPHP | WPM | MTN-TURB | MTN-ELEC | 2400308687 | 8000H COMPRESSOR SKID, COUNTER | ELECTRICAL CHECK | REL NMAT PRC SETC | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-10-03 | 2024-10-10 | 2024-10-09 | 2024-03-17 | 2024-02-16 | 40 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | G | DKHB-0478 | MMR | DK50 | MR0094 | PTW MISS
0 | 2 | HDA-TFO | WRO | MTN-TELE | PRODTECH | 2300005732 | E31 ESD HW Replacement | Process paramater control | REL MANC NMAT PRC SETC | APPR AWSD | 24 | 0 |  | 2024-03-09 | 2024-03-13 | 2024-03-09 | 2023-07-10 | 2023-05-26 | 10 | REL | APPR OPND | HD /B /03/HDBE-CPF-0201 | ESD CONTROLLER PANEL |  | G |  | MIN | DK60
0 | 2 | HDA-TFO | WRO | MTN-TELE | VEN-ELEC | 2300005732 | E31 ESD HW Replacement | Installation of ESD modules | REL MANC NMAT PRC SETC | APPR AWSD | 12 | 0 |  | 2024-03-09 | 2024-03-13 | 2024-03-11 | 2023-07-10 | 2023-05-26 | 20 | REL | APPR OPND | HD /B /03/HDBE-CPF-0201 | ESD CONTROLLER PANEL |  | G |  | MIN | DK60
0 | 2 | HDA-TFO | WRO | MTN-TELE | MTN-TELE | 2300005732 | E31 ESD HW Replacement | Assistance with installation, testing | REL MANC NMAT PRC SETC | APPR AWSD | 4 | 0 |  | 2024-03-09 | 2024-03-13 | 2024-03-12 | 2023-07-10 | 2023-05-26 | 30 | REL | APPR OPND | HD /B /03/HDBE-CPF-0201 | ESD CONTROLLER PANEL |  | G |  | MIN | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100022643 | ANOC HDA fuel gas system repassivation a | L3 permit and preparation | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 8.7 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2022-02-05 | 2020-02-16 | 5 | REL | APPR OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100022643 | ANOC HDA fuel gas system repassivation a | L3 repassivation and painting work see-- | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 67 | 0 |  | 2023-04-24 | 2023-04-27 | 2023-04-25 | 2022-02-05 | 2020-02-16 | 10 | REL | APPR OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 3 | HDASW | WDF | MTN-MECH | MTN-SCAF | 2100022866 | CMAT:Replace 20" (HCV downstream P-53023 | L3 Bygning af stillads | REL MANC PRC SETC | APPR AWSC RDBL | 78.4 | 0 | Gorm SD | 2025-01-01 | 2025-01-14 | 2025-01-01 | 2019-09-12 | 2019-06-14 | 10 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | HDASW | WDF | MTN-MECH | MTN-RIGG | 2100022866 | CMAT:Replace 20" (HCV downstream P-53023 | L3 Rigger assistance opsætting af tajler | REL MANC PRC SETC | APPR AWSC RDBL | 17.4 | 0 | Gorm SD | 2025-01-01 | 2025-01-14 | 2025-01-06 | 2019-09-12 | 2019-06-14 | 20 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | HDASW | WDF | MTN-MECH | PRODTECH | 2100022866 | CMAT:Replace 20" (HCV downstream P-53023 | L3 Isolation - COOLING MEDIUM COOLER | REL MANC PRC SETC | APPR AWSC RDBL | 6 | 0 | Gorm SD | 2025-01-01 | 2025-01-14 | 2025-01-08 | 2019-09-12 | 2019-06-14 | 30 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | HDASW | WDF | MTN-MECH | MTN-PIPF | 2100022866 | CMAT:Replace 20" (HCV downstream P-53023 | L2 Udskiftning af 20" butterfly | REL MANC PRC SETC | APPR AWSC RDBL | 17.4 | 0 | Gorm SD | 2025-01-01 | 2025-01-14 | 2025-01-09 | 2019-09-12 | 2019-06-14 | 40 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | HDASW | WDF | MTN-MECH | PRODTECH | 2100022866 | CMAT:Replace 20" (HCV downstream P-53023 | L3 De-Isolation | REL MANC PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-14 | 2025-01-10 | 2019-09-12 | 2019-06-14 | 50 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | HDASW | WDF | MTN-MECH | MTN-RIGG | 2100022866 | CMAT:Replace 20" (HCV downstream P-53023 | L3 Rigger assistance nedtagning af tajle | REL MANC PRC SETC | APPR AWSC RDBL | 17.4 | 0 |  | 2025-01-01 | 2025-01-14 | 2025-01-09 | 2019-09-12 | 2019-06-14 | 60 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | HDASW | WDF | MTN-MECH | MTN-SCAF | 2100022866 | CMAT:Replace 20" (HCV downstream P-53023 | L3 Nedtagning af stillads | REL MANC PRC SETC | APPR AWSC RDBL | 52.3 | 0 |  | 2025-01-01 | 2025-01-14 | 2025-01-11 | 2019-09-12 | 2019-06-14 | 70 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023099 | Vibrations mapping HDA L1&2. | Operating P-3601 & P-5312 | REL MANC PRC SETC | APPR AWSC RDBL | 0.5 | 0 | OIM10 | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2020-05-12 | 2020-02-12 | 10 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMR | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100023099 | Vibrations mapping HDA L1&2. | Mapping vibration levels | REL MANC PRC SETC | APPR AWSC RDBL | 6 | 0 | OIM10 | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2020-05-12 | 2020-02-12 | 20 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMR | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023099 | Vibrations mapping HDA L1&2. | Operating P-3602 & P-5312 | REL MANC PRC SETC | APPR AWSC RDBL | 0.5 | 0 | OIM10 | 2024-09-18 | 2024-09-21 | 2024-09-19 | 2020-05-12 | 2020-02-12 | 30 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMR | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100023099 | Vibrations mapping HDA L1&2. | Mapping vibration levels | REL MANC PRC SETC | APPR AWSC RDBL | 6 | 0 | OIM10 | 2024-09-18 | 2024-09-21 | 2024-09-19 | 2020-05-12 | 2020-02-12 | 40 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMR | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023099 | Vibrations mapping HDA L1&2. | Operating P-3602 & P-5312 | REL MANC PRC SETC | APPR AWSC RDBL | 0.5 | 0 | OIM10 | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2020-05-12 | 2020-02-12 | 50 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMR | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100023099 | Vibrations mapping HDA L1&2. | Mapping vibration levels | REL MANC PRC SETC | APPR AWSC RDBL | 6 | 0 | OIM10 | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2020-05-12 | 2020-02-12 | 60 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMR | DK60
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023099 | Vibrations mapping HDA L1&2. | Operating P-3602 & P-5313 | REL MANC PRC SETC | APPR AWSC RDBL | 0.5 | 0 | OIM10 | 2024-09-18 | 2024-09-21 | 2024-09-21 | 2020-05-12 | 2020-02-12 | 70 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMR | DK60
0 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100023099 | Vibrations mapping HDA L1&2. | Mapping vibration levels | REL MANC PRC SETC | APPR AWSC RDBL | 6 | 0 | OIM10 | 2024-09-18 | 2024-09-21 | 2024-09-21 | 2020-05-12 | 2020-02-12 | 80 | REL | APPR OPND | HD /A /9 | SPECIFIC APPLICATION |  | A |  | MMR | DK60
0 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023454 | PMAT:HDA Change out 1" Loading valve | Safing | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 | PROD | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2019-05-06 | 2018-05-11 | 10 | REL | APPR OPND | HD /A /26 | METERING PRODUCED LIQUID PROCESSING |  | C |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023454 | PMAT:HDA Change out 1" Loading valve | Change out 1" Loading valve | REL MANC PRC SETC | APPR AWSC RDBL | 8 | 0 | Michael Skaarup | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2019-05-06 | 2018-05-11 | 20 | REL | APPR OPND | HD /A /26 | METERING PRODUCED LIQUID PROCESSING |  | C |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023454 | PMAT:HDA Change out 1" Loading valve | Desafing | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 | PROD | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2019-05-06 | 2018-05-11 | 30 | REL | APPR OPND | HD /A /26 | METERING PRODUCED LIQUID PROCESSING |  | C |  | MMS | DK60
0 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023454 | PMAT:HDA Change out 1" Loading valve | Leaktest | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 | Michael Skaarup | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2019-05-06 | 2018-05-11 | 40 | REL | APPR OPND | HD /A /26 | METERING PRODUCED LIQUID PROCESSING |  | C |  | MMS | DK60
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-PIPF | MTN-SCAF | 2100023578 | CMAT:Replace spool on HBA | L3 Preparation | REL MANC PRC SETC | APPR AWSC RDBL | 26.1 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-01 | 2018-03-22 | 2018-02-10 | 10 | REL | APPR OPND | HB /A /03 | ESD AND FIRE & GAS | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-PIPF | MTN-PIPF | 2100023578 | CMAT:Replace spool on HBA | L3 Preparation | REL MANC PRC SETC | APPR AWSC RDBL | 17.4 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-01 | 2018-03-22 | 2018-02-10 | 20 | REL | APPR OPND | HB /A /03 | ESD AND FIRE & GAS | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-PIPF | MTN-SCAF | 2100023578 | CMAT:Replace spool on HBA | L3 Scaffolding | REL MANC PRC SETC | APPR AWSC RDBL | 17.4 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-02 | 2018-03-22 | 2018-02-10 | 30 | REL | APPR OPND | HB /A /03 | ESD AND FIRE & GAS | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-PIPF | PRODTECH | 2100023578 | CMAT:Replace spool on HBA | L3 Safing of the spool | REL MANC PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-04 | 2018-03-22 | 2018-02-10 | 40 | REL | APPR OPND | HB /A /03 | ESD AND FIRE & GAS | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-PIPF | MTN-SCAF | 2100023578 | CMAT:Replace spool on HBA | L3 Rigging assistance during spool repl. | REL MANC PRC SETC | APPR AWSC RDBL | 17.4 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-06 | 2018-03-22 | 2018-02-10 | 50 | REL | APPR OPND | HB /A /03 | ESD AND FIRE & GAS | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-PIPF | MTN-PIPF | 2100023578 | CMAT:Replace spool on HBA | L3 Removal of the spool | REL MANC PRC SETC | APPR AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-06 | 2018-03-22 | 2018-02-10 | 60 | REL | APPR OPND | HB /A /03 | ESD AND FIRE & GAS | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-PIPF | MTN-PIPF | 2100023578 | CMAT:Replace spool on HBA | L2 Installation of the new spool | REL MANC PRC SETC | APPR AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-06 | 2018-03-22 | 2018-02-10 | 70 | REL | APPR OPND | HB /A /03 | ESD AND FIRE & GAS | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-PIPF | PRODTECH | 2100023578 | CMAT:Replace spool on HBA | L2 Desafing and leak test | REL MANC PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-07 | 2018-03-22 | 2018-02-10 | 80 | REL | APPR OPND | HB /A /03 | ESD AND FIRE & GAS | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-PIPF | MTN-SCAF | 2100023578 | CMAT:Replace spool on HBA | L3 Clean-up | REL MANC PRC SETC | APPR AWSC RDBL | 17.4 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-09 | 2018-03-22 | 2018-02-10 | 90 | REL | APPR OPND | HB /A /03 | ESD AND FIRE & GAS | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-PIPF | MTN-PIPF | 2100023578 | CMAT:Replace spool on HBA | L3 Clean-up | REL MANC PRC SETC | APPR AWSC RDBL | 17.4 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-09 | 2018-03-22 | 2018-02-10 | 100 | REL | APPR OPND | HB /A /03 | ESD AND FIRE & GAS | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HCAPWELL | WDF | MTN-PIPF | MTN-SCAF | 2100023578 | CMAT:Replace spool on HBA | L3 Removal of scaffolding | REL MANC PRC SETC | APPR AWSC RDBL | 26.1 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-11 | 2018-03-22 | 2018-02-10 | 110 | REL | APPR OPND | HB /A /03 | ESD AND FIRE & GAS | 99000119 | A |  | MMS | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | PRODTECH | 2100023637 | SMAT:REPL HCV's up/downHBDB-P-5366 | L3 Isolate for replace of valves | REL PRT MANC PRC SETC | APPR AWSC RDBL | 13 | 0 | + | 2025-01-01 | 2025-01-14 | 2025-01-01 | 2019-03-09 | 2018-12-09 | 15 | REL | APPR OPND | HB /D /76 | COOLING WATER | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-RIGG | 2100023637 | SMAT:REPL HCV's up/downHBDB-P-5366 | L3 Help removing HCV's | REL PRT MANC PRC SETC | APPR AWSC RDBL | 12 | 0 | + | 2025-01-01 | 2025-01-14 | 2025-01-04 | 2019-03-09 | 2018-12-09 | 20 | REL | APPR OPND | HB /D /76 | COOLING WATER | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-MECH | 2100023637 | SMAT:REPL HCV's up/downHBDB-P-5366 | L2 Replace HCV's | REL PRT MANC PRC SETC | APPR AWSC RDBL | 12 | 0 | + | 2025-01-01 | 2025-01-14 | 2025-01-06 | 2019-03-09 | 2018-12-09 | 30 | REL | APPR OPND | HB /D /76 | COOLING WATER | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | MTN-RIGG | 2100023637 | SMAT:REPL HCV's up/downHBDB-P-5366 | L3 Help put in new HCV's | REL PRT MANC PRC SETC | APPR AWSC RDBL | 12 | 0 | + | 2025-01-01 | 2025-01-14 | 2025-01-09 | 2019-03-09 | 2018-12-09 | 32 | REL | APPR OPND | HB /D /76 | COOLING WATER | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBDSW | WDF | MTN-MECH | PRODTECH | 2100023637 | SMAT:REPL HCV's up/downHBDB-P-5366 | L3 De-Isolate for replace of valves | REL PRT MANC PRC SETC | APPR AWSC RDBL | 10 | 0 | + | 2025-01-01 | 2025-01-14 | 2025-01-11 | 2019-03-09 | 2018-12-09 | 35 | REL | APPR OPND | HB /D /76 | COOLING WATER | 99000119 | F |  | MMS | DK50
0 | 3 | HDA-IPHP | WDF | MTN-MECH | MTN-SCAF | 2100023845 | CMAT:Udskift 20" Ventil-HDAD-E-5305A | Bygning af stillads | REL CSER MANC PRC SETC | APPR AWSC RDBL | 42 | 0 |  | 2025-01-01 | 2025-01-14 | 2025-01-01 | 2018-01-30 | 2017-11-01 | 10 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | HDA-IPHP | WDF | MTN-MECH | MTN-SCAF | 2100023845 | CMAT:Udskift 20" Ventil-HDAD-E-5305A | Rigger assistance opsætting af tajler | REL CSER MANC PRC SETC | APPR AWSC RDBL | 17.4 | 0 |  | 2025-01-01 | 2025-01-14 | 2025-01-05 | 2018-01-30 | 2017-11-01 | 20 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | HDA-IPHP | WDF | MTN-MECH | PRODTECH | 2100023845 | CMAT:Udskift 20" Ventil-HDAD-E-5305A | Safing - COOLING MEDIUM COOLER | REL CSER MANC PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-14 | 2025-01-07 | 2018-01-30 | 2017-11-01 | 30 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | HDA-IPHP | WDF | MTN-MECH | MTN-MECH | 2100023845 | CMAT:Udskift 20" Ventil-HDAD-E-5305A | Udskiftning af 20" butterfly | REL CSER MANC PRC SETC | APPR AWSC RDBL | 17.4 | 0 |  | 2025-01-01 | 2025-01-14 | 2025-01-08 | 2018-01-30 | 2017-11-01 | 40 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | HDA-IPHP | WDF | MTN-MECH | PRODTECH | 2100023845 | CMAT:Udskift 20" Ventil-HDAD-E-5305A | Desafing | REL CSER MANC PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-14 | 2025-01-10 | 2018-01-30 | 2017-11-01 | 50 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | HDA-IPHP | WDF | MTN-MECH | MTN-SCAF | 2100023845 | CMAT:Udskift 20" Ventil-HDAD-E-5305A | Rigger assistance nedtagning af tajler | REL CSER MANC PRC SETC | APPR AWSC RDBL | 17.4 | 0 |  | 2025-01-01 | 2025-01-14 | 2025-01-08 | 2018-01-30 | 2017-11-01 | 60 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
0 | 3 | HDA-IPHP | WDF | MTN-MECH | MTN-SCAF | 2100023845 | CMAT:Udskift 20" Ventil-HDAD-E-5305A | Nedtagning af stillads | REL CSER MANC PRC SETC | APPR AWSC RDBL | 30 | 0 |  | 2025-01-01 | 2025-01-14 | 2025-01-11 | 2018-01-30 | 2017-11-01 | 70 | REL | APPR OPND | HD /A /76 | COOLING WATER | 99000120 | F |  | MMS | DK60
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100025855 | CMAT:Replace HBAA-HCV-03778 | L3 Scaffold build | REL MANC PRC SETC | APPR AWSC RDBL | 5 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-04-12 | 2018-11-13 | 10 | REL | APPR OPND | HB /A /01/HBAA-HCV-03778 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100025855 | CMAT:Replace HBAA-HCV-03778 | L3 Isolate HBAA-HCV-03778 | REL MANC PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2019-04-12 | 2018-11-13 | 20 | REL | APPR OPND | HB /A /01/HBAA-HCV-03778 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100025855 | CMAT:Replace HBAA-HCV-03778 | L3 Rigger assistance/rigging gear | REL MANC PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2019-04-12 | 2018-11-13 | 25 | REL | APPR OPND | HB /A /01/HBAA-HCV-03778 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100025855 | CMAT:Replace HBAA-HCV-03778 | L2 Replace HBAA-HCV-03778 | REL MANC PRC SETC | APPR AWSC RDBL | 14 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2019-04-12 | 2018-11-13 | 30 | REL | APPR OPND | HB /A /01/HBAA-HCV-03778 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100025855 | CMAT:Replace HBAA-HCV-03778 | L3 De-isolate/test HBAA-HCV-03778 | REL MANC PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-04-12 | 2018-11-13 | 40 | REL | APPR OPND | HB /A /01/HBAA-HCV-03778 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100025855 | CMAT:Replace HBAA-HCV-03778 | L3 Scaffold removed | REL MANC PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-04-12 | 2018-11-13 | 50 | REL | APPR OPND | HB /A /01/HBAA-HCV-03778 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-ROUS | 2100025855 | CMAT:Replace HBAA-HCV-03778 | L3 Firewatch during WO | REL MANC PRC SETC | APPR AWSC RDBL | 14 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2019-04-12 | 2018-11-13 | 60 | REL | APPR OPND | HB /A /01/HBAA-HCV-03778 | HAND CONTROL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025957 | SMAT:Flange face corr on strainer side | Isolate for replace spool nearby P-5366 | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-12-25 | 2018-09-26 | 20 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025957 | SMAT:Flange face corr on strainer side | Replace spool | REL MANC PRC SETC | APPR AWSC RDBL | 17 | 0 | CCW shut down job | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-12-25 | 2018-09-26 | 30 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025957 | SMAT:Flange face corr on strainer side | De-isolate after replaced spool | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2018-12-25 | 2018-09-26 | 40 | REL | APPR OPND | HB /D /51/HBDB-P-5366 | UTILITY SEAWATER PUMP (100%) | 99000119 | F |  | MMS | DK50
2025-W1-2 | 4 | HBB05-GL | WDF | MTN-MECH | MTN-MECH | 2100026236 | CMAT:Replace PI for closing. Well 05 | L3 isolate PI | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-16 | 2019-09-22 | 10 | REL | APPR OPND | HB /B /07/HBBB-FP-5943 | VALVE CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 4 | HBB05-GL | WDF | MTN-MECH | MTN-MECH | 2100026236 | CMAT:Replace PI for closing. Well 05 | L2 change PI | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-16 | 2019-09-22 | 20 | REL | APPR OPND | HB /B /07/HBBB-FP-5943 | VALVE CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 4 | HBB05-GL | WDF | MTN-MECH | MTN-MECH | 2100026236 | CMAT:Replace PI for closing. Well 05 | L3 deisolate and check PI | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-16 | 2019-09-22 | 30 | REL | APPR OPND | HB /B /07/HBBB-FP-5943 | VALVE CONTROL PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | PRODTECH | MTN-PIPF | 2100026238 | LOTI:HBB10 Liftgas Flowelement rep-retur | Mount new Flowelement | REL PCNF PRT CSER MANC PRC SETC | APPR AWSC RDBL | 8.7 | 0 | LOTI | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-08-30 | 2019-08-25 | 40 | REL | APPR OPND | HB /B /37/HBBB-FE-291002 | FLOW ELEMENT (METERING) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | PRODTECH | MTN-SCAF | 2100026238 | LOTI:HBB10 Liftgas Flowelement rep-retur | Rig of flowelement | REL PCNF PRT CSER MANC PRC SETC | APPR AWSC RDBL | 8.7 | 0 | LOTI | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-08-30 | 2019-08-25 | 45 | REL | APPR OPND | HB /B /37/HBBB-FE-291002 | FLOW ELEMENT (METERING) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | PRODTECH | PRODTECH | 2100026238 | LOTI:HBB10 Liftgas Flowelement rep-retur | Desafing | REL PCNF PRT CSER MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-08-30 | 2019-08-25 | 50 | REL | APPR OPND | HB /B /37/HBBB-FE-291002 | FLOW ELEMENT (METERING) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 4 | HBBLIFTG | WDF | PRODTECH | MTN-PIPF | 2100026238 | LOTI:HBB10 Liftgas Flowelement rep-retur | Asbuilt | REL PCNF PRT CSER MANC PRC SETC | APPR AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-08-30 | 2019-08-25 | 60 | REL | APPR OPND | HB /B /37/HBBB-FE-291002 | FLOW ELEMENT (METERING) | 99000119 | F |  | MIN | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | PRODTECH | 2100026250 | CMAT:Replace DBB on HBBB-FIT-290402 (Val | L3 Isolation of HBBB-FIT-290402 | REL PRT MANC PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-08-21 | 2019-05-23 | 10 | REL | APPR OPND | HB /B /37/HBBB-FIT-290402 | FLOW INDICATOR TRANSMITTER (METERING) | 99000119 | C |  | MIN | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | MTN-MECH | 2100026250 | CMAT:Replace DBB on HBBB-FIT-290402 (Val | L2 Replace DBB HBBB-FIT-290402 | REL PRT MANC PRC SETC | APPR AWSC RDBL | 5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-08-21 | 2019-05-23 | 20 | REL | APPR OPND | HB /B /37/HBBB-FIT-290402 | FLOW INDICATOR TRANSMITTER (METERING) | 99000119 | C |  | MIN | DK50
2026-W13-14 | 3 | HBB04-GL | WDF | MTN-MECH | PRODTECH | 2100026250 | CMAT:Replace DBB on HBBB-FIT-290402 (Val | L3 De-Isolation/test HBBB-FIT-290402 | REL PRT MANC PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-08-21 | 2019-05-23 | 30 | REL | APPR OPND | HB /B /37/HBBB-FIT-290402 | FLOW INDICATOR TRANSMITTER (METERING) | 99000119 | C |  | MIN | DK50
0 | 4 | HDAPW | WDF | MTN-MECH | PRODTECH | 2100026990 | CMAT:HCV for dræn har int lækage V-5013 | Safing | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-12-29 | 2017-08-01 | 10 | REL | APPR OPND | HD /A /28 | CLOSED DRAINS/OPEN DRAINS | 99000120 | F |  | MMS | DK60
0 | 4 | HDAPW | WDF | MTN-MECH | MTN-MECH | 2100026990 | CMAT:HCV for dræn har int lækage V-5013 | Udskifte 2" ventilen | REL MANC PRC SETC | APPR AWSC RDBL | 8 | 0 | See revision code | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-12-29 | 2017-08-01 | 20 | REL | APPR OPND | HD /A /28 | CLOSED DRAINS/OPEN DRAINS | 99000120 | F |  | MMS | DK60
0 | 4 | HDAPW | WDF | MTN-MECH | PRODTECH | 2100026990 | CMAT:HCV for dræn har int lækage V-5013 | Desafing | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 | PROD | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2017-12-29 | 2017-08-01 | 30 | REL | APPR OPND | HD /A /28 | CLOSED DRAINS/OPEN DRAINS | 99000120 | F |  | MMS | DK60
0 | 4 | HDAPW | WDF | MTN-MECH | PRODTECH | 2100026990 | CMAT:HCV for dræn har int lækage V-5013 | Leaktest | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 | PROD | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2017-12-29 | 2017-08-01 | 40 | REL | APPR OPND | HD /A /28 | CLOSED DRAINS/OPEN DRAINS | 99000120 | F |  | MMS | DK60
2026-W13-14 | 4 | HBDHPSEP | WDF | MTN-MECH | PRODTECH | 2100027104 | SMAT:Udskift bleedventil V/ HCV-36003/04 | Safing af ventil | REL PRT MANC PRC SETC | APPR AWSC RDBL | 4 | 0 | PROD | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2018-03-08 | 2017-10-09 | 10 | REL | APPR OPND | HB /A /12/HBAA-HCV-36003 | LO - HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBDHPSEP | WDF | MTN-MECH | MTN-MECH | 2100027104 | SMAT:Udskift bleedventil V/ HCV-36003/04 | Udskiftning af bleed ventil/blind flang | REL PRT MANC PRC SETC | APPR AWSC RDBL | 6 | 0 | SD job | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2018-03-08 | 2017-10-09 | 20 | REL | APPR OPND | HB /A /12/HBAA-HCV-36003 | LO - HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBDHPSEP | WDF | MTN-MECH | PRODTECH | 2100027104 | SMAT:Udskift bleedventil V/ HCV-36003/04 | Desafing og leaktest | REL PRT MANC PRC SETC | APPR AWSC RDBL | 4 | 0 | PROD | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2018-03-08 | 2017-10-09 | 30 | REL | APPR OPND | HB /A /12/HBAA-HCV-36003 | LO - HAND CONTROL VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100027208 | CMAT:+ Change out 1" by-pass valve for H | L3 Isolate 1" by-pass globe valve | REL MANC PRC SETC | APPR AWSC RDBL | 3 | 0 | RCE | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-01-25 | 2018-12-16 | 10 | REL | APPR OPND | HB /A /34/HBAA-XCV-38010 | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100027208 | CMAT:+ Change out 1" by-pass valve for H | L3 Replace 1" by-pass globe valve | REL MANC PRC SETC | APPR AWSC RDBL | 3 | 0 | RCE | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-01-25 | 2018-12-16 | 30 | REL | APPR OPND | HB /A /34/HBAA-XCV-38010 | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100027208 | CMAT:+ Change out 1" by-pass valve for H | L3 Replace studbolt on PI-38015 | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 | RCE | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-01-25 | 2018-12-16 | 35 | REL | APPR OPND | HB /A /34/HBAA-XCV-38010 | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100027208 | CMAT:+ Change out 1" by-pass valve for H | L3 De-Isolate 1" by-pass globe valve | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 | RCE | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-01-25 | 2018-12-16 | 40 | REL | APPR OPND | HB /A /34/HBAA-XCV-38010 | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100027208 | CMAT:+ Change out 1" by-pass valve for H | L3 Test new 1" by-pass globe valve | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 | RCE | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2019-01-25 | 2018-12-16 | 50 | REL | APPR OPND | HB /A /34/HBAA-XCV-38010 | DOUBLE BLOCK AND BLEED BALL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100045218 | HBBA-A-3103 High press pump not running | Isolate system to prevent Shut Down | REL PCNF MANC PPRT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-05-25 | 2021-02-24 | 10 | PCNF REL | APPR OPND | HB /B /07/HBBA-A-3103 | HYDRAULIC PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-ELEC | 2100045218 | HBBA-A-3103 High press pump not running | Further investigation of failure require | REL PCNF MANC PPRT PRC SETC | APPR AWSC RDBL | 4 | 4 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-05-25 | 2021-02-24 | 20 | PCNF REL | APPR OPND | HB /B /07/HBBA-A-3103 | HYDRAULIC PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-ELEC | 2100045218 | HBBA-A-3103 High press pump not running | Install new PIT | REL PCNF MANC PPRT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2021-05-25 | 2021-02-24 | 30 | REL | APPR OPND | HB /B /07/HBBA-A-3103 | HYDRAULIC PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | VEN-MECH | 2100051549 | Replace grease nipple on HCV-34047 | prep for job | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-10-10 | 2021-12-14 | 10 | REL | APPR OPND | HB /B /10/HBBA-HCV-34047 | LO - HAND CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100051549 | Replace grease nipple on HCV-34047 | isolate valve | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2022-10-10 | 2021-12-14 | 20 | REL | APPR OPND | HB /B /10/HBBA-HCV-34047 | LO - HAND CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | VEN-MECH | 2100051549 | Replace grease nipple on HCV-34047 | replace grease nippel / check valve | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-10-10 | 2021-12-14 | 30 | REL | APPR OPND | HB /B /10/HBBA-HCV-34047 | LO - HAND CONTROL VALVE | 99000119 | A |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100051549 | Replace grease nipple on HCV-34047 | de-isolate, leak test, etc. | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2022-10-10 | 2021-12-14 | 40 | REL | APPR OPND | HB /B /10/HBBA-HCV-34047 | LO - HAND CONTROL VALVE | 99000119 | A |  | MMS | DK50
0 | 4 | NE | WDF | MTN-MECH | MTN-ROPE | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | HDA - Replace of Handrail EL +22000 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-15 | 2022-09-21 | 2022-04-24 | 10 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | HDA-L1-HR-01 - Report photo 1 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-15 | 2022-09-21 | 2022-04-24 | 20 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Build Scaffold | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 18 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-15 | 2022-09-21 | 2022-04-24 | 30 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Drill holes for handrail base/mount | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-16 | 2022-09-21 | 2022-04-24 | 40 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Paint/prime drilled holes | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-17 | 2022-09-21 | 2022-04-24 | 41 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Mount and secure handrail base/mount | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-17 | 2022-09-21 | 2022-04-24 | 50 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Install new handrail | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-18 | 2022-09-21 | 2022-04-24 | 60 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Remove Scaffold | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 9 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-18 | 2022-09-21 | 2022-04-24 | 70 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Installation Report | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-19 | 2022-09-21 | 2022-04-24 | 80 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | HDA-L1-HR-02 - Report photo 5 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-19 | 2022-09-21 | 2022-04-24 | 90 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Build Scaffold | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 18 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-19 | 2022-09-21 | 2022-04-24 | 100 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Install/mount new handrail | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-20 | 2022-09-21 | 2022-04-24 | 110 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Remove Scaffold | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 9 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-21 | 2022-09-21 | 2022-04-24 | 120 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Installation Report | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-21 | 2022-09-21 | 2022-04-24 | 130 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | HDA-L1-HR-03 - Report photo 3 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-21 | 2022-09-21 | 2022-04-24 | 140 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Build Scaffold | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 18 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-21 | 2022-09-21 | 2022-04-24 | 150 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Drill holes in deck plate | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 18 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-23 | 2022-09-21 | 2022-04-24 | 160 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Paint/prime drilled holes | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 16 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-24 | 2022-09-21 | 2022-04-24 | 161 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Install new handrail | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 24 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-24 | 2022-09-21 | 2022-04-24 | 170 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-ROPE | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Fixate nuts from bottom | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 36 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-26 | 2022-09-21 | 2022-04-24 | 180 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Remove Scaffold | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 9 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-27 | 2022-09-21 | 2022-04-24 | 190 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Installation Report | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-28 | 2022-09-21 | 2022-04-24 | 200 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100062366 | DWESR HDA - Replace of Handrail EL +2200 | Mount clamps (18pcs) | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 9 | 0 |  | 2024-09-15 | 2024-09-28 | 2024-09-28 | 2022-09-21 | 2022-04-24 | 210 | REL | APPR OPND | HD /A /86/22000 - HANDRAILS | 22000 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100074522 | Halfdan Alpha - Deluge Waterlocks | Halfdan Alpha - Deluge Waterlocks | REL NMAT PRC SETC | APPR AWSC RDBL | 0 | 0 |  | 2023-11-04 | 2023-11-04 | 2023-11-04 | 2022-12-01 | 2022-07-04 | 10 | REL | APPR OPND | HD /A /01/P-G | PIPING GROUP |  | A |  | MMS | DK60
2024-W17-18 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100089004 | Faultfinding on HT HBD 1870 Q18 | Mount insolation | REL PCNF MANC NMAT PRC SETC | APPR AWSC RDBL | 0 | 0 | W09-W10 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2026-03-27 | 2023-10-09 | 140 | PCNF REL | APPR OPND | HB /D /61/HBDC-DP-1870-18 | HEAT TRACING (HTJB-1870-0018) |  | A |  | MEL | DK50 |  | PROK | 2024-05-04
2024-W39-40 | 4 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100089005 | Faultfinding on HT HBD 1870 Q71 | Mount insolation | REL PCNF MANC NMAT PRC SETC | APPR AWSC RDBL | 0 | 0 | W09-W10 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2026-03-27 | 2023-10-09 | 150 | PCNF REL | APPR OPND | HB /D /61/HBDC-DP-1870-71 | HEAT TRACING (HTJB-1870-0071) |  | A |  | MEL | DK50 |  | PROK | 2024-05-19
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100089006 | Faultfinding on HT HBD 1870 Q77 | Isolate Circuit 0077 on DP-1870. | REL PCNF MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2026-03-27 | 2023-10-09 | 100 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-77 | HEAT TRACING (HTJB-1870-0077) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100089006 | Faultfinding on HT HBD 1870 Q77 | Remov. 1m insolation by JB, both ends | REL PCNF MANC NMAT PRC SETC | APPR AWSC RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2026-03-27 | 2023-10-09 | 110 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-77 | HEAT TRACING (HTJB-1870-0077) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100089006 | Faultfinding on HT HBD 1870 Q77 | Short HT cable/ new termin kit both ends | REL PCNF MANC NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2026-03-27 | 2023-10-09 | 120 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-77 | HEAT TRACING (HTJB-1870-0077) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100089006 | Faultfinding on HT HBD 1870 Q77 | Megger test of HT cable | REL PCNF MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2026-03-27 | 2023-10-09 | 130 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-77 | HEAT TRACING (HTJB-1870-0077) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100089006 | Faultfinding on HT HBD 1870 Q77 | DeIsolate Circuit 0077 on DP-1870. | REL PCNF MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2026-03-27 | 2023-10-09 | 140 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-77 | HEAT TRACING (HTJB-1870-0077) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100089006 | Faultfinding on HT HBD 1870 Q77 | Mount insolation | REL PCNF MANC NMAT PRC SETC | APPR AWSC RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2026-03-27 | 2023-10-09 | 150 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-77 | HEAT TRACING (HTJB-1870-0077) |  | A |  | MEL | DK50 |  | PROK
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100089006 | Faultfinding on HT HBD 1870 Q77 | Remove scaffold | REL PCNF MANC NMAT PRC SETC | APPR AWSC RDBL | 10 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2026-03-27 | 2023-10-09 | 160 | REL | APPR OPND | HB /D /61/HBDC-DP-1870-77 | HEAT TRACING (HTJB-1870-0077) |  | A |  | MEL | DK50 |  | PROK
2024-W41-42 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096689 | FLM 1" Air Valve is Leaking | FLM 1" Air Valve is Leaking | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-02-09 | 2023-09-27 | 10 | REL | APPR OPND | HB /D /07 | INSTRUMENT AIR/GAS - HYDRAULIC POWER |  | A |  | MMS | DK50 |  |  | 2024-04-22
2024-W35-36 | 3 | HBA09-GL | WDF | MTN-INST | MTN-INST | 2100096925 | HBA09 liftgas flow transmitter fail | HBA09 liftgas flow transmitter fail | REL PCNF MANC PRC SETC | APPR AWSC RDBL | 3 | 11 |  | 2024-09-03 | 2024-09-05 | 2024-09-03 | 2024-02-24 | 2023-10-12 | 10 | PCNF REL | APPR OPND | HB /A /37/HBAA-FIT-29093 | FLOW INDICATOR TRANSMITTER (METERING) |  | A |  | MIN | DK50
2024-W35-36 | 3 | HBA09-GL | WDF | MTN-INST | MTN-INST | 2100096925 | HBA09 liftgas flow transmitter fail | Investigation | REL PCNF MANC PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-09-03 | 2024-09-05 | 2024-09-03 | 2024-02-24 | 2023-10-12 | 20 | REL | APPR OPND | HB /A /37/HBAA-FIT-29093 | FLOW INDICATOR TRANSMITTER (METERING) |  | A |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-PIPF | MTN-SCAF | 2200002988 | CMAT:Replacement of 1" HCV valve flare s | L3 Construction of welding tent | REL MANC PRC SETC | APPR AWSC RDBL | 34.8 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-01 | 2018-03-23 | 2018-03-03 | 10 | REL | APPR OPND | HB /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-PIPF | VEN-ELEC | 2200002988 | CMAT:Replacement of 1" HCV valve flare s | L3 Establishing positive pressure and wo | REL MANC PRC SETC | APPR AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-04 | 2018-03-23 | 2018-03-03 | 20 | REL | APPR OPND | HB /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-PIPF | PRODTECH | 2200002988 | CMAT:Replacement of 1" HCV valve flare s | L3 Safing of the purge line | REL MANC PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-05 | 2018-03-23 | 2018-03-03 | 30 | REL | APPR OPND | HB /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200002988 | CMAT:Replacement of 1" HCV valve flare s | L3 Cutting away the old globe valve | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-06 | 2018-03-23 | 2018-03-03 | 40 | REL | APPR OPND | HB /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200002988 | CMAT:Replacement of 1" HCV valve flare s | L1 Welding on new flange | REL MANC PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-06 | 2018-03-23 | 2018-03-03 | 50 | REL | APPR OPND | HB /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200002988 | CMAT:Replacement of 1" HCV valve flare s | L2 install new valve+blind flange | REL MANC PRC SETC | APPR AWSC RDBL | 2.7 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-06 | 2018-03-23 | 2018-03-03 | 60 | REL | APPR OPND | HB /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-PIPF | PRODTECH | 2200002988 | CMAT:Replacement of 1" HCV valve flare s | L3 Desafing and leak test | REL MANC PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-08 | 2018-03-23 | 2018-03-03 | 70 | REL | APPR OPND | HB /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-PIPF | VEN-ELEC | 2200002988 | CMAT:Replacement of 1" HCV valve flare s | L3 Removal of blowers and lights | REL MANC PRC SETC | APPR AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-09 | 2018-03-23 | 2018-03-03 | 80 | REL | APPR OPND | HB /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-PIPF | MTN-SCAF | 2200002988 | CMAT:Replacement of 1" HCV valve flare s | L3 Demol of tent | REL MANC PRC SETC | APPR AWSC RDBL | 17.4 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-10 | 2018-03-23 | 2018-03-03 | 90 | REL | APPR OPND | HB /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-PIPF | MTN-PAIN | 2200002988 | CMAT:Replacement of 1" HCV valve flare s | L3 Preparation for painting of the flang | REL MANC PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-01 | 2018-03-23 | 2018-03-03 | 100 | REL | APPR OPND | HB /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-PIPF | MTN-PAIN | 2200002988 | CMAT:Replacement of 1" HCV valve flare s | L2 Painting of the flanges | REL MANC PRC SETC | APPR AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-07 | 2018-03-23 | 2018-03-03 | 110 | REL | APPR OPND | HB /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-PIPF | MTN-PAIN | 2200002988 | CMAT:Replacement of 1" HCV valve flare s | L3 Clean-up | REL MANC PRC SETC | APPR AWSC RDBL | 4.7 | 0 |  | 2025-01-01 | 2025-01-12 | 2025-01-11 | 2018-03-23 | 2018-03-03 | 120 | REL | APPR OPND | HB /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000119 | F |  | MMS | DK50
2025-W1-2 | 3 | HBAPWELL | WGN | MTN-INST | MTN-INST | 2200003042 | SMAT:Change out three PI's at A-3112 | L3 Isolate PI-30172 | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-02-27 | 2018-11-29 | 10 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 3 | HBAPWELL | WGN | MTN-INST | MTN-INST | 2200003042 | SMAT:Change out three PI's at A-3112 | L3 Change out PI-30172 (see WO200641148) | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 | IOP PtW-136700 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-02-27 | 2018-11-29 | 20 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 3 | HBAPWELL | WGN | MTN-INST | MTN-INST | 2200003042 | SMAT:Change out three PI's at A-3112 | L3 Test new PI | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-02-27 | 2018-11-29 | 30 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 3 | HBAPWELL | WGN | MTN-INST | MTN-INST | 2200003042 | SMAT:Change out three PI's at A-3112 | L3 De-isolate PI-30172 | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-02-27 | 2018-11-29 | 40 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 3 | HBAPWELL | WGN | MTN-INST | MTN-INST | 2200003042 | SMAT:Change out three PI's at A-3112 | L3 Isolate PI-30291 | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-02-27 | 2018-11-29 | 50 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 3 | HBAPWELL | WGN | MTN-INST | MTN-INST | 2200003042 | SMAT:Change out three PI's at A-3112 | L3 Change out PI-30291 | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 | IOP PtW-136702 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-02-27 | 2018-11-29 | 60 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 3 | HBAPWELL | WGN | MTN-INST | MTN-INST | 2200003042 | SMAT:Change out three PI's at A-3112 | L3 Test new PI | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-02-27 | 2018-11-29 | 70 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 3 | HBAPWELL | WGN | MTN-INST | MTN-INST | 2200003042 | SMAT:Change out three PI's at A-3112 | L3 De-isolate PI-30291 | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-02-27 | 2018-11-29 | 80 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 3 | HBAPWELL | WGN | MTN-INST | MTN-INST | 2200003042 | SMAT:Change out three PI's at A-3112 | L3 Isolate PI-30302 | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2019-02-27 | 2018-11-29 | 90 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 3 | HBAPWELL | WGN | MTN-INST | MTN-INST | 2200003042 | SMAT:Change out three PI's at A-3112 | L3 Change out PI-30302 | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 | IOP PtW-136705 | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2019-02-27 | 2018-11-29 | 100 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 3 | HBAPWELL | WGN | MTN-INST | MTN-INST | 2200003042 | SMAT:Change out three PI's at A-3112 | L3 Test new PI | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2019-02-27 | 2018-11-29 | 110 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2025-W1-2 | 3 | HBAPWELL | WGN | MTN-INST | MTN-INST | 2200003042 | SMAT:Change out three PI's at A-3112 | L3 De-isolate PI-30302 | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2019-02-27 | 2018-11-29 | 120 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBFUELG | WGN | MTN-MECH | MTN-MECH | 2200003207 | SMAT:NO HBD Cavity Bleed REPLment to Pl | Cavity Bleed replacement to Plug | REL MANC PRC SETC | APPR AWSC RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 10 | REL | APPR OPND | HB /D /34/HBDC-HCV-290001-U | HCV UPSTREAM PSV-290001 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBFUELG | WGN | MTN-MECH | MTN-MECH | 2200003207 | SMAT:NO HBD Cavity Bleed REPLment to Pl | Mat are available and checked through | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 20 | REL | APPR OPND | HB /D /34/HBDC-HCV-290001-U | HCV UPSTREAM PSV-290001 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBFUELG | WGN | MTN-MECH | PRODTECH | 2200003207 | SMAT:NO HBD Cavity Bleed REPLment to Pl | Safing. | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 30 | REL | APPR OPND | HB /D /34/HBDC-HCV-290001-U | HCV UPSTREAM PSV-290001 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBFUELG | WGN | MTN-MECH | MTN-MECH | 2200003207 | SMAT:NO HBD Cavity Bleed REPLment to Pl | Cavity Bleed replacement to Plugs | REL MANC PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2018-04-12 | 2018-01-12 | 40 | REL | APPR OPND | HB /D /34/HBDC-HCV-290001-U | HCV UPSTREAM PSV-290001 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBFUELG | WGN | MTN-MECH | PRODTECH | 2200003207 | SMAT:NO HBD Cavity Bleed REPLment to Pl | Desafing/leaktest | REL MANC PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2018-04-12 | 2018-01-12 | 50 | REL | APPR OPND | HB /D /34/HBDC-HCV-290001-U | HCV UPSTREAM PSV-290001 | 99000119 | F |  | MMS | DK50
2024-W37-38 | 1 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200012946 | Acid clean of sewage system | Acid clean of sewage system - OTS | REL MANC PRC SETC | APPR AWSC RDBL | 336 | 0 | W37-38 | 2024-03-11 | 2024-03-28 | 2024-03-11 | 2023-01-19 | 2023-01-04 | 10 | REL | APPR OPND | HB /C /82/HBCM-A-5132 | SEWAGE TREATMENT UNIT |  | A |  | MMS | DK50
2024-W37-38 | 1 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200012946 | Acid clean of sewage system |  | REL MANC PRC SETC | APPR AWSC RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-28 | 2024-03-28 | 2023-01-19 | 2023-01-04 | 20 | REL | APPR OPND | HB /C /82/HBCM-A-5132 | SEWAGE TREATMENT UNIT |  | A |  | MMS | DK50
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211312 | 4Y 11KV N-SWB MAINT HBDC-N-1851 | ISOLATION BY PRODUCTION | REL MANC PPRT PRC SETC | APPR AWSC RDBL | 1 | 0 | W13 DK50-M-6110 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-09-01 | 2022-06-05 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C | DKHB-0509 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211312 | 4Y 11KV N-SWB MAINT HBDC-N-1851 | 11KV N-SWB MAINT HBDC-N-1851 | REL MANC PPRT PRC SETC | APPR AWSC RDBL | 12 | 0 | W13 DK50-M-6110 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-09-01 | 2022-06-05 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C | DKHB-0509 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211312 | 4Y 11KV N-SWB MAINT HBDC-N-1851 | DE-ISOLATION BY PRODUCTION | REL MANC PPRT PRC SETC | APPR AWSC RDBL | 1 | 0 | W13 DK50-M-6110 | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-09-01 | 2022-06-05 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C | DKHB-0509 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211313 | 4Y 11KV N-SWB MAINT HBDC-N-1851-K01 | ISOLATION ELECTRICAL | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 | W49-50 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-09-01 | 2022-06-05 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K01 | SPARE VCB FEEDER |  | C | DKHB-0512 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211313 | 4Y 11KV N-SWB MAINT HBDC-N-1851-K01 | 11KV N-SWB MAINT HBDC-N-1851-K01 | REL MANC PRC SETC | APPR AWSC RDBL | 16 | 0 | W49-50 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-09-01 | 2022-06-05 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K01 | SPARE VCB FEEDER |  | C | DKHB-0512 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211313 | 4Y 11KV N-SWB MAINT HBDC-N-1851-K01 | DE-ISOLATION ELECTRICAL | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 | W49-50 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-09-01 | 2022-06-05 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K01 | SPARE VCB FEEDER |  | C | DKHB-0512 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211320 | 4Y 11KV N-SWB MAINT HBDC-N-1851-K08 | ISOLATION ELECTRICAL | REL PRT MANC PRC SETC | APPR AWSC RDBL | 1 | 0 | W49-50 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-09-01 | 2022-06-05 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K08 | K08 |  | C | DKHB-0667 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211320 | 4Y 11KV N-SWB MAINT HBDC-N-1851-K08 | 11KV N-SWB MAINT HBDC-N-1851-K08 | REL PRT MANC PRC SETC | APPR AWSC RDBL | 8 | 0 | W49-50 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-09-01 | 2022-06-05 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K08 | K08 |  | C | DKHB-0667 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211320 | 4Y 11KV N-SWB MAINT HBDC-N-1851-K08 | DE-ISOLATION ELECTRICAL | REL PRT MANC PRC SETC | APPR AWSC RDBL | 1 | 0 | W49-50 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-09-01 | 2022-06-05 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K08 | K08 |  | C | DKHB-0667 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211331 | 4Y 3KV N-SWB MAINT HBCA-N-1801 | ISOLATION ELECTRICAL | REL PCNF PRT MANC PRC SETC | APPR AWSC RDBL | 1 | 2 | W49-50 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 10 | PCNF REL | APPR OPND | HB /C /61/HBCA-N-1801 | AUXILIARY 3 KV SWITCHBOARD |  | C | DKHB-0551 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | MTN-RIGG | 2400211331 | 4Y 3KV N-SWB MAINT HBCA-N-1801 | Rigging assistance | REL PCNF PRT MANC PRC SETC | APPR AWSC RDBL | 2 | 2 | W49-50 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 15 | PCNF REL | APPR OPND | HB /C /61/HBCA-N-1801 | AUXILIARY 3 KV SWITCHBOARD |  | C | DKHB-0551 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211331 | 4Y 3KV N-SWB MAINT HBCA-N-1801 | 3KV N-SWB MAINT HBCA-N-1801 | REL PCNF PRT MANC PRC SETC | APPR AWSC RDBL | 24 | 0 | W49-50 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 20 | PCNF REL | APPR OPND | HB /C /61/HBCA-N-1801 | AUXILIARY 3 KV SWITCHBOARD |  | C | DKHB-0551 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211331 | 4Y 3KV N-SWB MAINT HBCA-N-1801 | DE-ISOLATION ELECTRICAL | REL PCNF PRT MANC PRC SETC | APPR AWSC RDBL | 1 | 2 | W49-50 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 30 | PCNF REL | APPR OPND | HB /C /61/HBCA-N-1801 | AUXILIARY 3 KV SWITCHBOARD |  | C | DKHB-0551 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211335 | 4Y 3KV N-SWB MAINT HBDC-N-1852 | ISOLATION ELECTRICAL - Busbar A | REL PCNF PRT MANC PRC SETC | APPR AWSC RDBL | 3 | 0 | W49-50 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 40 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | C | DKHB-0543 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211335 | 4Y 3KV N-SWB MAINT HBDC-N-1852 | 3KV N-SWB MAINT HBDC-N-1852 - Busbar A | REL PCNF PRT MANC PRC SETC | APPR AWSC RDBL | 16 | 0 | W49-50 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 50 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | C | DKHB-0543 | MEL | DK50 | EL0024
2024-W49-50 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211335 | 4Y 3KV N-SWB MAINT HBDC-N-1852 | DE-ISOLATION ELECTRICAL - Busbar A | REL PCNF PRT MANC PRC SETC | APPR AWSC RDBL | 3 | 0 | W49-50 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 60 | PCNF REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | C | DKHB-0543 | MEL | DK50 | EL0024
2024-W37-38 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211397 | 4Y 400V E-SWB INSP HBCA-N-1840B-01 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-10-01 | 2022-07-20 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-01 | SECTION NO.01 |  | C | DKHB-0407 | MEL | DK50 | EL0024
2024-W37-38 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211397 | 4Y 400V E-SWB INSP HBCA-N-1840B-01 | 400V E-SWB INSP HBCA-N-1840B-01 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 18 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-10-01 | 2022-07-20 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-01 | SECTION NO.01 |  | C | DKHB-0407 | MEL | DK50 | EL0024
2024-W37-38 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211397 | 4Y 400V E-SWB INSP HBCA-N-1840B-01 | 400V E-SWB INSP HBCA-N-1840B-01 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-10-01 | 2022-07-20 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-01 | SECTION NO.01 |  | C | DKHB-0407 | MEL | DK50 | EL0024
2024-W37-38 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211397 | 4Y 400V E-SWB INSP HBCA-N-1840B-01 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-10-01 | 2022-07-20 | 40 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-01 | SECTION NO.01 |  | C | DKHB-0407 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211411 | 4Y 400V E-SWB INSP HBDD-N-1855-B03 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-09-01 | 2022-06-20 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B03 | SECTION B03 |  | C | DKHB-0426 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211411 | 4Y 400V E-SWB INSP HBDD-N-1855-B03 | 400V E-SWB INSP HBDD-N-1855-B03 | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-09-01 | 2022-06-20 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B03 | SECTION B03 |  | C | DKHB-0426 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211411 | 4Y 400V E-SWB INSP HBDD-N-1855-B03 | 400V E-SWB INSP HBDD-N-1855-B03 | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-09-01 | 2022-06-20 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B03 | SECTION B03 |  | C | DKHB-0426 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211411 | 4Y 400V E-SWB INSP HBDD-N-1855-B03 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-09-01 | 2022-06-20 | 40 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B03 | SECTION B03 |  | C | DKHB-0426 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211439 | 4Y 400V N-DP MAINT HBDB-DP-1871/1874 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /D /61/HBDB-DP-1871 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0632 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211439 | 4Y 400V N-DP MAINT HBDB-DP-1871/1874 | 400V N-DP MAINT HBDB-DP-1871/1874 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /D /61/HBDB-DP-1871 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0632 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211439 | 4Y 400V N-DP MAINT HBDB-DP-1871/1874 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /D /61/HBDB-DP-1871 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0632 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211440 | 4Y 400V N-DP MAINT HBDB-DP-1872 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /D /61/HBDB-DP-1872 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0633 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211440 | 4Y 400V N-DP MAINT HBDB-DP-1872 | 400V N-DP MAINT HBDB-DP-1872 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /D /61/HBDB-DP-1872 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0633 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211440 | 4Y 400V N-DP MAINT HBDB-DP-1872 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /D /61/HBDB-DP-1872 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0633 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211441 | 4Y 400V N-DP MAINT HBDB-DP-1873 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /D /61/HBDB-DP-1873 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0630 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211441 | 4Y 400V N-DP MAINT HBDB-DP-1873 | 400V N-DP MAINT HBDB-DP-1873 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /D /61/HBDB-DP-1873 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0630 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211441 | 4Y 400V N-DP MAINT HBDB-DP-1873 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /D /61/HBDB-DP-1873 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0630 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211442 | 4Y 400V N-DP MAINT HBDC-DP-1870 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /D /61/HBDC-DP-1870 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0631 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211442 | 4Y 400V N-DP MAINT HBDC-DP-1870 | 400V N-DP MAINT HBDC-DP-1870 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 10 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /D /61/HBDC-DP-1870 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0631 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211442 | 4Y 400V N-DP MAINT HBDC-DP-1870 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /D /61/HBDC-DP-1870 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0631 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211443 | 4Y 400V N-DP MAINT HBDC-LP-1804 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /D /61/HBDC-LP-1804 | LEVEL 2 OFFICE LIGHTING & SMALL POWER |  | C | DKHB-0637 | MEL | DK50 | EL0044
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211443 | 4Y 400V N-DP MAINT HBDC-LP-1804 | 400V N-DP MAINT HBDC-LP-1804 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /D /61/HBDC-LP-1804 | LEVEL 2 OFFICE LIGHTING & SMALL POWER |  | C | DKHB-0637 | MEL | DK50 | EL0044
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211443 | 4Y 400V N-DP MAINT HBDC-LP-1804 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /D /61/HBDC-LP-1804 | LEVEL 2 OFFICE LIGHTING & SMALL POWER |  | C | DKHB-0637 | MEL | DK50 | EL0044
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211444 | 4Y 400V N-DP MAINT HBDD-LP-1802 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /D /61/HBDD-LP-1802 | LIGHTING & SMALL POWER DISTRIBUTION PANE |  | C | DKHB-0636 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211444 | 4Y 400V N-DP MAINT HBDD-LP-1802 | 400V N-DP MAINT HBDD-LP-1802 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /D /61/HBDD-LP-1802 | LIGHTING & SMALL POWER DISTRIBUTION PANE |  | C | DKHB-0636 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211444 | 4Y 400V N-DP MAINT HBDD-LP-1802 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /D /61/HBDD-LP-1802 | LIGHTING & SMALL POWER DISTRIBUTION PANE |  | C | DKHB-0636 | MEL | DK50 | EL0024
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211449 | 4Y 400V N-DP HD SMALL POWER/HT | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0404 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211449 | 4Y 400V N-DP HD SMALL POWER/HT | 400V N-DP HD SMALL POWER/HT INSP | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 14 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0404 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211449 | 4Y 400V N-DP HD SMALL POWER/HT | 400V N-DP HD SMALL POWER/HT INSP | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0404 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211449 | 4Y 400V N-DP HD SMALL POWER/HT | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-12-01 | 2022-09-04 | 40 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0404 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211450 | 4Y 400V N-DP HD SMALL POWER/HT | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HD /B /61/HDBD-DP-1850 | HEAT TRACING POWER DISTRIBUTION BOARD |  | A | DKHD-0456 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211450 | 4Y 400V N-DP HD SMALL POWER/HT | 400V N-DP HD SMALL POWER/HT INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HD /B /61/HDBD-DP-1850 | HEAT TRACING POWER DISTRIBUTION BOARD |  | A | DKHD-0456 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211450 | 4Y 400V N-DP HD SMALL POWER/HT | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HD /B /61/HDBD-DP-1850 | HEAT TRACING POWER DISTRIBUTION BOARD |  | A | DKHD-0456 | MEL | DK60 | EL0023
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211451 | 4Y 400V N-DP MAINT HBDE-LP-1805 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /D /61/HBDE-LP-1805 | LEVEL 4 WORKSHOP POWER DB |  | C | DKHB-0634 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211451 | 4Y 400V N-DP MAINT HBDE-LP-1805 | 400V N-DP MAINT HBDE-LP-1805 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 10 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /D /61/HBDE-LP-1805 | LEVEL 4 WORKSHOP POWER DB |  | C | DKHB-0634 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211451 | 4Y 400V N-DP MAINT HBDE-LP-1805 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /D /61/HBDE-LP-1805 | LEVEL 4 WORKSHOP POWER DB |  | C | DKHB-0634 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211452 | 4Y 400V N-SWB MAINT HBCA-N-1810 | ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 1 | W37-38 | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2022-12-01 | 2022-09-04 | 10 | PCNF REL | APPR OPND | HB /C /61/HBCA-N-1810 | AUXILIARY UTILITY SWITCHBOARD |  | C | DKHB-0579 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211452 | 4Y 400V N-SWB MAINT HBCA-N-1810 | 400V N-SWB MAINT HBCA-N-1810 | REL PCNF PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 20 | 16 | W37-38 | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2022-12-01 | 2022-09-04 | 20 | PCNF REL | APPR OPND | HB /C /61/HBCA-N-1810 | AUXILIARY UTILITY SWITCHBOARD |  | C | DKHB-0579 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211452 | 4Y 400V N-SWB MAINT HBCA-N-1810 | 400V N-SWB MAINT HBCA-N-1810 | REL PCNF PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 1 | W37-38 | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2022-12-01 | 2022-09-04 | 30 | PCNF REL | APPR OPND | HB /C /61/HBCA-N-1810 | AUXILIARY UTILITY SWITCHBOARD |  | C | DKHB-0579 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211452 | 4Y 400V N-SWB MAINT HBCA-N-1810 | DE-ISOLATION BY PRODUCTION | REL PCNF PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 1 | W37-38 | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2022-12-01 | 2022-09-04 | 40 | PCNF REL | APPR OPND | HB /C /61/HBCA-N-1810 | AUXILIARY UTILITY SWITCHBOARD |  | C | DKHB-0579 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211453 | 4Y 400V N-SWB MAINT HBCA-N-1810-01 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-01 | SECTION NO.01 |  | C | DKHB-0561 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211453 | 4Y 400V N-SWB MAINT HBCA-N-1810-01 | 400V N-SWB MAINT HBCA-N-1810-01 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 16 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-01 | SECTION NO.01 |  | C | DKHB-0561 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211453 | 4Y 400V N-SWB MAINT HBCA-N-1810-01 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-10-01 | 2022-07-05 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-01 | SECTION NO.01 |  | C | DKHB-0561 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211455 | 4Y 400V N-SWB MAINT HBCA-N-1810-03 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-03 | SECTION NO.03 |  | C | DKHB-0565 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211455 | 4Y 400V N-SWB MAINT HBCA-N-1810-03 | 400V N-SWB MAINT HBCA-N-1810-03 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 13 | 0 | W37-38 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-03 | SECTION NO.03 |  | C | DKHB-0565 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211455 | 4Y 400V N-SWB MAINT HBCA-N-1810-03 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-13 | 2024-03-13 | 2022-10-01 | 2022-07-05 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-03 | SECTION NO.03 |  | C | DKHB-0565 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211460 | 4Y 400V N-SWB MAINT HBCA-N-1810-08 | ISOLATION BY ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W49 Caverion | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-08 | SECTION NO.08 |  | C | DKHB-0577 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211460 | 4Y 400V N-SWB MAINT HBCA-N-1810-08 | 400V N-SWB MAINT HBCA-N-1810-08 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 | W49 Caverion | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-08 | SECTION NO.08 |  | C | DKHB-0577 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211460 | 4Y 400V N-SWB MAINT HBCA-N-1810-08 | 400V N-SWB MAINT HBCA-N-1810-08 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 | W49 Caverion | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-10-01 | 2022-07-05 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-08 | SECTION NO.08 |  | C | DKHB-0577 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211460 | 4Y 400V N-SWB MAINT HBCA-N-1810-08 | DE-ISOLATION BY ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W49 Caverion | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-10-01 | 2022-07-05 | 40 | REL | APPR OPND | HB /C /61/HBCA-N-1810-08 | SECTION NO.08 |  | C | DKHB-0577 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211461 | 4Y 400V N-SWB MAINT HBCA-N-1810-09 | ISOLATION BY ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W49 Caverion | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-09 | SECTION NO.09 |  | C | DKHB-0578 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211461 | 4Y 400V N-SWB MAINT HBCA-N-1810-09 | 400V N-SWB MAINT HBCA-N-1810-09 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 | W49 Caverion | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-10-01 | 2022-07-05 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-09 | SECTION NO.09 |  | C | DKHB-0578 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211461 | 4Y 400V N-SWB MAINT HBCA-N-1810-09 | 400V N-SWB MAINT HBCA-N-1810-09 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 | W49 Caverion | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-10-01 | 2022-07-05 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-09 | SECTION NO.09 |  | C | DKHB-0578 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211461 | 4Y 400V N-SWB MAINT HBCA-N-1810-09 | DE-ISOLATION BY ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W49 Caverion | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-10-01 | 2022-07-05 | 40 | REL | APPR OPND | HB /C /61/HBCA-N-1810-09 | SECTION NO.09 |  | C | DKHB-0578 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211481 | 4Y 400V N-SWB MAINT HBDD-N-1854-B02 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W03 Caverion | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-11-01 | 2022-08-05 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B02 | CUBICLE B02 |  | C | DKHB-0624 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211481 | 4Y 400V N-SWB MAINT HBDD-N-1854-B02 | 400V N-SWB MAINT HBDD-N-1854-B02 | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W03 Caverion | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-11-01 | 2022-08-05 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B02 | CUBICLE B02 |  | C | DKHB-0624 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211481 | 4Y 400V N-SWB MAINT HBDD-N-1854-B02 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W03 Caverion | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2022-11-01 | 2022-08-05 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B02 | CUBICLE B02 |  | C | DKHB-0624 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211483 | 4Y 400V N-SWB MAINT HBDD-N-1854-B04 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W03 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-11-01 | 2022-08-05 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B04 | CUBICLE B04 |  | C | DKHB-0626 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211483 | 4Y 400V N-SWB MAINT HBDD-N-1854-B04 | 400V N-SWB MAINT HBDD-N-1854-B04 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 7 | 0 | W03 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-11-01 | 2022-08-05 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B04 | CUBICLE B04 |  | C | DKHB-0626 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211483 | 4Y 400V N-SWB MAINT HBDD-N-1854-B04 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W03 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-11-01 | 2022-08-05 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B04 | CUBICLE B04 |  | C | DKHB-0626 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211494 | 4Y 400V N-SWB MAINT HBAA-N-1801 | ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 | W15-W16 | 2024-04-12 | 2024-04-20 | 2024-04-12 | 2022-12-01 | 2022-09-19 | 10 | REL | APPR OPND | HB /A /61/HBAA-N-1801 | LOW VOLTAGE SWITCHBOARD |  | C | DKHB-0548 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211494 | 4Y 400V N-SWB MAINT HBAA-N-1801 | 400V N-SWB MAINT HBAA-N-1801 | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 68 | 0 | W15-W16 | 2024-04-12 | 2024-04-20 | 2024-04-12 | 2022-12-01 | 2022-09-19 | 20 | REL | APPR OPND | HB /A /61/HBAA-N-1801 | LOW VOLTAGE SWITCHBOARD |  | C | DKHB-0548 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211494 | 4Y 400V N-SWB MAINT HBAA-N-1801 | 400V N-SWB MAINT HBAA-N-1801 | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 23 | 0 | W15-W16 | 2024-04-12 | 2024-04-20 | 2024-04-16 | 2022-12-01 | 2022-09-19 | 30 | REL | APPR OPND | HB /A /61/HBAA-N-1801 | LOW VOLTAGE SWITCHBOARD |  | C | DKHB-0548 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211494 | 4Y 400V N-SWB MAINT HBAA-N-1801 | DE-ISOLATION ELECTRICAL | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 | W15-W16 | 2024-04-12 | 2024-04-20 | 2024-04-20 | 2022-12-01 | 2022-09-19 | 40 | REL | APPR OPND | HB /A /61/HBAA-N-1801 | LOW VOLTAGE SWITCHBOARD |  | C | DKHB-0548 | MEL | DK50 | EL0024
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211522 | 4Y 400V N-SWB HDBE-N-1811 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2022-08-01 | 2022-05-05 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811 | ELECTRICAL SWITCHBOARD |  | C | DKHD-0467 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211522 | 4Y 400V N-SWB HDBE-N-1811 | 400V N-SWB HDBE-N-1811 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2022-08-01 | 2022-05-05 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811 | ELECTRICAL SWITCHBOARD |  | C | DKHD-0467 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211522 | 4Y 400V N-SWB HDBE-N-1811 | 400V N-SWB HDBE-N-1811 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2022-08-01 | 2022-05-05 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811 | ELECTRICAL SWITCHBOARD |  | C | DKHD-0467 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211522 | 4Y 400V N-SWB HDBE-N-1811 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2022-08-01 | 2022-05-05 | 40 | REL | APPR OPND | HD /B /61/HDBE-N-1811 | ELECTRICAL SWITCHBOARD |  | C | DKHD-0467 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211523 | 4Y 400V N-SWB HDBE-N-1811-01 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-01 | COMPT. NO. 01 |  | C | DKHD-0457 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211523 | 4Y 400V N-SWB HDBE-N-1811-01 | 400V N-SWB HDBE-N-1811-01 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 20 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-01 | COMPT. NO. 01 |  | C | DKHD-0457 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211523 | 4Y 400V N-SWB HDBE-N-1811-01 | 400V N-SWB HDBE-N-1811-01 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-08-01 | 2022-05-05 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-01 | COMPT. NO. 01 |  | C | DKHD-0457 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211523 | 4Y 400V N-SWB HDBE-N-1811-01 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-13 | 2022-08-01 | 2022-05-05 | 40 | REL | APPR OPND | HD /B /61/HDBE-N-1811-01 | COMPT. NO. 01 |  | C | DKHD-0457 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211524 | 4Y 400V N-SWB HDBE-N-1811-02 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-02 | COMPT. NO. 02 |  | C | DKHD-0458 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211524 | 4Y 400V N-SWB HDBE-N-1811-02 | 400V N-SWB HDBE-N-1811-02 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 18 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-02 | COMPT. NO. 02 |  | C | DKHD-0458 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211524 | 4Y 400V N-SWB HDBE-N-1811-02 | 400V N-SWB HDBE-N-1811-02 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-08-01 | 2022-05-05 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-02 | COMPT. NO. 02 |  | C | DKHD-0458 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211524 | 4Y 400V N-SWB HDBE-N-1811-02 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-08-01 | 2022-05-05 | 40 | REL | APPR OPND | HD /B /61/HDBE-N-1811-02 | COMPT. NO. 02 |  | C | DKHD-0458 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211525 | 4Y 400V N-SWB HDBE-N-1811-03 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W50 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-03 | COMPT. NO. 03 |  | C | DKHD-0459 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211525 | 4Y 400V N-SWB HDBE-N-1811-03 | 400V N-SWB HDBE-N-1811-03 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 14 | 0 | W50 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-03 | COMPT. NO. 03 |  | C | DKHD-0459 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211525 | 4Y 400V N-SWB HDBE-N-1811-03 | 400V N-SWB HDBE-N-1811-03 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 | W50 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-08-01 | 2022-05-05 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-03 | COMPT. NO. 03 |  | C | DKHD-0459 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211525 | 4Y 400V N-SWB HDBE-N-1811-03 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W50 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-08-01 | 2022-05-05 | 40 | REL | APPR OPND | HD /B /61/HDBE-N-1811-03 | COMPT. NO. 03 |  | C | DKHD-0459 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211526 | 4Y 400V N-SWB HDBE-N-1811-04 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W50 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-04 | COMPT. NO. 04 |  | C | DKHD-0460 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211526 | 4Y 400V N-SWB HDBE-N-1811-04 | 400V N-SWB HDBE-N-1811-04 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 | W50 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-04 | COMPT. NO. 04 |  | C | DKHD-0460 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211526 | 4Y 400V N-SWB HDBE-N-1811-04 | 400V N-SWB HDBE-N-1811-04 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W50 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-04 | COMPT. NO. 04 |  | C | DKHD-0460 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211526 | 4Y 400V N-SWB HDBE-N-1811-04 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W50 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-08-01 | 2022-05-05 | 40 | REL | APPR OPND | HD /B /61/HDBE-N-1811-04 | COMPT. NO. 04 |  | C | DKHD-0460 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211527 | 4Y 400V N-SWB HDBE-N-1811-05 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W50 Caverion | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-05 | COMPT. NO. 05 |  | C | DKHD-0461 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211527 | 4Y 400V N-SWB HDBE-N-1811-05 | 400V N-SWB HDBE-N-1811-05 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 22 | 0 | W50 Caverion | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-05 | COMPT. NO. 05 |  | C | DKHD-0461 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211527 | 4Y 400V N-SWB HDBE-N-1811-05 | 400V N-SWB HDBE-N-1811-05 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 | W50 Caverion | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-08-01 | 2022-05-05 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-05 | COMPT. NO. 05 |  | C | DKHD-0461 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211527 | 4Y 400V N-SWB HDBE-N-1811-05 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W50 Caverion | 2024-03-11 | 2024-03-13 | 2024-03-13 | 2022-08-01 | 2022-05-05 | 40 | REL | APPR OPND | HD /B /61/HDBE-N-1811-05 | COMPT. NO. 05 |  | C | DKHD-0461 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211530 | 4Y 400V N-SWB HDBE-N-1811-08 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W50 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-08 | COMPT. NO. 08 |  | C | DKHD-0464 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211530 | 4Y 400V N-SWB HDBE-N-1811-08 | 400V N-SWB HDBE-N-1811-08 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 10 | 0 | W50 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-08 | COMPT. NO. 08 |  | C | DKHD-0464 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211530 | 4Y 400V N-SWB HDBE-N-1811-08 | 400V N-SWB HDBE-N-1811-08 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 | W50 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-08 | COMPT. NO. 08 |  | C | DKHD-0464 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211530 | 4Y 400V N-SWB HDBE-N-1811-08 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W50 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-08-01 | 2022-05-05 | 40 | REL | APPR OPND | HD /B /61/HDBE-N-1811-08 | COMPT. NO. 08 |  | C | DKHD-0464 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211531 | 4Y 400V N-SWB HDBE-N-1811-09 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-09 | COMPT. NO. 09 |  | C | DKHD-0465 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211531 | 4Y 400V N-SWB HDBE-N-1811-09 | 400V N-SWB HDBE-N-1811-09 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-09 | COMPT. NO. 09 |  | C | DKHD-0465 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211531 | 4Y 400V N-SWB HDBE-N-1811-09 | 400V N-SWB HDBE-N-1811-09 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-09 | COMPT. NO. 09 |  | C | DKHD-0465 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211531 | 4Y 400V N-SWB HDBE-N-1811-09 | STATIC SWITCH INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2022-08-01 | 2022-05-05 | 40 | REL | APPR OPND | HD /B /61/HDBE-N-1811-09 | COMPT. NO. 09 |  | C | DKHD-0465 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211531 | 4Y 400V N-SWB HDBE-N-1811-09 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-13 | 2024-03-13 | 2022-08-01 | 2022-05-05 | 50 | REL | APPR OPND | HD /B /61/HDBE-N-1811-09 | COMPT. NO. 09 |  | C | DKHD-0465 | MEL | DK60 | EL0023
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211533 | 4Y 400V N-SWB MAINT HBB | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W15-W16 | 2024-04-12 | 2024-04-14 | 2024-04-12 | 2022-12-01 | 2022-09-04 | 10 | REL | APPR OPND | HB /B /61/SWITCHBOARDS | SWITCHBOARDS |  | C | DKHB-0550 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211533 | 4Y 400V N-SWB MAINT HBB | 400V N-SWB MAINT HBB | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 24 | 0 | W15-W16 | 2024-04-12 | 2024-04-14 | 2024-04-12 | 2022-12-01 | 2022-09-04 | 20 | REL | APPR OPND | HB /B /61/SWITCHBOARDS | SWITCHBOARDS |  | C | DKHB-0550 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211533 | 4Y 400V N-SWB MAINT HBB | 400V N-SWB MAINT HBB | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 | W15-W16 | 2024-04-12 | 2024-04-14 | 2024-04-13 | 2022-12-01 | 2022-09-04 | 30 | REL | APPR OPND | HB /B /61/SWITCHBOARDS | SWITCHBOARDS |  | C | DKHB-0550 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211533 | 4Y 400V N-SWB MAINT HBB | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W15-W16 | 2024-04-12 | 2024-04-14 | 2024-04-14 | 2022-12-01 | 2022-09-04 | 40 | REL | APPR OPND | HB /B /61/SWITCHBOARDS | SWITCHBOARDS |  | C | DKHB-0550 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211543 | 4Y 690V N-SWB MAINT HBDD-N-1853-A02 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A02 | CUBICLE A02 |  | C | DKHB-0649 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211543 | 4Y 690V N-SWB MAINT HBDD-N-1853-A02 | 690V N-SWB MAINT HBDD-N-1853-A02 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 5 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A02 | CUBICLE A02 |  | C | DKHB-0649 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211543 | 4Y 690V N-SWB MAINT HBDD-N-1853-A02 | 690V N-SWB MAINT HBDD-N-1853-A02 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A02 | CUBICLE A02 |  | C | DKHB-0649 | MEL | DK50 | EL0024
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211543 | 4Y 690V N-SWB MAINT HBDD-N-1853-A02 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W37-38 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-08-01 | 2022-05-05 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A02 | CUBICLE A02 |  | C | DKHB-0649 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211547 | 4Y 690V N-SWB MAINT HBDD-N-1853-B02 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W03 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B02-BA | CUBICLE B02 |  | C | DKHB-0650 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211547 | 4Y 690V N-SWB MAINT HBDD-N-1853-B02 | 690V N-SWB MAINT HBDD-N-1853-B02 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 | W03 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B02-BA | CUBICLE B02 |  | C | DKHB-0650 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400211547 | 4Y 690V N-SWB MAINT HBDD-N-1853-B02 | 690V N-SWB MAINT HBDD-N-1853-B02 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W03 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-08-01 | 2022-05-05 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B02-BA | CUBICLE B02 |  | C | DKHB-0650 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400211547 | 4Y 690V N-SWB MAINT HBDD-N-1853-B02 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W03 Caverion | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2022-08-01 | 2022-05-05 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B02-BA | CUBICLE B02 |  | C | DKHB-0650 | MEL | DK50 | EL0024
0 | A | NOSD | WPM | VEN-INSP | MTN-RIGG | 2400213785 | ILI-PIGGING-RECEIVING_P4302_12"_DFF-HDA | PREPARE-SCAFFOLDING | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 5 | 0 |  | 2024-12-19 | 2025-01-02 | 2024-12-19 | 2022-12-31 | 2022-10-01 | 10 | REL | APPR OPND | HD /A /86/INSP-PIGGING | INSP-SCHEDULING-TAG-PIGGING |  | A | DKPLILI14 | INP | DK60
0 | A | NOSD | WPM | VEN-INSP | MTN-SCAF | 2400213785 | ILI-PIGGING-RECEIVING_P4302_12"_DFF-HDA | INSTALL-SCAFFOLDING | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 50 | 0 |  | 2024-12-19 | 2025-01-02 | 2024-12-19 | 2022-12-31 | 2022-10-01 | 20 | REL | APPR OPND | HD /A /86/INSP-PIGGING | INSP-SCHEDULING-TAG-PIGGING |  | A | DKPLILI14 | INP | DK60
0 | A | NOSD | WPM | VEN-INSP | PRODTECH | 2400213785 | ILI-PIGGING-RECEIVING_P4302_12"_DFF-HDA | PRODUCTION_PIG-RECEIVING | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-12-19 | 2025-01-02 | 2024-12-24 | 2022-12-31 | 2022-10-01 | 30 | REL | APPR OPND | HD /A /86/INSP-PIGGING | INSP-SCHEDULING-TAG-PIGGING |  | A | DKPLILI14 | INP | DK60
0 | A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400213785 | ILI-PIGGING-RECEIVING_P4302_12"_DFF-HDA | CONTRACTOR_PIG-RECEIVING | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 96 | 0 |  | 2024-12-19 | 2025-01-02 | 2024-12-25 | 2022-12-31 | 2022-10-01 | 40 | REL | APPR OPND | HD /A /86/INSP-PIGGING | INSP-SCHEDULING-TAG-PIGGING |  | A | DKPLILI14 | INP | DK60
0 | A | NOSD | WPM | VEN-INSP | MTN-SCAF | 2400213785 | ILI-PIGGING-RECEIVING_P4302_12"_DFF-HDA | REMOVE-SCAFFOLDING | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 30 | 0 |  | 2024-12-19 | 2025-01-02 | 2024-12-30 | 2022-12-31 | 2022-10-01 | 50 | REL | APPR OPND | HD /A /86/INSP-PIGGING | INSP-SCHEDULING-TAG-PIGGING |  | A | DKPLILI14 | INP | DK60
0 | A | NOSD | WPM | VEN-INSP | MTN-RIGG | 2400213785 | ILI-PIGGING-RECEIVING_P4302_12"_DFF-HDA | CLEAN-UP | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 5 | 0 |  | 2024-12-19 | 2025-01-02 | 2025-01-02 | 2022-12-31 | 2022-10-01 | 60 | REL | APPR OPND | HD /A /86/INSP-PIGGING | INSP-SCHEDULING-TAG-PIGGING |  | A | DKPLILI14 | INP | DK60
2024-W25-26 | C | NOSD | WPM | MTN-INST | VEN-INST | 2400220544 | 1Y WCM HBAA-AE-34117 - METERING (VENDOR) | WCM HBAA-AE-34117 - METERING (VENDOR) | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2023-01-11 | 2022-12-06 | 10 | REL | APPR OPND | HB /A /11/HBAA-AE-34117 | BS&W ANALYSER ELEMENT (METERING) |  | A | DKHB-6011 | MIN | DK50 | IN0014
2024-W25-26 | C | NOSD | WPM | MTN-INST | MTN-RIGG | 2400220544 | 1Y WCM HBAA-AE-34117 - METERING (VENDOR) | VENDOR ASISTANCE FOR METERING MAINT | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2023-01-11 | 2022-12-06 | 20 | REL | APPR OPND | HB /A /11/HBAA-AE-34117 | BS&W ANALYSER ELEMENT (METERING) |  | A | DKHB-6011 | MIN | DK50 | IN0014
2024-W25-26 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400220544 | 1Y WCM HBAA-AE-34117 - METERING (VENDOR) | VENDOR ASISTANCE FOR METERING MAINT | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-12 | 2023-01-11 | 2022-12-06 | 30 | REL | APPR OPND | HB /A /11/HBAA-AE-34117 | BS&W ANALYSER ELEMENT (METERING) |  | A | DKHB-6011 | MIN | DK50 | IN0014
2024-W25-26 | C | NOSD | WPM | MTN-INST | MTN-ELEC | 2400220544 | 1Y WCM HBAA-AE-34117 - METERING (VENDOR) | VENDOR ASISTANCE FOR METERING MAINT | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-13 | 2023-01-11 | 2022-12-06 | 40 | REL | APPR OPND | HB /A /11/HBAA-AE-34117 | BS&W ANALYSER ELEMENT (METERING) |  | A | DKHB-6011 | MIN | DK50 | IN0014
2024-W25-26 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400220544 | 1Y WCM HBAA-AE-34117 - METERING (VENDOR) | VENDOR ASISTANCE FOR METERING MAINT | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W25-26 | 2024-03-11 | 2024-03-14 | 2024-03-14 | 2023-01-11 | 2022-12-06 | 60 | REL | APPR OPND | HB /A /11/HBAA-AE-34117 | BS&W ANALYSER ELEMENT (METERING) |  | A | DKHB-6011 | MIN | DK50 | IN0014
2024-W25-26 | C | NOSD | WPM | MTN-INST | VEN-INST | 2400221633 | 1Y HBD OIL EXPORT WCM- METERING (VENDOR) | HBD OIL EXPORT WCM- METERING (VENDOR) | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 | W25-26 | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2023-01-23 | 2022-12-18 | 10 | REL | APPR OPND | HB /D /23/HBDB-AE-365101 | ANALYZER ELEMENT (METERING) |  | A | DKHB-6003 | MIN | DK50 | IN0014
2024-W25-26 | C | NOSD | WPM | MTN-INST | MTN-ELEC | 2400221633 | 1Y HBD OIL EXPORT WCM- METERING (VENDOR) | VENDOR ASISTANCE FOR METERING MAINT | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W25-26 | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2023-01-23 | 2022-12-18 | 20 | REL | APPR OPND | HB /D /23/HBDB-AE-365101 | ANALYZER ELEMENT (METERING) |  | A | DKHB-6003 | MIN | DK50 | IN0014
2024-W25-26 | C | NOSD | WPM | MTN-INST | MTN-RIGG | 2400221633 | 1Y HBD OIL EXPORT WCM- METERING (VENDOR) | VENDOR ASISTANCE FOR METERING MAINT | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 | W25-26 | 2024-03-11 | 2024-03-15 | 2024-03-12 | 2023-01-23 | 2022-12-18 | 30 | REL | APPR OPND | HB /D /23/HBDB-AE-365101 | ANALYZER ELEMENT (METERING) |  | A | DKHB-6003 | MIN | DK50 | IN0014
2024-W25-26 | C | NOSD | WPM | MTN-INST | MTN-MECH | 2400221633 | 1Y HBD OIL EXPORT WCM- METERING (VENDOR) | VENDOR ASISTANCE FOR METERING MAINT | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 | W25-26 | 2024-03-11 | 2024-03-15 | 2024-03-13 | 2023-01-23 | 2022-12-18 | 40 | REL | APPR OPND | HB /D /23/HBDB-AE-365101 | ANALYZER ELEMENT (METERING) |  | A | DKHB-6003 | MIN | DK50 | IN0014
2024-W25-26 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400221633 | 1Y HBD OIL EXPORT WCM- METERING (VENDOR) | VENDOR ASISTANCE FOR METERING MAINT | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W25-26 | 2024-03-11 | 2024-03-15 | 2024-03-14 | 2023-01-23 | 2022-12-18 | 50 | REL | APPR OPND | HB /D /23/HBDB-AE-365101 | ANALYZER ELEMENT (METERING) |  | A | DKHB-6003 | MIN | DK50 | IN0014
0 | D | NOSD | WPM | MTN-MECH | PRODTECH | 2400233037 | 1Y DRAIN CLEANING HDA/HDB | ISOLATION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W43-44 | 2024-03-11 | 2024-03-19 | 2024-03-11 | 2023-03-02 | 2023-01-14 | 9 | REL | APPR OPND | HD /A /28/DRAIN-DISPOSAL | DRAIN DISPOSAL |  | A | DKHD-2036 | MMS | DK60 | FM0023
0 | D | NOSD | WPM | MTN-MECH | VEN-MECH | 2400233037 | 1Y DRAIN CLEANING HDA/HDB | DRAIN CLEANING HDA/HDB | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 144 | 0 | W43-44 | 2024-03-11 | 2024-03-19 | 2024-03-11 | 2023-03-02 | 2023-01-14 | 10 | REL | APPR OPND | HD /A /28/DRAIN-DISPOSAL | DRAIN DISPOSAL |  | A | DKHD-2036 | MMS | DK60 | FM0023
0 | D | NOSD | WPM | MTN-MECH | PRODTECH | 2400233037 | 1Y DRAIN CLEANING HDA/HDB | DE-ISOLATION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W43-44 | 2024-03-11 | 2024-03-19 | 2024-03-19 | 2023-03-02 | 2023-01-14 | 14 | REL | APPR OPND | HD /A /28/DRAIN-DISPOSAL | DRAIN DISPOSAL |  | A | DKHD-2036 | MMS | DK60 | FM0023
2024-W23-24 | C | HBD-GLY | WPM | MTN-MECH | MTN-ELEC | 2400259044 | 6M GLYCOL REG. CHECK - HBDB-A-4160 | GLYCOL REG. CHECK - HBDB-A-4160 | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 4.5 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2023-06-11 | 2023-05-23 | 10 | REL | APPR OPND | HB /D /30/HBDB-A-4160 | GLYCOL REGENERATION PACKAGE |  | C | DKHB-0218 | MMR | DK50 | MR0134 | PROK
2024-W23-24 | C | HBD-GLY | WPM | MTN-MECH | MTN-MECH | 2400259044 | 6M GLYCOL REG. CHECK - HBDB-A-4160 | GLYCOL REG. CHECK - HBDB-A-4160 | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2023-06-11 | 2023-05-23 | 20 | REL | APPR OPND | HB /D /30/HBDB-A-4160 | GLYCOL REGENERATION PACKAGE |  | C | DKHB-0218 | MMR | DK50 | MR0134 | PROK
0 | A | NOSD | WPM | VEN-INSP | PRODTECH | 2400269577 | ILI-PIGGING-RECEIVING_P4303_14"_HBA-HDA | PRODUCTION_PIG-RECEIVING | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 20 | 0 |  | 2024-05-24 | 2024-05-31 | 2024-05-24 | 2024-12-31 | 2024-10-30 | 10 | REL | APPR OPND | HD /A /86/INSP-PIGGING | INSP-SCHEDULING-TAG-PIGGING |  | A | DKPLILI15 | INP | DK60
0 | A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400269577 | ILI-PIGGING-RECEIVING_P4303_14"_HBA-HDA | CONTRACTOR_PIG-RECEIVING | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 96 | 0 |  | 2024-05-24 | 2024-05-31 | 2024-05-26 | 2024-12-31 | 2024-10-30 | 20 | REL | APPR OPND | HD /A /86/INSP-PIGGING | INSP-SCHEDULING-TAG-PIGGING |  | A | DKPLILI15 | INP | DK60
2026-W13-14 | D | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400274727 | 1Y HVAC FUME CUPBRD VENDOR HBDB-X-12418 | HVAC FUME CUPBRD VENDOR HBDB-X-12418 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2023-10-01 | 2023-08-15 | 10 | REL | APPR OPND | HB /D /09/HBDB-X-12418 | FUME CUPBOARD |  | A | DKHB-2012 | MEL | DK50 | EL0014 | PROK
2024-W51-52 | D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400282122 | 2Y REMOTE WELL PANEL MAINT-HBAA-A-3113 | REMOTE WELL PANEL MAINT-HBAA-A-3113 | REL PCNF PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 5 | 1 | 23-W51-52 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-10-27 | 2023-08-15 | 10 | PCNF REL | APPR OPND | HB /A /07/HBAA-A-3113 | WIRELINE REMOTE CONTROL UNIT |  | A | DKHB-2056 | MMS | DK50 | MS0064
2024-W51-52 | D | NOSD | WPM | MTN-MECH | MTN-INST | 2400282122 | 2Y REMOTE WELL PANEL MAINT-HBAA-A-3113 | REMOTE WELL PANEL MAINT-HBAA-A-3113 | REL PCNF PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 3 | 23-W51-52 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-10-27 | 2023-08-15 | 20 | PCNF REL | APPR OPND | HB /A /07/HBAA-A-3113 | WIRELINE REMOTE CONTROL UNIT |  | A | DKHB-2056 | MMS | DK50 | MS0064
2026-W13-14 | C | NOSD | WPM | MTN-INST | VEN-INST | 2400285986 | 1Y OIW ANALYSER - METERING | OIW ANALYSER - METERING | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2023-11-09 | 2023-10-04 | 10 | REL | APPR OPND | HB /D /27/HBDB-AT-507501 | ANALYZ.TRANSM.-OIL IN WATER (METERING) |  | A | DKHB-6006 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | MTN-INST | 2400285986 | 1Y OIW ANALYSER - METERING | VENDOR ASISTANCE FOR METERING MAINT | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-03-11 | 2024-03-14 | 2024-03-12 | 2023-11-09 | 2023-10-04 | 20 | REL | APPR OPND | HB /D /27/HBDB-AT-507501 | ANALYZ.TRANSM.-OIL IN WATER (METERING) |  | A | DKHB-6006 | MIN | DK50 | IN0014
2026-W13-14 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400285986 | 1Y OIW ANALYSER - METERING | VENDOR ASISTANCE FOR METERING MAINT | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-11 | 2024-03-14 | 2024-03-13 | 2023-11-09 | 2023-10-04 | 30 | REL | APPR OPND | HB /D /27/HBDB-AT-507501 | ANALYZ.TRANSM.-OIL IN WATER (METERING) |  | A | DKHB-6006 | MIN | DK50 | IN0014
2024-W51-52 | B | NOSD | WPM | PRODLABO | PRODLABO | 2400294015 | 3M PW SAMPLE F. NORM CON. HBDB-SC-507021 | PW SAMPLE F. NORM CON. HBDB-SC-507021 | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W51-52 | 2023-12-26 | 2023-12-26 | 2023-12-26 | 2024-01-05 | 2023-12-26 | 10 | REL | APPR OPND | HB /D /27/HBDB-SC-507021 | SAMPLE CONNECTION |  | A | DK600008422 | PRD | DK50
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302719 | 2Y 400V N-DP HD SMALL POWER/HT | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0404 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302719 | 2Y 400V N-DP HD SMALL POWER/HT | 400V N-DP HD SMALL POWER/HT INSP | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0404 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400302719 | 2Y 400V N-DP HD SMALL POWER/HT | 400V N-DP HD SMALL POWER/HT INSP | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-02-15 | 2023-12-22 | 30 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0404 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302719 | 2Y 400V N-DP HD SMALL POWER/HT | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-02-15 | 2023-12-22 | 40 | REL | APPR OPND | HD /A /61/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHD-0404 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302720 | 2Y 400V N-DP HD SMALL POWER/HT | 400V N-DP HD SMALL POWER/HT INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4.5 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /B /61/HDBD-DP-1850 | HEAT TRACING POWER DISTRIBUTION BOARD |  | A | DKHD-0456 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400302720 | 2Y 400V N-DP HD SMALL POWER/HT | 400V N-DP HD SMALL POWER/HT INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /B /61/HDBD-DP-1850 | HEAT TRACING POWER DISTRIBUTION BOARD |  | A | DKHD-0456 | MEL | DK60 | EL0023 | PROK
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302721 | 2Y 400V N-SWB HDBE-N-1811-01 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-01 | COMPT. NO. 01 |  | A | DKHD-0457 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302721 | 2Y 400V N-SWB HDBE-N-1811-01 | 400V N-SWB HDBE-N-1811-01 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-01 | COMPT. NO. 01 |  | A | DKHD-0457 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302721 | 2Y 400V N-SWB HDBE-N-1811-01 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-01 | COMPT. NO. 01 |  | A | DKHD-0457 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302722 | 2Y 400V N-SWB HDBE-N-1811-02 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-02 | COMPT. NO. 02 |  | A | DKHD-0458 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302722 | 2Y 400V N-SWB HDBE-N-1811-02 | 400V N-SWB HDBE-N-1811-02 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-02 | COMPT. NO. 02 |  | A | DKHD-0458 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302722 | 2Y 400V N-SWB HDBE-N-1811-02 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-02 | COMPT. NO. 02 |  | A | DKHD-0458 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302723 | 2Y 400V N-SWB HDBE-N-1811-03 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-03 | COMPT. NO. 03 |  | A | DKHD-0459 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302723 | 2Y 400V N-SWB HDBE-N-1811-03 | 400V N-SWB HDBE-N-1811-03 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-03 | COMPT. NO. 03 |  | A | DKHD-0459 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302723 | 2Y 400V N-SWB HDBE-N-1811-03 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-03 | COMPT. NO. 03 |  | A | DKHD-0459 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302724 | 2Y 400V N-SWB HDBE-N-1811-04 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-04 | COMPT. NO. 04 |  | A | DKHD-0460 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302724 | 2Y 400V N-SWB HDBE-N-1811-04 | 400V N-SWB HDBE-N-1811-04 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-04 | COMPT. NO. 04 |  | A | DKHD-0460 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302724 | 2Y 400V N-SWB HDBE-N-1811-04 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-04 | COMPT. NO. 04 |  | A | DKHD-0460 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302725 | 2Y 400V N-SWB HDBE-N-1811-05 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-05 | COMPT. NO. 05 |  | A | DKHD-0461 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302725 | 2Y 400V N-SWB HDBE-N-1811-05 | 400V N-SWB HDBE-N-1811-05 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-05 | COMPT. NO. 05 |  | A | DKHD-0461 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302725 | 2Y 400V N-SWB HDBE-N-1811-05 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-05 | COMPT. NO. 05 |  | A | DKHD-0461 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302726 | 2Y 400V N-SWB HDBE-N-1811-06 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-06 | COMPT. NO. 06 |  | A | DKHD-0462 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302726 | 2Y 400V N-SWB HDBE-N-1811-06 | 400V N-SWB HDBE-N-1811-06 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-06 | COMPT. NO. 06 |  | A | DKHD-0462 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302726 | 2Y 400V N-SWB HDBE-N-1811-06 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-06 | COMPT. NO. 06 |  | A | DKHD-0462 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302727 | 2Y 400V N-SWB HDBE-N-1811-07 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-07 | COMPT. NO. 07 |  | A | DKHD-0463 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302727 | 2Y 400V N-SWB HDBE-N-1811-07 | 400V N-SWB HDBE-N-1811-07 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-07 | COMPT. NO. 07 |  | A | DKHD-0463 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302727 | 2Y 400V N-SWB HDBE-N-1811-07 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-07 | COMPT. NO. 07 |  | A | DKHD-0463 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302728 | 2Y 400V N-SWB HDBE-N-1811-08 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-08 | COMPT. NO. 08 |  | A | DKHD-0464 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302728 | 2Y 400V N-SWB HDBE-N-1811-08 | 400V N-SWB HDBE-N-1811-08 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 7 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-08 | COMPT. NO. 08 |  | A | DKHD-0464 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302728 | 2Y 400V N-SWB HDBE-N-1811-08 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-08 | COMPT. NO. 08 |  | A | DKHD-0464 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302729 | 2Y 400V N-SWB HDBE-N-1811-09 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-09 | COMPT. NO. 09 |  | A | DKHD-0465 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302729 | 2Y 400V N-SWB HDBE-N-1811-09 | 400V N-SWB HDBE-N-1811-09 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-09 | COMPT. NO. 09 |  | A | DKHD-0465 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400302729 | 2Y 400V N-SWB HDBE-N-1811-09 | STATIC SWITCH INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-09 | COMPT. NO. 09 |  | A | DKHD-0465 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302729 | 2Y 400V N-SWB HDBE-N-1811-09 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-27 | 2024-08-27 | 2024-02-15 | 2023-12-22 | 40 | REL | APPR OPND | HD /B /61/HDBE-N-1811-09 | COMPT. NO. 09 |  | A | DKHD-0465 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302730 | 2Y 400V N-SWB HDBE-N-1811-10 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811-10 | COMPT. NO. 10 |  | A | DKHD-0466 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302730 | 2Y 400V N-SWB HDBE-N-1811-10 | 400V N-SWB HDBE-N-1811-10 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811-10 | COMPT. NO. 10 |  | A | DKHD-0466 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302730 | 2Y 400V N-SWB HDBE-N-1811-10 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811-10 | COMPT. NO. 10 |  | A | DKHD-0466 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302731 | 2Y 400V N-SWB HDBE-N-1811 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 10 | REL | APPR OPND | HD /B /61/HDBE-N-1811 | ELECTRICAL SWITCHBOARD |  | A | DKHD-0467 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400302731 | 2Y 400V N-SWB HDBE-N-1811 | 400V N-SWB HDBE-N-1811 INSPECTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 20 | REL | APPR OPND | HD /B /61/HDBE-N-1811 | ELECTRICAL SWITCHBOARD |  | A | DKHD-0467 | MEL | DK60 | EL0023
0 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400302731 | 2Y 400V N-SWB HDBE-N-1811 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-15 | 2023-12-22 | 30 | REL | APPR OPND | HD /B /61/HDBE-N-1811 | ELECTRICAL SWITCHBOARD |  | A | DKHD-0467 | MEL | DK60 | EL0023
0 | D | NOSD | WPM | MTN-MECH | PRODTECH | 2400307688 | 1Y DRAIN CLEANING HDA/HDB | ISOLATION | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-15 | 2024-03-23 | 2024-03-15 | 2024-03-02 | 2024-01-15 | 9 | REL | APPR OPND | HD /A /28/DRAIN-DISPOSAL | DRAIN DISPOSAL |  | A | DKHD-2036 | MMS | DK60 | FM0023
0 | D | NOSD | WPM | MTN-MECH | VEN-MECH | 2400307688 | 1Y DRAIN CLEANING HDA/HDB | DRAIN CLEANING HDA/HDB | REL NMAT PRC SETC | APPR AWSC RDBL | 144 | 0 |  | 2024-03-15 | 2024-03-23 | 2024-03-15 | 2024-03-02 | 2024-01-15 | 10 | REL | APPR OPND | HD /A /28/DRAIN-DISPOSAL | DRAIN DISPOSAL |  | A | DKHD-2036 | MMS | DK60 | FM0023
0 | D | NOSD | WPM | MTN-MECH | PRODTECH | 2400307688 | 1Y DRAIN CLEANING HDA/HDB | DE-ISOLATION | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-15 | 2024-03-23 | 2024-03-23 | 2024-03-02 | 2024-01-15 | 14 | REL | APPR OPND | HD /A /28/DRAIN-DISPOSAL | DRAIN DISPOSAL |  | A | DKHD-2036 | MMS | DK60 | FM0023
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307852 | 2Y 11KV N-SWB MAINT HBDC-N-1851 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | A | DKHB-0509 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400307852 | 2Y 11KV N-SWB MAINT HBDC-N-1851 | 11KV N-SWB MAINT HBDC-N-1851 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | A | DKHB-0509 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307852 | 2Y 11KV N-SWB MAINT HBDC-N-1851 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | A | DKHB-0509 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307853 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K01 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K01 | SPARE VCB FEEDER |  | A | DKHB-0512 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400307853 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K01 | 11KV N-SWB MAINT HBDC-N-1851-K01 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K01 | SPARE VCB FEEDER |  | A | DKHB-0512 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307853 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K01 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K01 | SPARE VCB FEEDER |  | A | DKHB-0512 | MEL | DK50 | EL0024
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307854 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K02 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K02 | TRANSFORMER FEEDER HBDC-TN-1859 |  | A | DKHB-0515 | MEL | DK50 | EL0024 |  | 2024-05-03
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307854 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K02 | 11KV N-SWB MAINT HBDC-N-1851-K02 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K02 | TRANSFORMER FEEDER HBDC-TN-1859 |  | A | DKHB-0515 | MEL | DK50 | EL0024 |  | 2024-05-04
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307854 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K02 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K02 | TRANSFORMER FEEDER HBDC-TN-1859 |  | A | DKHB-0515 | MEL | DK50 | EL0024 |  | 2024-05-05
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307855 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K03 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K03 | TRANSFORMER FEEDER HBDD-TN-1860 |  | A | DKHB-0516 | MEL | DK50 | EL0024 |  | 2024-04-18
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307855 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K03 | 11KV N-SWB MAINT HBDC-N-1851-K03 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K03 | TRANSFORMER FEEDER HBDD-TN-1860 |  | A | DKHB-0516 | MEL | DK50 | EL0024 |  | 2024-04-19
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307855 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K03 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K03 | TRANSFORMER FEEDER HBDD-TN-1860 |  | A | DKHB-0516 | MEL | DK50 | EL0024 |  | 2024-04-21
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307856 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K04 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K04 | TRANSFORMER FEEDER HBDC-TN-1856 |  | A | DKHB-0518 | MEL | DK50 | EL0024 |  | 2024-05-03
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307856 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K04 | 11KV N-SWB MAINT HBDC-N-1851-K04 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K04 | TRANSFORMER FEEDER HBDC-TN-1856 |  | A | DKHB-0518 | MEL | DK50 | EL0024 |  | 2024-05-04
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307856 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K04 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K04 | TRANSFORMER FEEDER HBDC-TN-1856 |  | A | DKHB-0518 | MEL | DK50 | EL0024 |  | 2024-05-05
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307857 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K05 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K05 | INCOMER FROM GENERATOR HBDC-G-1650 |  | A | DKHB-0519 | MEL | DK50 | EL0024 |  | 2024-04-18
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307857 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K05 | 11KV N-SWB MAINT HBDC-N-1851-K05 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2.5 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K05 | INCOMER FROM GENERATOR HBDC-G-1650 |  | A | DKHB-0519 | MEL | DK50 | EL0024 |  | 2024-04-19
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307857 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K05 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K05 | INCOMER FROM GENERATOR HBDC-G-1650 |  | A | DKHB-0519 | MEL | DK50 | EL0024 |  | 2024-04-20
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307858 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K06 | ISOLATION ELECTRICAL | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K06 | K06 BUS MEASURING |  | A | DKHB-0521 | MEL | DK50 | EL0024 | PROK
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307858 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K06 | 11KV N-SWB MAINT HBDC-N-1851-K06 | REL MANC PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K06 | K06 BUS MEASURING |  | A | DKHB-0521 | MEL | DK50 | EL0024 | PROK
2024-W37-38 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307858 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K06 | DE-ISOLATION ELECTRICAL | REL MANC PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-20 | 2024-09-20 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K06 | K06 BUS MEASURING |  | A | DKHB-0521 | MEL | DK50 | EL0024 | PROK
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307859 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K07 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K07 | BUS TIE BREAKER |  | A | DKHB-0522 | MEL | DK50 | EL0024 | PROK | 2024-05-05
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307859 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K07 | 11KV N-SWB MAINT HBDC-N-1851-K07 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K07 | BUS TIE BREAKER |  | A | DKHB-0522 | MEL | DK50 | EL0024 | PROK | 2024-05-06
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307859 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K07 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K07 | BUS TIE BREAKER |  | A | DKHB-0522 | MEL | DK50 | EL0024 | PROK | 2024-05-07
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307860 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K09 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K09 | INCOMER FROM GENERATOR HBDC-G-1660 |  | A | DKHB-0525 | MEL | DK50 | EL0024 |  | 2024-05-01
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307860 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K09 | 11KV N-SWB MAINT HBDC-N-1851-K09 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2.5 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K09 | INCOMER FROM GENERATOR HBDC-G-1660 |  | A | DKHB-0525 | MEL | DK50 | EL0024 |  | 2024-05-02
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307860 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K09 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K09 | INCOMER FROM GENERATOR HBDC-G-1660 |  | A | DKHB-0525 | MEL | DK50 | EL0024 |  | 2024-05-04
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307861 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K10 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K10 | TRANSFORMER FEEDER HBDC-TN-1857 |  | A | DKHB-0526 | MEL | DK50 | EL0024 | PROK | 2024-04-18
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307861 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K10 | 11KV N-SWB MAINT HBDC-N-1851-K10 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 |  | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K10 | TRANSFORMER FEEDER HBDC-TN-1857 |  | A | DKHB-0526 | MEL | DK50 | EL0024 | PROK | 2024-04-19
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307861 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K10 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K10 | TRANSFORMER FEEDER HBDC-TN-1857 |  | A | DKHB-0526 | MEL | DK50 | EL0024 | PROK | 2024-04-20
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307862 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K11 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K11 | TRANSFORMER FEEDER HBDD-TN-1861 |  | A | DKHB-0527 | MEL | DK50 | EL0024 | PROK | 2024-04-18
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307862 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K11 | 11KV N-SWB MAINT HBDC-N-1851-K11 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K11 | TRANSFORMER FEEDER HBDD-TN-1861 |  | A | DKHB-0527 | MEL | DK50 | EL0024 | PROK | 2024-04-19
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307862 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K11 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K11 | TRANSFORMER FEEDER HBDD-TN-1861 |  | A | DKHB-0527 | MEL | DK50 | EL0024 | PROK | 2024-04-20
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307863 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K12 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K12 | TRANSFORMER FEEDER HBDC-TN-1863 |  | A | DKHB-0528 | MEL | DK50 | EL0024 |  | 2024-05-05
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307863 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K12 | 11KV N-SWB MAINT HBDC-N-1851-K12 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K12 | TRANSFORMER FEEDER HBDC-TN-1863 |  | A | DKHB-0528 | MEL | DK50 | EL0024 |  | 2024-05-06
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307863 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K12 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K12 | TRANSFORMER FEEDER HBDC-TN-1863 |  | A | DKHB-0528 | MEL | DK50 | EL0024 |  | 2024-05-07
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307864 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K13 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K13 | TRANSFORMER FEEDER HBDC-TN-1858 |  | A | DKHB-0529 | MEL | DK50 | EL0024 |  | 2024-04-17
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307864 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K13 | 11KV N-SWB MAINT HBDC-N-1851-K13 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K13 | TRANSFORMER FEEDER HBDC-TN-1858 |  | A | DKHB-0529 | MEL | DK50 | EL0024 |  | 2024-04-19
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307864 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K13 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K13 | TRANSFORMER FEEDER HBDC-TN-1858 |  | A | DKHB-0529 | MEL | DK50 | EL0024 |  | 2024-04-20
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307865 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K14 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K14 | SPARE VCB FEEDER |  | A | DKHB-0530 | MEL | DK50 | EL0024 |  | 2024-04-16
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307865 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K14 | 11KV N-SWB MAINT HBDC-N-1851-K14 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2.5 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K14 | SPARE VCB FEEDER |  | A | DKHB-0530 | MEL | DK50 | EL0024 |  | 2024-04-17
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307865 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K14 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K14 | SPARE VCB FEEDER |  | A | DKHB-0530 | MEL | DK50 | EL0024 |  | 2024-04-18
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307866 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K15 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K15 | TRANSFORMER FEEDER HBDC-TN-1879 |  | A | DKHB-0531 | MEL | DK50 | EL0024 |  | 2024-05-03
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307866 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K15 | 11KV N-SWB MAINT HBDC-N-1851-K15 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K15 | TRANSFORMER FEEDER HBDC-TN-1879 |  | A | DKHB-0531 | MEL | DK50 | EL0024 |  | 2024-05-04
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307866 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K15 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K15 | TRANSFORMER FEEDER HBDC-TN-1879 |  | A | DKHB-0531 | MEL | DK50 | EL0024 |  | 2024-05-05
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307867 | 2Y 3KV N-SWB INSP HBDC-N-1852 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | A | DKHB-0543 | MEL | DK50 | EL0024 |  | 2024-05-05
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307867 | 2Y 3KV N-SWB INSP HBDC-N-1852 | 3KV N-SWB INSP HBDC-N-1852 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | A | DKHB-0543 | MEL | DK50 | EL0024 |  | 2024-05-06
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307867 | 2Y 3KV N-SWB INSP HBDC-N-1852 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852 | 3KV MAIN HV SWITCHBOARD |  | A | DKHB-0543 | MEL | DK50 | EL0024 |  | 2024-05-07
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307877 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M10 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M10 | M10 |  | A | DKHB-0560 | MEL | DK50 | EL0024 |  | 2024-04-22
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307877 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M10 | 3KV N-SWB MAINT HBDC-N-1852-M10 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M10 | M10 |  | A | DKHB-0560 | MEL | DK50 | EL0024 |  | 2024-04-23
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307877 | 2Y 3KV N-SWB MAINT HBDC-N-1852-M10 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M10 | M10 |  | A | DKHB-0560 | MEL | DK50 | EL0024 |  | 2024-04-24
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400307885 | 2Y 11/3KV TRAFO MAINT HBDC-TN-1856 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | C | DKHB-0610 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400307885 | 2Y 11/3KV TRAFO MAINT HBDC-TN-1856 | 11/3KV TRAFO MAINT HBDC-TN-1856 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 5 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | C | DKHB-0610 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307885 | 2Y 11/3KV TRAFO MAINT HBDC-TN-1856 | 11/3KV TRAFO MAINT HBDC-TN-1856 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | C | DKHB-0610 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400307885 | 2Y 11/3KV TRAFO MAINT HBDC-TN-1856 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-03-08 | 2024-01-13 | 40 | REL | APPR OPND | HB /D /61/HBDC-TN-1856 | 11/3KV POWER TRANSFORMER |  | C | DKHB-0610 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400307886 | 2Y 11/3KV TRAFO MAINT HBDC-TN-1857 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-TN-1857 | 11/3KV POWER TRANSFORMER |  | C | DKHB-0611 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400307886 | 2Y 11/3KV TRAFO MAINT HBDC-TN-1857 | 11/3KV TRAFO MAINT HBDC-TN-1857 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-TN-1857 | 11/3KV POWER TRANSFORMER |  | C | DKHB-0611 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307886 | 2Y 11/3KV TRAFO MAINT HBDC-TN-1857 | 11/3KV TRAFO MAINT HBDC-TN-1857 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-TN-1857 | 11/3KV POWER TRANSFORMER |  | C | DKHB-0611 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400307886 | 2Y 11/3KV TRAFO MAINT HBDC-TN-1857 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-03-08 | 2024-01-13 | 40 | REL | APPR OPND | HB /D /61/HBDC-TN-1857 | 11/3KV POWER TRANSFORMER |  | C | DKHB-0611 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307887 | 2Y 11/3KV TRAFO MAINT HBDC-TN-1858 | ISOLATION BY ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-TN-1858 | 11/3KV POWER TRANSFORMER |  | C | DKHB-0612 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400307887 | 2Y 11/3KV TRAFO MAINT HBDC-TN-1858 | 11/3KV TRAFO MAINT HBDC-TN-1858 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-TN-1858 | 11/3KV POWER TRANSFORMER |  | C | DKHB-0612 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307887 | 2Y 11/3KV TRAFO MAINT HBDC-TN-1858 | 11/3KV TRAFO MAINT HBDC-TN-1858 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-TN-1858 | 11/3KV POWER TRANSFORMER |  | C | DKHB-0612 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307887 | 2Y 11/3KV TRAFO MAINT HBDC-TN-1858 | DE-ISOLATION BY ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-03-08 | 2024-01-13 | 40 | REL | APPR OPND | HB /D /61/HBDC-TN-1858 | 11/3KV POWER TRANSFORMER |  | C | DKHB-0612 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400307888 | 2Y 11/6KV TRAFO MAINT HBDD-TN-1879 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-TN-1879 | 11/6KV POWER TRANSFORMER |  | C | DKHB-0647 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400307888 | 2Y 11/6KV TRAFO MAINT HBDD-TN-1879 | 11/6KV TRAFO MAINT HBDD-TN-1879 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-TN-1879 | 11/6KV POWER TRANSFORMER |  | C | DKHB-0647 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400307888 | 2Y 11/6KV TRAFO MAINT HBDD-TN-1879 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-TN-1879 | 11/6KV POWER TRANSFORMER |  | C | DKHB-0647 | MEL | DK50 | EL0024
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307889 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K08 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K08 | K08 |  | A | DKHB-0667 | MEL | DK50 | EL0024 |  | 2024-05-10
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307889 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K08 | 11KV N-SWB MAINT HBDC-N-1851-K08 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K08 | K08 |  | A | DKHB-0667 | MEL | DK50 | EL0024 |  | 2024-05-11
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400307889 | 2Y 11KV N-SWB MAINT HBDC-N-1851-K08 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-03-08 | 2024-01-13 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851-K08 | K08 |  | A | DKHB-0667 | MEL | DK50 | EL0024 |  | 2024-05-12
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309045 | 2Y 400V N-SWB INSP HBDD-N-1854 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854 | 400V PROCESS/UTILITY SWITCHBOARD |  | C | DKHB-0580 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309045 | 2Y 400V N-SWB INSP HBDD-N-1854 | 400V N-SWB INSP HBDD-N-1854 | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854 | 400V PROCESS/UTILITY SWITCHBOARD |  | C | DKHB-0580 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309045 | 2Y 400V N-SWB INSP HBDD-N-1854 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854 | 400V PROCESS/UTILITY SWITCHBOARD |  | C | DKHB-0580 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309046 | 2Y 400V N-SWB MAINT HBDD-N-1854-A01 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A01 | CUBICLE A01 |  | A | DKHB-0581 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309046 | 2Y 400V N-SWB MAINT HBDD-N-1854-A01 | 400V N-SWB MAINT HBDD-N-1854-A01 | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A01 | CUBICLE A01 |  | A | DKHB-0581 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309046 | 2Y 400V N-SWB MAINT HBDD-N-1854-A01 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A01 | CUBICLE A01 |  | A | DKHB-0581 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309047 | 2Y 400V N-SWB MAINT HBDD-N-1854-A02 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A02 | CUBICLE A02 |  | C | DKHB-0582 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309047 | 2Y 400V N-SWB MAINT HBDD-N-1854-A02 | 400V N-SWB MAINT HBDD-N-1854-A02 | REL NMAT PRC SETC | APPR AWSC RDBL | 5.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A02 | CUBICLE A02 |  | C | DKHB-0582 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309047 | 2Y 400V N-SWB MAINT HBDD-N-1854-A02 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A02 | CUBICLE A02 |  | C | DKHB-0582 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309048 | 2Y 400V N-SWB MAINT HBDD-N-1854-A03 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A03 | CUBICLE A03 |  | C | DKHB-0583 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309048 | 2Y 400V N-SWB MAINT HBDD-N-1854-A03 | 400V N-SWB MAINT HBDD-N-1854-A03 | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A03 | CUBICLE A03 |  | C | DKHB-0583 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309048 | 2Y 400V N-SWB MAINT HBDD-N-1854-A03 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A03 | CUBICLE A03 |  | C | DKHB-0583 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | HBD-IPHP | WPM | MTN-ELEC | PRODTECH | 2400309049 | 2Y 400V N-SWB MAINT HBDD-N-1854-A04 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A04 | CUBICLE A04 |  | C | DKHB-0584 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | HBD-IPHP | WPM | MTN-ELEC | VEN-ELEC | 2400309049 | 2Y 400V N-SWB MAINT HBDD-N-1854-A04 | 400V N-SWB MAINT HBDD-N-1854-A04 | REL NMAT PRC SETC | APPR AWSC RDBL | 6.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A04 | CUBICLE A04 |  | C | DKHB-0584 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | HBD-IPHP | WPM | MTN-ELEC | PRODTECH | 2400309049 | 2Y 400V N-SWB MAINT HBDD-N-1854-A04 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A04 | CUBICLE A04 |  | C | DKHB-0584 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309050 | 2Y 400V N-SWB MAINT HBDD-N-1854-A05 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-15 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A05 | CUBICLE A05 |  | C | DKHB-0585 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309050 | 2Y 400V N-SWB MAINT HBDD-N-1854-A05 | 400V N-SWB MAINT HBDD-N-1854-A05 | REL NMAT PRC SETC | APPR AWSC RDBL | 9.5 | 0 |  | 2024-03-13 | 2024-03-15 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A05 | CUBICLE A05 |  | C | DKHB-0585 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309050 | 2Y 400V N-SWB MAINT HBDD-N-1854-A05 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-15 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A05 | CUBICLE A05 |  | C | DKHB-0585 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | HB-GEN2 | WPM | MTN-ELEC | PRODTECH | 2400309051 | 2Y 400V N-SWB MAINT HBDD-N-1854-A06 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A06 | CUBICLE A06 |  | C | DKHB-0588 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | HB-GEN2 | WPM | MTN-ELEC | VEN-ELEC | 2400309051 | 2Y 400V N-SWB MAINT HBDD-N-1854-A06 | 400V N-SWB MAINT HBDD-N-1854-A06 | REL NMAT PRC SETC | APPR AWSC RDBL | 6.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A06 | CUBICLE A06 |  | C | DKHB-0588 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | HB-GEN2 | WPM | MTN-ELEC | PRODTECH | 2400309051 | 2Y 400V N-SWB MAINT HBDD-N-1854-A06 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A06 | CUBICLE A06 |  | C | DKHB-0588 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309052 | 2Y 400V N-SWB MAINT HBDD-N-1854-A07 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A07 | CUBICLE A07 |  | C | DKHB-0589 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309052 | 2Y 400V N-SWB MAINT HBDD-N-1854-A07 | 400V N-SWB MAINT HBDD-N-1854-A07 | REL NMAT PRC SETC | APPR AWSC RDBL | 8.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A07 | CUBICLE A07 |  | C | DKHB-0589 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309052 | 2Y 400V N-SWB MAINT HBDD-N-1854-A07 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A07 | CUBICLE A07 |  | C | DKHB-0589 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309053 | 2Y 400V N-SWB MAINT HBDD-N-1854-A08 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A08 | CUBICLE A08 |  | C | DKHB-0590 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309053 | 2Y 400V N-SWB MAINT HBDD-N-1854-A08 | 400V N-SWB MAINT HBDD-N-1854-A08 | REL NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A08 | CUBICLE A08 |  | C | DKHB-0590 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309053 | 2Y 400V N-SWB MAINT HBDD-N-1854-A08 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A08 | CUBICLE A08 |  | C | DKHB-0590 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309054 | 2Y 400V N-SWB MAINT HBDD-N-1854-A09 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A09 | CUBICLE A09 |  | A | DKHB-0591 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309054 | 2Y 400V N-SWB MAINT HBDD-N-1854-A09 | 400V N-SWB MAINT HBDD-N-1854-A09 | REL NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A09 | CUBICLE A09 |  | A | DKHB-0591 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309054 | 2Y 400V N-SWB MAINT HBDD-N-1854-A09 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A09 | CUBICLE A09 |  | A | DKHB-0591 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309055 | 2Y 400V N-SWB MAINT HBDD-N-1854-A10 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A10 | CUBICLE A10 |  | C | DKHB-0592 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309055 | 2Y 400V N-SWB MAINT HBDD-N-1854-A10 | 400V N-SWB MAINT HBDD-N-1854-A10 | REL NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A10 | CUBICLE A10 |  | C | DKHB-0592 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309055 | 2Y 400V N-SWB MAINT HBDD-N-1854-A10 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A10 | CUBICLE A10 |  | C | DKHB-0592 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309056 | 2Y 400V N-SWB MAINT HBDD-N-1854-A11 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A11 | CUBICLE A11 |  | C | DKHB-0593 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309056 | 2Y 400V N-SWB MAINT HBDD-N-1854-A11 | 400V N-SWB MAINT HBDD-N-1854-A11 | REL NMAT PRC SETC | APPR AWSC RDBL | 5.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A11 | CUBICLE A11 |  | C | DKHB-0593 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309056 | 2Y 400V N-SWB MAINT HBDD-N-1854-A11 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A11 | CUBICLE A11 |  | C | DKHB-0593 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309057 | 2Y 400V N-SWB MAINT HBDD-N-1854-A12 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A12 | CUBICLE A12 |  | C | DKHB-0594 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309057 | 2Y 400V N-SWB MAINT HBDD-N-1854-A12 | 400V N-SWB MAINT HBDD-N-1854-A12 | REL NMAT PRC SETC | APPR AWSC RDBL | 3.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A12 | CUBICLE A12 |  | C | DKHB-0594 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309057 | 2Y 400V N-SWB MAINT HBDD-N-1854-A12 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A12 | CUBICLE A12 |  | C | DKHB-0594 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309058 | 2Y 400V N-SWB MAINT HBDD-N-1854-A13 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A13 | CUBICLE A13 |  | C | DKHB-0595 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309058 | 2Y 400V N-SWB MAINT HBDD-N-1854-A13 | 400V N-SWB MAINT HBDD-N-1854-A13 | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A13 | CUBICLE A13 |  | C | DKHB-0595 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309058 | 2Y 400V N-SWB MAINT HBDD-N-1854-A13 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A13 | CUBICLE A13 |  | C | DKHB-0595 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309059 | 2Y 400V N-SWB MAINT HBDD-N-1854-A14 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A14 | CUBICLE A14 |  | C | DKHB-0596 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309059 | 2Y 400V N-SWB MAINT HBDD-N-1854-A14 | 400V N-SWB MAINT HBDD-N-1854-A14 | REL NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A14 | CUBICLE A14 |  | C | DKHB-0596 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309059 | 2Y 400V N-SWB MAINT HBDD-N-1854-A14 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A14 | CUBICLE A14 |  | C | DKHB-0596 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309060 | 2Y 400V N-SWB MAINT HBDD-N-1854-A15 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A15 | CUBICLE A15 |  | A | DKHB-0597 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309060 | 2Y 400V N-SWB MAINT HBDD-N-1854-A15 | 400V N-SWB MAINT HBDD-N-1854-A15 | REL NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A15 | CUBICLE A15 |  | A | DKHB-0597 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309060 | 2Y 400V N-SWB MAINT HBDD-N-1854-A15 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A15 | CUBICLE A15 |  | A | DKHB-0597 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309061 | 2Y 400V N-SWB MAINT HBDD-N-1854-A16 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A16 | CUBICLE A16 |  | C | DKHB-0598 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309061 | 2Y 400V N-SWB MAINT HBDD-N-1854-A16 | 400V N-SWB MAINT HBDD-N-1854-A16 | REL NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A16 | CUBICLE A16 |  | C | DKHB-0598 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309061 | 2Y 400V N-SWB MAINT HBDD-N-1854-A16 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-A16 | CUBICLE A16 |  | C | DKHB-0598 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309062 | 2Y 690V N-SWB MAINT HBDD-N-1853-A04 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A04 | CUBICLE A04 |  | C | DKHB-0606 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309062 | 2Y 690V N-SWB MAINT HBDD-N-1853-A04 | 690V N-SWB MAINT HBDD-N-1853-A04 | REL NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A04 | CUBICLE A04 |  | C | DKHB-0606 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309062 | 2Y 690V N-SWB MAINT HBDD-N-1853-A04 | 690V N-SWB MAINT HBDD-N-1853-A04 | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A04 | CUBICLE A04 |  | C | DKHB-0606 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309062 | 2Y 690V N-SWB MAINT HBDD-N-1853-A04 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A04 | CUBICLE A04 |  | C | DKHB-0606 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309063 | 2Y 690V N-SWB MAINT HBDD-N-1853-B01 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B01 | CUBICLE B01 |  | C | DKHB-0609 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309063 | 2Y 690V N-SWB MAINT HBDD-N-1853-B01 | 690V N-SWB MAINT HBDD-N-1853-B01 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 5 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B01 | CUBICLE B01 |  | C | DKHB-0609 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309063 | 2Y 690V N-SWB MAINT HBDD-N-1853-B01 | 690V N-SWB MAINT HBDD-N-1853-B01 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B01 | CUBICLE B01 |  | C | DKHB-0609 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309063 | 2Y 690V N-SWB MAINT HBDD-N-1853-B01 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-03-23 | 2024-01-28 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B01 | CUBICLE B01 |  | C | DKHB-0609 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309064 | 2Y 690V N-SWB MAINT HBDD-N-1853-B03 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B03_BA | CUBICLE B03 |  | C | DKHB-0621 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309064 | 2Y 690V N-SWB MAINT HBDD-N-1853-B03 | 690V N-SWB MAINT HBDD-N-1853-B03 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 5 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B03_BA | CUBICLE B03 |  | C | DKHB-0621 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309064 | 2Y 690V N-SWB MAINT HBDD-N-1853-B03 | 690V N-SWB MAINT HBDD-N-1853-B03 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B03_BA | CUBICLE B03 |  | C | DKHB-0621 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309064 | 2Y 690V N-SWB MAINT HBDD-N-1853-B03 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-03-23 | 2024-01-28 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B03_BA | CUBICLE B03 |  | C | DKHB-0621 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309065 | 2Y 400V N-SWB MAINT HBDD-N-1854-B01 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B01 | CUBICLE B01 |  | A | DKHB-0623 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309065 | 2Y 400V N-SWB MAINT HBDD-N-1854-B01 | 400V N-SWB MAINT HBDD-N-1854-B01 | REL NMAT PRC SETC | APPR AWSC RDBL | 2.5 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B01 | CUBICLE B01 |  | A | DKHB-0623 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309065 | 2Y 400V N-SWB MAINT HBDD-N-1854-B01 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B01 | CUBICLE B01 |  | A | DKHB-0623 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309066 | 2Y 400V N-SWB MAINT HBDD-N-1854-B02 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B02 | CUBICLE B02 |  | A | DKHB-0624 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309066 | 2Y 400V N-SWB MAINT HBDD-N-1854-B02 | 400V N-SWB MAINT HBDD-N-1854-B02 | REL NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B02 | CUBICLE B02 |  | A | DKHB-0624 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309066 | 2Y 400V N-SWB MAINT HBDD-N-1854-B02 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B02 | CUBICLE B02 |  | A | DKHB-0624 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309067 | 2Y 400V N-SWB MAINT HBDD-N-1854-B03 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B03 | CUBICLE B03 |  | C | DKHB-0625 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309067 | 2Y 400V N-SWB MAINT HBDD-N-1854-B03 | 400V N-SWB MAINT HBDD-N-1854-B03 | REL NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B03 | CUBICLE B03 |  | C | DKHB-0625 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309067 | 2Y 400V N-SWB MAINT HBDD-N-1854-B03 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B03 | CUBICLE B03 |  | C | DKHB-0625 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309068 | 2Y 400V N-SWB MAINT HBDD-N-1854-B04 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B04 | CUBICLE B04 |  | C | DKHB-0626 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309068 | 2Y 400V N-SWB MAINT HBDD-N-1854-B04 | 400V N-SWB MAINT HBDD-N-1854-B04 | REL NMAT PRC SETC | APPR AWSC RDBL | 5.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B04 | CUBICLE B04 |  | C | DKHB-0626 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309068 | 2Y 400V N-SWB MAINT HBDD-N-1854-B04 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B04 | CUBICLE B04 |  | C | DKHB-0626 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309069 | 2Y 400V N-SWB MAINT HBDD-N-1854-B05 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B05 | CUBICLE B05 |  | C | DKHB-0627 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309069 | 2Y 400V N-SWB MAINT HBDD-N-1854-B05 | 400V N-SWB MAINT HBDD-N-1854-B05 | REL NMAT PRC SETC | APPR AWSC RDBL | 6.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B05 | CUBICLE B05 |  | C | DKHB-0627 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309069 | 2Y 400V N-SWB MAINT HBDD-N-1854-B05 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B05 | CUBICLE B05 |  | C | DKHB-0627 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309070 | 2Y 400V N-SWB MAINT HBDD-N-1854-B06 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B06 | CUBICLE B06 |  | C | DKHB-0628 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309070 | 2Y 400V N-SWB MAINT HBDD-N-1854-B06 | 400V N-SWB MAINT HBDD-N-1854-B06 | REL NMAT PRC SETC | APPR AWSC RDBL | 4.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B06 | CUBICLE B06 |  | C | DKHB-0628 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309070 | 2Y 400V N-SWB MAINT HBDD-N-1854-B06 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B06 | CUBICLE B06 |  | C | DKHB-0628 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309071 | 2Y 400V N-SWB MAINT HBDD-N-1854-B07 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B07 | CUBICLE B07 |  | C | DKHB-0638 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309071 | 2Y 400V N-SWB MAINT HBDD-N-1854-B07 | 400V N-SWB MAINT HBDD-N-1854-B07 | REL NMAT PRC SETC | APPR AWSC RDBL | 6.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B07 | CUBICLE B07 |  | C | DKHB-0638 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309071 | 2Y 400V N-SWB MAINT HBDD-N-1854-B07 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B07 | CUBICLE B07 |  | C | DKHB-0638 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | HBD-IPHP | WPM | MTN-ELEC | PRODTECH | 2400309072 | 2Y 400V N-SWB MAINT HBDD-N-1854-B08 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B08 | CUBICLE B08 |  | C | DKHB-0639 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | HBD-IPHP | WPM | MTN-ELEC | VEN-ELEC | 2400309072 | 2Y 400V N-SWB MAINT HBDD-N-1854-B08 | 400V N-SWB MAINT HBDD-N-1854-B08 | REL NMAT PRC SETC | APPR AWSC RDBL | 4.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B08 | CUBICLE B08 |  | C | DKHB-0639 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | HBD-IPHP | WPM | MTN-ELEC | PRODTECH | 2400309072 | 2Y 400V N-SWB MAINT HBDD-N-1854-B08 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B08 | CUBICLE B08 |  | C | DKHB-0639 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309073 | 2Y 400V N-SWB MAINT HBDD-N-1854-B09 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B09 | CUBICLE B09 |  | C | DKHB-0640 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309073 | 2Y 400V N-SWB MAINT HBDD-N-1854-B09 | 400V N-SWB MAINT HBDD-N-1854-B09 | REL NMAT PRC SETC | APPR AWSC RDBL | 8.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B09 | CUBICLE B09 |  | C | DKHB-0640 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309073 | 2Y 400V N-SWB MAINT HBDD-N-1854-B09 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B09 | CUBICLE B09 |  | C | DKHB-0640 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309074 | 2Y 400V N-SWB MAINT HBDD-N-1854-B10 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B10 | CUBICLE B10 |  | C | DKHB-0642 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309074 | 2Y 400V N-SWB MAINT HBDD-N-1854-B10 | 400V N-SWB MAINT HBDD-N-1854-B10 | REL NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B10 | CUBICLE B10 |  | C | DKHB-0642 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309074 | 2Y 400V N-SWB MAINT HBDD-N-1854-B10 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B10 | CUBICLE B10 |  | C | DKHB-0642 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309075 | 2Y 400V N-SWB MAINT HBDD-N-1854-B11 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B11 | CUBICLE B11 |  | C | DKHB-0643 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309075 | 2Y 400V N-SWB MAINT HBDD-N-1854-B11 | 400V N-SWB MAINT HBDD-N-1854-B11 | REL NMAT PRC SETC | APPR AWSC RDBL | 4.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B11 | CUBICLE B11 |  | C | DKHB-0643 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309075 | 2Y 400V N-SWB MAINT HBDD-N-1854-B11 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B11 | CUBICLE B11 |  | C | DKHB-0643 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309076 | 2Y 400V N-SWB MAINT HBDD-N-1854-B12 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B12 | CUBICLE B12 |  | C | DKHB-0644 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309076 | 2Y 400V N-SWB MAINT HBDD-N-1854-B12 | 400V N-SWB MAINT HBDD-N-1854-B12 | REL NMAT PRC SETC | APPR AWSC RDBL | 3.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B12 | CUBICLE B12 |  | C | DKHB-0644 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309076 | 2Y 400V N-SWB MAINT HBDD-N-1854-B12 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B12 | CUBICLE B12 |  | C | DKHB-0644 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309077 | 2Y 400V N-SWB MAINT HBDD-N-1854-B13 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B13 | CUBICLE B13 |  | C | DKHB-0645 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309077 | 2Y 400V N-SWB MAINT HBDD-N-1854-B13 | 400V N-SWB MAINT HBDD-N-1854-B13 | REL NMAT PRC SETC | APPR AWSC RDBL | 3.5 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B13 | CUBICLE B13 |  | C | DKHB-0645 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309077 | 2Y 400V N-SWB MAINT HBDD-N-1854-B13 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B13 | CUBICLE B13 |  | C | DKHB-0645 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309078 | 2Y 400V N-SWB MAINT HBDD-N-1854-B14 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B14 | CUBICLE B14 |  | C | DKHB-0646 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309078 | 2Y 400V N-SWB MAINT HBDD-N-1854-B14 | 400V N-SWB MAINT HBDD-N-1854-B14 | REL NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B14 | CUBICLE B14 |  | C | DKHB-0646 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309078 | 2Y 400V N-SWB MAINT HBDD-N-1854-B14 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1854-B14 | CUBICLE B14 |  | C | DKHB-0646 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309079 | 2Y 690V N-SWB MAINT HBDD-N-1853-B02 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-23 | 2024-01-28 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B02-BA | CUBICLE B02 |  | C | DKHB-0650 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309079 | 2Y 690V N-SWB MAINT HBDD-N-1853-B02 | 690V N-SWB MAINT HBDD-N-1853-B02 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4.5 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-23 | 2024-01-28 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B02-BA | CUBICLE B02 |  | C | DKHB-0650 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309079 | 2Y 690V N-SWB MAINT HBDD-N-1853-B02 | 690V N-SWB MAINT HBDD-N-1853-B02 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-03-23 | 2024-01-28 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B02-BA | CUBICLE B02 |  | C | DKHB-0650 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400309079 | 2Y 690V N-SWB MAINT HBDD-N-1853-B02 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-03-23 | 2024-01-28 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1853-B02-BA | CUBICLE B02 |  | C | DKHB-0650 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | PRODLABO | PRODLABO | 2400314557 | 3M PW SAMPLE F. NORM CON. HBDB-SC-507021 | PW SAMPLE F. NORM CON. HBDB-SC-507021 | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-04-05 | 2024-03-26 | 10 | REL | APPR OPND | HB /D /27/HBDB-SC-507021 | SAMPLE CONNECTION |  | A | DK600008422 | PRD | DK50
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314615 | 2Y 400V E-SWB INSP HBDD-N-1855-A01 | ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A01 | SECTION A01 |  | C | DKHB-0416 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314615 | 2Y 400V E-SWB INSP HBDD-N-1855-A01 | 400V E-SWB INSP HBDD-N-1855-A01 | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A01 | SECTION A01 |  | C | DKHB-0416 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314615 | 2Y 400V E-SWB INSP HBDD-N-1855-A01 | DE-ISOLATION BY PRODUCTION | REL PRT MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A01 | SECTION A01 |  | C | DKHB-0416 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314616 | 2Y 400V E-SWB INSP HBDD-N-1855-A02 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A02 | SECTION A02 |  | C | DKHB-0417 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314616 | 2Y 400V E-SWB INSP HBDD-N-1855-A02 | 400V E-SWB INSP HBDD-N-1855-A02 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A02 | SECTION A02 |  | C | DKHB-0417 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314616 | 2Y 400V E-SWB INSP HBDD-N-1855-A02 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A02 | SECTION A02 |  | C | DKHB-0417 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314617 | 2Y 400V E-SWB INSP HBDD-N-1855-A03 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A03 | SECTION A03 |  | C | DKHB-0418 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314617 | 2Y 400V E-SWB INSP HBDD-N-1855-A03 | 400V E-SWB INSP HBDD-N-1855-A03 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A03 | SECTION A03 |  | C | DKHB-0418 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314617 | 2Y 400V E-SWB INSP HBDD-N-1855-A03 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A03 | SECTION A03 |  | C | DKHB-0418 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314618 | 2Y 400V E-SWB INSP HBDD-N-1855-A04 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A04 | SECTION A04 |  | C | DKHB-0419 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314618 | 2Y 400V E-SWB INSP HBDD-N-1855-A04 | 400V E-SWB INSP HBDD-N-1855-A04 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A04 | SECTION A04 |  | C | DKHB-0419 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314618 | 2Y 400V E-SWB INSP HBDD-N-1855-A04 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A04 | SECTION A04 |  | C | DKHB-0419 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314619 | 2Y 400V E-SWB INSP HBDD-N-1855-A05 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A05 | SECTION A05 |  | C | DKHB-0420 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314619 | 2Y 400V E-SWB INSP HBDD-N-1855-A05 | 400V E-SWB INSP HBDD-N-1855-A05 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A05 | SECTION A05 |  | C | DKHB-0420 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314619 | 2Y 400V E-SWB INSP HBDD-N-1855-A05 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A05 | SECTION A05 |  | C | DKHB-0420 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314620 | 2Y 400V E-SWB INSP HBDD-N-1855-A06 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A06 | SECTION A06 |  | C | DKHB-0421 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314620 | 2Y 400V E-SWB INSP HBDD-N-1855-A06 | 400V E-SWB INSP HBDD-N-1855-A06 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A06 | SECTION A06 |  | C | DKHB-0421 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314620 | 2Y 400V E-SWB INSP HBDD-N-1855-A06 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A06 | SECTION A06 |  | C | DKHB-0421 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314621 | 2Y 400V E-SWB INSP HBDD-N-1855-A08 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A08 | SECTION A08 |  | C | DKHB-0422 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314621 | 2Y 400V E-SWB INSP HBDD-N-1855-A08 | 400V E-SWB INSP HBDD-N-1855-A08 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A08 | SECTION A08 |  | C | DKHB-0422 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314621 | 2Y 400V E-SWB INSP HBDD-N-1855-A08 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A08 | SECTION A08 |  | C | DKHB-0422 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314622 | 2Y 400V E-SWB INSP HBDD-N-1855-A09 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A09 | SECTION A09 |  | C | DKHB-0423 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314622 | 2Y 400V E-SWB INSP HBDD-N-1855-A09 | 400V E-SWB INSP HBDD-N-1855-A09 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A09 | SECTION A09 |  | C | DKHB-0423 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314622 | 2Y 400V E-SWB INSP HBDD-N-1855-A09 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-A09 | SECTION A09 |  | C | DKHB-0423 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314623 | 2Y 400V E-SWB INSP HBDD-N-1855-B01 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B01 | SECTION B01 |  | C | DKHB-0424 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314623 | 2Y 400V E-SWB INSP HBDD-N-1855-B01 | 400V E-SWB INSP HBDD-N-1855-B01 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B01 | SECTION B01 |  | C | DKHB-0424 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314623 | 2Y 400V E-SWB INSP HBDD-N-1855-B01 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B01 | SECTION B01 |  | C | DKHB-0424 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314624 | 2Y 400V E-SWB INSP HBDD-N-1855-B02 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B02 | SECTION B02 |  | C | DKHB-0425 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314624 | 2Y 400V E-SWB INSP HBDD-N-1855-B02 | 400V E-SWB INSP HBDD-N-1855-B02 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B02 | SECTION B02 |  | C | DKHB-0425 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314624 | 2Y 400V E-SWB INSP HBDD-N-1855-B02 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B02 | SECTION B02 |  | C | DKHB-0425 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314625 | 2Y 400V E-SWB INSP HBDD-N-1855-B03 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B03 | SECTION B03 |  | C | DKHB-0426 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314625 | 2Y 400V E-SWB INSP HBDD-N-1855-B03 | 400V E-SWB INSP HBDD-N-1855-B03 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B03 | SECTION B03 |  | C | DKHB-0426 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314625 | 2Y 400V E-SWB INSP HBDD-N-1855-B03 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B03 | SECTION B03 |  | C | DKHB-0426 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314626 | 2Y 400V E-SWB INSP HBDD-N-1855-B04 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B04 | SECTION B04 |  | C | DKHB-0427 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314626 | 2Y 400V E-SWB INSP HBDD-N-1855-B04 | 400V E-SWB INSP HBDD-N-1855-B04 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B04 | SECTION B04 |  | C | DKHB-0427 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314626 | 2Y 400V E-SWB INSP HBDD-N-1855-B04 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B04 | SECTION B04 |  | C | DKHB-0427 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314627 | 2Y 400V E-SWB INSP HBDD-N-1855-B05 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B05 | SECTION B05 |  | C | DKHB-0428 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314627 | 2Y 400V E-SWB INSP HBDD-N-1855-B05 | 400V E-SWB INSP HBDD-N-1855-B05 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B05 | SECTION B05 |  | C | DKHB-0428 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314627 | 2Y 400V E-SWB INSP HBDD-N-1855-B05 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B05 | SECTION B05 |  | C | DKHB-0428 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314628 | 2Y 400V E-SWB INSP HBDD-N-1855-B06 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B06 | SECTION B06 |  | C | DKHB-0429 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314628 | 2Y 400V E-SWB INSP HBDD-N-1855-B06 | 400V E-SWB INSP HBDD-N-1855-B06 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B06 | SECTION B06 |  | C | DKHB-0429 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314628 | 2Y 400V E-SWB INSP HBDD-N-1855-B06 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B06 | SECTION B06 |  | C | DKHB-0429 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314629 | 2Y 400V E-SWB INSP HBDD-N-1855-B07 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B07 | SECTION B07 |  | C | DKHB-0430 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314629 | 2Y 400V E-SWB INSP HBDD-N-1855-B07 | 400V E-SWB INSP HBDD-N-1855-B07 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B07 | SECTION B07 |  | C | DKHB-0430 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314629 | 2Y 400V E-SWB INSP HBDD-N-1855-B07 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B07 | SECTION B07 |  | C | DKHB-0430 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314630 | 2Y 400V E-SWB INSP HBDD-N-1855-B08 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B08 | SECTION B08 |  | C | DKHB-0431 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314630 | 2Y 400V E-SWB INSP HBDD-N-1855-B08 | 400V E-SWB INSP HBDD-N-1855-B08 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B08 | SECTION B08 |  | C | DKHB-0431 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314630 | 2Y 400V E-SWB INSP HBDD-N-1855-B08 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B08 | SECTION B08 |  | C | DKHB-0431 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314631 | 2Y 400V E-SWB INSP HBDD-N-1855-B09 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B09 | SECTION B09 |  | C | DKHB-0432 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314631 | 2Y 400V E-SWB INSP HBDD-N-1855-B09 | 400V E-SWB INSP HBDD-N-1855-B09 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B09 | SECTION B09 |  | C | DKHB-0432 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314631 | 2Y 400V E-SWB INSP HBDD-N-1855-B09 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855-B09 | SECTION B09 |  | C | DKHB-0432 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400314633 | 2Y 690V N-SWB INSP HBDD-N-1853 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-04-07 | 2024-02-12 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1853 | 690V PROCESS/UTILITY SWITCHBOARD |  | C | DKHB-0601 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314633 | 2Y 690V N-SWB INSP HBDD-N-1853 | 690V N-SWB INSP HBDD-N-1853 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-04-07 | 2024-02-12 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1853 | 690V PROCESS/UTILITY SWITCHBOARD |  | C | DKHB-0601 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400314633 | 2Y 690V N-SWB INSP HBDD-N-1853 | 690V N-SWB INSP HBDD-N-1853 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-04-07 | 2024-02-12 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1853 | 690V PROCESS/UTILITY SWITCHBOARD |  | C | DKHB-0601 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400314633 | 2Y 690V N-SWB INSP HBDD-N-1853 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-04-07 | 2024-02-12 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1853 | 690V PROCESS/UTILITY SWITCHBOARD |  | C | DKHB-0601 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400314634 | 2Y 690V N-SWB MAINT HBDD-N-1853-A01 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-04-07 | 2024-02-12 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A01 | CUBICLE A01 |  | C | DKHB-0602 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314634 | 2Y 690V N-SWB MAINT HBDD-N-1853-A01 | 690V N-SWB MAINT HBDD-N-1853-A01 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-04-07 | 2024-02-12 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A01 | CUBICLE A01 |  | C | DKHB-0602 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400314634 | 2Y 690V N-SWB MAINT HBDD-N-1853-A01 | 690V N-SWB MAINT HBDD-N-1853-A01 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-04-07 | 2024-02-12 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A01 | CUBICLE A01 |  | C | DKHB-0602 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400314634 | 2Y 690V N-SWB MAINT HBDD-N-1853-A01 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-04-07 | 2024-02-12 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A01 | CUBICLE A01 |  | C | DKHB-0602 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400314635 | 2Y 690V N-SWB MAINT HBDD-N-1853-A03 | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-04-07 | 2024-02-12 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A03 | CUBICLE A03 |  | C | DKHB-0603 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314635 | 2Y 690V N-SWB MAINT HBDD-N-1853-A03 | 690V N-SWB MAINT HBDD-N-1853-A03 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-04-07 | 2024-02-12 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A03 | CUBICLE A03 |  | C | DKHB-0603 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400314635 | 2Y 690V N-SWB MAINT HBDD-N-1853-A03 | 690V N-SWB MAINT HBDD-N-1853-A03 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-04-07 | 2024-02-12 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A03 | CUBICLE A03 |  | C | DKHB-0603 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400314635 | 2Y 690V N-SWB MAINT HBDD-N-1853-A03 | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-04-07 | 2024-02-12 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A03 | CUBICLE A03 |  | C | DKHB-0603 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314636 | 2Y 690V N-SWB MAINT HBDD-N-1853-A02 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-04-07 | 2024-02-12 | 10 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A02 | CUBICLE A02 |  | C | DKHB-0649 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314636 | 2Y 690V N-SWB MAINT HBDD-N-1853-A02 | 690V N-SWB MAINT HBDD-N-1853-A02 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-04-07 | 2024-02-12 | 20 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A02 | CUBICLE A02 |  | C | DKHB-0649 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400314636 | 2Y 690V N-SWB MAINT HBDD-N-1853-A02 | 690V N-SWB MAINT HBDD-N-1853-A02 | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-04-07 | 2024-02-12 | 30 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A02 | CUBICLE A02 |  | C | DKHB-0649 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314636 | 2Y 690V N-SWB MAINT HBDD-N-1853-A02 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-04-07 | 2024-02-12 | 40 | REL | APPR OPND | HB /D /61/HBDD-N-1853-A02 | CUBICLE A02 |  | C | DKHB-0649 | MEL | DK50 | EL0024
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315850 | 2Y 400V E-DP INSP HBDD-DP-1960-AO2 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-07-01 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO2 | SECTION A02 |  | A | DKHB-0439 | MEL | DK50 | EL0024 |  | 2024-05-06
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315850 | 2Y 400V E-DP INSP HBDD-DP-1960-AO2 | 400V E-DP INSP HBDD-DP-1960-AO2 | REL NMAT PRC SETC | APPR AWSC RDBL | 20 | 0 |  | 2024-06-27 | 2024-07-01 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO2 | SECTION A02 |  | A | DKHB-0439 | MEL | DK50 | EL0024 |  | 2024-05-07
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315850 | 2Y 400V E-DP INSP HBDD-DP-1960-AO2 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-07-01 | 2024-07-01 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO2 | SECTION A02 |  | A | DKHB-0439 | MEL | DK50 | EL0024 |  | 2024-05-10
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315851 | 2Y 400V E-DP HBDD-DP-1960-AO3 INSP | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-06-29 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO3 | SECTION A03 |  | A | DKHB-0440 | MEL | DK50 | EL0024 |  | 2024-04-14
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315851 | 2Y 400V E-DP HBDD-DP-1960-AO3 INSP | 400V E-DP HBDD-DP-1960-AO3 INSP | REL NMAT PRC SETC | APPR AWSC RDBL | 13 | 0 |  | 2024-06-27 | 2024-06-29 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO3 | SECTION A03 |  | A | DKHB-0440 | MEL | DK50 | EL0024 |  | 2024-04-15
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315851 | 2Y 400V E-DP HBDD-DP-1960-AO3 INSP | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-06-29 | 2024-06-29 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO3 | SECTION A03 |  | A | DKHB-0440 | MEL | DK50 | EL0024 |  | 2024-04-17
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315852 | 2Y 400V E-DP INSP HBDD-DP-1960-AO4 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-06-30 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO4 | SECTION A04 |  | A | DKHB-0441 | MEL | DK50 | EL0024 |  | 2024-04-25
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315852 | 2Y 400V E-DP INSP HBDD-DP-1960-AO4 | 400V E-DP INSP HBDD-DP-1960-AO4 | REL NMAT PRC SETC | APPR AWSC RDBL | 15 | 0 |  | 2024-06-27 | 2024-06-30 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO4 | SECTION A04 |  | A | DKHB-0441 | MEL | DK50 | EL0024 |  | 2024-04-26
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315852 | 2Y 400V E-DP INSP HBDD-DP-1960-AO4 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-06-30 | 2024-06-30 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-AO4 | SECTION A04 |  | A | DKHB-0441 | MEL | DK50 | EL0024 |  | 2024-04-28
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315853 | 2Y 400V E-DP INSP HBDD-DP-1960-BO1 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-06-30 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO1 | SECTION B01 |  | A | DKHB-0442 | MEL | DK50 | EL0024 |  | 2024-04-27
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315853 | 2Y 400V E-DP INSP HBDD-DP-1960-BO1 | 400V E-DP INSP HBDD-DP-1960-BO1 | REL NMAT PRC SETC | APPR AWSC RDBL | 15 | 0 |  | 2024-06-27 | 2024-06-30 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO1 | SECTION B01 |  | A | DKHB-0442 | MEL | DK50 | EL0024 |  | 2024-04-28
2024-W17-18 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315853 | 2Y 400V E-DP INSP HBDD-DP-1960-BO1 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-06-30 | 2024-06-30 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO1 | SECTION B01 |  | A | DKHB-0442 | MEL | DK50 | EL0024 |  | 2024-04-30
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315854 | 2Y 400V E-DP INSP HBDD-DP-1960-BO2 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-07-02 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO2 | SECTION B02 |  | A | DKHB-0443 | MEL | DK50 | EL0024 |  | 2024-04-11
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315854 | 2Y 400V E-DP INSP HBDD-DP-1960-BO2 | 400V E-DP INSP HBDD-DP-1960-BO2 | REL NMAT PRC SETC | APPR AWSC RDBL | 24 | 0 |  | 2024-06-27 | 2024-07-02 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO2 | SECTION B02 |  | A | DKHB-0443 | MEL | DK50 | EL0024 |  | 2024-04-12
2024-W15-16 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315854 | 2Y 400V E-DP INSP HBDD-DP-1960-BO2 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-07-02 | 2024-07-02 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO2 | SECTION B02 |  | A | DKHB-0443 | MEL | DK50 | EL0024 |  | 2024-04-16
2024-W15-16 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315855 | 2Y 400V E-DP INSP HBDD-DP-1960-BO3 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-07-07 | 2024-07-12 | 2024-07-07 | 2024-04-22 | 2024-03-07 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO3 | SECTION B03 |  | A | DKHB-0444 | MEL | DK50 | EL0024 |  | 2024-04-08
2024-W15-16 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315855 | 2Y 400V E-DP INSP HBDD-DP-1960-BO3 | 400V E-DP INSP HBDD-DP-1960-BO3 | REL NMAT PRC SETC | APPR AWSC RDBL | 26 | 0 |  | 2024-07-07 | 2024-07-12 | 2024-07-07 | 2024-04-22 | 2024-03-07 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO3 | SECTION B03 |  | A | DKHB-0444 | MEL | DK50 | EL0024 |  | 2024-04-09
2024-W15-16 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315855 | 2Y 400V E-DP INSP HBDD-DP-1960-BO3 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-07-07 | 2024-07-12 | 2024-07-12 | 2024-04-22 | 2024-03-07 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-BO3 | SECTION B03 |  | A | DKHB-0444 | MEL | DK50 | EL0024 |  | 2024-04-13
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315856 | 2Y 400V E-DP INSP HBDD-DP-1960-CO1 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-CO1 | SECTION C01 |  | A | DKHB-0446 | MEL | DK50 | EL0024 |  | 2024-05-12
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315856 | 2Y 400V E-DP INSP HBDD-DP-1960-CO1 | 400V E-DP INSP HBDD-DP-1960-CO1 | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-CO1 | SECTION C01 |  | A | DKHB-0446 | MEL | DK50 | EL0024 |  | 2024-05-13
2024-W19-20 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315856 | 2Y 400V E-DP INSP HBDD-DP-1960-CO1 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-CO1 | SECTION C01 |  | A | DKHB-0446 | MEL | DK50 | EL0024 |  | 2024-05-14
2024-W21-22 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315857 | 2Y 400V E-DP INSP HBDD-DP-1960-CO2 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-06-30 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-CO2 | SECTION C02 |  | A | DKHB-0447 | MEL | DK50 | EL0024 |  | 2024-05-22
2024-W21-22 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315857 | 2Y 400V E-DP INSP HBDD-DP-1960-CO2 | 400V E-DP INSP HBDD-DP-1960-CO2 | REL NMAT PRC SETC | APPR AWSC RDBL | 14 | 0 |  | 2024-06-27 | 2024-06-30 | 2024-06-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-CO2 | SECTION C02 |  | A | DKHB-0447 | MEL | DK50 | EL0024 |  | 2024-05-23
2024-W21-22 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315857 | 2Y 400V E-DP INSP HBDD-DP-1960-CO2 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-06-27 | 2024-06-30 | 2024-06-30 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960-CO2 | SECTION C02 |  | A | DKHB-0447 | MEL | DK50 | EL0024 |  | 2024-05-25
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315861 | 2Y 400V N-DP INSP HBDB-DP-1873 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /61/HBDB-DP-1873 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0630 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400315861 | 2Y 400V N-DP INSP HBDB-DP-1873 | 400V N-DP INSP HBDB-DP-1873 | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /61/HBDB-DP-1873 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0630 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315861 | 2Y 400V N-DP INSP HBDB-DP-1873 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /61/HBDB-DP-1873 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0630 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315862 | 2Y 400V N-DP INSP HBDC-DP-1870 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /61/HBDC-DP-1870 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0631 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400315862 | 2Y 400V N-DP INSP HBDC-DP-1870 | 400V N-DP INSP HBDC-DP-1870 | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /61/HBDC-DP-1870 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0631 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315862 | 2Y 400V N-DP INSP HBDC-DP-1870 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /61/HBDC-DP-1870 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0631 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315863 | 2Y 400V N-DP INSP HBDB-DP-1871/1874 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /61/HBDB-DP-1871 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0632 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400315863 | 2Y 400V N-DP INSP HBDB-DP-1871/1874 | 400V N-DP INSP HBDB-DP-1871/1874 | REL NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /61/HBDB-DP-1871 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0632 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315863 | 2Y 400V N-DP INSP HBDB-DP-1871/1874 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /61/HBDB-DP-1871 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0632 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315864 | 2Y 400V N-DP INSP HBDB-DP-1872 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /61/HBDB-DP-1872 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0633 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400315864 | 2Y 400V N-DP INSP HBDB-DP-1872 | 400V N-DP INSP HBDB-DP-1872 | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /61/HBDB-DP-1872 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0633 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315864 | 2Y 400V N-DP INSP HBDB-DP-1872 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /61/HBDB-DP-1872 | HEAT TRACING DISTRIBUTION BOARD |  | C | DKHB-0633 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315865 | 2Y 400V N-DP INSP HBDE-LP-1805 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /61/HBDE-LP-1805 | LEVEL 4 WORKSHOP POWER DB |  | C | DKHB-0634 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400315865 | 2Y 400V N-DP INSP HBDE-LP-1805 | 400V N-DP INSP HBDE-LP-1805 | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /61/HBDE-LP-1805 | LEVEL 4 WORKSHOP POWER DB |  | C | DKHB-0634 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315865 | 2Y 400V N-DP INSP HBDE-LP-1805 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /61/HBDE-LP-1805 | LEVEL 4 WORKSHOP POWER DB |  | C | DKHB-0634 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315866 | 2Y 400V N-DP INSP HBDD-LP-1802 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /61/HBDD-LP-1802 | LIGHTING & SMALL POWER DISTRIBUTION PANE |  | C | DKHB-0636 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400315866 | 2Y 400V N-DP INSP HBDD-LP-1802 | 400V N-DP INSP HBDD-LP-1802 | REL NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /61/HBDD-LP-1802 | LIGHTING & SMALL POWER DISTRIBUTION PANE |  | C | DKHB-0636 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315866 | 2Y 400V N-DP INSP HBDD-LP-1802 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /61/HBDD-LP-1802 | LIGHTING & SMALL POWER DISTRIBUTION PANE |  | C | DKHB-0636 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315867 | 2Y 400V N-DP INSP HBDC-LP-1804 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /61/HBDC-LP-1804 | LEVEL 2 OFFICE LIGHTING & SMALL POWER |  | C | DKHB-0637 | MEL | DK50 | EL0044
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400315867 | 2Y 400V N-DP INSP HBDC-LP-1804 | 400V N-DP INSP HBDC-LP-1804 | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 20 | REL | APPR OPND | HB /D /61/HBDC-LP-1804 | LEVEL 2 OFFICE LIGHTING & SMALL POWER |  | C | DKHB-0637 | MEL | DK50 | EL0044
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315867 | 2Y 400V N-DP INSP HBDC-LP-1804 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-22 | 2024-02-27 | 30 | REL | APPR OPND | HB /D /61/HBDC-LP-1804 | LEVEL 2 OFFICE LIGHTING & SMALL POWER |  | C | DKHB-0637 | MEL | DK50 | EL0044
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321297 | 2Y 400V UPS-DP INSP. HBCA-DP-1920/21 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-07-22 | 2024-07-25 | 2024-07-22 | 2024-05-07 | 2024-03-22 | 10 | REL | APPR OPND | HB /C /06/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHB-0433 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321297 | 2Y 400V UPS-DP INSP. HBCA-DP-1920/21 | 400V UPS-DP INSP. HBCA-DP-1920/21 | REL NMAT PRC SETC | APPR AWSC RDBL | 24 | 0 |  | 2024-07-22 | 2024-07-25 | 2024-07-22 | 2024-05-07 | 2024-03-22 | 20 | REL | APPR OPND | HB /C /06/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHB-0433 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321297 | 2Y 400V UPS-DP INSP. HBCA-DP-1920/21 | 400V UPS-DP INSP. HBCA-DP-1920/21 | REL NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-07-22 | 2024-07-25 | 2024-07-25 | 2024-05-07 | 2024-03-22 | 30 | REL | APPR OPND | HB /C /06/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHB-0433 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321297 | 2Y 400V UPS-DP INSP. HBCA-DP-1920/21 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-07-22 | 2024-07-25 | 2024-07-25 | 2024-05-07 | 2024-03-22 | 40 | REL | APPR OPND | HB /C /06/DISTRIBUTION-PANELS | DISTRIBUTION PANELS |  | A | DKHB-0433 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321298 | 2Y 3KV N-SWB INSP HBCA-N-1801 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-04-13 | 2024-04-14 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1801 | AUXILIARY 3 KV SWITCHBOARD |  | C | DKHB-0551 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321298 | 2Y 3KV N-SWB INSP HBCA-N-1801 | 3KV N-SWB INSP HBCA-N-1801 | REL NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-04-13 | 2024-04-14 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1801 | AUXILIARY 3 KV SWITCHBOARD |  | C | DKHB-0551 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321298 | 2Y 3KV N-SWB INSP HBCA-N-1801 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-04-13 | 2024-04-14 | 2024-04-14 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1801 | AUXILIARY 3 KV SWITCHBOARD |  | C | DKHB-0551 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321299 | 2Y 3KV N-SWB MAINT HBCA-N-1801-A01 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-04-13 | 2024-04-14 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1801-A01 | FEEDER TO HBCA-TN-1801 3/0.4KV |  | C | DKHB-0553 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321299 | 2Y 3KV N-SWB MAINT HBCA-N-1801-A01 | 3KV N-SWB MAINT HBCA-N-1801-A01 | REL NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-04-13 | 2024-04-14 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1801-A01 | FEEDER TO HBCA-TN-1801 3/0.4KV |  | C | DKHB-0553 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321299 | 2Y 3KV N-SWB MAINT HBCA-N-1801-A01 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-04-13 | 2024-04-14 | 2024-04-14 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1801-A01 | FEEDER TO HBCA-TN-1801 3/0.4KV |  | C | DKHB-0553 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321300 | 2Y 3KV N-SWB MAINT HBCA-N-1801-A02 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-04-13 | 2024-04-14 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1801-A02 | SPARE |  | C | DKHB-0555 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321300 | 2Y 3KV N-SWB MAINT HBCA-N-1801-A02 | 3KV N-SWB MAINT HBCA-N-1801-A02 | REL NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-04-13 | 2024-04-14 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1801-A02 | SPARE |  | C | DKHB-0555 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321300 | 2Y 3KV N-SWB MAINT HBCA-N-1801-A02 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-04-13 | 2024-04-14 | 2024-04-14 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1801-A02 | SPARE |  | C | DKHB-0555 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321301 | 2Y 3KV N-SWB MAINT HBCA-N-1801-A03 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-04-13 | 2024-04-14 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1801-A03 | INCOMER FROM HBDC-TN-1858 11/3KV |  | C | DKHB-0559 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321301 | 2Y 3KV N-SWB MAINT HBCA-N-1801-A03 | 3KV N-SWB MAINT HBCA-N-1801-A03 | REL NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-04-13 | 2024-04-14 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1801-A03 | INCOMER FROM HBDC-TN-1858 11/3KV |  | C | DKHB-0559 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321301 | 2Y 3KV N-SWB MAINT HBCA-N-1801-A03 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-04-13 | 2024-04-14 | 2024-04-14 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1801-A03 | INCOMER FROM HBDC-TN-1858 11/3KV |  | C | DKHB-0559 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321302 | 2Y 400V N-SWB INSP HBCA-N-1810-01 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-01 | SECTION NO.01 |  | C | DKHB-0561 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321302 | 2Y 400V N-SWB INSP HBCA-N-1810-01 | 400V N-SWB INSP HBCA-N-1810-01 | REL NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-01 | SECTION NO.01 |  | C | DKHB-0561 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321302 | 2Y 400V N-SWB INSP HBCA-N-1810-01 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-01 | SECTION NO.01 |  | C | DKHB-0561 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321303 | 2Y 400V N-SWB MAINT HBCA-N-1810-02 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-02 | SECTION NO.02 |  | C | DKHB-0563 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321303 | 2Y 400V N-SWB MAINT HBCA-N-1810-02 | 400V N-SWB MAINT HBCA-N-1810-02 | REL NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-02 | SECTION NO.02 |  | C | DKHB-0563 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321303 | 2Y 400V N-SWB MAINT HBCA-N-1810-02 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-02 | SECTION NO.02 |  | C | DKHB-0563 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321304 | 2Y 400V N-SWB MAINT HBCA-N-1810-03 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-03 | SECTION NO.03 |  | C | DKHB-0565 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321304 | 2Y 400V N-SWB MAINT HBCA-N-1810-03 | 400V N-SWB MAINT HBCA-N-1810-03 | REL NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-03 | SECTION NO.03 |  | C | DKHB-0565 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321304 | 2Y 400V N-SWB MAINT HBCA-N-1810-03 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-03 | SECTION NO.03 |  | C | DKHB-0565 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321305 | 2Y 400V N-SWB MAINT HBCA-N-1810-04 | ISOLATION BY ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-04 | SECTION NO.04 |  | C | DKHB-0573 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321305 | 2Y 400V N-SWB MAINT HBCA-N-1810-04 | 400V N-SWB MAINT HBCA-N-1810-04 | REL NMAT PRC SETC | APPR AWSC RDBL | 2.5 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-04 | SECTION NO.04 |  | C | DKHB-0573 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321305 | 2Y 400V N-SWB MAINT HBCA-N-1810-04 | DE-ISOLATION BY ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-04 | SECTION NO.04 |  | C | DKHB-0573 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321306 | 2Y 400V N-SWB MAINT HBCA-N-1810-05 | ISOLATION BY ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-05 | SECTION NO.05 |  | C | DKHB-0574 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321306 | 2Y 400V N-SWB MAINT HBCA-N-1810-05 | 400V N-SWB MAINT HBCA-N-1810-05 | REL NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-05 | SECTION NO.05 |  | C | DKHB-0574 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321306 | 2Y 400V N-SWB MAINT HBCA-N-1810-05 | DE-ISOLATION BY ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-05 | SECTION NO.05 |  | C | DKHB-0574 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321307 | 2Y 400V N-SWB MAINT HBCA-N-1810-06 | ISOLATION BY ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-13 | 2024-04-13 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-06 | SECTION NO.06 |  | C | DKHB-0575 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321307 | 2Y 400V N-SWB MAINT HBCA-N-1810-06 | 400V N-SWB MAINT HBCA-N-1810-06 | REL NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-04-13 | 2024-04-13 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-06 | SECTION NO.06 |  | C | DKHB-0575 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321307 | 2Y 400V N-SWB MAINT HBCA-N-1810-06 | DE-ISOLATION BY ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-13 | 2024-04-13 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-06 | SECTION NO.06 |  | C | DKHB-0575 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321308 | 2Y 400V N-SWB MAINT HBCA-N-1810-07 | ISOLATION BY ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-13 | 2024-04-13 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-07 | SECTION NO.07 |  | C | DKHB-0576 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321308 | 2Y 400V N-SWB MAINT HBCA-N-1810-07 | 400V N-SWB MAINT HBCA-N-1810-07 | REL NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 |  | 2024-04-13 | 2024-04-13 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-07 | SECTION NO.07 |  | C | DKHB-0576 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321308 | 2Y 400V N-SWB MAINT HBCA-N-1810-07 | DE-ISOLATION BY ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-13 | 2024-04-13 | 2024-04-13 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-07 | SECTION NO.07 |  | C | DKHB-0576 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321309 | 2Y 400V N-SWB MAINT HBCA-N-1810-08 | ISOLATION BY ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-08 | SECTION NO.08 |  | C | DKHB-0577 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321309 | 2Y 400V N-SWB MAINT HBCA-N-1810-08 | 400V N-SWB MAINT HBCA-N-1810-08 | REL NMAT PRC SETC | APPR AWSC RDBL | 3.5 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-08 | SECTION NO.08 |  | C | DKHB-0577 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321309 | 2Y 400V N-SWB MAINT HBCA-N-1810-08 | DE-ISOLATION BY ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-08 | SECTION NO.08 |  | C | DKHB-0577 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321310 | 2Y 400V N-SWB MAINT HBCA-N-1810-09 | ISOLATION BY ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810-09 | SECTION NO.09 |  | C | DKHB-0578 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321310 | 2Y 400V N-SWB MAINT HBCA-N-1810-09 | 400V N-SWB MAINT HBCA-N-1810-09 | REL NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810-09 | SECTION NO.09 |  | C | DKHB-0578 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400321310 | 2Y 400V N-SWB MAINT HBCA-N-1810-09 | DE-ISOLATION BY ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-05-01 | 2024-05-02 | 2024-05-01 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810-09 | SECTION NO.09 |  | C | DKHB-0578 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400321311 | 2Y 400V N-SWB INSP HBCA-N-1810 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 10 | REL | APPR OPND | HB /C /61/HBCA-N-1810 | AUXILIARY UTILITY SWITCHBOARD |  | C | DKHB-0579 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321311 | 2Y 400V N-SWB INSP HBCA-N-1810 | 400V N-SWB INSP HBCA-N-1810 | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 20 | REL | APPR OPND | HB /C /61/HBCA-N-1810 | AUXILIARY UTILITY SWITCHBOARD |  | C | DKHB-0579 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400321311 | 2Y 400V N-SWB INSP HBCA-N-1810 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-05-07 | 2024-03-13 | 30 | REL | APPR OPND | HB /C /61/HBCA-N-1810 | AUXILIARY UTILITY SWITCHBOARD |  | C | DKHB-0579 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322692 | 2Y 400V E-SWB HBCA-N-1840A-04 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-05-22 | 2024-03-28 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-04 | SECTION NO.04 |  | C | DKHB-0399 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322692 | 2Y 400V E-SWB HBCA-N-1840A-04 | 400V E-SWB HBCA-N-1840A-04 INSPECTION | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-05-22 | 2024-03-28 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-04 | SECTION NO.04 |  | C | DKHB-0399 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322692 | 2Y 400V E-SWB HBCA-N-1840A-04 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-05-22 | 2024-03-28 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-04 | SECTION NO.04 |  | C | DKHB-0399 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322693 | 2Y 400V E-SWB INSP HBCA-N-1840A-05 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-06 | 2024-04-07 | 2024-04-06 | 2024-05-22 | 2024-04-06 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-05 | SECTION NO.05 |  | C | DKHB-0400 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322693 | 2Y 400V E-SWB INSP HBCA-N-1840A-05 | 400V E-SWB INSP HBCA-N-1840A-05 | REL NMAT PRC SETC | APPR AWSC RDBL | 9 | 0 |  | 2024-04-06 | 2024-04-07 | 2024-04-06 | 2024-05-22 | 2024-04-06 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-05 | SECTION NO.05 |  | C | DKHB-0400 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322693 | 2Y 400V E-SWB INSP HBCA-N-1840A-05 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-06 | 2024-04-07 | 2024-04-07 | 2024-05-22 | 2024-04-06 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-05 | SECTION NO.05 |  | C | DKHB-0400 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322694 | 2Y 400V E-SWB INSP HBCA-N-1840A-06 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-06 | SECTION NO.06 |  | C | DKHB-0401 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322694 | 2Y 400V E-SWB INSP HBCA-N-1840A-06 | 400V E-SWB INSP HBCA-N-1840A-06 | REL NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-06 | SECTION NO.06 |  | C | DKHB-0401 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322694 | 2Y 400V E-SWB INSP HBCA-N-1840A-06 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-06 | SECTION NO.06 |  | C | DKHB-0401 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322695 | 2Y 400V E-SWB INSP HBCA-N-1840A-07 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-05-22 | 2024-03-28 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-07 | SECTION NO.07 |  | C | DKHB-0402 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322695 | 2Y 400V E-SWB INSP HBCA-N-1840A-07 | 400V E-SWB INSP HBCA-N-1840A-07 | REL NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-05-22 | 2024-03-28 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-07 | SECTION NO.07 |  | C | DKHB-0402 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322695 | 2Y 400V E-SWB INSP HBCA-N-1840A-07 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-05-22 | 2024-03-28 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-07 | SECTION NO.07 |  | C | DKHB-0402 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322696 | 2Y 400V E-SWB INSP HBCA-N-1840A-08 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-08 | SECTION NO.08 |  | C | DKHB-0403 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322696 | 2Y 400V E-SWB INSP HBCA-N-1840A-08 | 400V E-SWB HBCA-N-1840A-08 INSPECTION | REL NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-08 | SECTION NO.08 |  | C | DKHB-0403 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322696 | 2Y 400V E-SWB INSP HBCA-N-1840A-08 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-08 | SECTION NO.08 |  | C | DKHB-0403 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322697 | 2Y 400V E-SWB INSP HBCA-N-1840A-09 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-09 | SECTION NO.09 |  | C | DKHB-0404 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322697 | 2Y 400V E-SWB INSP HBCA-N-1840A-09 | 400V 400V E-SWB INSP HBCA-N-1840A-09 | REL NMAT PRC SETC | APPR AWSC RDBL | 9 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-09 | SECTION NO.09 |  | C | DKHB-0404 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322697 | 2Y 400V E-SWB INSP HBCA-N-1840A-09 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-07 | 2024-05-22 | 2024-04-06 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-09 | SECTION NO.09 |  | C | DKHB-0404 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322698 | 2Y 400V E-SWB INSP HBCA-N-1840A-10 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-10 | SECTION NO.10 |  | C | DKHB-0405 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322698 | 2Y 400V E-SWB INSP HBCA-N-1840A-10 | 400V E-SWB INSP HBCA-N-1840A-10 | REL NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-10 | SECTION NO.10 |  | C | DKHB-0405 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322698 | 2Y 400V E-SWB INSP HBCA-N-1840A-10 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-10 | SECTION NO.10 |  | C | DKHB-0405 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322699 | 2Y 400V E-SWB INSP HBCA-N-1840A-11 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-11 | SECTION NO.11 |  | C | DKHB-0406 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322699 | 2Y 400V E-SWB INSP HBCA-N-1840A-11 | 400V E-SWB INSP HBCA-N-1840A-11 | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-11 | SECTION NO.11 |  | C | DKHB-0406 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322699 | 2Y 400V E-SWB INSP HBCA-N-1840A-11 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-11 | SECTION NO.11 |  | C | DKHB-0406 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322700 | 2Y 400V E-SWB INSP HBCA-N-1840B-01 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-01 | SECTION NO.01 |  | C | DKHB-0407 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322700 | 2Y 400V E-SWB INSP HBCA-N-1840B-01 | 400V E-SWB INSP HBCA-N-1840B-01 | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-01 | SECTION NO.01 |  | C | DKHB-0407 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322700 | 2Y 400V E-SWB INSP HBCA-N-1840B-01 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-01 | SECTION NO.01 |  | C | DKHB-0407 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322701 | 2Y 400V E-SWB INSP HBCA-N-1840B-02 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-02 | SECTION NO.02 |  | C | DKHB-0408 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322701 | 2Y 400V E-SWB INSP HBCA-N-1840B-02 | 400V E-SWB INSP HBCA-N-1840B-02 | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-02 | SECTION NO.02 |  | C | DKHB-0408 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322701 | 2Y 400V E-SWB INSP HBCA-N-1840B-02 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-02 | SECTION NO.02 |  | C | DKHB-0408 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322702 | 2Y 400V E-SWB INSP HBCA-N-1840B-03 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-03 | SECTION NO.03 |  | C | DKHB-0409 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322702 | 2Y 400V E-SWB INSP HBCA-N-1840B-03 | 400V E-SWB INSP HBCA-N-1840B-03 | REL NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-03 | SECTION NO.03 |  | C | DKHB-0409 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322702 | 2Y 400V E-SWB INSP HBCA-N-1840B-03 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840B-03 | SECTION NO.03 |  | C | DKHB-0409 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322707 | 2Y 400V UPS-DP INSP HB | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-08 | 2024-04-11 | 2024-04-08 | 2024-05-22 | 2024-04-06 | 10 | REL | APPR OPND | HB /B /06/UPS-BOARDS-400V | 400V UPS DISTRIBUTION BOARDS |  | A | DKHB-0473 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322707 | 2Y 400V UPS-DP INSP HB | 400V UPS-DP INSP HBB | REL NMAT PRC SETC | APPR AWSC RDBL | 20 | 0 |  | 2024-04-08 | 2024-04-11 | 2024-04-08 | 2024-05-22 | 2024-04-06 | 20 | REL | APPR OPND | HB /B /06/UPS-BOARDS-400V | 400V UPS DISTRIBUTION BOARDS |  | A | DKHB-0473 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322707 | 2Y 400V UPS-DP INSP HB | 400V UPS-DP INSP HBB | REL NMAT PRC SETC | APPR AWSC RDBL | 2.5 | 0 |  | 2024-04-08 | 2024-04-11 | 2024-04-10 | 2024-05-22 | 2024-04-06 | 30 | REL | APPR OPND | HB /B /06/UPS-BOARDS-400V | 400V UPS DISTRIBUTION BOARDS |  | A | DKHB-0473 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322707 | 2Y 400V UPS-DP INSP HB | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-04-08 | 2024-04-11 | 2024-04-11 | 2024-05-22 | 2024-04-06 | 40 | REL | APPR OPND | HB /B /06/UPS-BOARDS-400V | 400V UPS DISTRIBUTION BOARDS |  | A | DKHB-0473 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322708 | 2Y 400V N-SWB MAINT HBB | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W15-W16 | 2024-04-12 | 2024-04-13 | 2024-04-12 | 2024-05-22 | 2024-03-28 | 10 | REL | APPR OPND | HB /B /61/SWITCHBOARDS | SWITCHBOARDS |  | C | DKHB-0550 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322708 | 2Y 400V N-SWB MAINT HBB | 400V N-SWB MAINT HBB | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 12 | 0 | W15-W16 | 2024-04-12 | 2024-04-13 | 2024-04-12 | 2024-05-22 | 2024-03-28 | 20 | REL | APPR OPND | HB /B /61/SWITCHBOARDS | SWITCHBOARDS |  | C | DKHB-0550 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322708 | 2Y 400V N-SWB MAINT HBB | 400V N-SWB MAINT HBB | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 3 | 0 | W15-W16 | 2024-04-12 | 2024-04-13 | 2024-04-13 | 2024-05-22 | 2024-03-28 | 30 | REL | APPR OPND | HB /B /61/SWITCHBOARDS | SWITCHBOARDS |  | C | DKHB-0550 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322708 | 2Y 400V N-SWB MAINT HBB | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 | W15-W16 | 2024-04-12 | 2024-04-13 | 2024-04-13 | 2024-05-22 | 2024-03-28 | 40 | REL | APPR OPND | HB /B /61/SWITCHBOARDS | SWITCHBOARDS |  | C | DKHB-0550 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322709 | 2Y 230V N-DP MAINT HBBA-DP-18777 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-05-22 | 2024-03-28 | 10 | REL | APPR OPND | HB /B /61/HBBA-DP-18777 | DISTRIBUTION PANEL |  | C | DKHB-0669 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322709 | 2Y 230V N-DP MAINT HBBA-DP-18777 | 230V N-DP MAINT HBBA-DP-18777 | REL NMAT PRC SETC | APPR AWSC RDBL | 5.5 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-05-22 | 2024-03-28 | 20 | REL | APPR OPND | HB /B /61/HBBA-DP-18777 | DISTRIBUTION PANEL |  | C | DKHB-0669 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322709 | 2Y 230V N-DP MAINT HBBA-DP-18777 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-29 | 2024-05-22 | 2024-03-28 | 30 | REL | APPR OPND | HB /B /61/HBBA-DP-18777 | DISTRIBUTION PANEL |  | C | DKHB-0669 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322710 | 2Y 230V N-DP MAINT HBBA-DP-18778 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-05-22 | 2024-03-28 | 10 | REL | APPR OPND | HB /B /61/HBBA-DP-18778 | DISTRIBUTION PANEL |  | C | DKHB-0670 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322710 | 2Y 230V N-DP MAINT HBBA-DP-18778 | 230V N-DP MAINT HBBA-DP-18778 | REL NMAT PRC SETC | APPR AWSC RDBL | 5.5 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-05-22 | 2024-03-28 | 20 | REL | APPR OPND | HB /B /61/HBBA-DP-18778 | DISTRIBUTION PANEL |  | C | DKHB-0670 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322710 | 2Y 230V N-DP MAINT HBBA-DP-18778 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWSC RDBL | 1 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-29 | 2024-05-22 | 2024-03-28 | 30 | REL | APPR OPND | HB /B /61/HBBA-DP-18778 | DISTRIBUTION PANEL |  | C | DKHB-0670 | MEL | DK50 | EL0024
2024-W23-24 | C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400329563 | 6M GLYCOL REG. CHECK - HBDB-A-4160 | GLYCOL REG. CHECK - HBDB-A-4160 | REL NMAT PRC SETC | APPR AWSC RDBL | 4.5 | 0 |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-06-11 | 2024-05-23 | 10 | REL | APPR OPND | HB /D /30/HBDB-A-4160 | GLYCOL REGENERATION PACKAGE |  | C | DKHB-0218 | MMR | DK50 | MR0134 | PROK | 2024-05-21
2024-W23-24 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329563 | 6M GLYCOL REG. CHECK - HBDB-A-4160 | GLYCOL REG. CHECK - HBDB-A-4160 | REL NMAT PRC SETC | APPR AWSC RDBL | 4 | 0 |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-06-11 | 2024-05-23 | 20 | REL | APPR OPND | HB /D /30/HBDB-A-4160 | GLYCOL REGENERATION PACKAGE |  | C | DKHB-0218 | MMR | DK50 | MR0134 | PROK | 2024-05-23
2024-W15-16 | B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329570 | 2Y REMOTE WELL PANEL MAINT-HBAA-A-3114 | REMOTE WELL PANEL MAINT-HBAA-A-3114 | REL NMAT PRC SETC | APPR AWSC RDBL | 5 | 0 | W17-W18 | 2024-05-03 | 2024-05-04 | 2024-05-03 | 2024-06-18 | 2024-05-03 | 10 | REL | APPR OPND | HB /A /07/HBAA-A-3114 | WELLHEAD CONTROL PANEL |  | A | DKHB-2060 | MMS | DK50 | MS0064 |  | 2024-04-10
2024-W15-16 | B | NOSD | WPM | MTN-MECH | MTN-INST | 2400329570 | 2Y REMOTE WELL PANEL MAINT-HBAA-A-3114 | REMOTE WELL PANEL MAINT-HBAA-A-3114 | REL NMAT PRC SETC | APPR AWSC RDBL | 1.5 | 0 | W17-W18 | 2024-05-03 | 2024-05-04 | 2024-05-04 | 2024-06-18 | 2024-05-03 | 20 | REL | APPR OPND | HB /A /07/HBAA-A-3114 | WELLHEAD CONTROL PANEL |  | A | DKHB-2060 | MMS | DK50 | MS0064 |  | 2024-04-11
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400329571 | 1Y BRIDGE TROLLEY 10T HBAZ-X-2800 | BRIDGE TROLLEY MAINTENANCE | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2024-06-23 | 2024-05-18 | 10 | REL | APPR OPND | HB /A /78/HBAZ-X-2800 | 10 MT BRIDGE TROLLEY |  | C | DKHB-2074 | MMS | DK50 | MS0154 |  | 2024-04-22
2024-W25-26 | C | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400329571 | 1Y BRIDGE TROLLEY 10T HBAZ-X-2800 | BRIDGE TROLLEY MAINTENANCE | REL MANC NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-09 | 2024-06-23 | 2024-05-18 | 20 | REL | APPR OPND | HB /A /78/HBAZ-X-2800 | 10 MT BRIDGE TROLLEY |  | C | DKHB-2074 | MMS | DK50 | MS0154 |  | 2024-04-23
0 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400329586 | 1Y HP/LP FLAREGAS - CO2 METERING(VENDOR) | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-05-13 | 2024-05-19 | 2024-05-13 | 2024-06-18 | 2024-05-13 | 10 | REL | APPR OPND | HD /A /36/METERING | FLARE AND VENT METERING |  | A | DKHD-6003 | MIN | DK60 | IN0013
0 | C | NOSD | WPM | MTN-INST | MTN-RIGG | 2400329586 | 1Y HP/LP FLAREGAS - CO2 METERING(VENDOR) | METERING SCAFFOLDING | REL NMAT PRC SETC | APPR AWSC RDBL | 8 | 0 |  | 2024-05-13 | 2024-05-19 | 2024-05-13 | 2024-06-18 | 2024-05-13 | 20 | REL | APPR OPND | HD /A /36/METERING | FLARE AND VENT METERING |  | A | DKHD-6003 | MIN | DK60 | IN0013
0 | C | NOSD | WPM | MTN-INST | VEN-INST | 2400329586 | 1Y HP/LP FLAREGAS - CO2 METERING(VENDOR) | 1Y FISCAL METERING MAINTENANCE PROCEDURE | REL NMAT PRC SETC | APPR AWSC RDBL | 40 | 0 |  | 2024-05-13 | 2024-05-19 | 2024-05-14 | 2024-06-18 | 2024-05-13 | 30 | REL | APPR OPND | HD /A /36/METERING | FLARE AND VENT METERING |  | A | DKHD-6003 | MIN | DK60 | IN0013
0 | C | NOSD | WPM | MTN-INST | PRODTECH | 2400329586 | 1Y HP/LP FLAREGAS - CO2 METERING(VENDOR) | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-05-13 | 2024-05-19 | 2024-05-19 | 2024-06-18 | 2024-05-13 | 40 | REL | APPR OPND | HD /A /36/METERING | FLARE AND VENT METERING |  | A | DKHD-6003 | MIN | DK60 | IN0013
2026-W13-14 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400330057 | 1Y SYS 10 INSTR/CHOKE VLV MAINT-HBA | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-05-22 | 2024-05-30 | 2024-05-22 | 2024-06-27 | 2024-05-22 | 10 | REL | APPR OPND | HB /A /10/HC-EXTRACTION-WELLS | HC EXTRACTION WELLS |  | C | DKHB-0184 | MMS | DK50 | MS0074
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400330057 | 1Y SYS 10 INSTR/CHOKE VLV MAINT-HBA | SYS 10 INSTR/CHOKE VLV MAINT-HBA | REL NMAT PRC SETC | APPR AWSC RDBL | 20 | 0 |  | 2024-05-22 | 2024-05-30 | 2024-05-23 | 2024-06-27 | 2024-05-22 | 20 | REL | APPR OPND | HB /A /10/HC-EXTRACTION-WELLS | HC EXTRACTION WELLS |  | C | DKHB-0184 | MMS | DK50 | MS0074
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-INST | 2400330057 | 1Y SYS 10 INSTR/CHOKE VLV MAINT-HBA | SYS 10 INSTR/CHOKE VLV MAINT-HBA | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-05-22 | 2024-05-30 | 2024-05-27 | 2024-06-27 | 2024-05-22 | 30 | REL | APPR OPND | HB /A /10/HC-EXTRACTION-WELLS | HC EXTRACTION WELLS |  | C | DKHB-0184 | MMS | DK50 | MS0074
2026-W13-14 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400330057 | 1Y SYS 10 INSTR/CHOKE VLV MAINT-HBA | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWSC RDBL | 6 | 0 |  | 2024-05-22 | 2024-05-30 | 2024-05-28 | 2024-06-27 | 2024-05-22 | 40 | REL | APPR OPND | HB /A /10/HC-EXTRACTION-WELLS | HC EXTRACTION WELLS |  | C | DKHB-0184 | MMS | DK50 | MS0074
2026-W13-14 | B | NOSD | WPM | PRODLABO | PRODLABO | 2400333115 | 3M PW SAMPLE F. NORM CON. HBDB-SC-507021 | PW SAMPLE F. NORM CON. HBDB-SC-507021 | REL NMAT PRC SETC | APPR AWSC RDBL | 2 | 0 |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-07-05 | 2024-06-25 | 10 | REL | APPR OPND | HB /D /27/HBDB-SC-507021 | SAMPLE CONNECTION |  | A | DK600008422 | PRD | DK50
2026-W13-14 | 3 | HB-DIFF | WDF | MTN-ELEC | PRODTECH | 2100024781 | SMAT:PWR fault on 1851A SCADA RIO | L3 Move all essential equipment to N-185 | REL PRT MANC PRC SETC | APPR AWSC | 5 | 0 | W13 DK50-M-6110 | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2018-10-02 | 2018-08-23 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W13-14 | 3 | HB-DIFF | WDF | MTN-ELEC | MTN-ELEC | 2100024781 | SMAT:PWR fault on 1851A SCADA RIO | L3 Cross ref output signals on remaining | REL PRT MANC PRC SETC | APPR AWSC | 2 | 0 | W13 DK50-M-6110 | 2024-09-18 | 2024-09-21 | 2024-09-19 | 2018-10-02 | 2018-08-23 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W13-14 | 3 | HB-DIFF | WDF | MTN-ELEC | MTN-ELEC | 2100024781 | SMAT:PWR fault on 1851A SCADA RIO | L3 Bridge out the Redundancy module | REL PRT MANC PRC SETC | APPR AWSC | 3 | 0 | W13 DK50-M-6110 | 2024-09-18 | 2024-09-21 | 2024-09-19 | 2018-10-02 | 2018-08-23 | 40 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W13-14 | 3 | HB-DIFF | WDF | MTN-ELEC | MTN-ELEC | 2100024781 | SMAT:PWR fault on 1851A SCADA RIO | L3 Replace Redundancy Module | REL PRT MANC PRC SETC | APPR AWSC | 1 | 0 | W13 DK50-M-6110 | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2018-10-02 | 2018-08-23 | 50 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W13-14 | 3 | HB-DIFF | WDF | MTN-ELEC | MTN-ELEC | 2100024781 | SMAT:PWR fault on 1851A SCADA RIO | L3 Run self test on new Module | REL PRT MANC PRC SETC | APPR AWSC | 1 | 0 | W13 DK50-M-6110 | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2018-10-02 | 2018-08-23 | 60 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W13-14 | 3 | HB-DIFF | WDF | MTN-ELEC | MTN-ELEC | 2100024781 | SMAT:PWR fault on 1851A SCADA RIO | L3 Remove DC Bridge | REL PRT MANC PRC SETC | APPR AWSC | 1 | 0 | W13 DK50-M-6110 | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2018-10-02 | 2018-08-23 | 70 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W13-14 | 3 | HB-DIFF | WDF | MTN-ELEC | PRODTECH | 2100024781 | SMAT:PWR fault on 1851A SCADA RIO | L3 Move essential Equipment back to A si | REL PRT MANC PRC SETC | APPR AWSC | 3 | 0 | W13 DK50-M-6110 | 2024-09-18 | 2024-09-21 | 2024-09-21 | 2018-10-02 | 2018-08-23 | 80 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024757 | Cables in EXD needs to be bonded -> HBBA | Finding powered spare wires | REL PCNF MANC NMAT PPRT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 20 | 0 | W13-W14 | 2024-03-25 | 2024-03-28 | 2024-03-25 | 2022-03-04 | 2020-03-14 | 60 | REL | APPR OPND | HB /B /05/HBBA-N-1812 | EMERGENCY SWITCHBOARD |  | A |  | MEL | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024757 | Cables in EXD needs to be bonded -> HBBA | Disconnect spare wires | REL PCNF MANC NMAT PPRT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 6 | 0 | W13-W14 | 2024-03-25 | 2024-03-28 | 2024-03-27 | 2022-03-04 | 2020-03-14 | 70 | REL | APPR OPND | HB /B /05/HBBA-N-1812 | EMERGENCY SWITCHBOARD |  | A |  | MEL | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024757 | Cables in EXD needs to be bonded -> HBBA | Mount spare wires to ground | REL PCNF MANC NMAT PPRT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 4 | 0 | W13-W14 | 2024-03-25 | 2024-03-28 | 2024-03-27 | 2022-03-04 | 2020-03-14 | 80 | REL | APPR OPND | HB /B /05/HBBA-N-1812 | EMERGENCY SWITCHBOARD |  | A |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100074996 | HBC/78: Replace hydraulic hoses, 7pcs. | Isolate/de-isolate of crane HBCO-A-6101 | REL MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 4 | 0 | W05-W06 | 2024-09-15 | 2024-11-21 | 2024-09-15 | 2023-03-11 | 2022-10-27 | 10 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100074996 | HBC/78: Replace hydraulic hoses, 7pcs. | Measure hydraulic hoses | REL MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 6 | 0 | W05-W06 | 2024-09-15 | 2024-11-21 | 2024-09-16 | 2023-03-11 | 2022-10-27 | 30 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100074996 | HBC/78: Replace hydraulic hoses, 7pcs. | Isolate/de-isolate of crane HBCO-A-6101 | REL MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 4 | 0 | W05-W06 | 2024-09-15 | 2024-11-21 | 2024-11-16 | 2023-03-11 | 2022-10-27 | 40 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100074996 | HBC/78: Replace hydraulic hoses, 7pcs. | Build/demol of scaffold for access | REL MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 24 | 0 | W05-W06 | 2024-09-15 | 2024-11-21 | 2024-11-16 | 2023-03-11 | 2022-10-27 | 50 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100074996 | HBC/78: Replace hydraulic hoses, 7pcs. | Replace hydraulic hoses, 7 pcs | REL MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 15 | 0 | W05-W06 | 2024-09-15 | 2024-11-21 | 2024-11-19 | 2023-03-11 | 2022-10-27 | 60 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100074996 | HBC/78: Replace hydraulic hoses, 7pcs. | Top up oil and test crane | REL MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W05-W06 | 2024-09-15 | 2024-11-21 | 2024-11-20 | 2023-03-11 | 2022-10-27 | 70 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100074996 | HBC/78: Replace hydraulic hoses, 7pcs. | Operation of crane | REL MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W05-W06 | 2024-09-15 | 2024-11-21 | 2024-11-21 | 2023-03-11 | 2022-10-27 | 80 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078739 | HBC/78 Investigation on hydraulic heater | Onshore action | REL PCNF MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 1 | 0 |  | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2023-05-27 | 2023-01-12 | 30 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100079878 | HBD/78: Replace worn hoses inside pedest | Isolation/deisolation of crane | REL PRT MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 1 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-06-16 | 2023-02-01 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100079878 | HBD/78: Replace worn hoses inside pedest | Measuring of hydr. hose acc. attached | REL PRT MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 10 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-06-16 | 2023-02-01 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100079878 | HBD/78: Replace worn hoses inside pedest | Send hose measurment to SR | REL PRT MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 1 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2023-06-16 | 2023-02-01 | 30 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100087427 | HBD/78 Damaged hydraulic hose | Isolate/Deisolate crane | REL PRT MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 2 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-09-08 | 2023-04-26 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100087427 | HBD/78 Damaged hydraulic hose | Measure hose and send info to SR | REL PRT MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 3 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-09-08 | 2023-04-26 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094512 | HBA/78: Sealed roof between HVAC and cra | Sealed roof between HVAC and cranr cabin | REL MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 3 | 0 | W47-48 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-01-01 | 2023-08-19 | 10 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100094512 | HBA/78: Sealed roof between HVAC and cra | Ass. MECH | REL MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 3 | 0 | W47-48 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-01-01 | 2023-08-19 | 20 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106771 | 09-04-2024. Morten Lentz. we have Prefor | Inhibit FSH | REL MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-07-09 | 2024-02-25 | 10 | REL | APPR OPND | HB /C /01/HBCM-FSH-03025 | FLOW SWITCH HIGH |  | A |  | MIN | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106771 | 09-04-2024. Morten Lentz. we have Prefor | Check FSH thread - replace if needed | REL MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 5 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-07-09 | 2024-02-25 | 20 | REL | APPR OPND | HB /C /01/HBCM-FSH-03025 | FLOW SWITCH HIGH |  | A |  | MIN | DK50
2026-W1-2 | 2 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100108176 | HBD/78 Diesel fuel hose/drain fittcorrod | Isolation/deisolation of crane | REL PRT MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-04-11 | 2024-02-26 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 2 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100108176 | HBD/78 Diesel fuel hose/drain fittcorrod | Measurement of hose length/size | REL PRT MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-04-11 | 2024-02-26 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 2 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100108176 | HBD/78 Diesel fuel hose/drain fittcorrod | Ass. MTN-CRAN with ROPE acces | REL PRT MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 4 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-04-11 | 2024-02-26 | 30 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 2 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100108176 | HBD/78 Diesel fuel hose/drain fittcorrod | Send email to SR with need spares | REL PRT MANC NMAT PRC SETC | APPR AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-04-11 | 2024-02-26 | 40 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100054703 | LOTI: HBDC-PSV-396501 External leak from | Isolate and depressurize system | REL MANC PRC SETC | APPR AWDO RFRZ ROUT | 1.5 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2021-12-22 | 2021-09-23 | 10 | REL | APPR OPND | HB /D /75/HBDC-PSV-396501 | PRESSURE SAFETY RELIEF VALVE | 99000121 | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100054703 | LOTI: HBDC-PSV-396501 External leak from | Dismantle seeping PSV | REL MANC PRC SETC | APPR AWDO RFRZ ROUT | 1 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2021-12-22 | 2021-09-23 | 20 | REL | APPR OPND | HB /D /75/HBDC-PSV-396501 | PRESSURE SAFETY RELIEF VALVE | 99000121 | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100054703 | LOTI: HBDC-PSV-396501 External leak from | Install certified PSV | REL MANC PRC SETC | APPR AWDO RFRZ ROUT | 1 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2021-12-22 | 2021-09-23 | 30 | REL | APPR OPND | HB /D /75/HBDC-PSV-396501 | PRESSURE SAFETY RELIEF VALVE | 99000121 | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100054703 | LOTI: HBDC-PSV-396501 External leak from | Pressurize system and test for leakages | REL MANC PRC SETC | APPR AWDO RFRZ ROUT | 1.5 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2021-12-22 | 2021-09-23 | 40 | REL | APPR OPND | HB /D /75/HBDC-PSV-396501 | PRESSURE SAFETY RELIEF VALVE | 99000121 | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | CON-WELD | 2100024378 | FLMR Missing railing HBA-HBD bridge. | Missing railing HBA-HBD bridge | REL NMAT PRC SETC | APPR AWDO RDBL ROUT | 0 | 0 |  | 2021-08-01 | 2021-08-01 | 2021-08-01 | 2020-08-26 | 2020-03-29 | 10 | REL | APPR OPND | HB /A /86/BRIDGE-HBA-HBD | BRIDGE HBA TO HBD | DK0500014733 | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100024378 | FLMR Missing railing HBA-HBD bridge. | Install missing handrail links | REL NMAT PRC SETC | APPR AWDO RDBL ROUT | 4 | 0 |  | 2021-08-01 | 2021-08-01 | 2021-08-01 | 2020-08-26 | 2020-03-29 | 20 | REL | APPR OPND | HB /A /86/BRIDGE-HBA-HBD | BRIDGE HBA TO HBD | DK0500014733 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-CRAN | 2100025886 | ANOS HBA/78: Loose handrails at boom fod | L3 Isolation of HBAB-X-6130 | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 1 | 0 | W01-02 | 2023-04-24 | 2023-06-08 | 2023-04-24 | 2018-01-30 | 2017-12-21 | 9 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100025886 | ANOS HBA/78: Loose handrails at boom fod | L3 Build scaffolding | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 43.6 | 0 | W01-02 | 2023-04-24 | 2023-06-08 | 2023-04-24 | 2018-01-30 | 2017-12-21 | 10 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100025886 | ANOS HBA/78: Loose handrails at boom fod | L3 Build tent for welding of handrails | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 43.6 | 0 |  | 2023-04-24 | 2023-06-08 | 2023-05-03 | 2018-01-30 | 2017-12-21 | 20 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100025886 | ANOS HBA/78: Loose handrails at boom fod | L1 Welding of handrails in both sides | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 30.2 | 0 |  | 2023-04-24 | 2023-06-08 | 2023-05-11 | 2018-01-30 | 2017-12-21 | 30 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100025886 | ANOS HBA/78: Loose handrails at boom fod | L3 Sandblastning and Paint handrails | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 80.4 | 0 |  | 2023-04-24 | 2023-06-08 | 2023-05-14 | 2018-01-30 | 2017-12-21 | 40 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100025886 | ANOS HBA/78: Loose handrails at boom fod | L3 Remove Scaffolding | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 80.4 | 0 |  | 2023-04-24 | 2023-06-08 | 2023-05-23 | 2018-01-30 | 2017-12-21 | 50 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-CRAN | 2100025886 | ANOS HBA/78: Loose handrails at boom fod | L3 De-Isolation of HBAB-X-6130 | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 1 | 0 |  | 2023-04-24 | 2023-06-08 | 2023-06-08 | 2018-01-30 | 2017-12-21 | 60 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | CON-ROPE | 2100040112 | ANOC HBD - Corr Knotted Rope Supports | HBD - Corroded Knotted Rope Supports | REL PCNF NMAT PRC SETC | APPR AWDO RDBL ROUT | 0 | 0 |  | 2021-01-01 | 2021-01-04 | 2021-01-01 | 2021-02-11 | 2020-11-13 | 10 | REL | APPR OPND | HB /D /02/HBDB-KNR-061001 | KNOTTED ROPE (40M) |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040112 | ANOC HBD - Corr Knotted Rope Supports | Set up rope for outboard working | REL PCNF NMAT PRC SETC | APPR AWDO RDBL ROUT | 3 | 1 |  | 2021-01-01 | 2021-01-04 | 2021-01-01 | 2021-02-11 | 2020-11-13 | 20 | PCNF REL | APPR OPND | HB /D /02/HBDB-KNR-061001 | KNOTTED ROPE (40M) |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040112 | ANOC HBD - Corr Knotted Rope Supports | Prep and prime corroded areas | REL PCNF NMAT PRC SETC | APPR AWDO RDBL ROUT | 40 | 15 |  | 2021-01-01 | 2021-01-04 | 2021-01-01 | 2021-02-11 | 2020-11-13 | 30 | PCNF REL | APPR OPND | HB /D /02/HBDB-KNR-061001 | KNOTTED ROPE (40M) |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040112 | ANOC HBD - Corr Knotted Rope Supports | Coat to paint spec | REL PCNF NMAT PRC SETC | APPR AWDO RDBL ROUT | 40 | 33 |  | 2021-01-01 | 2021-01-04 | 2021-01-02 | 2021-02-11 | 2020-11-13 | 40 | PCNF REL | APPR OPND | HB /D /02/HBDB-KNR-061001 | KNOTTED ROPE (40M) |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100040112 | ANOC HBD - Corr Knotted Rope Supports | QC Paint report | REL PCNF NMAT PRC SETC | APPR AWDO RDBL ROUT | 5 | 0 |  | 2021-01-01 | 2021-01-04 | 2021-01-03 | 2021-02-11 | 2020-11-13 | 50 | REL | APPR OPND | HB /D /02/HBDB-KNR-061001 | KNOTTED ROPE (40M) |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040112 | ANOC HBD - Corr Knotted Rope Supports | Derigg ropes | REL PCNF NMAT PRC SETC | APPR AWDO RDBL ROUT | 3 | 6 |  | 2021-01-01 | 2021-01-04 | 2021-01-04 | 2021-02-11 | 2020-11-13 | 60 | PCNF REL | APPR OPND | HB /D /02/HBDB-KNR-061001 | KNOTTED ROPE (40M) |  | A |  | MFM | DK50
0 | 4 | NOSD | WDF | MTN-ROPE | VEN-MECH | 2100043684 | FLMR HDB - Bent retaining bar boatlandin | HDB - Bent retaining bar boatlanding | REL NMAT PRC SETC | APPR AWDO RDBL ROUT | 0 | 0 |  | 2021-03-21 | 2021-03-21 | 2021-03-21 | 2021-08-18 | 2021-03-21 | 10 | REL | APPR OPND | HD /B /86/LADDER | ESCAPE LADDER TO SEA |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100043684 | FLMR HDB - Bent retaining bar boatlandin | Bolt retainer bar back on grating | REL NMAT PRC SETC | APPR AWDO RDBL ROUT | 2 | 0 |  | 2021-03-21 | 2021-03-21 | 2021-03-21 | 2021-08-18 | 2021-03-21 | 20 | REL | APPR OPND | HD /B /86/LADDER | ESCAPE LADDER TO SEA |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061506 | HDB/78: Adjust hoist and lower function | Check correct equipment is delievered | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 1 | 0 |  | 2024-03-28 | 2024-04-02 | 2024-03-28 | 2022-05-08 | 2022-02-07 | 10 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061506 | HDB/78: Adjust hoist and lower function | Measure flow according to attach flow di | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 12 | 0 |  | 2024-03-28 | 2024-04-02 | 2024-03-28 | 2022-05-08 | 2022-02-07 | 20 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100061506 | HDB/78: Adjust hoist and lower function | Assist VEN-CRAN and operating crane | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 12 | 0 |  | 2024-03-28 | 2024-04-02 | 2024-03-28 | 2022-05-08 | 2022-02-07 | 30 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100061506 | HDB/78: Adjust hoist and lower function | Isolate crane HDBR-A-6102 | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 1 | 0 |  | 2024-03-28 | 2024-04-02 | 2024-03-31 | 2022-05-08 | 2022-02-07 | 40 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061506 | HDB/78: Adjust hoist and lower function | Troubleshoot on hoist/lower function | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 12 | 0 |  | 2024-03-28 | 2024-04-02 | 2024-03-31 | 2022-05-08 | 2022-02-07 | 50 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100061506 | HDB/78: Adjust hoist and lower function | De-isolate crane HDBR-A-6102 | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 1 | 0 |  | 2024-03-28 | 2024-04-02 | 2024-04-01 | 2022-05-08 | 2022-02-07 | 60 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061506 | HDB/78: Adjust hoist and lower function | Test and clean-up | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 1 | 0 |  | 2024-03-28 | 2024-04-02 | 2024-04-02 | 2022-05-08 | 2022-02-07 | 70 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100063342 | HBC/78: Dismantle Aux. brake system | Isolate crane HBCO-A-6101 | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-09 | 2023-02-06 | 2022-06-11 | 10 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100063342 | HBC/78: Dismantle Aux. brake system | Dismount hydraulic connections to aux br | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 6 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-09 | 2023-02-06 | 2022-06-11 | 20 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100063342 | HBC/78: Dismantle Aux. brake system | Dismount electrical connections to aux b | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 6 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-09 | 2023-02-06 | 2022-06-11 | 30 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100063342 | HBC/78: Dismantle Aux. brake system | Dismount Aux brakes/man-riding brakes | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 6 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-10 | 2023-02-06 | 2022-06-11 | 40 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100063342 | HBC/78: Dismantle Aux. brake system | De-isolate crane HBCO-A-6101 | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-11 | 2023-02-06 | 2022-06-11 | 50 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100063342 | HBC/78: Dismantle Aux. brake system | Test, inspect for leaks and clean up | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 2 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-11 | 2023-02-06 | 2022-06-11 | 60 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100063342 | HBC/78: Dismantle Aux. brake system | Assist VEN-CRAN and operating crane | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 6 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-11 | 2023-02-06 | 2022-06-11 | 70 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100063342 | HBC/78: Dismantle Aux. brake system | Update drawings and send to crane specia | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 2 | 0 |  | 2024-03-09 | 2024-03-12 | 2024-03-12 | 2023-02-06 | 2022-06-11 | 80 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NE | WDF | MTN-INST | PRODTECH | 2100065402 | Hydraulic weep from ESDV-38504 supply | Production isolation | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 2 | 0 | 24-W03-04 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2022-11-12 | 2022-06-15 | 10 | REL | APPR OPND | HB /B /12/HBBA-ESDV-38504 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | NE | WDF | MTN-INST | MTN-INST | 2100065402 | Hydraulic weep from ESDV-38504 supply | Re-tighten fitting | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 1 | 0 | 24-W03-04 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2022-11-12 | 2022-06-15 | 20 | REL | APPR OPND | HB /B /12/HBBA-ESDV-38504 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 4 | NE | WDF | MTN-INST | PRODTECH | 2100065402 | Hydraulic weep from ESDV-38504 supply | Production deisolation w leak test | REL MANC NMAT PRC SETC | APPR AWDO RDBL ROUT | 2 | 0 | 24-W03-04 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2022-11-12 | 2022-06-15 | 30 | REL | APPR OPND | HB /B /12/HBBA-ESDV-38504 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50 |  | PROK
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | PRODTECH | 2100022753 | CMAT:+Install insulation blanket for tur | L3 Isolate equipment | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-01-29 | 2018-10-31 | 10 | REL | APPR OPND | HB /D /60/HBDC-GT-1650 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | MTN-LAGG | 2100022753 | CMAT:+Install insulation blanket for tur | L3 Remove lagging outside enclosure | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 8.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-01-29 | 2018-10-31 | 15 | REL | APPR OPND | HB /D /60/HBDC-GT-1650 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | MTN-TURB | 2100022753 | CMAT:+Install insulation blanket for tur | L3 Remove temporary insulation plates | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-01-29 | 2018-10-31 | 20 | REL | APPR OPND | HB /D /60/HBDC-GT-1650 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | MTN-TURB | 2100022753 | CMAT:+Install insulation blanket for tur | L3 Install insulation blanket | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2019-01-29 | 2018-10-31 | 25 | REL | APPR OPND | HB /D /60/HBDC-GT-1650 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | VEN-MECH | 2100022753 | CMAT:+Install insulation blanket for tur | L3 Install insulation blanket | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 13 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2019-01-29 | 2018-10-31 | 30 | REL | APPR OPND | HB /D /60/HBDC-GT-1650 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | MTN-LAGG | 2100022753 | CMAT:+Install insulation blanket for tur | L3 Install Lagging outside enclosure | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 8.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-01-29 | 2018-10-31 | 40 | REL | APPR OPND | HB /D /60/HBDC-GT-1650 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | PRODTECH | 2100022753 | CMAT:+Install insulation blanket for tur | L3 Remove isolation | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-01-29 | 2018-10-31 | 50 | REL | APPR OPND | HB /D /60/HBDC-GT-1650 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | PRODTECH | 2100022754 | CMAT:+Install insulation blanket for tur | L3 Isolate equipment | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-01-29 | 2018-10-31 | 10 | REL | APPR OPND | HB /D /60/HBDC-GT-1660 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | MTN-LAGG | 2100022754 | CMAT:+Install insulation blanket for tur | L3 Remove lagging outside enclosure | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 8.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-01-29 | 2018-10-31 | 20 | REL | APPR OPND | HB /D /60/HBDC-GT-1660 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | MTN-TURB | 2100022754 | CMAT:+Install insulation blanket for tur | L3 Remove temporary insulation plates | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-01-29 | 2018-10-31 | 30 | REL | APPR OPND | HB /D /60/HBDC-GT-1660 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | MTN-TURB | 2100022754 | CMAT:+Install insulation blanket for tur | L3 Install insulation blanket | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2019-01-29 | 2018-10-31 | 40 | REL | APPR OPND | HB /D /60/HBDC-GT-1660 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | VEN-MECH | 2100022754 | CMAT:+Install insulation blanket for tur | L3 Install insulation blanket | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 13 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2019-01-29 | 2018-10-31 | 50 | REL | APPR OPND | HB /D /60/HBDC-GT-1660 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | MTN-LAGG | 2100022754 | CMAT:+Install insulation blanket for tur | L3 Install Lagging outside enclosure | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 8.7 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-01-29 | 2018-10-31 | 60 | REL | APPR OPND | HB /D /60/HBDC-GT-1660 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 3 | HB-GEN1 | WDF | MTN-MECH | PRODTECH | 2100022754 | CMAT:+Install insulation blanket for tur | L3 Remove isolation | REL PRT MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-01-29 | 2018-10-31 | 70 | REL | APPR OPND | HB /D /60/HBDC-GT-1660 | GAS TURBINE |  | D |  | MMR | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100026118 | FFSP Replacement of spools in A-0380 | 3D measurement of spools in A-0380 | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 24 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-01 | 2024-07-30 | 2021-03-09 | 2020-03-14 | 10 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID | 99000087 | F |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026118 | FFSP Replacement of spools in A-0380 | Assist vendor with scope | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 6 | 0 | 24-W03-04 | 2024-07-30 | 2024-08-01 | 2024-07-30 | 2021-03-09 | 2020-03-14 | 20 | REL | APPR OPND | HB /D /01/HBDB-A-0380 | DELUGE VALVE SKID | 99000087 | F |  | MFM | DK50
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100031009 | ANOCR Corroded spots on cradle LB2 | Corroded spots on cradle LB2 | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-06-06 | 2023-06-08 | 2023-06-06 | 2021-04-01 | 2020-08-04 | 10 | PCNF REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100031009 | ANOCR Corroded spots on cradle LB2 | Rig up ropes | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 12 |  | 2023-06-06 | 2023-06-08 | 2023-06-06 | 2021-04-01 | 2020-08-04 | 20 | PCNF REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100031009 | ANOCR Corroded spots on cradle LB2 | Needle gun / Bristle blast areas | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 14 | 190 |  | 2023-06-06 | 2023-06-08 | 2023-06-06 | 2021-04-01 | 2020-08-04 | 30 | PCNF REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100031009 | ANOCR Corroded spots on cradle LB2 | Coating Application | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 48 | 6 |  | 2023-06-06 | 2023-06-08 | 2023-06-06 | 2021-04-01 | 2020-08-04 | 40 | PCNF REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100031009 | ANOCR Corroded spots on cradle LB2 | De-Rig Ropes | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2023-06-06 | 2023-06-08 | 2023-06-08 | 2021-04-01 | 2020-08-04 | 50 | PCNF REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100039873 | HDB/78: Faultfinding on Alarm in crane L | Faultfinding in crane cabin VHF/temperat | REL PCNF MANC NMAT PPRT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 | W07-W08 | 2024-09-17 | 2024-09-19 | 2024-09-17 | 2020-11-10 | 2020-10-21 | 10 | PCNF REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-TELE | MTN-ELEC | 2100039873 | HDB/78: Faultfinding on Alarm in crane L | Fault finding on screen bonding/control | REL PCNF MANC NMAT PPRT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-09-17 | 2024-09-19 | 2024-09-17 | 2020-11-10 | 2020-10-21 | 30 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100041328 | ANOV Rep scope after PVI: HBDC-V-3451 | Rep scope after PVI: HBDC-V-3451 | REL MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-28 | 2024-04-26 | 2024-03-28 | 2021-03-10 | 2020-12-10 | 10 | REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | E |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100041328 | ANOV Rep scope after PVI: HBDC-V-3451 | Building of Tent and Scaffolding | REL MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 150 | 0 |  | 2024-03-28 | 2024-04-26 | 2024-03-28 | 2021-03-10 | 2020-12-10 | 30 | REL | APPR OPND | HB /D /20/HBDC-V-3451 | HP SEPARATOR |  | E |  | MFM | DK50
2024-W41-42 | 4 | HBD-IPHP | WDF | MTN-TURB | MTN-TURB | 2100041438 | Replace IS cables in turbine hot end | Replace IS cables in turbine hot end | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-06 | 2021-03-11 | 10 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT | 99000119 | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | VEN-ROPE | 2100044308 | ANOC HBB - Corrosion on Jacket structure | HBB - Corrosion on Jacket structure | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-05-06 | 2021-02-05 | 10 | PCNF REL | APPR OPND | HB /B /86/JACKET - L.A.T. TO EL 19000 | JACKET STRUCTURE ABOVE WATER |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100044308 | ANOC HBB - Corrosion on Jacket structure | Set up Equipment | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 16 | 10 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-05-06 | 2021-02-05 | 20 | PCNF REL | APPR OPND | HB /B /86/JACKET - L.A.T. TO EL 19000 | JACKET STRUCTURE ABOVE WATER |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100044308 | ANOC HBB - Corrosion on Jacket structure | Blast Highlighted areas | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 96 | 96 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-05-06 | 2021-02-05 | 30 | PCNF REL | APPR OPND | HB /B /86/JACKET - L.A.T. TO EL 19000 | JACKET STRUCTURE ABOVE WATER |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100044308 | ANOC HBB - Corrosion on Jacket structure | Coating Application | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 90 | 75 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-05-06 | 2021-02-05 | 40 | PCNF REL | APPR OPND | HB /B /86/JACKET - L.A.T. TO EL 19000 | JACKET STRUCTURE ABOVE WATER |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100044308 | ANOC HBB - Corrosion on Jacket structure | Clean Area | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-05-06 | 2021-02-05 | 50 | PCNF REL | APPR OPND | HB /B /86/JACKET - L.A.T. TO EL 19000 | JACKET STRUCTURE ABOVE WATER |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100057884 | FLMR BA - BB Bridge - Replacement Gratin | BA - BB Bridge - Replacement Grating | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-01-19 | 2022-01-21 | 2022-01-19 | 2022-06-18 | 2022-01-19 | 10 | REL | APPR OPND | HB /A /86/BRIDGE-HBA-HBB | BRIDGE HBA TO HBB |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100057884 | FLMR BA - BB Bridge - Replacement Gratin | Measure grating incl. drawings | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2022-01-19 | 2022-01-21 | 2022-01-19 | 2022-06-18 | 2022-01-19 | 20 | REL | APPR OPND | HB /A /86/BRIDGE-HBA-HBB | BRIDGE HBA TO HBB |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100057884 | FLMR BA - BB Bridge - Replacement Gratin | Order materials | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2022-01-19 | 2022-01-21 | 2022-01-19 | 2022-06-18 | 2022-01-19 | 30 | REL | APPR OPND | HB /A /86/BRIDGE-HBA-HBB | BRIDGE HBA TO HBB |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100057884 | FLMR BA - BB Bridge - Replacement Gratin | Erect scaffold hardbarrier | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2022-01-19 | 2022-01-21 | 2022-01-19 | 2022-06-18 | 2022-01-19 | 40 | REL | APPR OPND | HB /A /86/BRIDGE-HBA-HBB | BRIDGE HBA TO HBB |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100057884 | FLMR BA - BB Bridge - Replacement Gratin | Change gratings | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 14 | 0 |  | 2022-01-19 | 2022-01-21 | 2022-01-20 | 2022-06-18 | 2022-01-19 | 50 | REL | APPR OPND | HB /A /86/BRIDGE-HBA-HBB | BRIDGE HBA TO HBB |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100057884 | FLMR BA - BB Bridge - Replacement Gratin | Demol Scaffold Hardbarrier | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2022-01-19 | 2022-01-21 | 2022-01-20 | 2022-06-18 | 2022-01-19 | 60 | REL | APPR OPND | HB /A /86/BRIDGE-HBA-HBB | BRIDGE HBA TO HBB |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PIPF | MTN-PIPF | 2100057884 | FLMR BA - BB Bridge - Replacement Gratin | Clean worksite | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2022-01-19 | 2022-01-21 | 2022-01-20 | 2022-06-18 | 2022-01-19 | 70 | REL | APPR OPND | HB /A /86/BRIDGE-HBA-HBB | BRIDGE HBA TO HBB |  | A |  | MFM | DK50
2024-W51-52 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100059575 | HBDB-E-5355 - C.M cooler E-5355 needs cl | Mount Platform Scaffold | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 4 | 0 | W51-52 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2022-03-28 | 2021-12-28 | 10 | REL | APPR OPND | HB /D /76/HBDB-E-5355 | COOLING MEDIUM COOLER |  | A |  | MMS | DK50
2024-W51-52 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100059575 | HBDB-E-5355 - C.M cooler E-5355 needs cl | Isolation of Valves And Changeover | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 3 | 0 | W51-52 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2022-03-28 | 2021-12-28 | 20 | REL | APPR OPND | HB /D /76/HBDB-E-5355 | COOLING MEDIUM COOLER |  | A |  | MMS | DK50
2024-W51-52 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100059575 | HBDB-E-5355 - C.M cooler E-5355 needs cl | Dismantle Cooling Plates/Spools | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1.5 | 0 | W51-52 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2022-03-28 | 2021-12-28 | 30 | REL | APPR OPND | HB /D /76/HBDB-E-5355 | COOLING MEDIUM COOLER |  | A |  | MMS | DK50
2024-W51-52 | 3 | NE | WDF | MTN-MECH | MTN-PAIN | 2100059575 | HBDB-E-5355 - C.M cooler E-5355 needs cl | Paint Spools | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 2 | 0 | W51-52 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2022-03-28 | 2021-12-28 | 40 | REL | APPR OPND | HB /D /76/HBDB-E-5355 | COOLING MEDIUM COOLER |  | A |  | MMS | DK50
2024-W51-52 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100059575 | HBDB-E-5355 - C.M cooler E-5355 needs cl | Flush Lines | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1.5 | 0 | W51-52 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2022-03-28 | 2021-12-28 | 50 | REL | APPR OPND | HB /D /76/HBDB-E-5355 | COOLING MEDIUM COOLER |  | A |  | MMS | DK50
2024-W51-52 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100059575 | HBDB-E-5355 - C.M cooler E-5355 needs cl | Assemble Cooling Plates/Spools | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1.5 | 0 | W51-52 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2022-03-28 | 2021-12-28 | 60 | REL | APPR OPND | HB /D /76/HBDB-E-5355 | COOLING MEDIUM COOLER |  | A |  | MMS | DK50
2024-W51-52 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100059575 | HBDB-E-5355 - C.M cooler E-5355 needs cl | De-isolate | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 3 | 0 | W51-52 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2022-03-28 | 2021-12-28 | 70 | REL | APPR OPND | HB /D /76/HBDB-E-5355 | COOLING MEDIUM COOLER |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061497 | HBB/78: Corroded valve block and pips li | HBB/78: Corroted valve block lifting cyl | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-09 | 2024-03-15 | 2024-03-09 | 2022-05-10 | 2022-02-09 | 10 | PCNF REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100061497 | HBB/78: Corroded valve block and pips li | Mechanical prep | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 108 | 0 |  | 2024-03-09 | 2024-03-15 | 2024-03-09 | 2022-05-10 | 2022-02-09 | 30 | PCNF REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100061497 | HBB/78: Corroded valve block and pips li | Coatings | REL PCNF MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 60 | 0 |  | 2024-03-09 | 2024-03-15 | 2024-03-13 | 2022-05-10 | 2022-02-09 | 40 | PCNF REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Prepare for dismount of Aux wire/hook | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 3 | 0 | W20-22 DK50-M-6990 | 2024-05-17 | 2024-10-10 | 2024-05-17 | 2022-03-17 | 2022-02-05 | 6 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Spool of Aux wire onto deck | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 24 | 0 | W20-22 DK50-M-6990 | 2024-05-17 | 2024-10-10 | 2024-05-17 | 2022-03-17 | 2022-02-05 | 7 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Assist with wire handling | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 | W20-22 DK50-M-6990 | 2024-05-17 | 2024-10-10 | 2024-05-17 | 2022-03-17 | 2022-02-05 | 8 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Assist with crane operation | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 | W20-22 DK50-M-6990 | 2024-05-17 | 2024-10-10 | 2024-05-17 | 2022-03-17 | 2022-02-05 | 9 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Isolate/de-isolate of crane HBDE-A-6150 | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 4 | 0 | W20-22 DK50-M-6990 | 2024-05-17 | 2024-10-10 | 2024-05-18 | 2022-03-17 | 2022-02-05 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Build/remove of scaffold/Gallows | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 100 | 0 | W20-22 DK50-M-6990 | 2024-05-17 | 2024-10-10 | 2024-05-19 | 2022-03-17 | 2022-02-05 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Disassembly of Aux winch | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 60 | 0 | W20-22 DK50-M-6990 | 2024-05-17 | 2024-10-10 | 2024-05-26 | 2022-03-17 | 2022-02-05 | 30 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Assist with rigging of winch/parts | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 60 | 0 | W20-22 DK50-M-6990 | 2024-05-17 | 2024-10-10 | 2024-05-26 | 2022-03-17 | 2022-02-05 | 50 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Prepare crane for service | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 | W20-22 DK50-M-6990 | 2024-05-17 | 2024-10-10 | 2024-05-29 | 2022-03-17 | 2022-02-05 | 60 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Back load winch for onshore overhaul | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 | W20-22 DK50-M-6990 | 2024-05-17 | 2024-10-10 | 2024-05-30 | 2022-03-17 | 2022-02-05 | 70 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Isolate/de-isolate of crane HBDE-A-6150 | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-17 | 2024-10-10 | 2024-09-27 | 2022-03-17 | 2022-02-05 | 80 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Build/remove of scaffold/Gallows | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 50 | 0 |  | 2024-05-17 | 2024-10-10 | 2024-09-28 | 2022-03-17 | 2022-02-05 | 90 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Installation of Aux winch | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 60 | 0 |  | 2024-05-17 | 2024-10-10 | 2024-10-02 | 2022-03-17 | 2022-02-05 | 100 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Assist with rigging of Winch/parts | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 60 | 0 |  | 2024-05-17 | 2024-10-10 | 2024-10-02 | 2022-03-17 | 2022-02-05 | 110 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Function test of aux winch | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-05-17 | 2024-10-10 | 2024-10-05 | 2022-03-17 | 2022-02-05 | 130 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Install Aux wire/hook | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2024-05-17 | 2024-10-10 | 2024-10-05 | 2022-03-17 | 2022-02-05 | 140 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Assist with crane operation | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-05-17 | 2024-10-10 | 2024-10-06 | 2022-03-17 | 2022-02-05 | 150 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Assist with wire handling | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-05-17 | 2024-10-10 | 2024-10-05 | 2022-03-17 | 2022-02-05 | 160 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Perform proof laod test of aux winch | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2024-05-17 | 2024-10-10 | 2024-10-07 | 2022-03-17 | 2022-02-05 | 170 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100061838 | HBD/78: Aux winch send onshore Overhaul | Assist with function/proof load test | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2024-05-17 | 2024-10-10 | 2024-10-07 | 2022-03-17 | 2022-02-05 | 180 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 |  | WDF | MTN-PAIN | MTN-PAIN | 2100071509 | FLMR New rubber strip for instrumentshop | New rubber strip for instrumentshop door | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-08-22 | 2022-08-23 | 2022-08-22 | 2023-01-04 | 2022-08-22 | 10 | REL | APPR OPND | HB /D /02/HBDE-FID-64172 | FIRE DOOR |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PAIN | MTN-PAIN | 2100071509 | FLMR New rubber strip for instrumentshop | Order materials | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2022-08-22 | 2022-08-23 | 2022-08-22 | 2023-01-04 | 2022-08-22 | 20 | REL | APPR OPND | HB /D /02/HBDE-FID-64172 | FIRE DOOR |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PAIN | MTN-PAIN | 2100071509 | FLMR New rubber strip for instrumentshop | Remove old rubber and clean doorframe | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2022-08-22 | 2022-08-23 | 2022-08-22 | 2023-01-04 | 2022-08-22 | 30 | REL | APPR OPND | HB /D /02/HBDE-FID-64172 | FIRE DOOR |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PAIN | MTN-PAIN | 2100071509 | FLMR New rubber strip for instrumentshop | Install new rubber strip | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2022-08-22 | 2022-08-23 | 2022-08-22 | 2023-01-04 | 2022-08-22 | 40 | REL | APPR OPND | HB /D /02/HBDE-FID-64172 | FIRE DOOR |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PAIN | MTN-PAIN | 2100071509 | FLMR New rubber strip for instrumentshop | Clean worksite | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2022-08-22 | 2022-08-23 | 2022-08-23 | 2023-01-04 | 2022-08-22 | 50 | REL | APPR OPND | HB /D /02/HBDE-FID-64172 | FIRE DOOR |  | A |  | MFM | DK50
0 | 3 |  | WDF | MTN-ROPE | MTN-ROPE | 2100071681 | FLM Missing grating at sea level escape | Missing grating at sea level escape | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-09-01 | 2022-09-04 | 2022-09-01 | 2023-01-14 | 2022-09-01 | 10 | REL | APPR OPND | HD /C /86/JACKET - ESCAPE TO SEA | ESCAPE LADDER TO SEA |  | A |  | MFM | DK60
0 | 3 |  | WDF | MTN-ROPE | MTN-ROPE | 2100071681 | FLM Missing grating at sea level escape | Set up Equipment | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2022-09-01 | 2022-09-04 | 2022-09-01 | 2023-01-14 | 2022-09-01 | 20 | REL | APPR OPND | HD /C /86/JACKET - ESCAPE TO SEA | ESCAPE LADDER TO SEA |  | A |  | MFM | DK60
0 | 3 |  | WDF | MTN-ROPE | MTN-ROPE | 2100071681 | FLM Missing grating at sea level escape | Remove and Replace Gratings | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2022-09-01 | 2022-09-04 | 2022-09-02 | 2023-01-14 | 2022-09-01 | 30 | REL | APPR OPND | HD /C /86/JACKET - ESCAPE TO SEA | ESCAPE LADDER TO SEA |  | A |  | MFM | DK60
0 | 3 |  | WDF | MTN-ROPE | MTN-ROPE | 2100071681 | FLM Missing grating at sea level escape | Clean Area | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2022-09-01 | 2022-09-04 | 2022-09-03 | 2023-01-14 | 2022-09-01 | 40 | REL | APPR OPND | HD /C /86/JACKET - ESCAPE TO SEA | ESCAPE LADDER TO SEA |  | A |  | MFM | DK60
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100072223 | HBB/78: Calibrate of winch load system | Calibrate winch load system | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-01-10 | 2022-08-28 | 10 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100072223 | HBB/78: Calibrate of winch load system | Operating crane under calibration | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2024-03-09 | 2024-03-11 | 2024-03-09 | 2023-01-10 | 2022-08-28 | 30 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W13-14 | 3 |  | WDF | MTN-PIPF | MTN-PAIN | 2100074656 | ANOP HBD-4-WF-003-1198-AN-U Bucked & Ben | HBD-4-WF-003-1198-AN-U Bucked & Bent | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-10-23 | 2022-10-28 | 2022-10-23 | 2023-03-07 | 2022-10-23 | 10 | REL | APPR OPND | HB /D /01/HBD-4-WF-003-1198-AN-U | 4 FIREWATER LINE |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PIPF | MTN-PAIN | 2100074656 | ANOP HBD-4-WF-003-1198-AN-U Bucked & Ben | Remove old Bracket | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2022-10-23 | 2022-10-28 | 2022-10-23 | 2023-03-07 | 2022-10-23 | 20 | REL | APPR OPND | HB /D /01/HBD-4-WF-003-1198-AN-U | 4 FIREWATER LINE |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PIPF | MTN-PAIN | 2100074656 | ANOP HBD-4-WF-003-1198-AN-U Bucked & Ben | Installing new Bracket | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2022-10-23 | 2022-10-28 | 2022-10-24 | 2023-03-07 | 2022-10-23 | 30 | REL | APPR OPND | HB /D /01/HBD-4-WF-003-1198-AN-U | 4 FIREWATER LINE |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PIPF | MTN-PAIN | 2100074656 | ANOP HBD-4-WF-003-1198-AN-U Bucked & Ben | Clean Area | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2022-10-23 | 2022-10-28 | 2022-10-25 | 2023-03-07 | 2022-10-23 | 40 | REL | APPR OPND | HB /D /01/HBD-4-WF-003-1198-AN-U | 4 FIREWATER LINE |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PIPF | MTN-ROPE | 2100074656 | ANOP HBD-4-WF-003-1198-AN-U Bucked & Ben | Survey, fabrication new support | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2022-10-23 | 2022-10-28 | 2022-10-26 | 2023-03-07 | 2022-10-23 | 50 | REL | APPR OPND | HB /D /01/HBD-4-WF-003-1198-AN-U | 4 FIREWATER LINE |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PIPF | MTN-PAIN | 2100074656 | ANOP HBD-4-WF-003-1198-AN-U Bucked & Ben | Paint new support | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2022-10-23 | 2022-10-28 | 2022-10-27 | 2023-03-07 | 2022-10-23 | 60 | REL | APPR OPND | HB /D /01/HBD-4-WF-003-1198-AN-U | 4 FIREWATER LINE |  | A |  | MFM | DK50
2026-W13-14 | 3 |  | WDF | MTN-PIPF | MTN-ROPE | 2100074656 | ANOP HBD-4-WF-003-1198-AN-U Bucked & Ben | Permit preparation | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2022-10-23 | 2022-10-28 | 2022-10-27 | 2023-03-07 | 2022-10-23 | 70 | REL | APPR OPND | HB /D /01/HBD-4-WF-003-1198-AN-U | 4 FIREWATER LINE |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100080209 | FLMR ANOS HBA-HBC Bridge - Repair Handra | HBA-HBC Bridge - Repair Handrail | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-06-25 | 2023-07-06 | 2023-06-25 | 2025-12-31 | 2023-06-25 | 10 | REL | APPR OPND | HB /A /86/BRIDGE-HBA-HBB | BRIDGE HBA TO HBB |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-ROPE | MTN-ROPE | 2100080209 | FLMR ANOS HBA-HBC Bridge - Repair Handra | Install missing handrail links 219 pcs | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 220 | 0 |  | 2023-06-25 | 2023-07-06 | 2023-06-25 | 2025-12-31 | 2023-06-25 | 20 | REL | APPR OPND | HB /A /86/BRIDGE-HBA-HBB | BRIDGE HBA TO HBB |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100093880 | ANOCR HBC - Repair Firewall EL. 22.000 | HBC - Paint Firewall EL 22.000 | REL PCNF MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-12-25 | 2024-03-23 | 2023-12-25 | 2025-12-31 | 2023-12-25 | 10 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100093880 | ANOCR HBC - Repair Firewall EL. 22.000 | Erect habitat for blasting setup equipme | REL PCNF MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 67 | 77 |  | 2023-12-25 | 2024-03-23 | 2024-03-23 | 2025-12-31 | 2023-12-25 | 30 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100093880 | ANOCR HBC - Repair Firewall EL. 22.000 | Blast and prime (spot and sweap) | REL PCNF MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 200 | 181 |  | 2023-12-25 | 2024-03-23 | 2024-03-23 | 2025-12-31 | 2023-12-25 | 40 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100093880 | ANOCR HBC - Repair Firewall EL. 22.000 | Coat Fire wall to spec | REL PCNF MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 200 | 143 |  | 2023-12-25 | 2024-03-23 | 2024-03-23 | 2025-12-31 | 2023-12-25 | 50 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100093880 | ANOCR HBC - Repair Firewall EL. 22.000 | Clean up work area dismantle habitat | REL PCNF MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 55 | 30 |  | 2023-12-25 | 2024-03-23 | 2024-03-23 | 2025-12-31 | 2023-12-25 | 60 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-SCAF | 2100093880 | ANOCR HBC - Repair Firewall EL. 22.000 | Dismantle scaffold | REL PCNF MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 50 | 10 |  | 2023-12-25 | 2024-03-23 | 2024-03-23 | 2025-12-31 | 2023-12-25 | 70 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100093880 | ANOCR HBC - Repair Firewall EL. 22.000 | QC Paint report | REL PCNF MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 15 | 7 |  | 2023-12-25 | 2024-03-23 | 2024-03-23 | 2025-12-31 | 2023-12-25 | 80 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100093880 | ANOCR HBC - Repair Firewall EL. 22.000 | Ordering of material | REL PCNF MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-12-25 | 2024-03-23 | 2024-03-23 | 2025-12-31 | 2023-12-25 | 90 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100093881 | ANOCR HBC - Repair Firewall EL. 25.000 | HBC - Paint Firewall EL 25.000 | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-12-25 | 2024-02-03 | 2023-12-25 | 2025-12-31 | 2023-12-25 | 10 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100093881 | ANOCR HBC - Repair Firewall EL. 25.000 | Set Up habitats and cleaning station | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 40 | 0 |  | 2023-12-25 | 2024-02-03 | 2023-12-25 | 2025-12-31 | 2023-12-25 | 20 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100093881 | ANOCR HBC - Repair Firewall EL. 25.000 | Prep and prime corroded areas | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 300 | 0 |  | 2023-12-25 | 2024-02-03 | 2023-12-27 | 2025-12-31 | 2023-12-25 | 30 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100093881 | ANOCR HBC - Repair Firewall EL. 25.000 | Paint to spec corroded areas | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 400 | 0 |  | 2023-12-25 | 2024-02-03 | 2024-01-12 | 2025-12-31 | 2023-12-25 | 40 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100093881 | ANOCR HBC - Repair Firewall EL. 25.000 | QC Paint report | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 16 | 0 |  | 2023-12-25 | 2024-02-03 | 2024-02-02 | 2025-12-31 | 2023-12-25 | 50 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100094710 | Paint job never finished. V-5754 | Paint job never finished. V-5754 | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-12-29 | 2024-01-02 | 2023-12-29 | 2026-06-16 | 2023-12-29 | 10 | REL | APPR OPND | HB /D /70/HBDC-V-5754 | HP FUEL GAS BUFFER VESSEL |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100094710 | Paint job never finished. V-5754 | Prep and prime unfinished areas | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 30 | 0 |  | 2023-12-29 | 2024-01-02 | 2023-12-29 | 2026-06-16 | 2023-12-29 | 20 | REL | APPR OPND | HB /D /70/HBDC-V-5754 | HP FUEL GAS BUFFER VESSEL |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100094710 | Paint job never finished. V-5754 | Paint to spec | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 25 | 0 |  | 2023-12-29 | 2024-01-02 | 2023-12-31 | 2026-06-16 | 2023-12-29 | 30 | REL | APPR OPND | HB /D /70/HBDC-V-5754 | HP FUEL GAS BUFFER VESSEL |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100094710 | Paint job never finished. V-5754 | QC Paint report | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2023-12-29 | 2024-01-02 | 2024-01-01 | 2026-06-16 | 2023-12-29 | 40 | REL | APPR OPND | HB /D /70/HBDC-V-5754 | HP FUEL GAS BUFFER VESSEL |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100094711 | Paint job never finished. V-5755 | Paint job never finished. V-5755 | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-12-29 | 2024-01-02 | 2023-12-29 | 2026-06-16 | 2023-12-29 | 10 | REL | APPR OPND | HB /D /70/HBDC-V-5755 | MP FUEL GAS BUFFER VESSEL |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100094711 | Paint job never finished. V-5755 | Prep and prime unfinished areas | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 30 | 0 |  | 2023-12-29 | 2024-01-02 | 2023-12-29 | 2026-06-16 | 2023-12-29 | 20 | REL | APPR OPND | HB /D /70/HBDC-V-5755 | MP FUEL GAS BUFFER VESSEL |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100094711 | Paint job never finished. V-5755 | Paint to spec | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 25 | 0 |  | 2023-12-29 | 2024-01-02 | 2023-12-31 | 2026-06-16 | 2023-12-29 | 30 | REL | APPR OPND | HB /D /70/HBDC-V-5755 | MP FUEL GAS BUFFER VESSEL |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100094711 | Paint job never finished. V-5755 | QC Paint report | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2023-12-29 | 2024-01-02 | 2024-01-01 | 2026-06-16 | 2023-12-29 | 40 | REL | APPR OPND | HB /D /70/HBDC-V-5755 | MP FUEL GAS BUFFER VESSEL |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097413 | ANOCR HBC - Repair Firewall EL. 40.100 | HBC - Repair Firewall EL. 40.100 | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-02-25 | 2024-04-05 | 2024-02-25 | 2025-12-31 | 2024-02-25 | 10 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097413 | ANOCR HBC - Repair Firewall EL. 40.100 | Set Up habitats and cleaning station | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 40 | 0 |  | 2024-02-25 | 2024-04-05 | 2024-02-25 | 2025-12-31 | 2024-02-25 | 20 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097413 | ANOCR HBC - Repair Firewall EL. 40.100 | Prep and prime corroded areas | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 300 | 0 |  | 2024-02-25 | 2024-04-05 | 2024-02-27 | 2025-12-31 | 2024-02-25 | 30 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097413 | ANOCR HBC - Repair Firewall EL. 40.100 | Paint to spec corroded areas | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 400 | 0 |  | 2024-02-25 | 2024-04-05 | 2024-03-14 | 2025-12-31 | 2024-02-25 | 40 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097413 | ANOCR HBC - Repair Firewall EL. 40.100 | QC Paint report | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 16 | 0 |  | 2024-02-25 | 2024-04-05 | 2024-04-04 | 2025-12-31 | 2024-02-25 | 50 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097414 | ANOCR HBC - Repair Firewall EL. 43.500 | HBC - Repair Firewall EL. 43.500 | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-02-25 | 2024-04-05 | 2024-02-25 | 2025-12-31 | 2024-02-25 | 10 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097414 | ANOCR HBC - Repair Firewall EL. 43.500 | Set Up habitats and cleaning station | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 40 | 0 |  | 2024-02-25 | 2024-04-05 | 2024-02-25 | 2025-12-31 | 2024-02-25 | 20 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097414 | ANOCR HBC - Repair Firewall EL. 43.500 | Prep and prime corroded areas | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 300 | 0 |  | 2024-02-25 | 2024-04-05 | 2024-02-27 | 2025-12-31 | 2024-02-25 | 30 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097414 | ANOCR HBC - Repair Firewall EL. 43.500 | Paint to spec corroded areas | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 400 | 0 |  | 2024-02-25 | 2024-04-05 | 2024-03-14 | 2025-12-31 | 2024-02-25 | 40 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097414 | ANOCR HBC - Repair Firewall EL. 43.500 | QC Paint report | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 16 | 0 |  | 2024-02-25 | 2024-04-05 | 2024-04-04 | 2025-12-31 | 2024-02-25 | 50 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097415 | ANOCR HBC - Repair Firewall EL. 46.900 | HBC - Repair Firewall EL. 46.900 | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-02-27 | 2024-04-08 | 2024-02-27 | 2025-12-31 | 2024-02-27 | 10 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097415 | ANOCR HBC - Repair Firewall EL. 46.900 | Set up Habitat and clean station | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 40 | 0 |  | 2024-02-27 | 2024-04-08 | 2024-02-27 | 2025-12-31 | 2024-02-27 | 20 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097415 | ANOCR HBC - Repair Firewall EL. 46.900 | Prep and prime corroded areas | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 300 | 0 |  | 2024-02-27 | 2024-04-08 | 2024-02-29 | 2025-12-31 | 2024-02-27 | 30 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097415 | ANOCR HBC - Repair Firewall EL. 46.900 | Paint to spec corroded areas | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 400 | 0 |  | 2024-02-27 | 2024-04-08 | 2024-03-16 | 2025-12-31 | 2024-02-27 | 40 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100097415 | ANOCR HBC - Repair Firewall EL. 46.900 | QC Paint report | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 16 | 0 |  | 2024-02-27 | 2024-04-08 | 2024-04-06 | 2025-12-31 | 2024-02-27 | 50 | REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100098023 | ANOCR HBB - Paint Riser R4319 | HBB - Paint Riser R4319 | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-10 | 2024-03-22 | 2024-03-10 | 2025-12-31 | 2024-03-10 | 10 | REL | APPR OPND | HB /B /23/HBBA-RI-664319 | R4319 - 8" HALFDAN BB TO P4310 |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100098023 | ANOCR HBB - Paint Riser R4319 | Set up ropes | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2024-03-10 | 2024-03-22 | 2024-03-10 | 2025-12-31 | 2024-03-10 | 20 | REL | APPR OPND | HB /B /23/HBBA-RI-664319 | R4319 - 8" HALFDAN BB TO P4310 |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100098023 | ANOCR HBB - Paint Riser R4319 | Blast Highlighted areas | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 48 | 0 |  | 2024-03-10 | 2024-03-22 | 2024-03-11 | 2025-12-31 | 2024-03-10 | 30 | REL | APPR OPND | HB /B /23/HBBA-RI-664319 | R4319 - 8" HALFDAN BB TO P4310 |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100098023 | ANOCR HBB - Paint Riser R4319 | Coating Application | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 48 | 0 |  | 2024-03-10 | 2024-03-22 | 2024-03-16 | 2025-12-31 | 2024-03-10 | 40 | REL | APPR OPND | HB /B /23/HBBA-RI-664319 | R4319 - 8" HALFDAN BB TO P4310 |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100098023 | ANOCR HBB - Paint Riser R4319 | Clean Area | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2024-03-10 | 2024-03-22 | 2024-03-21 | 2025-12-31 | 2024-03-10 | 50 | REL | APPR OPND | HB /B /23/HBBA-RI-664319 | R4319 - 8" HALFDAN BB TO P4310 |  | A |  | MFM | DK50
2026-W13-14 | 4 |  | WDF | MTN-PAIN | MTN-PAIN | 2100098023 | ANOCR HBB - Paint Riser R4319 | De rig ropes | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2024-03-10 | 2024-03-22 | 2024-03-21 | 2025-12-31 | 2024-03-10 | 60 | REL | APPR OPND | HB /B /23/HBBA-RI-664319 | R4319 - 8" HALFDAN BB TO P4310 |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104968 | HBB/78 EMG light - replace battery | HBB/78 EMG light - replace battery | REL MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-05-13 | 2023-12-30 | 10 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100104968 | HBB/78 EMG light - replace battery | Isolate and prove dead | REL MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-05-13 | 2023-12-30 | 20 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104968 | HBB/78 EMG light - replace battery | replace defect lamp with new one. | REL MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-05-13 | 2023-12-30 | 30 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100104968 | HBB/78 EMG light - replace battery | Deisolate and put back in service | REL MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-05-13 | 2023-12-30 | 40 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104968 | HBB/78 EMG light - replace battery | test equipment | REL MANC PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-25 | 2024-03-26 | 2024-03-26 | 2024-05-13 | 2023-12-30 | 50 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | C |  | MEL | DK50 |  | PROK
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400215545 | 1Y HAZARDOUS OPEN DRAIN MAINT-HBB | ISOLATION BY PRODUCTION | REL MANC PPRT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 2 | 0 | W05-06 BL-Team | 2024-03-09 | 2024-03-30 | 2024-03-09 | 2022-11-23 | 2022-10-24 | 10 | REL | APPR OPND | HB /B /28/HAZARDOUS-OPEN-DRAIN | HBB HAZARDOUS OPEN DRAIN |  | C | DKHB-0016 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400215545 | 1Y HAZARDOUS OPEN DRAIN MAINT-HBB | HAZARDOUS OPEN DRAIN MAINT-HBB | REL MANC PPRT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 8 | 0 | W05-06 BL-Team | 2024-03-09 | 2024-03-30 | 2024-03-09 | 2022-11-23 | 2022-10-24 | 20 | REL | APPR OPND | HB /B /28/HAZARDOUS-OPEN-DRAIN | HBB HAZARDOUS OPEN DRAIN |  | C | DKHB-0016 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400215545 | 1Y HAZARDOUS OPEN DRAIN MAINT-HBB | HAZARDOUS OPEN DRAIN MAINT-HBB | REL MANC PPRT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 4 | 0 | W05-06 BL-Team | 2024-03-09 | 2024-03-30 | 2024-03-11 | 2022-11-23 | 2022-10-24 | 30 | REL | APPR OPND | HB /B /28/HAZARDOUS-OPEN-DRAIN | HBB HAZARDOUS OPEN DRAIN |  | C | DKHB-0016 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-INST | 2400215545 | 1Y HAZARDOUS OPEN DRAIN MAINT-HBB | HAZARDOUS OPEN DRAIN MAINT-HBB | REL MANC PPRT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 4 | 0 | W05-06 BL-Team | 2024-03-09 | 2024-03-30 | 2024-03-11 | 2022-11-23 | 2022-10-24 | 40 | REL | APPR OPND | HB /B /28/HAZARDOUS-OPEN-DRAIN | HBB HAZARDOUS OPEN DRAIN |  | C | DKHB-0016 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400215545 | 1Y HAZARDOUS OPEN DRAIN MAINT-HBB | DE-ISOLATION BY PRODUCTION | REL MANC PPRT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 2 | 0 | W05-06 BL-Team | 2024-03-09 | 2024-03-30 | 2024-03-12 | 2022-11-23 | 2022-10-24 | 50 | REL | APPR OPND | HB /B /28/HAZARDOUS-OPEN-DRAIN | HBB HAZARDOUS OPEN DRAIN |  | C | DKHB-0016 | MMR | DK50 | MR0054
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400215545 | 1Y HAZARDOUS OPEN DRAIN MAINT-HBB | Mechanical clean of open drain - OTS | REL MANC PPRT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 336 | 0 |  | 2024-03-09 | 2024-03-30 | 2024-03-13 | 2022-11-23 | 2022-10-24 | 60 | REL | APPR OPND | HB /B /28/HAZARDOUS-OPEN-DRAIN | HBB HAZARDOUS OPEN DRAIN |  | C | DKHB-0016 | MMR | DK50 | MR0054
2026-W13-14 | C | HB WI SD | WPM | MTN-MECH | PRODTECH | 2400274217 | 1Y WI PIG REC./LNCHR TEST-HBAA-EP-3813 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2023-09-21 | 2023-08-16 | 10 | REL | APPR OPND | HB /A /50/HBAA-EP-3813 | WTR INJECTION PIG RECEIVER/PROD GAS LAU |  | C | DKHB-0004 | MMS | DK50 | MS0094
2026-W13-14 | C | HB WI SD | WPM | MTN-MECH | MTN-INST | 2400274217 | 1Y WI PIG REC./LNCHR TEST-HBAA-EP-3813 | WI PIG REC./LNCHR TEST-HBAA-EP-3813 | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2023-09-21 | 2023-08-16 | 20 | REL | APPR OPND | HB /A /50/HBAA-EP-3813 | WTR INJECTION PIG RECEIVER/PROD GAS LAU |  | C | DKHB-0004 | MMS | DK50 | MS0094
2026-W13-14 | C | HB WI SD | WPM | MTN-MECH | MTN-MECH | 2400274217 | 1Y WI PIG REC./LNCHR TEST-HBAA-EP-3813 | WI PIG REC./LNCHR TEST-HBAA-EP-3813 | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-08-22 | 2024-08-24 | 2024-08-23 | 2023-09-21 | 2023-08-16 | 30 | REL | APPR OPND | HB /A /50/HBAA-EP-3813 | WTR INJECTION PIG RECEIVER/PROD GAS LAU |  | C | DKHB-0004 | MMS | DK50 | MS0094
2026-W13-14 | C | HB WI SD | WPM | MTN-MECH | PRODTECH | 2400274217 | 1Y WI PIG REC./LNCHR TEST-HBAA-EP-3813 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-22 | 2024-08-24 | 2024-08-24 | 2023-09-21 | 2023-08-16 | 40 | REL | APPR OPND | HB /A /50/HBAA-EP-3813 | WTR INJECTION PIG RECEIVER/PROD GAS LAU |  | C | DKHB-0004 | MMS | DK50 | MS0094
2024-W17-18 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400322691 | 6M CLOSED DRAIN DISPOSAL MAINT-HBB | CLOSED DRAIN DISPOSAL MAINT-HBB | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 0.5 | 0 | W17-W18 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-22 | 2024-05-03 | 10 | REL | APPR OPND | HB /B /28/DRAIN-DISPOSAL | DRAIN DISPOSAL |  | A | DKHB-0220 | MMS | DK50 | MR0054 |  | 2024-04-22
2026-W13-14 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400325376 | 6M HAZARDOUS OPEN DRAIN MAINT-HBB | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-05-04 | 2024-05-06 | 2024-05-04 | 2024-05-23 | 2024-05-04 | 10 | REL | APPR OPND | HB /B /28/HAZARDOUS-OPEN-DRAIN | HBB HAZARDOUS OPEN DRAIN |  | C | DKHB-0016 | MMR | DK50 | MR0054
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325376 | 6M HAZARDOUS OPEN DRAIN MAINT-HBB | HAZARDOUS OPEN DRAIN MAINT-HBB | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 8 | 0 | W17-W18 | 2024-05-04 | 2024-05-06 | 2024-05-04 | 2024-05-23 | 2024-05-04 | 20 | REL | APPR OPND | HB /B /28/HAZARDOUS-OPEN-DRAIN | HBB HAZARDOUS OPEN DRAIN |  | C | DKHB-0016 | MMR | DK50 | MR0054
2026-W13-14 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400325376 | 6M HAZARDOUS OPEN DRAIN MAINT-HBB | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 2 | 0 | W17-W18 | 2024-05-04 | 2024-05-06 | 2024-05-06 | 2024-05-23 | 2024-05-04 | 30 | REL | APPR OPND | HB /B /28/HAZARDOUS-OPEN-DRAIN | HBB HAZARDOUS OPEN DRAIN |  | C | DKHB-0016 | MMR | DK50 | MR0054
2026-W13-14 | B | NOSD | WPM | MTN-MECH | PRODTECH | 2400334357 | 6M DIESEL TRANSFER SYSTEM MAINT - HBC | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-28 | 2024-06-30 | 2024-06-28 | 2024-07-14 | 2024-06-28 | 10 | REL | APPR OPND | HB /C /71/HBCM-P-5732 | DIESEL TRANSFER PUMP |  | C | DKHB-0070 | MMR | DK50 | MR0074
2026-W13-14 | B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400334357 | 6M DIESEL TRANSFER SYSTEM MAINT - HBC | DIESEL TRANSFER SYSTEM MAINT - HBC | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2024-06-28 | 2024-06-30 | 2024-06-28 | 2024-07-14 | 2024-06-28 | 20 | REL | APPR OPND | HB /C /71/HBCM-P-5732 | DIESEL TRANSFER PUMP |  | C | DKHB-0070 | MMR | DK50 | MR0074
2026-W13-14 | B | NOSD | WPM | MTN-MECH | PRODTECH | 2400334357 | 6M DIESEL TRANSFER SYSTEM MAINT - HBC | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-06-28 | 2024-06-30 | 2024-06-29 | 2024-07-14 | 2024-06-28 | 30 | REL | APPR OPND | HB /C /71/HBCM-P-5732 | DIESEL TRANSFER PUMP |  | C | DKHB-0070 | MMR | DK50 | MR0074
2024-W15-16 | D | NE | WPM | MTN-MECH | MTN-MECH | 2400334579 | 3M IG SKID INSPECTION HBDB-A-0850 | IG SKID INSPECTION HBDB-A-0850 | REL NMAT PRC SETC | APPR AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-05 | 2024-07-05 | 2024-07-05 | 2024-07-20 | 2024-07-05 | 10 | REL | APPR OPND | HB /D /74/HBDB-A-0850 | INERT GAS PACKAGE |  | A | DKHB-0022 | MMR | DK50 | MR0034 |  | 2024-04-11
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100026512 | CMAT:Swap hydraulic return line(s) HBAA- | L3 Isolation of HBAA-ESDV-38048/49 | REL MANC PRC SETC | APPR AWDO AWSC RDBL ROUT | 6 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2019-07-22 | 2019-06-12 | 10 | REL | APPR OPND | HB /A /34/HBAA-ESDV-38048 | EMERGENCY SHUTDOWN VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100026512 | CMAT:Swap hydraulic return line(s) HBAA- | L3 Swap hydraulic supply as in report | REL MANC PRC SETC | APPR AWDO AWSC RDBL ROUT | 16 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2019-07-22 | 2019-06-12 | 20 | REL | APPR OPND | HB /A /34/HBAA-ESDV-38048 | EMERGENCY SHUTDOWN VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100026512 | CMAT:Swap hydraulic return line(s) HBAA- | L3 De-Isolate/test HBAA-ESDV-38048/49 | REL MANC PRC SETC | APPR AWDO AWSC RDBL ROUT | 6 | 0 |  | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2019-07-22 | 2019-06-12 | 30 | REL | APPR OPND | HB /A /34/HBAA-ESDV-38048 | EMERGENCY SHUTDOWN VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBA15-PW | WDF | MTN-MECH | PRODTECH | 2100022516 | CMAT:HBAA-A-3111 changeout Damage pressu | L3 Isolation of pressure gauge on wellhe | REL PRT MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2019-11-22 | 2019-10-13 | 10 | REL | APPR OPND | HB /A /07/HBAA-A-3111 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBA15-PW | WDF | MTN-MECH | MTN-MECH | 2100022516 | CMAT:HBAA-A-3111 changeout Damage pressu | L2 Changeout Damage pressure gauge on we | REL PRT MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2019-11-22 | 2019-10-13 | 20 | REL | APPR OPND | HB /A /07/HBAA-A-3111 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 3 | HBA15-PW | WDF | MTN-MECH | PRODTECH | 2100022516 | CMAT:HBAA-A-3111 changeout Damage pressu | L3 De-Isolation/test pressure gauge on w | REL PRT MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2019-11-22 | 2019-10-13 | 30 | REL | APPR OPND | HB /A /07/HBAA-A-3111 | WELLHEAD CONTROL PANEL | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-PIPF | 2100025900 | ANOP CMAT:Replace spool corr flanges | Prepare Permit (Weld) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2019-12-09 | 2018-12-14 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100025900 | ANOP CMAT:Replace spool corr flanges | Prepare Permit (Scaff) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2019-12-09 | 2018-12-14 | 20 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | VEN-ELEC | 2100025900 | ANOP CMAT:Replace spool corr flanges | Prepare Permit (El) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2019-12-09 | 2018-12-14 | 22 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-PIPF | 2100025900 | ANOP CMAT:Replace spool corr flanges | Prepare lifting procedure (Scaff) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-02 | 2019-12-09 | 2018-12-14 | 24 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-PIPF | 2100025900 | ANOP CMAT:Replace spool corr flanges | Check Mat (Weld) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-02 | 2019-12-09 | 2018-12-14 | 30 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100025900 | ANOP CMAT:Replace spool corr flanges | Install Scaff overboard (Scaff) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 90.5 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2019-12-09 | 2018-12-14 | 40 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100025900 | ANOP CMAT:Replace spool corr flanges | Install/demol liftning equipment (Scaff) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 8 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-12 | 2019-12-09 | 2018-12-14 | 42 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100025900 | ANOP CMAT:Replace spool corr flanges | Isolate (Prod) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 12 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-07 | 2019-12-09 | 2018-12-14 | 50 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | VEN-ELEC | 2100025900 | ANOP CMAT:Replace spool corr flanges | Demol/Iinstall instrument (El) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 17.4 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-13 | 2019-12-09 | 2018-12-14 | 52 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-PIPF | 2100025900 | ANOP CMAT:Replace spool corr flanges | Demol spool and Valve (Weld) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 17.4 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-10 | 2019-12-09 | 2018-12-14 | 60 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100025900 | ANOP CMAT:Replace spool corr flanges | Scaff Ass Weld (Scaff) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 8.7 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-11 | 2019-12-09 | 2018-12-14 | 70 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-PIPF | 2100025900 | ANOP CMAT:Replace spool corr flanges | Install spool and valve (Weld) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 17.4 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-12 | 2019-12-09 | 2018-12-14 | 80 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100025900 | ANOP CMAT:Replace spool corr flanges | De-Isolate (Prod) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 12 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-16 | 2019-12-09 | 2018-12-14 | 90 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-SCAF | 2100025900 | ANOP CMAT:Replace spool corr flanges | Demol Scaff overboard (Scaff) | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 30.2 | 0 | 200676325+650842+628251 | 2025-01-01 | 2025-01-20 | 2025-01-18 | 2019-12-09 | 2018-12-14 | 100 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100025900 | ANOP CMAT:Replace spool corr flanges | Drawing of spool | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 13 | 0 |  | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2019-12-09 | 2018-12-14 | 170 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | C |  | MFM | DK50
2025-W1-2 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100025901 | FFSPR Replace spool with corroded flange | Replace spool with corroded flanges | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | 200650842+628251+650915 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-01-26 | 2020-02-01 | 10 | REL | APPR OPND | HB /A /01/HBAA-A-0371 | DELUGE SKID WELL ACCESS DECK | 99000087 | D |  | MFM | DK50
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100027211 | SMAT:Change out drain valves for EP-3812 | HBA-EP-3812 | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 0 | 0 | RCE PTW 214610 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-06-24 | 2019-01-25 | 10 | REL | APPR OPND | HB /A /34/HBAA-EP-3812 | LIFT GAS PIG RECEIVER | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100027211 | SMAT:Change out drain valves for EP-3812 | L3 Isolate for replacing valves - Prod | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | RCE | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-06-24 | 2019-01-25 | 20 | REL | APPR OPND | HB /A /34/HBAA-EP-3812 | LIFT GAS PIG RECEIVER | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100027211 | SMAT:Change out drain valves for EP-3812 | L3 Replace valve globe valve - Mech | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | RCE | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-06-24 | 2019-01-25 | 30 | REL | APPR OPND | HB /A /34/HBAA-EP-3812 | LIFT GAS PIG RECEIVER | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100027211 | SMAT:Change out drain valves for EP-3812 | L3 Replace ball valve - Mech | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 3 | 0 | RCE | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-06-24 | 2019-01-25 | 40 | REL | APPR OPND | HB /A /34/HBAA-EP-3812 | LIFT GAS PIG RECEIVER | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100027211 | SMAT:Change out drain valves for EP-3812 | L3 Leak test - Prod | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | RCE | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2019-06-24 | 2019-01-25 | 50 | REL | APPR OPND | HB /A /34/HBAA-EP-3812 | LIFT GAS PIG RECEIVER | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | PRODTECH | 2100027211 | SMAT:Change out drain valves for EP-3812 | L3 De-isolate HBA-EP-3812 - Prod | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | RCE | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2019-06-24 | 2019-01-25 | 60 | REL | APPR OPND | HB /A /34/HBAA-EP-3812 | LIFT GAS PIG RECEIVER | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | HBALIFTG | WDF | MTN-MECH | MTN-MECH | 2100027211 | SMAT:Change out drain valves for EP-3812 | L3 Cleaning work site - Mech | REL MANC PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | RCE | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2019-06-24 | 2019-01-25 | 70 | REL | APPR OPND | HB /A /34/HBAA-EP-3812 | LIFT GAS PIG RECEIVER | 99000119 | F |  | MMS | DK50
2024-W23-24 | 3 | HB WI SD | WDF | MTN-ROPE | MTN-PAIN | 2100036981 | FFSP Hole in 6"-DPS-050-4019-AA | Hole in 6"-DPS-050-4019-AA | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2020-12-04 | 2020-09-05 | 10 | REL | APPR OPND | HB /A /28/HBA-6-DPS-050-4019-AA-U | 6 CLOSED DRAIN SOUR LINE | 99000087 | A |  | MFM | DK50
2024-W23-24 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-MECH | 2100090885 | Hydr seeps on panel for ESDV-345104 | Hydr seeps on panel for ESDV-345104 | REL PRT MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-09-29 | 2023-05-17 | 10 | REL | APPR OPND | HB /D /34/HBDB-ESDV-345104 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2024-W23-24 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-MECH | 2100090885 | Hydr seeps on panel for ESDV-345104 | Isolate hydraulic supply to panel | REL PRT MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-09-29 | 2023-05-17 | 20 | REL | APPR OPND | HB /D /34/HBDB-ESDV-345104 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2024-W23-24 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-MECH | 2100090885 | Hydr seeps on panel for ESDV-345104 | De-pressurize system | REL PRT MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-09-29 | 2023-05-17 | 30 | REL | APPR OPND | HB /D /34/HBDB-ESDV-345104 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2024-W23-24 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-MECH | 2100090885 | Hydr seeps on panel for ESDV-345104 | Re-tighten hydraulic fittings | REL PRT MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-09-29 | 2023-05-17 | 40 | REL | APPR OPND | HB /D /34/HBDB-ESDV-345104 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2024-W23-24 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-MECH | 2100090885 | Hydr seeps on panel for ESDV-345104 | De-isolate hydraulic supply to panel | REL PRT MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-09-29 | 2023-05-17 | 50 | REL | APPR OPND | HB /D /34/HBDB-ESDV-345104 | EMERGENCY SHUTDOWN VALVE |  | A |  | MMS | DK50
2024-W49-50 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099090 | UPS-1950B tripped by bypass key | UPS-1950B tripped by bypass key | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 0 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2023-11-12 | 2023-09-28 | 10 | REL | APPR OPND | HB /D /06/HBDD-AE-1950B | 400/230V AC UPS SYSTEM CABINET |  | C |  | MEL | DK50 |  | PROK
2024-W49-50 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099090 | UPS-1950B tripped by bypass key | Sitevisit - TBT. | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 0.5 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2023-11-12 | 2023-09-28 | 20 | REL | APPR OPND | HB /D /06/HBDD-AE-1950B | 400/230V AC UPS SYSTEM CABINET |  | C |  | MEL | DK50 |  | PROK
2024-W49-50 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099090 | UPS-1950B tripped by bypass key | Isolate - HBDD-AE-1950B | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 0.5 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2023-11-12 | 2023-09-28 | 30 | REL | APPR OPND | HB /D /06/HBDD-AE-1950B | 400/230V AC UPS SYSTEM CABINET |  | C |  | MEL | DK50 |  | PROK
2024-W49-50 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099090 | UPS-1950B tripped by bypass key | Investigate / trouble shoting | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2023-11-12 | 2023-09-28 | 40 | REL | APPR OPND | HB /D /06/HBDD-AE-1950B | 400/230V AC UPS SYSTEM CABINET |  | C |  | MEL | DK50 |  | PROK
2024-W49-50 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099090 | UPS-1950B tripped by bypass key | Santicion for testing. | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2023-11-12 | 2023-09-28 | 50 | REL | APPR OPND | HB /D /06/HBDD-AE-1950B | 400/230V AC UPS SYSTEM CABINET |  | C |  | MEL | DK50 |  | PROK
2024-W49-50 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099090 | UPS-1950B tripped by bypass key | De-isolate accordingly. | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 0.5 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2023-11-12 | 2023-09-28 | 60 | REL | APPR OPND | HB /D /06/HBDD-AE-1950B | 400/230V AC UPS SYSTEM CABINET |  | C |  | MEL | DK50 |  | PROK
2024-W49-50 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099090 | UPS-1950B tripped by bypass key | System check up - clean up | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2023-11-12 | 2023-09-28 | 70 | REL | APPR OPND | HB /D /06/HBDD-AE-1950B | 400/230V AC UPS SYSTEM CABINET |  | C |  | MEL | DK50 |  | PROK
2024-W49-50 | 2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099090 | UPS-1950B tripped by bypass key | Documentation. | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 0.5 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2023-11-12 | 2023-09-28 | 80 | REL | APPR OPND | HB /D /06/HBDD-AE-1950B | 400/230V AC UPS SYSTEM CABINET |  | C |  | MEL | DK50 |  | PROK
0 | A | HDAFLARE | WPM | MTN-MECH | PRODTECH | 2400235954 | 1Y FLARE SYSTEM INSPECTION HDA | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2023-03-21 | 2023-02-19 | 10 | REL | APPR OPND | HD /A /36/HP-FLARE-SYSTEM | HP FLARE SYSTEM |  | A | DKHD-0056 | MMR | DK60 | MR0143 | PROK
0 | A | HDAFLARE | WPM | MTN-MECH | MTN-ELEC | 2400235954 | 1Y FLARE SYSTEM INSPECTION HDA | FLARE SYSTEM ELEC INSPECTION HDA | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2023-03-21 | 2023-02-19 | 20 | REL | APPR OPND | HD /A /36/HP-FLARE-SYSTEM | HP FLARE SYSTEM |  | A | DKHD-0056 | MMR | DK60 | MR0143 | PROK
0 | A | HDAFLARE | WPM | MTN-MECH | MTN-INST | 2400235954 | 1Y FLARE SYSTEM INSPECTION HDA | FLARE INSTRUMENT CALIBRATION HDA | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2023-03-21 | 2023-02-19 | 30 | REL | APPR OPND | HD /A /36/HP-FLARE-SYSTEM | HP FLARE SYSTEM |  | A | DKHD-0056 | MMR | DK60 | MR0143 | PROK
0 | A | HDAFLARE | WPM | MTN-MECH | MTN-MECH | 2400235954 | 1Y FLARE SYSTEM INSPECTION HDA | FLARE SYSTEM INSPECTION HDA | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2023-03-21 | 2023-02-19 | 40 | REL | APPR OPND | HD /A /36/HP-FLARE-SYSTEM | HP FLARE SYSTEM |  | A | DKHD-0056 | MMR | DK60 | MR0143 | PROK
0 | A | HDAFLARE | WPM | MTN-MECH | PRODTECH | 2400235954 | 1Y FLARE SYSTEM INSPECTION HDA | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-28 | 2024-03-29 | 2024-03-29 | 2023-03-21 | 2023-02-19 | 50 | REL | APPR OPND | HD /A /36/HP-FLARE-SYSTEM | HP FLARE SYSTEM |  | A | DKHD-0056 | MMR | DK60 | MR0143 | PROK
2026-W13-14 | D | HCAPWELL | WPM | PRODTECH | PRODTECH | 2400281166 | PIGGING, P4312 - 20" HBB-DFG GAS 6W | P4312_HBB-DFG | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2023-10-04 | 2023-09-28 | 10 | REL | APPR OPND | HB /B /34/HBBY-PL-674312 | P4312 - 20" HBB-DFG GAS PIPELINE |  | A | DKPLCLEAN01 | INP | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284413 | PSV Exchange - HBDC-PSV-596102 | Isolation of PSV | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /07/HBDC-PSV-596102 | PRESSURE SAFETY VALVE PUMP |  | C | DKHB-PSV084 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284413 | PSV Exchange - HBDC-PSV-596102 | Prod Assist (breaking containment) | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /07/HBDC-PSV-596102 | PRESSURE SAFETY VALVE PUMP |  | C | DKHB-PSV084 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284413 | PSV Exchange - HBDC-PSV-596102 | Install re-certified PSV | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /07/HBDC-PSV-596102 | PRESSURE SAFETY VALVE PUMP |  | C | DKHB-PSV084 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284413 | PSV Exchange - HBDC-PSV-596102 | De-isolation and leak test | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /07/HBDC-PSV-596102 | PRESSURE SAFETY VALVE PUMP |  | C | DKHB-PSV084 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284413 | PSV Exchange - HBDC-PSV-596102 | Documentation & CNF WO | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /07/HBDC-PSV-596102 | PRESSURE SAFETY VALVE PUMP |  | C | DKHB-PSV084 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284413 | PSV Exchange - HBDC-PSV-596102 | Check PSV flanges & alignment | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /07/HBDC-PSV-596102 | PRESSURE SAFETY VALVE PUMP |  | C | DKHB-PSV084 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284438 | PSV Exchange - HBDC-PSV-395401 | Isolation of PSV | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /75/HBDC-PSV-395401 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV192 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284438 | PSV Exchange - HBDC-PSV-395401 | Prod Assist (breaking containment) | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /75/HBDC-PSV-395401 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV192 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284438 | PSV Exchange - HBDC-PSV-395401 | Install re-certified PSV | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /75/HBDC-PSV-395401 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV192 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284438 | PSV Exchange - HBDC-PSV-395401 | De-isolation and leak test | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /75/HBDC-PSV-395401 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV192 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284438 | PSV Exchange - HBDC-PSV-395401 | Documentation & CNF WO | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /75/HBDC-PSV-395401 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV192 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284438 | PSV Exchange - HBDC-PSV-395401 | Check PSV flanges & alignment | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /75/HBDC-PSV-395401 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV192 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284439 | PSV Exchange - HBDC-PSV-395601 | Isolation of PSV | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /75/HBDC-PSV-395601 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV194 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284439 | PSV Exchange - HBDC-PSV-395601 | Prod Assist (breaking containment) | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /75/HBDC-PSV-395601 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV194 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284439 | PSV Exchange - HBDC-PSV-395601 | Install re-certified PSV | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /75/HBDC-PSV-395601 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV194 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284439 | PSV Exchange - HBDC-PSV-395601 | De-isolation and leak test | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /75/HBDC-PSV-395601 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV194 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284439 | PSV Exchange - HBDC-PSV-395601 | Documentation & CNF WO | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /75/HBDC-PSV-395601 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV194 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284439 | PSV Exchange - HBDC-PSV-395601 | Check PSV flanges & alignment | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /75/HBDC-PSV-395601 | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV194 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284442 | PSV Exchange - HBDC-PSV-396701B | Isolation of PSV | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 10 | REL | APPR OPND | HB /D /75/HBDC-PSV-396701B | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV202 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284442 | PSV Exchange - HBDC-PSV-396701B | Prod Assist (breaking containment) | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 20 | REL | APPR OPND | HB /D /75/HBDC-PSV-396701B | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV202 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284442 | PSV Exchange - HBDC-PSV-396701B | Install re-certified PSV | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 2024-10-12 | 30 | REL | APPR OPND | HB /D /75/HBDC-PSV-396701B | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV202 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284442 | PSV Exchange - HBDC-PSV-396701B | De-isolation and leak test | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 40 | REL | APPR OPND | HB /D /75/HBDC-PSV-396701B | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV202 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284442 | PSV Exchange - HBDC-PSV-396701B | Documentation & CNF WO | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 50 | REL | APPR OPND | HB /D /75/HBDC-PSV-396701B | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV202 | MMS | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284442 | PSV Exchange - HBDC-PSV-396701B | Check PSV flanges & alignment | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-12-31 | 2024-10-12 | 60 | REL | APPR OPND | HB /D /75/HBDC-PSV-396701B | PRESSURE SAFETY RELIEF VALVE |  | C | DKHB-PSV202 | MMS | DK50
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284470 | PSV Exchange - HDBM-VPSV-50075 | Isolation of PSV | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 10 | REL | APPR OPND | HD /B /85/HDBM-VPSV-50075 | VACUUM BREAKER |  | C | DKHD-PSV139 | MMS | DK60
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284470 | PSV Exchange - HDBM-VPSV-50075 | Prod Assist (breaking containment) | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 20 | REL | APPR OPND | HD /B /85/HDBM-VPSV-50075 | VACUUM BREAKER |  | C | DKHD-PSV139 | MMS | DK60
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284470 | PSV Exchange - HDBM-VPSV-50075 | Install re-certified PSV | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 2024-10-19 | 30 | REL | APPR OPND | HD /B /85/HDBM-VPSV-50075 | VACUUM BREAKER |  | C | DKHD-PSV139 | MMS | DK60
0 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284470 | PSV Exchange - HDBM-VPSV-50075 | De-isolation and leak test | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 40 | REL | APPR OPND | HD /B /85/HDBM-VPSV-50075 | VACUUM BREAKER |  | C | DKHD-PSV139 | MMS | DK60
0 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284470 | PSV Exchange - HDBM-VPSV-50075 | Documentation & CNF WO | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 50 | REL | APPR OPND | HD /B /85/HDBM-VPSV-50075 | VACUUM BREAKER |  | C | DKHD-PSV139 | MMS | DK60
0 | A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284470 | PSV Exchange - HDBM-VPSV-50075 | Check PSV flanges & alignment | REL CSER MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-10-19 | 2024-10-21 | 2024-10-21 | 2024-12-31 | 2024-10-19 | 60 | REL | APPR OPND | HD /B /85/HDBM-VPSV-50075 | VACUUM BREAKER |  | C | DKHD-PSV139 | MMS | DK60
0 | B | NOSD | WPM | MTN-MECH | VEN-CRAN | 2400285995 | 6M CRANE, HDBR-A-6102 (VENDOR) | CRANE, HDBR-A-6102 INSPECTION | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 24 | 0 | W09-W10 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-01-27 | 2024-01-11 | 10 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | C | DKHD-0702 | MMS | DK60 | MS0153
0 | B | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400285995 | 6M CRANE, HDBR-A-6102 (VENDOR) | CRANE, POWER PACK, HDBR-AM-6102 | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W09-W10 | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-01-27 | 2024-01-11 | 20 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | C | DKHD-0702 | MMS | DK60 | MS0153
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400291741 | PIGGING, P4312 - 20" HBB-DFG GAS 6W | P4312_HBB-DFG | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2023-12-13 | 2023-12-07 | 10 | REL | APPR OPND | HB /B /34/HBBY-PL-674312 | P4312 - 20" HBB-DFG GAS PIPELINE |  | A | DKPLCLEAN01 | INP | DK50
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400293884 | PIGGING, P4312 - 20" HBB-DFG GAS 6W | P4312_HBB-DFG | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-12-27 | 2023-12-21 | 10 | REL | APPR OPND | HB /B /34/HBBY-PL-674312 | P4312 - 20" HBB-DFG GAS PIPELINE |  | A | DKPLCLEAN01 | INP | DK50
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400298404 | PIGGING, P4312 - 20" HBB-DFG GAS 6W | P4312_HBB-DFG | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-12 | 2024-04-12 | 2024-04-12 | 2024-01-10 | 2024-01-04 | 10 | REL | APPR OPND | HB /B /34/HBBY-PL-674312 | P4312 - 20" HBB-DFG GAS PIPELINE |  | A | DKPLCLEAN01 | INP | DK50
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400298729 | PIGGING, P4312 - 20" HBB-DFG GAS 6W | P4312_HBB-DFG | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-01-24 | 2024-01-18 | 10 | REL | APPR OPND | HB /B /34/HBBY-PL-674312 | P4312 - 20" HBB-DFG GAS PIPELINE |  | A | DKPLCLEAN01 | INP | DK50
2026-W13-14 | C | NOSD | WPM | PRODLABO | PRODLABO | 2400302324 | 2M GAS SAMPLE FOR CO2 EMISSION | GAS SAMPLE FOR CO2 EMISSION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-02-11 | 2024-01-31 | 10 | REL | APPR OPND | HB /D /70/HBDC-V-5755 | MP FUEL GAS BUFFER VESSEL |  | A | DK600007513 | PRD | DK50
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400302429 | PIGGING, P4312 - 20" HBB-DFG GAS 6W | P4312_HBB-DFG | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-02-07 | 2024-02-01 | 10 | REL | APPR OPND | HB /B /34/HBBY-PL-674312 | P4312 - 20" HBB-DFG GAS PIPELINE |  | A | DKPLCLEAN01 | INP | DK50
2024-W23-24 | A | HBD-IPHP | WPM | MTN-TURB | MTN-INST | 2400308688 | 8000H IN/OUTSIDE SKID, COUNTER | FUNCTION TEST & CALIBRATION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-10-03 | 2024-10-06 | 2024-10-03 | 2024-03-17 | 2024-02-16 | 10 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | C | DKHB-0478 | MMR | DK50 | MR0094 | PTW MISS
2024-W23-24 | A | HBD-IPHP | WPM | MTN-TURB | MTN-MECH | 2400308688 | 8000H IN/OUTSIDE SKID, COUNTER | VISUAL INSPECTION & FUNCTION TEST | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-10-03 | 2024-10-06 | 2024-10-05 | 2024-03-17 | 2024-02-16 | 20 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | C | DKHB-0478 | MMR | DK50 | MR0094 | PTW MISS
2026-W13-14 | A | HBD-IPHP | WPM | MTN-INST | VEN-ELEC | 2400308689 | 8000H,FG DETECTORS, FZ-838 - HBDC-A-4352 | HBD FZ838 IP/HP COMP DETCTR VEND ASSIST | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-03-17 | 2024-02-16 | 10 | REL | APPR OPND | HB /D /03/FZ-838-IP-HP-TURBINE-ENCL | FIRE ZONE 838 IP HP TURBINE ENCL |  | F | DKHB-2038 | MIN | DK50 | IN0074
2026-W13-14 | A | HBD-IPHP | WPM | MTN-INST | MTN-INST | 2400308689 | 8000H,FG DETECTORS, FZ-838 - HBDC-A-4352 | SUPPORT, DETECTOR CHECK, HDAF-A-4301 | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-03-17 | 2024-02-16 | 20 | REL | APPR OPND | HB /D /03/FZ-838-IP-HP-TURBINE-ENCL | FIRE ZONE 838 IP HP TURBINE ENCL |  | F | DKHB-2038 | MIN | DK50 | IN0074
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400309109 | PIGGING, P4312 - 20" HBB-DFG GAS 6W | P4312_HBB-DFG | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-12-20 | 2024-12-20 | 2024-12-20 | 2024-03-20 | 2024-03-05 | 10 | REL | APPR OPND | HB /B /34/HBBY-PL-674312 | P4312 - 20" HBB-DFG GAS PIPELINE |  | A | DKPLCLEAN01 | INP | DK50
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314614 | 2Y 400V E-SWB INSP HBDD-N-1855 | ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 10 | REL | APPR OPND | HB /D /05/HBDD-N-1855 | 400V EMERGENCY SWITCHBOARD |  | C | DKHB-0415 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400314614 | 2Y 400V E-SWB INSP HBDD-N-1855 | 400V E-SWB INSP HBDD-N-1855 | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 20 | REL | APPR OPND | HB /D /05/HBDD-N-1855 | 400V EMERGENCY SWITCHBOARD |  | C | DKHB-0415 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400314614 | 2Y 400V E-SWB INSP HBDD-N-1855 | DE-ISOLATION BY PRODUCTION | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-04-07 | 2024-02-21 | 30 | REL | APPR OPND | HB /D /05/HBDD-N-1855 | 400V EMERGENCY SWITCHBOARD |  | C | DKHB-0415 | MEL | DK50 | EL0024
2026-W13-14 | C | NOSD | WPM | PRODLABO | PRODLABO | 2400315100 | 2M GAS SAMPLE FOR CO2 EMISSION | GAS SAMPLE FOR CO2 EMISSION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-04-11 | 2024-03-31 | 10 | REL | APPR OPND | HB /D /70/HBDC-V-5755 | MP FUEL GAS BUFFER VESSEL |  | A | DK600007513 | PRD | DK50
2026-W13-14 | C | HB-GEN2 | WPM | MTN-TURB | PRODTECH | 2400315273 | 4000H MAIN GEN SERVICE HBDC-A-1660 | ISOLATION BY PRODUCTION | REL PCNF MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-02-06 | 2024-01-18 | 5 | PCNF REL | APPR OPND | HB /D /60/HBDC-A-1660 | MAIN GENERATOR UNIT |  | C | DKHB-0641 | MMR | DK50 | MR0114
2026-W13-14 | C | HB-GEN2 | WPM | MTN-TURB | MTN-TURB | 2400315273 | 4000H MAIN GEN SERVICE HBDC-A-1660 | MAIN GEN SERVICE HBDC-A-1660 | REL PCNF MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-02-06 | 2024-01-18 | 10 | PCNF REL | APPR OPND | HB /D /60/HBDC-A-1660 | MAIN GENERATOR UNIT |  | C | DKHB-0641 | MMR | DK50 | MR0114
2026-W13-14 | C | HB-GEN2 | WPM | MTN-TURB | VEN-INST | 2400315273 | 4000H MAIN GEN SERVICE HBDC-A-1660 | MAIN GEN SERVICE HBDC-A-1660 | REL PCNF MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-02-06 | 2024-01-18 | 20 | PCNF REL | APPR OPND | HB /D /60/HBDC-A-1660 | MAIN GENERATOR UNIT |  | C | DKHB-0641 | MMR | DK50 | MR0114
2026-W13-14 | C | HB-GEN2 | WPM | MTN-TURB | PRODTECH | 2400315273 | 4000H MAIN GEN SERVICE HBDC-A-1660 | DE-ISOLATION BY PRODUCTION | REL PCNF MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-02-06 | 2024-01-18 | 30 | PCNF REL | APPR OPND | HB /D /60/HBDC-A-1660 | MAIN GENERATOR UNIT |  | C | DKHB-0641 | MMR | DK50 | MR0114
2024-W23-24 | C | HBD-IPHP | WPM | MTN-TURB | MTN-TURB | 2400315275 | 2500H TURBINE ENGINE WASH - HBDC-CT-4352 | TURBINE ENGINE WASH - HBDC-CT-4352 | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 7 | 0 |  | 2024-05-11 | 2024-05-12 | 2024-05-11 | 2024-04-13 | 2024-03-25 | 10 | REL | APPR OPND | HB /D /31/HBDC-A-4352 | IP/HP COMPRESSOR UNIT |  | C | DKHB-4001 | MMR | DK50 | MR0094
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315846 | 2Y 400V UPS-DP INSPECTION HBDC-DP-1965 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-04-22 | 2024-03-07 | 10 | REL | APPR OPND | HB /D /06/HBDC-DP-1965 | 400/230VAC UPS SUB DISTRIBUTION PANEL A |  | A | DKHB-0434 | MEL | DK50 | EL0024 |  | 2024-04-29
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315846 | 2Y 400V UPS-DP INSPECTION HBDC-DP-1965 | 400V UPS-DP INSPECTION HBDC-DP-1965 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-04-22 | 2024-03-07 | 20 | REL | APPR OPND | HB /D /06/HBDC-DP-1965 | 400/230VAC UPS SUB DISTRIBUTION PANEL A |  | A | DKHB-0434 | MEL | DK50 | EL0024 |  | 2024-04-30
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315846 | 2Y 400V UPS-DP INSPECTION HBDC-DP-1965 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-07 | 2024-06-08 | 2024-06-08 | 2024-04-22 | 2024-03-07 | 30 | REL | APPR OPND | HB /D /06/HBDC-DP-1965 | 400/230VAC UPS SUB DISTRIBUTION PANEL A |  | A | DKHB-0434 | MEL | DK50 | EL0024 |  | 2024-05-01
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315847 | 2Y 400V UPS-DP INSPECTION HBDC-DP-1966 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-04-22 | 2024-03-07 | 10 | REL | APPR OPND | HB /D /06/HBDC-DP-1966 | 400/230VAC UPS SUB DISTRIBUTION PANEL B |  | A | DKHB-0435 | MEL | DK50 | EL0024 |  | 2024-04-29
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315847 | 2Y 400V UPS-DP INSPECTION HBDC-DP-1966 | 400V UPS-DP INSPECTION HBDC-DP-1966 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-04-22 | 2024-03-07 | 20 | REL | APPR OPND | HB /D /06/HBDC-DP-1966 | 400/230VAC UPS SUB DISTRIBUTION PANEL B |  | A | DKHB-0435 | MEL | DK50 | EL0024 |  | 2024-04-30
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315847 | 2Y 400V UPS-DP INSPECTION HBDC-DP-1966 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-07 | 2024-06-08 | 2024-06-08 | 2024-04-22 | 2024-03-07 | 30 | REL | APPR OPND | HB /D /06/HBDC-DP-1966 | 400/230VAC UPS SUB DISTRIBUTION PANEL B |  | A | DKHB-0435 | MEL | DK50 | EL0024 |  | 2024-05-02
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315848 | 2Y 400V UPS-DP INSPECTION HBDD-DP-1967 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-07 | 2024-07-08 | 2024-07-07 | 2024-04-22 | 2024-03-07 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1967 | 400/230VAC UPS SUB DISTRIBUTION PANEL C |  | A | DKHB-0436 | MEL | DK50 | EL0024 |  | 2024-05-01
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315848 | 2Y 400V UPS-DP INSPECTION HBDD-DP-1967 | 400V UPS-DP INSPECTION HBDD-DP-1967 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-07-07 | 2024-07-08 | 2024-07-07 | 2024-04-22 | 2024-03-07 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1967 | 400/230VAC UPS SUB DISTRIBUTION PANEL C |  | A | DKHB-0436 | MEL | DK50 | EL0024 |  | 2024-05-02
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315848 | 2Y 400V UPS-DP INSPECTION HBDD-DP-1967 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-07-07 | 2024-07-08 | 2024-07-08 | 2024-04-22 | 2024-03-07 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1967 | 400/230VAC UPS SUB DISTRIBUTION PANEL C |  | A | DKHB-0436 | MEL | DK50 | EL0024 |  | 2024-05-04
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315849 | 2Y 400V UPS-DP INSPECTION HBDD-DP-1960 | ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-04-22 | 2024-03-07 | 10 | REL | APPR OPND | HB /D /06/HBDD-DP-1960 | 400/230VAC UPS DISTRIBUTION PANEL |  | A | DKHB-0437 | MEL | DK50 | EL0024 |  | 2024-05-01
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315849 | 2Y 400V UPS-DP INSPECTION HBDD-DP-1960 | 400V UPS-DP INSPECTION HBDD-DP-1960 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-04-22 | 2024-03-07 | 20 | REL | APPR OPND | HB /D /06/HBDD-DP-1960 | 400/230VAC UPS DISTRIBUTION PANEL |  | A | DKHB-0437 | MEL | DK50 | EL0024 |  | 2024-05-02
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315849 | 2Y 400V UPS-DP INSPECTION HBDD-DP-1960 | DE-ISOLATION ELECTRICAL | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-06-07 | 2024-06-08 | 2024-06-08 | 2024-04-22 | 2024-03-07 | 30 | REL | APPR OPND | HB /D /06/HBDD-DP-1960 | 400/230VAC UPS DISTRIBUTION PANEL |  | A | DKHB-0437 | MEL | DK50 | EL0024 |  | 2024-05-03
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400315858 | 2Y 400V E-DP INSP HBDD-LP-1811 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-07 | 2024-03-08 | 2024-03-07 | 2024-04-22 | 2024-03-07 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1811 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | C | DKHB-0458 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400315858 | 2Y 400V E-DP INSP HBDD-LP-1811 | 400V E-DP INSP HBDD-LP-1811 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-03-07 | 2024-03-08 | 2024-03-07 | 2024-04-22 | 2024-03-07 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1811 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | C | DKHB-0458 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400315858 | 2Y 400V E-DP INSP HBDD-LP-1811 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-07 | 2024-03-08 | 2024-03-08 | 2024-04-22 | 2024-03-07 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1811 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | C | DKHB-0458 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400315859 | 2Y 400V E-DP INSP HBDD-LP-1813 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-07 | 2024-03-08 | 2024-03-07 | 2024-04-22 | 2024-03-07 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1813 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | C | DKHB-0459 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400315859 | 2Y 400V E-DP INSP HBDD-LP-1813 | 400V E-DP INSP HBDD-LP-1813 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-03-07 | 2024-03-08 | 2024-03-07 | 2024-04-22 | 2024-03-07 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1813 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | C | DKHB-0459 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400315859 | 2Y 400V E-DP INSP HBDD-LP-1813 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-07 | 2024-03-08 | 2024-03-08 | 2024-04-22 | 2024-03-07 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1813 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | C | DKHB-0459 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400315860 | 2Y 400V E-DP INSP HBDD-LP-1814 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-07 | 2024-03-08 | 2024-03-07 | 2024-04-22 | 2024-03-07 | 10 | REL | APPR OPND | HB /D /05/HBDD-LP-1814 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | C | DKHB-0460 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400315860 | 2Y 400V E-DP INSP HBDD-LP-1814 | 400V E-DP INSP HBDD-LP-1814 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-03-07 | 2024-03-08 | 2024-03-07 | 2024-04-22 | 2024-03-07 | 20 | REL | APPR OPND | HB /D /05/HBDD-LP-1814 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | C | DKHB-0460 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400315860 | 2Y 400V E-DP INSP HBDD-LP-1814 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-07 | 2024-03-08 | 2024-03-07 | 2024-04-22 | 2024-03-07 | 30 | REL | APPR OPND | HB /D /05/HBDD-LP-1814 | EMERGENCY LIGHTING & SMALL POWER DISTRIB |  | C | DKHB-0460 | MEL | DK50 | EL0024
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400315908 | PIGGING, P4303 - 14" HBA-HDA OIL 2W | P4303_HBA-HDA | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-04-20 | 2024-04-20 | 2024-04-20 | 2024-04-26 | 2024-04-20 | 10 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A | DK610077786 | INP | DK50
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400316138 | PIGGING, P4312 - 20" HBB-DFG GAS 6W | P4312_HBB-DFG | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2024-05-01 | 2024-04-16 | 10 | REL | APPR OPND | HB /B /34/HBBY-PL-674312 | P4312 - 20" HBB-DFG GAS PIPELINE |  | A | DKPLCLEAN01 | INP | DK50
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400321363 | PIGGING, P4303 - 14" HBA-HDA OIL 2W | P4303_HBA-HDA | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-04 | 2024-05-04 | 2024-05-04 | 2024-05-10 | 2024-05-04 | 10 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A | DK610077786 | INP | DK50
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322703 | 2Y 400V E-SWB INSP HBCA-N-1840 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840 | EMERGENCY SWBD. (RENAMED A&B) |  | C | DKHB-0410 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322703 | 2Y 400V E-SWB INSP HBCA-N-1840 | 400V E-SWB INSP HBCA-N-1840 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-05-22 | 2024-04-06 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840 | EMERGENCY SWBD. (RENAMED A&B) |  | C | DKHB-0410 | MEL | DK50 | EL0024
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400322703 | 2Y 400V E-SWB INSP HBCA-N-1840 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-08-06 | 2024-08-07 | 2024-08-07 | 2024-05-22 | 2024-04-06 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840 | EMERGENCY SWBD. (RENAMED A&B) |  | C | DKHB-0410 | MEL | DK50 | EL0024
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322706 | 2Y 24VDC UPS-DP INSP HBB | ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-12 | 2024-04-08 | 2024-05-22 | 2024-04-06 | 10 | REL | APPR OPND | HB /B /06/UPS-BOARDS-24V | 24V UPS DISTRIBUTION BOARDS |  | A | DKHB-0472 | MEL | DK50 | EL0024 | PROK | 2024-04-22
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322706 | 2Y 24VDC UPS-DP INSP HBB | 24VDC UPS-DP INSP HBB | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 23 | 0 | W15-W16 | 2024-04-08 | 2024-04-12 | 2024-04-08 | 2024-05-22 | 2024-04-06 | 20 | REL | APPR OPND | HB /B /06/UPS-BOARDS-24V | 24V UPS DISTRIBUTION BOARDS |  | A | DKHB-0472 | MEL | DK50 | EL0024 | PROK | 2024-04-23
2024-W17-18 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322706 | 2Y 24VDC UPS-DP INSP HBB | DE-ISOLATION ELECTRICAL | REL MANC NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-12 | 2024-04-12 | 2024-05-22 | 2024-04-06 | 30 | REL | APPR OPND | HB /B /06/UPS-BOARDS-24V | 24V UPS DISTRIBUTION BOARDS |  | A | DKHB-0472 | MEL | DK50 | EL0024 | PROK | 2024-04-26
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400325402 | PIGGING, P4303 - 14" HBA-HDA OIL 2W | P4303_HBA-HDA | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-24 | 2024-05-18 | 10 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A | DK610077786 | INP | DK50
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400328748 | 2Y 24VDC UPS-SWB INSPECTION HBAA-N-1802 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-04-22 | 2024-04-25 | 2024-04-22 | 2024-06-06 | 2024-04-21 | 10 | REL | APPR OPND | HB /A /06/HBAA-N-1802 | 24 V DC SWITCHBOARD |  | A | DKHB-0412 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400328748 | 2Y 24VDC UPS-SWB INSPECTION HBAA-N-1802 | 24VDC UPS-SWB INSPECTION HBAA-N-1802 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 22 | 0 |  | 2024-04-22 | 2024-04-25 | 2024-04-22 | 2024-06-06 | 2024-04-21 | 20 | REL | APPR OPND | HB /A /06/HBAA-N-1802 | 24 V DC SWITCHBOARD |  | A | DKHB-0412 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328748 | 2Y 24VDC UPS-SWB INSPECTION HBAA-N-1802 | 24VDC UPS-SWB INSPECTION HBAA-N-1802 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2024-04-22 | 2024-04-25 | 2024-04-23 | 2024-06-06 | 2024-04-21 | 30 | REL | APPR OPND | HB /A /06/HBAA-N-1802 | 24 V DC SWITCHBOARD |  | A | DKHB-0412 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400328748 | 2Y 24VDC UPS-SWB INSPECTION HBAA-N-1802 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-04-22 | 2024-04-25 | 2024-04-24 | 2024-06-06 | 2024-04-21 | 40 | REL | APPR OPND | HB /A /06/HBAA-N-1802 | 24 V DC SWITCHBOARD |  | A | DKHB-0412 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400328749 | 2Y 24 VDC N-SWB INSPECTION HBAA-N-1816 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-04-21 | 2024-04-22 | 2024-04-21 | 2024-06-06 | 2024-04-21 | 10 | REL | APPR OPND | HB /A /06/HBAA-N-1816 | MAIN SWITCH BOARD |  | A | DKHB-0413 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400328749 | 2Y 24 VDC N-SWB INSPECTION HBAA-N-1816 | 24 VDC N-SWB FUNC TEST HBAA-N-1816 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 8 | 0 |  | 2024-04-21 | 2024-04-22 | 2024-04-21 | 2024-06-06 | 2024-04-21 | 20 | REL | APPR OPND | HB /A /06/HBAA-N-1816 | MAIN SWITCH BOARD |  | A | DKHB-0413 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328749 | 2Y 24 VDC N-SWB INSPECTION HBAA-N-1816 | 24 VDC N-SWB FUNC TEST HBAA-N-1816 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-04-21 | 2024-04-22 | 2024-04-21 | 2024-06-06 | 2024-04-21 | 30 | REL | APPR OPND | HB /A /06/HBAA-N-1816 | MAIN SWITCH BOARD |  | A | DKHB-0413 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400328749 | 2Y 24 VDC N-SWB INSPECTION HBAA-N-1816 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-04-21 | 2024-04-22 | 2024-04-22 | 2024-06-06 | 2024-04-21 | 40 | REL | APPR OPND | HB /A /06/HBAA-N-1816 | MAIN SWITCH BOARD |  | A | DKHB-0413 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400328750 | 2Y 24 VDC N-DP INSPECTION HBAA-DP-1815 | ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2024-04-21 | 2024-04-22 | 2024-04-21 | 2024-06-06 | 2024-04-21 | 10 | REL | APPR OPND | HB /A /06/HBAA-DP-1815 | DISTRIBUTION PANEL 24VDC |  | A | DKHB-0414 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400328750 | 2Y 24 VDC N-DP INSPECTION HBAA-DP-1815 | 24 VDC N-DP INSPECTION HBAA-DP-1815 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 6 | 0 |  | 2024-04-21 | 2024-04-22 | 2024-04-21 | 2024-06-06 | 2024-04-21 | 20 | REL | APPR OPND | HB /A /06/HBAA-DP-1815 | DISTRIBUTION PANEL 24VDC |  | A | DKHB-0414 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328750 | 2Y 24 VDC N-DP INSPECTION HBAA-DP-1815 | 24 VDC N-DP INSPECTION HBAA-DP-1815 | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-04-21 | 2024-04-22 | 2024-04-21 | 2024-06-06 | 2024-04-21 | 30 | REL | APPR OPND | HB /A /06/HBAA-DP-1815 | DISTRIBUTION PANEL 24VDC |  | A | DKHB-0414 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400328750 | 2Y 24 VDC N-DP INSPECTION HBAA-DP-1815 | DE-ISOLATION BY PRODUCTION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 3 | 0 |  | 2024-04-21 | 2024-04-22 | 2024-04-22 | 2024-06-06 | 2024-04-21 | 40 | REL | APPR OPND | HB /A /06/HBAA-DP-1815 | DISTRIBUTION PANEL 24VDC |  | A | DKHB-0414 | MEL | DK50 | EL0024 | PROK
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400328799 | PIGGING, P4303 - 14" HBA-HDA OIL 2W | P4303_HBA-HDA | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-07 | 2024-06-01 | 10 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A | DK610077786 | INP | DK50
2026-W13-14 | C | NOSD | WPM | PRODLABO | PRODLABO | 2400329446 | 2M GAS SAMPLE FOR CO2 EMISSION | GAS SAMPLE FOR CO2 EMISSION | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2024-05-31 | 2024-05-31 | 2024-05-31 | 2024-06-11 | 2024-05-31 | 10 | REL | APPR OPND | HB /D /70/HBDC-V-5755 | MP FUEL GAS BUFFER VESSEL |  | A | DK600007513 | PRD | DK50
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400329645 | PIGGING, P4303 - 14" HBA-HDA OIL 2W | P4303_HBA-HDA | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-15 | 2024-06-15 | 2024-06-15 | 2024-06-21 | 2024-06-15 | 10 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A | DK610077786 | INP | DK50
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400329648 | PIGGING, P4312 - 20" HBB-DFG GAS 6W | P4312_HBB-DFG | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2024-06-12 | 2024-05-28 | 10 | REL | APPR OPND | HB /B /34/HBBY-PL-674312 | P4312 - 20" HBB-DFG GAS PIPELINE |  | A | DKPLCLEAN01 | INP | DK50
2026-W13-14 | D | NOSD | WPM | PRODTECH | PRODTECH | 2400333252 | PIGGING, P4303 - 14" HBA-HDA OIL 2W | P4303_HBA-HDA | REL NMAT PRC SETC | APPR AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2024-06-29 | 2024-06-29 | 2024-06-29 | 2024-07-05 | 2024-06-29 | 10 | REL | APPR OPND | HB /A /12/HBAY-PL-674303 | P4303 - 14" HBA-HDA OIL PIPELINE |  | A | DK610077786 | INP | DK50
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100032577 | Defect filter cartridge HDB-FIL-1206 | Erect scaffold | REL GMPS MANC PRC SETC | APPR APOG WMAT RDBL | 8 | 0 |  | 2024-09-15 | 2024-12-19 | 2024-09-15 | 2020-09-16 | 2020-06-18 | 10 | REL | APPR OPND | HD /B /09/HDBM-FIL-1206 | FILTER COALESCER |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100032577 | Defect filter cartridge HDB-FIL-1206 | Isolate | REL GMPS MANC PRC SETC | APPR APOG WMAT RDBL | 3 | 0 |  | 2024-09-15 | 2024-12-19 | 2024-09-17 | 2020-09-16 | 2020-06-18 | 20 | REL | APPR OPND | HD /B /09/HDBM-FIL-1206 | FILTER COALESCER |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100032577 | Defect filter cartridge HDB-FIL-1206 | Take down and backload filters | REL GMPS MANC PRC SETC | APPR APOG WMAT RDBL | 3 | 0 |  | 2024-09-15 | 2024-12-19 | 2024-09-17 | 2020-09-16 | 2020-06-18 | 30 | REL | APPR OPND | HD /B /09/HDBM-FIL-1206 | FILTER COALESCER |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100032577 | Defect filter cartridge HDB-FIL-1206 | Install new filters when manufactured | REL GMPS MANC PRC SETC | APPR APOG WMAT RDBL | 3 | 0 |  | 2024-09-15 | 2024-12-19 | 2024-12-18 | 2020-09-16 | 2020-06-18 | 40 | REL | APPR OPND | HD /B /09/HDBM-FIL-1206 | FILTER COALESCER |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100032577 | Defect filter cartridge HDB-FIL-1206 | De-isolate | REL GMPS MANC PRC SETC | APPR APOG WMAT RDBL | 2 | 0 |  | 2024-09-15 | 2024-12-19 | 2024-12-19 | 2020-09-16 | 2020-06-18 | 50 | REL | APPR OPND | HD /B /09/HDBM-FIL-1206 | FILTER COALESCER |  | A |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100032577 | Defect filter cartridge HDB-FIL-1206 | Remove scaffold | REL GMPS MANC PRC SETC | APPR APOG WMAT RDBL | 6 | 0 |  | 2024-09-15 | 2024-12-19 | 2024-12-19 | 2020-09-16 | 2020-06-18 | 60 | REL | APPR OPND | HD /B /09/HDBM-FIL-1206 | FILTER COALESCER |  | A |  | MEL | DK60 |  | PROK
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100045751 | LOTI: Findings on pot water maker HBCM-A | Prepare Permit/Tools/Matr | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 2 | 1 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-25 | 2021-04-04 | 2021-02-23 | 10 | PCNF REL | APPR OPND | HB /C /85/HBCM-A-1032 | POTABLE WATER MAKER UNIT | 99000121 | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100045751 | LOTI: Findings on pot water maker HBCM-A | Prod isolation/permit | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 3 | 31 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-25 | 2021-04-04 | 2021-02-23 | 20 | PCNF REL | APPR OPND | HB /C /85/HBCM-A-1032 | POTABLE WATER MAKER UNIT | 99000121 | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100045751 | LOTI: Findings on pot water maker HBCM-A | Replace/repair faulty parts | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 8 | 38 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-25 | 2021-04-04 | 2021-02-23 | 30 | PCNF REL | APPR OPND | HB /C /85/HBCM-A-1032 | POTABLE WATER MAKER UNIT | 99000121 | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-INST | 2100045751 | LOTI: Findings on pot water maker HBCM-A | Replace/repair faulty parts | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 8 | 14 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-25 | 2021-04-04 | 2021-02-23 | 40 | PCNF REL | APPR OPND | HB /C /85/HBCM-A-1032 | POTABLE WATER MAKER UNIT | 99000121 | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100045751 | LOTI: Findings on pot water maker HBCM-A | Prod deisolate w function/leak test | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 2 | 0 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-27 | 2021-04-04 | 2021-02-23 | 50 | PCNF REL | APPR OPND | HB /C /85/HBCM-A-1032 | POTABLE WATER MAKER UNIT | 99000121 | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100045751 | LOTI: Findings on pot water maker HBCM-A | Housekeeping | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 1 | 1 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-27 | 2021-04-04 | 2021-02-23 | 60 | PCNF REL | APPR OPND | HB /C /85/HBCM-A-1032 | POTABLE WATER MAKER UNIT | 99000121 | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100045751 | LOTI: Findings on pot water maker HBCM-A | New gauge type | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 0 | 0 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-25 | 2021-04-04 | 2021-02-23 | 70 | PCNF REL | APPR OPND | HB /C /85/HBCM-A-1032 | POTABLE WATER MAKER UNIT | 99000121 | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100045751 | LOTI: Findings on pot water maker HBCM-A | Replace calibration pots | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 4 | 0 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-25 | 2021-04-04 | 2021-02-23 | 80 | PCNF REL | APPR OPND | HB /C /85/HBCM-A-1032 | POTABLE WATER MAKER UNIT | 99000121 | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100045751 | LOTI: Findings on pot water maker HBCM-A | Replace solenoids | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 2 | 0 | W13-W14 | 2024-03-25 | 2024-03-27 | 2024-03-25 | 2021-04-04 | 2021-02-23 | 90 | PCNF REL | APPR OPND | HB /C /85/HBCM-A-1032 | POTABLE WATER MAKER UNIT | 99000121 | C |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | HBFUELG | WDF | MTN-MECH | MTN-RIGG | 2100055906 | Malfunction on HBDC-PCV-575101 | Prepare rigging plan | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 2 | 2 | W43-44 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-01-13 | 2021-10-15 | 5 | PCNF REL | INIT OPND | HB /D /70/HBDC-PCV-575101 | PRESSURE CONTROL VALVE | 99000119 | F |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | HBFUELG | WDF | MTN-MECH | MTN-MECH | 2100055906 | Malfunction on HBDC-PCV-575101 | Prepare matr/tools | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 2 | 9 | W43-44 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-01-13 | 2021-10-15 | 10 | PCNF REL | APPR OPND | HB /D /70/HBDC-PCV-575101 | PRESSURE CONTROL VALVE | 99000119 | F |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | HBFUELG | WDF | MTN-MECH | MTN-MECH | 2100055906 | Malfunction on HBDC-PCV-575101 | Production isolation | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 3 | 0 | W43-44 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-01-13 | 2021-10-15 | 20 | PCNF REL | APPR OPND | HB /D /70/HBDC-PCV-575101 | PRESSURE CONTROL VALVE | 99000119 | F |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | HBFUELG | WDF | MTN-MECH | MTN-RIGG | 2100055906 | Malfunction on HBDC-PCV-575101 | Rigger Assistance | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 4 | 1 | W43-44 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-01-13 | 2021-10-15 | 30 | PCNF REL | APPR OPND | HB /D /70/HBDC-PCV-575101 | PRESSURE CONTROL VALVE | 99000119 | F |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | HBFUELG | WDF | MTN-MECH | MTN-MECH | 2100055906 | Malfunction on HBDC-PCV-575101 | Replace Vlv internals | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 12 | 0 | W43-44 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-01-13 | 2021-10-15 | 40 | PCNF REL | APPR OPND | HB /D /70/HBDC-PCV-575101 | PRESSURE CONTROL VALVE | 99000119 | F |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | HBFUELG | WDF | MTN-MECH | MTN-INST | 2100055906 | Malfunction on HBDC-PCV-575101 | Function/Stroke test | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 2 | 0 | W43-44 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-01-13 | 2021-10-15 | 50 | PCNF REL | APPR OPND | HB /D /70/HBDC-PCV-575101 | PRESSURE CONTROL VALVE | 99000119 | F |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | HBFUELG | WDF | MTN-MECH | MTN-MECH | 2100055906 | Malfunction on HBDC-PCV-575101 | Function/Stroke test | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 2 | 0 | W43-44 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-01-13 | 2021-10-15 | 60 | PCNF REL | APPR OPND | HB /D /70/HBDC-PCV-575101 | PRESSURE CONTROL VALVE | 99000119 | F |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | HBFUELG | WDF | MTN-MECH | MTN-MECH | 2100055906 | Malfunction on HBDC-PCV-575101 | Production deisolation w leak test | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 3 | 0 | W43-44 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-01-13 | 2021-10-15 | 70 | PCNF REL | APPR OPND | HB /D /70/HBDC-PCV-575101 | PRESSURE CONTROL VALVE | 99000119 | F |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100065398 | HT broken HBDC-DP-1870-79 | Raise scaffolding 1. time | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 48 | 33 | W49-50 | 2024-08-03 | 2024-08-04 | 2023-12-13 | 2022-07-10 | 2022-04-11 | 50 | PCNF REL | APPR OPND | HB /D /61/HBDC-DP-1870-79 | HEAT TRACING (HTJB-1870-0079) |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100065398 | HT broken HBDC-DP-1870-79 | Remove insulation | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 24 | 0 |  | 2024-08-03 | 2024-08-04 | 2024-08-03 | 2022-07-10 | 2022-04-11 | 70 | PCNF REL | APPR OPND | HB /D /61/HBDC-DP-1870-79 | HEAT TRACING (HTJB-1870-0079) |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100065398 | HT broken HBDC-DP-1870-79 | Install insulation | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 24 | 0 |  | 2024-08-03 | 2024-08-04 | 2024-08-03 | 2022-07-10 | 2022-04-11 | 100 | PCNF REL | APPR OPND | HB /D /61/HBDC-DP-1870-79 | HEAT TRACING (HTJB-1870-0079) |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100065398 | HT broken HBDC-DP-1870-79 | Megger test heat trace circuit | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 1 | 0 |  | 2024-08-03 | 2024-08-04 | 2024-08-03 | 2022-07-10 | 2022-04-11 | 110 | PCNF REL | APPR OPND | HB /D /61/HBDC-DP-1870-79 | HEAT TRACING (HTJB-1870-0079) |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100065398 | HT broken HBDC-DP-1870-79 | Remove scaffolding 1. time | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 48 | 20 |  | 2024-08-03 | 2024-08-04 | 2024-08-03 | 2022-07-10 | 2022-04-11 | 130 | PCNF REL | APPR OPND | HB /D /61/HBDC-DP-1870-79 | HEAT TRACING (HTJB-1870-0079) |  | C |  | MEL | DK50
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100071227 | %Defect breaker for HDBM-FANM-1201A | Isolate and prove dead | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-01-02 | 2022-08-20 | 10 | PCNF REL | APPR OPND | HD /B /61/HDBE-N-1811-05-01 | HDBD-FAN-1201A, AHU-1 |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071227 | %Defect breaker for HDBM-FANM-1201A | Change breaker for HDBM-FANM-1201A | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 4 | 1 | W45-46 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-01-02 | 2022-08-20 | 20 | PCNF REL | APPR OPND | HD /B /61/HDBE-N-1811-05-01 | HDBD-FAN-1201A, AHU-1 |  | C |  | MEL | DK60
0 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100071227 | %Defect breaker for HDBM-FANM-1201A | De-isolate and test | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-01-02 | 2022-08-20 | 30 | PCNF REL | APPR OPND | HD /B /61/HDBE-N-1811-05-01 | HDBD-FAN-1201A, AHU-1 |  | C |  | MEL | DK60
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100077372 | Change breaker in HBCA-N-1840A-5-6 | Isolate and prove dead | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 1 | 0 | W47-48 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2023-05-02 | 2022-12-18 | 10 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-5-6 | POTABALE WATER MAKER UNIT HBCM-LCP-1001 |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100077372 | Change breaker in HBCA-N-1840A-5-6 | Change breaker OBS rebuild with old part | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 6 | 0 | W47-48 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2023-05-02 | 2022-12-18 | 20 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-5-6 | POTABALE WATER MAKER UNIT HBCM-LCP-1001 |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100077372 | Change breaker in HBCA-N-1840A-5-6 | De-isolate and test | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT SCH RDBL | 1 | 0 | W47-48 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2023-05-02 | 2022-12-18 | 30 | REL | APPR OPND | HB /C /05/HBCA-N-1840A-5-6 | POTABALE WATER MAKER UNIT HBCM-LCP-1001 |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096930 | Blower 0392 not working FWP 0332 | Blower 0392 not working FWP 0332 | REL GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 0 | 0 | 24-W05-06 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-01-05 | 2023-08-23 | 10 | REL | APPR OPND | HB /C /01/HBCM-BM-0392 | PKG VENTILATION FAN |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100096930 | Blower 0392 not working FWP 0332 | Isolate and prove dead | REL GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 1 | 0 | 24-W05-06 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-01-05 | 2023-08-23 | 20 | REL | APPR OPND | HB /C /01/HBCM-BM-0392 | PKG VENTILATION FAN |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096930 | Blower 0392 not working FWP 0332 | Faultfinding. | REL GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 3 | 0 | 24-W05-06 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-01-05 | 2023-08-23 | 30 | REL | APPR OPND | HB /C /01/HBCM-BM-0392 | PKG VENTILATION FAN |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096930 | Blower 0392 not working FWP 0332 | Demount old cable | REL GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 2 | 0 | 24-W05-06 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-01-05 | 2023-08-23 | 40 | REL | APPR OPND | HB /C /01/HBCM-BM-0392 | PKG VENTILATION FAN |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096930 | Blower 0392 not working FWP 0332 | Mount new cable | REL GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 3 | 0 | 24-W05-06 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-01-05 | 2023-08-23 | 50 | REL | APPR OPND | HB /C /01/HBCM-BM-0392 | PKG VENTILATION FAN |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100096930 | Blower 0392 not working FWP 0332 | Deisolate and test. | REL GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 1 | 0 | 24-W05-06 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-01-05 | 2023-08-23 | 60 | REL | APPR OPND | HB /C /01/HBCM-BM-0392 | PKG VENTILATION FAN |  | C |  | MEL | DK50 |  | PROK
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | 2200009824-0002-COATING | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 0 | 10 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 2 | PCNF REL | APPR OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | 2200009824-0003-CONSUMER-GOODS | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 0 | 0 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 3 | PCNF REL | APPR OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | 2200009824-0004-RENT-ALTRAD | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 0 | 0 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 4 | PCNF REL | APPR OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | 2200009824-0005-RENT-MOURITSEN | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 0 | 0 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 5 | PCNF REL | APPR OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | 2022 FM-Paint Campaign DK50-IM-2250 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 0 | 0 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 10 | PCNF REL | APPR OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | BULK 1; PREP SCAF/ROPE/GEAR + DISMANTLE | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 60 | 108 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 20 | PCNF REL | APPR OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | BULK 2; TEST, QC-LOG; HARD-SOFT BARRIERS | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 15 | 29 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 30 | PCNF REL | APPR OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | BULK 3; CLEAN, BLAST, TOOLS, CLEAN-UP | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 75 | 654 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 40 | PCNF REL | APPR OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | BULK 4; PRIMER CLOSE SURFACE | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 15 | 84 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 50 | PCNF REL | APPR OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | BULK 5; REPAINT TO SPEC | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 75 | 369 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 60 | PCNF REL | APPR OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | BULK 6; WASTE, CLEAN-UP, RE-PREP | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 24 | 130 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 70 | PCNF REL | APPR OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | Altrad container 44148 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 0 | 0 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 90 | PCNF REL | INIT OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | HBC Level 2 Bulkhead - 2200009824 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 250 | 40 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 100 | PCNF REL | INIT OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200009824 | ANOC 2022 FM-Paint Campaign DK50-M-2250 | HBA Level 1 structur | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT SCH RDBL | 40 | 0 |  | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2022-09-28 | 2022-05-01 | 110 | PCNF REL | INIT OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
0 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100026386 | Replacement dewpoint transmitter Air com | Isolate equipment | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 1 | 0 | W41-42 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2020-02-19 | 2019-11-21 | 10 | PCNF REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | C |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100026386 | Replacement dewpoint transmitter Air com | Exchange dewmeter | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 3 | 3 | W41-42 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2020-02-19 | 2019-11-21 | 20 | PCNF REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | C |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-INST | PRODTECH | 2100026386 | Replacement dewpoint transmitter Air com | Remove isolation | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 1 | 0 | W41-42 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2020-02-19 | 2019-11-21 | 30 | PCNF REL | APPR OPND | HD /B /07/HDBC-A-5401 | PACKAGE |  | C |  | MMS | DK60
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100045752 | Replace Defect HPFI relays N-1801 | Isolate accordingly | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 2 | 0.5 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-06-05 | 2021-03-07 | 10 | PCNF REL | APPR OPND | HB /A /61/HBAA-N-1801 | LOW VOLTAGE SWITCHBOARD |  | F |  | MEL | DK50 |  |  | 2024-05-25
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100045752 | Replace Defect HPFI relays N-1801 | Replace relays | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 12 | 6 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-06-05 | 2021-03-07 | 20 | PCNF REL | APPR OPND | HB /A /61/HBAA-N-1801 | LOW VOLTAGE SWITCHBOARD |  | F |  | MEL | DK50 |  |  | 2024-05-26
2024-W25-26 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100045752 | Replace Defect HPFI relays N-1801 | De-isolate above | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 2 | 0.5 |  | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-06-05 | 2021-03-07 | 30 | PCNF REL | APPR OPND | HB /A /61/HBAA-N-1801 | LOW VOLTAGE SWITCHBOARD |  | F |  | MEL | DK50 |  |  | 2024-05-28
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100053901 | HT Replace damaged cable | Install insulation | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 12 | 0 |  | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2022-08-06 | 2021-12-09 | 30 | PCNF REL | APPR OPND | HB /A /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053901 | HT Replace damaged cable | Additional materials | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 0 |  | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2022-08-06 | 2021-12-09 | 60 | PCNF REL | INIT OPND | HB /A /79 | INSULATION/TRACE HEATING |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100073750 | P-5026 has defective memebranes | Isolate P-5026 | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-08 | 2023-02-27 | 2022-10-15 | 20 | REL | APPR OPND | HB /B /20/HBBA-P-5026 | PUMP |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100073750 | P-5026 has defective memebranes | Exhange membrane and check valves | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 15 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-08 | 2023-02-27 | 2022-10-15 | 30 | REL | APPR OPND | HB /B /20/HBBA-P-5026 | PUMP |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100073750 | P-5026 has defective memebranes | De-isolate P-5026 | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-11 | 2023-02-27 | 2022-10-15 | 40 | REL | APPR OPND | HB /B /20/HBBA-P-5026 | PUMP |  | A |  | MMR | DK50 |  | PROK
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100073750 | P-5026 has defective memebranes | additional materials | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-08 | 2023-02-27 | 2022-10-15 | 60 | REL | APPR OPND | HB /B /20/HBBA-P-5026 | PUMP |  | A |  | MMR | DK50 |  | PROK
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100084633 | New breaker for PM-5915 in 1801-Q2 | Isolate HBAA-N-1801 and prove dead. | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 1 | 0 | W37-38 | 2024-03-09 | 2024-03-14 | 2024-03-09 | 2023-07-31 | 2023-03-18 | 10 | REL | APPR OPND | HB /A /61/HBAA-N-1801-Q02 | HYD CLEAN UP PUMP HBAA-PM-5915 |  | C |  | MEL | DK50
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100084633 | New breaker for PM-5915 in 1801-Q2 | replace breakers & relays | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 24 | 0 | W37-38 | 2024-03-09 | 2024-03-14 | 2024-03-09 | 2023-07-31 | 2023-03-18 | 20 | REL | APPR OPND | HB /A /61/HBAA-N-1801-Q02 | HYD CLEAN UP PUMP HBAA-PM-5915 |  | C |  | MEL | DK50
2024-W37-38 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100084633 | New breaker for PM-5915 in 1801-Q2 | De-isolate and test. | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 1 | 0 | W37-38 | 2024-03-09 | 2024-03-14 | 2024-03-14 | 2023-07-31 | 2023-03-18 | 30 | REL | APPR OPND | HB /A /61/HBAA-N-1801-Q02 | HYD CLEAN UP PUMP HBAA-PM-5915 |  | C |  | MEL | DK50
0 | 4 | NOSD | WGN | MTN-INST | PRODTECH | 2200003043 | CHNG out PI indicator well 29(HDA | Isolate flowline | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 3 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2018-12-19 | 2018-07-22 | 5 | REL | APPR OPND | HD /A /34/INSTRUMENTS | INSTRUMENTS |  | A |  | MIN | DK60
0 | 4 | NOSD | WGN | MTN-INST | MTN-SCAF | 2200003043 | CHNG out PI indicator well 29(HDA | Build hop-up | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 6 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2018-12-19 | 2018-07-22 | 10 | REL | APPR OPND | HD /A /34/INSTRUMENTS | INSTRUMENTS |  | A |  | MIN | DK60
0 | 4 | NOSD | WGN | MTN-INST | MTN-INST | 2200003043 | CHNG out PI indicator well 29(HDA | Place B&B, replace PI with new | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 2 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2018-12-19 | 2018-07-22 | 20 | REL | APPR OPND | HD /A /34/INSTRUMENTS | INSTRUMENTS |  | A |  | MIN | DK60
0 | 4 | NOSD | WGN | MTN-INST | PRODTECH | 2200003043 | CHNG out PI indicator well 29(HDA | Deisolate flowline | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 3 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2018-12-19 | 2018-07-22 | 40 | REL | APPR OPND | HD /A /34/INSTRUMENTS | INSTRUMENTS |  | A |  | MIN | DK60
0 | 4 | NOSD | WGN | MTN-INST | MTN-SCAF | 2200003043 | CHNG out PI indicator well 29(HDA | Remove hup-up | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 3 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2018-12-19 | 2018-07-22 | 50 | REL | APPR OPND | HD /A /34/INSTRUMENTS | INSTRUMENTS |  | A |  | MIN | DK60
0 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010706 | Inspections of transmitter-bolts on HDA | Inspections of transmitter-bolts on HDA | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 0 | W05-06 | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2022-07-05 | 2022-05-26 | 10 | REL | APPR OPND | HD /A /37 | INJECTION WELL |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010706 | Inspections of transmitter-bolts on HDA | Boltscan HDA - Week 47-2022 | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 20 | 0 | W05-06 | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2022-07-05 | 2022-05-26 | 20 | REL | APPR OPND | HD /A /37 | INJECTION WELL |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010706 | Inspections of transmitter-bolts on HDA | Boltscan HDA - Week 48-2022 | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 20 | 0 | W05-06 | 2024-09-15 | 2024-09-23 | 2024-09-17 | 2022-07-05 | 2022-05-26 | 30 | REL | APPR OPND | HD /A /37 | INJECTION WELL |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010706 | Inspections of transmitter-bolts on HDA | Boltscan HDA - Week 49-2022 | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 20 | 0 | W05-06 | 2024-09-15 | 2024-09-23 | 2024-09-19 | 2022-07-05 | 2022-05-26 | 40 | REL | APPR OPND | HD /A /37 | INJECTION WELL |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010706 | Inspections of transmitter-bolts on HDA | Boltscan HDA - Week 50-2022 | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 20 | 0 | W05-06 | 2024-09-15 | 2024-09-23 | 2024-09-21 | 2022-07-05 | 2022-05-26 | 50 | REL | APPR OPND | HD /A /37 | INJECTION WELL |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010706 | Inspections of transmitter-bolts on HDA | new charger | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-23 | 2024-09-23 | 2022-07-05 | 2022-05-26 | 60 | REL | APPR OPND | HD /A /37 | INJECTION WELL |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | MTN-INST | 2200010706 | Inspections of transmitter-bolts on HDA | PMI gun to be recertified | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-23 | 2024-09-23 | 2022-07-05 | 2022-05-26 | 80 | REL | INIT OPND | HD /A /37 | INJECTION WELL |  | A |  | MMS | DK60
0 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010706 | Inspections of transmitter-bolts on HDA | Return MPI gun to HBC Maintenance | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-23 | 2024-09-23 | 2022-07-05 | 2022-05-26 | 90 | REL | INIT OPND | HD /A /37 | INJECTION WELL |  | A |  | MMS | DK60
0 | 3 | NE | WGN | MTN-ELEC | MTN-ELEC | 2200016124 | Haldfan A CCR furniture | Haldfan A CCR furniture | REL GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-04-08 | 2023-11-25 | 10 | REL | APPR OPND | HD /B | HALFDAN DB |  | A |  | MEL | DK60
0 | 4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004501 | DK60 - HOURS MTN - FLM - FIRST LEVEL MTN | DK60 - HOURS MTN - FLM - FIRST LEVEL MTN | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 95 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 10 | PCNF REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK60
0 | 4 | NOSD | WRO | MTN-ELEC | MTN-TELE | 2300004501 | DK60 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Telecom | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 1854 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 20 | PCNF REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK60
0 | 4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004501 | DK60 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Elec | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 574 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 30 | PCNF REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK60
0 | 4 | NOSD | WRO | MTN-ELEC | MTN-INST | 2300004501 | DK60 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Inst | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 603 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 40 | PCNF REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK60
0 | 4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004501 | DK60 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Mech | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 410 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 50 | PCNF REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK60
0 | 4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004501 | DK60 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Turb | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 110 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 60 | PCNF REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK60
0 | 4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004501 | DK60 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for MPM team | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 65 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 70 | PCNF REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK60
0 | 4 | NOSD | WRO | MTN-ELEC | MTN-ROUS | 2300004501 | DK60 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Maint Deck | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 52 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 80 | PCNF REL | APPR OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK60
0 | 4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004501 | DK60 - HOURS MTN - FLM - FIRST LEVEL MTN | Hours booking for Vibration Monitoring | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 81 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 90 | PCNF REL | INIT OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK60
0 | 4 | NOSD | WRO | MTN-ELEC | MTN-RIGG | 2300004501 | DK60 - HOURS MTN - FLM - FIRST LEVEL MTN |  | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 100 | PCNF REL | INIT OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK60
0 | 4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004501 | DK60 - HOURS MTN - FLM - FIRST LEVEL MTN |  | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT RDBL | 0 | 5 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2026-01-02 | 2023-07-17 | 110 | PCNF REL | INIT OPND | HD /A /84 | WORKSHOP/WAREHOUSE |  | A |  | MMT | DK60
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-RIGG | 2100069947 | HCV's For deeluge valve internal leaking | Prepare rigging plan | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 6 | 2 |  | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2022-08-02 | 2022-06-23 | 5 | PCNF REL | INIT OPND | HB /D /01/HBDB-HCV-038070 | BUTTERFLY VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100069947 | HCV's For deeluge valve internal leaking | Prepare Rigger equip/Lifting operation | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 12 | 6 |  | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2022-08-02 | 2022-06-23 | 10 | PCNF REL | APPR OPND | HB /D /01/HBDB-HCV-038070 | BUTTERFLY VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100069947 | HCV's For deeluge valve internal leaking | Production isolation | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 3 | 0 |  | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2022-08-02 | 2022-06-23 | 20 | PCNF REL | APPR OPND | HB /D /01/HBDB-HCV-038070 | BUTTERFLY VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100069947 | HCV's For deeluge valve internal leaking | Replace HCV-038070 | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 8 | 0 |  | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2022-08-02 | 2022-06-23 | 30 | PCNF REL | APPR OPND | HB /D /01/HBDB-HCV-038070 | BUTTERFLY VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100069947 | HCV's For deeluge valve internal leaking | Production De-isolation w Leaktest | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 3 | 0 |  | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2022-08-02 | 2022-06-23 | 50 | PCNF REL | APPR OPND | HB /D /01/HBDB-HCV-038070 | BUTTERFLY VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100069947 | HCV's For deeluge valve internal leaking | Additional valve/studs | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 0 | 0 |  | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2022-08-02 | 2022-06-23 | 60 | PCNF REL | APPR OPND | HB /D /01/HBDB-HCV-038070 | BUTTERFLY VALVE | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HB-FLARE | WDF | MTN-MECH | MTN-MECH | 2100069947 | HCV's For deeluge valve internal leaking | Gaskets for valve replacement | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 0 | 0 |  | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2022-08-02 | 2022-06-23 | 70 | PCNF REL | APPR OPND | HB /D /01/HBDB-HCV-038070 | BUTTERFLY VALVE | 99000119 | F |  | MMS | DK50
0 | B | NOSD | WPM | MTN-MECH | PRODTECH | 2400268115 | 5Y ANODE REPLACEMENT JOCKEY PUMPS | ISOLATION | REL GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-05-16 | 2024-04-26 | 2023-08-06 | 2023-05-18 | 10 | REL | APPR OPND | HD /B /01/FW-JOCKEY PUMPS | FIREWATER JOCKEY PUMPS |  | A | DKHD-2048 | MMS | DK60 | MS0013
0 | B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400268115 | 5Y ANODE REPLACEMENT JOCKEY PUMPS | JOCKEY PUMPS HDBC-P-0302/0303 | REL GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 24 | 0 | W17-W18 | 2024-04-26 | 2024-05-16 | 2024-04-26 | 2023-08-06 | 2023-05-18 | 20 | REL | APPR OPND | HD /B /01/FW-JOCKEY PUMPS | FIREWATER JOCKEY PUMPS |  | A | DKHD-2048 | MMS | DK60 | MS0013
0 | B | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400268115 | 5Y ANODE REPLACEMENT JOCKEY PUMPS | Rigging assistance | REL GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 48 | 0 | W17-W18 | 2024-04-26 | 2024-05-16 | 2024-05-01 | 2023-08-06 | 2023-05-18 | 25 | REL | APPR OPND | HD /B /01/FW-JOCKEY PUMPS | FIREWATER JOCKEY PUMPS |  | A | DKHD-2048 | MMS | DK60 | MS0013
0 | B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400268115 | 5Y ANODE REPLACEMENT JOCKEY PUMPS | JOCKEY PUMPS HDBC-P-0302/0303 | REL GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 24 | 0 | W17-W18 | 2024-04-26 | 2024-05-16 | 2024-05-10 | 2023-08-06 | 2023-05-18 | 30 | REL | APPR OPND | HD /B /01/FW-JOCKEY PUMPS | FIREWATER JOCKEY PUMPS |  | A | DKHD-2048 | MMS | DK60 | MS0013
0 | B | NOSD | WPM | MTN-MECH | PRODTECH | 2400268115 | 5Y ANODE REPLACEMENT JOCKEY PUMPS | DE-ISOLATION | REL GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-05-16 | 2024-05-15 | 2023-08-06 | 2023-05-18 | 40 | REL | APPR OPND | HD /B /01/FW-JOCKEY PUMPS | FIREWATER JOCKEY PUMPS |  | A | DKHD-2048 | MMS | DK60 | MS0013
0 | B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400268115 | 5Y ANODE REPLACEMENT JOCKEY PUMPS | Additional materials | REL GMPS MANC PRC SETC | APPR APOG SMAT AWSC RDBL | 0 | 0 | W17-W18 | 2024-04-26 | 2024-05-16 | 2024-05-16 | 2023-08-06 | 2023-05-18 | 50 | REL | INIT OPND | HD /B /01/FW-JOCKEY PUMPS | FIREWATER JOCKEY PUMPS |  | A | DKHD-2048 | MMS | DK60 | MS0013
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100099382 | Rusty handel for fire hosereel defect | Change Rusty handels | REL GMPS MANC PRC SETC | APPR APOG SMAT AWDO SCH RFRZ ROUT | 2 | 0 | W09-W10 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-03-30 | 2023-11-16 | 10 | REL | APPR OPND | HD /B /01/HDBE-WHR-0301 | WATER HOSE REEL |  | A |  | MMS | DK60
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100053572 | HBC/78: Replace worn hydraulic hoses | Isolate crane HBCO-A-6101 | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL ROUT | 1 | 1 | W05-W06 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-09-04 | 2021-07-26 | 90 | PCNF REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100053572 | HBC/78: Replace worn hydraulic hoses | Build scaffold | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL ROUT | 25 | 29 | W05-W06 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-09-04 | 2021-07-26 | 95 | PCNF REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100053572 | HBC/78: Replace worn hydraulic hoses | Replace bulkhead fitting for hose pos 67 | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL ROUT | 3 | 0 | W05-W06 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-09-04 | 2021-07-26 | 100 | PCNF REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100053572 | HBC/78: Replace worn hydraulic hoses | Test, inspect for leaks | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL ROUT | 1 | 0 | W05-W06 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-09-04 | 2021-07-26 | 125 | PCNF REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100026255 | HBB/78: No indication of the windspeed | Isolate crane | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W49-50 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2020-01-15 | 2019-10-17 | 70 | PCNF REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100026255 | HBB/78: No indication of the windspeed | De-isolate crane for test | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W49-50 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2020-01-15 | 2019-10-17 | 90 | PCNF REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-INST | MTN-INST | 2100026255 | HBB/78: No indication of the windspeed | QC, functioncheck, Clean-up | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W49-50 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2020-01-15 | 2019-10-17 | 100 | PCNF REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072249 | HBB/78 Replace -Q01 power switch in X1 | Isolation/deisolation of crane | REL GMPS MANC PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 4 | 0 | W11-W12 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2023-01-22 | 2022-09-09 | 10 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072249 | HBB/78 Replace -Q01 power switch in X1 | Replace -Q01 power switch in X1 | REL GMPS MANC PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 6 | 0 | W11-W12 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2023-01-22 | 2022-09-09 | 20 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ROUS | 2100072249 | HBB/78 Replace -Q01 power switch in X1 | Assist VEN-CRAN and operating crane test | REL GMPS MANC PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 6 | 0 | W11-W12 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2023-01-22 | 2022-09-09 | 30 | REL | APPR OPND | HB /B /78/HBBB-X-6120 | CRANE - 14 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100079018 | HBD/78 Water pump for windshield | Isolation/deisolation of crane | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W49-50 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-05-29 | 2023-01-14 | 10 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079018 | HBD/78 Water pump for windshield | Replace sprinkler container | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W49-50 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2023-05-29 | 2023-01-14 | 20 | REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089857 | FWP-0331 jacket water bellow not aligned | Identify bellow and qty to be replaced | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 4 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-11 | 2023-10-11 | 2023-05-29 | 10 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089857 | FWP-0331 jacket water bellow not aligned | Measure and draw protection shield | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-11 | 2023-10-11 | 2023-05-29 | 20 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089857 | FWP-0331 jacket water bellow not aligned | Measure piping | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-12 | 2023-10-11 | 2023-05-29 | 30 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089857 | FWP-0331 jacket water bellow not aligned | Install Bellow protection | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 8 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-12 | 2023-10-11 | 2023-05-29 | 40 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100089857 | FWP-0331 jacket water bellow not aligned | Isolate FWP from start | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-14 | 2023-10-11 | 2023-05-29 | 50 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100089857 | FWP-0331 jacket water bellow not aligned | Drain coolant & refill with new type | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 6 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-14 | 2023-10-11 | 2023-05-29 | 60 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089857 | FWP-0331 jacket water bellow not aligned | Drain coolant & refill with new type | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 6 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-16 | 2023-10-11 | 2023-05-29 | 65 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100089857 | FWP-0331 jacket water bellow not aligned | Rigging assistance | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 10 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-17 | 2023-10-11 | 2023-05-29 | 70 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089857 | FWP-0331 jacket water bellow not aligned | Dismantle spool | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 10 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-19 | 2023-10-11 | 2023-05-29 | 80 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089857 | FWP-0331 jacket water bellow not aligned | Install new spool/compensator | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 10 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-21 | 2023-10-11 | 2023-05-29 | 90 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100089857 | FWP-0331 jacket water bellow not aligned | De-isolate | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-23 | 2023-10-11 | 2023-05-29 | 110 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100089857 | FWP-0331 jacket water bellow not aligned | Test run of FWP | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-23 | 2023-10-11 | 2023-05-29 | 120 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089857 | FWP-0331 jacket water bellow not aligned | Additional materials | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 0 | 0 | W11-W12 | 2024-03-11 | 2024-03-24 | 2024-03-24 | 2023-10-11 | 2023-05-29 | 130 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | E |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098014 | ANOPR: biocide inj joint to east manifol | Insp biocide inj joint to east manifold | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 0 | 0 | W43-44 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2023-12-30 | 2023-10-21 | 10 | REL | APPR OPND | HB /A /10/HBA-14-PHS-033-4005-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | F |  | MFM | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098014 | ANOPR: biocide inj joint to east manifol | Gathering materials /Breaking of flanges | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 3 | 0 | W43-44 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2023-12-30 | 2023-10-21 | 30 | REL | INIT OPND | HB /A /10/HBA-14-PHS-033-4005-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | F |  | MFM | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098014 | ANOPR: biocide inj joint to east manifol | Inspection of flanges faces | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W43-44 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2023-12-30 | 2023-10-21 | 40 | REL | INIT OPND | HB /A /10/HBA-14-PHS-033-4005-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | F |  | MFM | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098014 | ANOPR: biocide inj joint to east manifol | Machining of flange face | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 4 | 0 | W43-44 | 2024-08-22 | 2024-08-24 | 2024-08-23 | 2023-12-30 | 2023-10-21 | 50 | REL | INIT OPND | HB /A /10/HBA-14-PHS-033-4005-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | F |  | MFM | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098014 | ANOPR: biocide inj joint to east manifol | Installing gaskets and torguing up | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W43-44 | 2024-08-22 | 2024-08-24 | 2024-08-24 | 2023-12-30 | 2023-10-21 | 60 | REL | INIT OPND | HB /A /10/HBA-14-PHS-033-4005-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | F |  | MFM | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098014 | ANOPR: biocide inj joint to east manifol | Cleaning area | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W43-44 | 2024-08-22 | 2024-08-24 | 2024-08-24 | 2023-12-30 | 2023-10-21 | 70 | REL | INIT OPND | HB /A /10/HBA-14-PHS-033-4005-FE-U | 14 HIGH PRESS WELL SOUR LINE |  | F |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | VEN-ROPE | 2100045005 | ANOS HBA - Damaged conductor Supports | HBA - Damaged conductors | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO ROUT | 0 | 0 |  | 2022-04-18 | 2022-04-19 | 2022-04-18 | 2021-03-05 | 2021-01-24 | 10 | PCNF REL | APPR OPND | HB /A /86/CASSION | RISER CASSION | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100045005 | ANOS HBA - Damaged conductor Supports | Installation of support | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO ROUT | 108 | 281 |  | 2022-04-18 | 2022-04-19 | 2022-04-18 | 2021-03-05 | 2021-01-24 | 20 | PCNF REL | APPR OPND | HB /A /86/CASSION | RISER CASSION | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100045005 | ANOS HBA - Damaged conductor Supports | Urgent: PO for wedges in el. +2 & +12 | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO ROUT | 0 | 0 |  | 2022-04-18 | 2022-04-19 | 2022-04-18 | 2021-03-05 | 2021-01-24 | 30 | PCNF REL | APPR OPND | HB /A /86/CASSION | RISER CASSION | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100045005 | ANOS HBA - Damaged conductor Supports | PO for wedges in el. +2.000 & + 12.000 | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO ROUT | 0 | 0 |  | 2022-04-18 | 2022-04-19 | 2022-04-18 | 2021-03-05 | 2021-01-24 | 40 | PCNF REL | APPR OPND | HB /A /86/CASSION | RISER CASSION | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100045005 | ANOS HBA - Damaged conductor Supports | Wegdes + CTR | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO ROUT | 0 | 0 |  | 2022-04-18 | 2022-04-19 | 2022-04-18 | 2021-03-05 | 2021-01-24 | 50 | PCNF REL | APPR OPND | HB /A /86/CASSION | RISER CASSION | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100045005 | ANOS HBA - Damaged conductor Supports | Ordering materials. | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO ROUT | 0 | 0 |  | 2022-04-18 | 2022-04-19 | 2022-04-18 | 2021-03-05 | 2021-01-24 | 60 | PCNF REL | APPR OPND | HB /A /86/CASSION | RISER CASSION | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100045005 | ANOS HBA - Damaged conductor Supports | Drilling holes to mount gratings | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO ROUT | 5 | 5 |  | 2022-04-18 | 2022-04-19 | 2022-04-18 | 2021-03-05 | 2021-01-24 | 70 | PCNF REL | INIT OPND | HB /A /86/CASSION | RISER CASSION | 99000087 | A |  | MFM | DK50
2026-W13-14 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400281937 | 4Y SW FILTER INSPECTION HBDB-FIL-5364/5 | ISOLATION BY PRODUCTION | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO ROUT | 1 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-10-19 | 2023-07-23 | 10 | PCNF REL | APPR OPND | HB /D /51/HBDB-FIL-5364 | SEAWATER FILTER |  | C | DKHB-0091 | MMS | DK50 | MS0124
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-INST | 2400281937 | 4Y SW FILTER INSPECTION HBDB-FIL-5364/5 | SW FILTER INSPECTION HBDB-FIL-5364/5 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO ROUT | 6.5 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-10-19 | 2023-07-23 | 20 | PCNF REL | APPR OPND | HB /D /51/HBDB-FIL-5364 | SEAWATER FILTER |  | C | DKHB-0091 | MMS | DK50 | MS0124
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400281937 | 4Y SW FILTER INSPECTION HBDB-FIL-5364/5 | SW FILTER INSPECTION HBDB-FIL-5364/5 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO ROUT | 16 | 6 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-10-19 | 2023-07-23 | 30 | PCNF REL | APPR OPND | HB /D /51/HBDB-FIL-5364 | SEAWATER FILTER |  | C | DKHB-0091 | MMS | DK50 | MS0124
2026-W13-14 | C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400281937 | 4Y SW FILTER INSPECTION HBDB-FIL-5364/5 | SW FILTER INSPECTION HBDB-FIL-5364/5 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO ROUT | 2 | 59 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-10-19 | 2023-07-23 | 40 | PCNF REL | APPR OPND | HB /D /51/HBDB-FIL-5364 | SEAWATER FILTER |  | C | DKHB-0091 | MMS | DK50 | MS0124
2026-W13-14 | C | NOSD | WPM | MTN-MECH | PRODTECH | 2400281937 | 4Y SW FILTER INSPECTION HBDB-FIL-5364/5 | DE-ISOLATION BY PRODUCTION | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO ROUT | 1 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-10-19 | 2023-07-23 | 50 | PCNF REL | APPR OPND | HB /D /51/HBDB-FIL-5364 | SEAWATER FILTER |  | C | DKHB-0091 | MMS | DK50 | MS0124
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053198 | HBA/78: Replace cabin inlet filter | Find and check materials and tools | REL GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2022-03-20 | 2021-10-21 | 10 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053198 | HBA/78: Replace cabin inlet filter | Isolate crane HBAB-X-6130 | REL GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2022-03-20 | 2021-10-21 | 20 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053198 | HBA/78: Replace cabin inlet filter | Replace cabin inlet filter | REL GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2022-03-20 | 2021-10-21 | 30 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053198 | HBA/78: Replace cabin inlet filter | Check cable with bag around in unit | REL GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-09 | 2022-03-20 | 2021-10-21 | 40 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053198 | HBA/78: Replace cabin inlet filter | De-isolate crane HBAB-X-6130 | REL GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-10 | 2022-03-20 | 2021-10-21 | 50 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053198 | HBA/78: Replace cabin inlet filter | Functioncheck and clean-up | REL GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-03-09 | 2024-03-10 | 2024-03-10 | 2022-03-20 | 2021-10-21 | 60 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053200 | HBD/78: Replace engine room door | Isolate/de-isolate of crane HBDE-A-6150 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W09-W10 | 2024-03-09 | 2024-03-15 | 2024-03-09 | 2022-07-21 | 2021-11-23 | 30 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100053200 | HBD/78: Replace engine room door | Build/demol of scaff/gallows | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 30 | 0 | W09-W10 | 2024-03-09 | 2024-03-15 | 2024-03-09 | 2022-07-21 | 2021-11-23 | 35 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053200 | HBD/78: Replace engine room door | Replace engine room door | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 6 | 0 | W09-W10 | 2024-03-09 | 2024-03-15 | 2024-03-12 | 2022-07-21 | 2021-11-23 | 40 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100053200 | HBD/78: Replace engine room door | Assist with handling/lift of door | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 30 | 0 | W09-W10 | 2024-03-09 | 2024-03-15 | 2024-03-12 | 2022-07-21 | 2021-11-23 | 50 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100070622 | HBA/78: Sweating hoses for oil filter | Isolation/deisolation of crane | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 4 | 0 | 24-W05-06 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2022-12-24 | 2022-08-11 | 10 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100070622 | HBA/78: Sweating hoses for oil filter | Replace hoses for oil filter | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 24 | 0 | 24-W05-06 | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2022-12-24 | 2022-08-11 | 20 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100070622 | HBA/78: Sweating hoses for oil filter | Assist and operating crane at leaktest | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 6 | 0 | 24-W05-06 | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2022-12-24 | 2022-08-11 | 30 | REL | APPR OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100070622 | HBA/78: Sweating hoses for oil filter |  | REL PRT GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 0 | 0 | 24-W05-06 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2022-12-24 | 2022-08-11 | 40 | REL | INIT OPND | HB /A /78/HBAB-X-6130 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | C | NOSD | WPM | VEN-ELEC | VEN-MECH | 2400054639 | 3M NOx in Exhaust, VENDOR, HBD | NOX CONCENTRATION IN GASTURBINES | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 30 | 108 | SR request | 2023-09-18 | 2023-09-24 | 2023-09-18 | 2019-12-18 | 2019-11-29 | 10 | PCNF REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | A |  | PRD | DK50
2026-W13-14 | C | NOSD | WPM | VEN-ELEC | MTN-TURB | 2400054639 | 3M NOx in Exhaust, VENDOR, HBD | Support vendor 8days | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 16 | 27 | SR request | 2023-09-18 | 2023-09-24 | 2023-09-20 | 2019-12-18 | 2019-11-29 | 20 | PCNF REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | A |  | PRD | DK50
2026-W13-14 | C | NOSD | WPM | VEN-ELEC | VEN-ELEC | 2400054639 | 3M NOx in Exhaust, VENDOR, HBD | Uprig 230 V power and air for container | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2023-09-18 | 2023-09-24 | 2023-09-23 | 2019-12-18 | 2019-11-29 | 30 | PCNF REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | A |  | PRD | DK50
2026-W13-14 | C | NOSD | WPM | VEN-ELEC | VEN-ELEC | 2400054639 | 3M NOx in Exhaust, VENDOR, HBD | Remove 230 V and air from container | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2023-09-18 | 2023-09-24 | 2023-09-23 | 2019-12-18 | 2019-11-29 | 40 | PCNF REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | A |  | PRD | DK50
2026-W13-14 | C | NOSD | WPM | VEN-ELEC | MTN-TURB | 2400054639 | 3M NOx in Exhaust, VENDOR, HBD | added materials | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2023-09-18 | 2023-09-24 | 2023-09-23 | 2019-12-18 | 2019-11-29 | 60 | PCNF REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | A |  | PRD | DK50
2026-W13-14 | C | NOSD | WPM | VEN-ELEC | MTN-TURB | 2400054639 | 3M NOx in Exhaust, VENDOR, HBD | Support vendor from 18th sep to 25th sep | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2023-09-18 | 2023-09-24 | 2023-09-23 | 2019-12-18 | 2019-11-29 | 80 | REL | INIT OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | A |  | PRD | DK50
2024-W23-24 | 3 | HB-GEN1 | WDF | MTN-TURB | MTN-TURB | 2100075489 | Turbine HMI-S for repair | Turbine HMI-S for repair | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2023-03-28 | 2022-11-13 | 10 | PCNF REL | APPR OPND | HB /D /60/HBDC-GT-1650 | GAS TURBINE |  | A |  | MMR | DK50
2024-W23-24 | 3 | HB-GEN1 | WDF | MTN-TURB | MTN-TURB | 2100075489 | Turbine HMI-S for repair | Re-installation of turbine slave HMI | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 2 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2023-03-28 | 2022-11-13 | 20 | PCNF REL | APPR OPND | HB /D /60/HBDC-GT-1650 | GAS TURBINE |  | A |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087422 | FWP-0331/ Expired cooling hoses | FWP-0331/ Expired cooling hoses | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 | W11-W12 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2023-04-25 | 2023-03-11 | 10 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100087422 | FWP-0331/ Expired cooling hoses | Isolate FWP | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W11-W12 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2023-04-25 | 2023-03-11 | 20 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087422 | FWP-0331/ Expired cooling hoses | Drain coolant - shall be re-used | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W11-W12 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2023-04-25 | 2023-03-11 | 30 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087422 | FWP-0331/ Expired cooling hoses | Replace hoses | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO AWSC RDBL RFRZ ROUT | 6 | 0 | W11-W12 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2023-04-25 | 2023-03-11 | 40 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087422 | FWP-0331/ Expired cooling hoses | Re-fill coolant. Top up power cool | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W11-W12 | 2024-03-11 | 2024-03-13 | 2024-03-13 | 2023-04-25 | 2023-03-11 | 50 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100087422 | FWP-0331/ Expired cooling hoses | De-isolate | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 | W11-W12 | 2024-03-11 | 2024-03-13 | 2024-03-13 | 2023-04-25 | 2023-03-11 | 60 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087422 | FWP-0331/ Expired cooling hoses | Additional materials | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 | W11-W12 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2023-04-25 | 2023-03-11 | 70 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087422 | FWP-0331/ Expired cooling hoses | Additional materials | REL GMPS MANC PPRT PRC SETC | APPR APOG SMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 | W11-W12 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2023-04-25 | 2023-03-11 | 80 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | D |  | MMS | DK50
2026-W13-14 | 1 | NOSD | WDF | MTN-TURB | MTN-ELEC | 2100073699 | Ventilation fault on A-1650 | Ventilation fault on A-1650 | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-22 | 2024-04-08 | 2022-09-14 | 2022-08-30 | 10 | PCNF REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | A |  | MEL | DK50
2026-W13-14 | 1 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100073699 | Ventilation fault on A-1650 | Troubleshoot on temporary Fault | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT | 30 | 60 | W15-W16 | 2024-04-08 | 2024-04-22 | 2024-04-08 | 2022-09-14 | 2022-08-30 | 20 | PCNF REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | A |  | MEL | DK50
2026-W13-14 | 1 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100073699 | Ventilation fault on A-1650 | Replace enclosure fan | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-22 | 2024-04-14 | 2022-09-14 | 2022-08-30 | 30 | PCNF REL | APPR OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | A |  | MEL | DK50
2026-W13-14 | 1 | NOSD | WDF | MTN-TURB | MTN-ROPE | 2100073699 | Ventilation fault on A-1650 | Survey for rigging fan change-out | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT | 15 | 0 | W15-W16 | 2024-04-08 | 2024-04-22 | 2024-04-14 | 2022-09-14 | 2022-08-30 | 50 | REL | INIT OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | A |  | MEL | DK50
2026-W13-14 | 1 | NOSD | WDF | MTN-TURB | MTN-SCAF | 2100073699 | Ventilation fault on A-1650 | Erect scaffold access/Lifting frame | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT | 50 | 0 | W15-W16 | 2024-04-08 | 2024-04-22 | 2024-04-14 | 2022-09-14 | 2022-08-30 | 60 | REL | INIT OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | A |  | MEL | DK50
2026-W13-14 | 1 | NOSD | WDF | MTN-TURB | MTN-SCAF | 2100073699 | Ventilation fault on A-1650 | Dismantle scaffold/Alterations | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG SMAT | 30 | 0 | W15-W16 | 2024-04-08 | 2024-04-22 | 2024-04-19 | 2022-09-14 | 2022-08-30 | 70 | REL | INIT OPND | HB /D /60/HBDC-A-1650 | MAIN GENERATOR UNIT |  | A |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WGN | PRODTECH | MTN-PAIN | 2200013549 | Replace Liners in V-5071/5072/5073 when | Replace Liners in V-5073 when required. | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT | 0 | 0 |  | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2026-01-26 | 2023-08-10 | 10 | PCNF REL | APPR OPND | HB /D /27/HBDB-V-5073 | HYDROCYCLONE VESSEL |  | A |  | PRD | DK50
2026-W13-14 | 4 | NOSD | WGN | PRODTECH | PRODTECH | 2200013549 | Replace Liners in V-5071/5072/5073 when | Additional liners, 17/4-2023 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT | 0 | 0 |  | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2026-01-26 | 2023-08-10 | 20 | PCNF REL | APPR OPND | HB /D /27/HBDB-V-5073 | HYDROCYCLONE VESSEL |  | A |  | PRD | DK50
2026-W13-14 | 4 | NOSD | WGN | PRODTECH | PRODTECH | 2200013549 | Replace Liners in V-5071/5072/5073 when | Requested Liners 3/8-2023 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT | 0 | 0 |  | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2026-01-26 | 2023-08-10 | 30 | PCNF REL | APPR OPND | HB /D /27/HBDB-V-5073 | HYDROCYCLONE VESSEL |  | A |  | PRD | DK50
2026-W13-14 | 4 | NOSD | WGN | PRODTECH | PRODTECH | 2200013549 | Replace Liners in V-5071/5072/5073 when | Requested Liners 11/9-2023 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT | 0 | 0 |  | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2026-01-26 | 2023-08-10 | 40 | PCNF REL | APPR OPND | HB /D /27/HBDB-V-5073 | HYDROCYCLONE VESSEL |  | A |  | PRD | DK50
2026-W13-14 | 4 | NOSD | WGN | PRODTECH | PRODTECH | 2200013549 | Replace Liners in V-5071/5072/5073 when | Requested Liners 25/9-2023 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT | 0 | 0 |  | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2026-01-26 | 2023-08-10 | 50 | PCNF REL | APPR OPND | HB /D /27/HBDB-V-5073 | HYDROCYCLONE VESSEL |  | A |  | PRD | DK50
2026-W13-14 | 4 | NOSD | WGN | PRODTECH | MTN-RIGG | 2200013549 | Replace Liners in V-5071/5072/5073 when | install rigging equipment | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT | 4 | 4 |  | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2026-01-26 | 2023-08-10 | 60 | PCNF REL | APPR OPND | HB /D /27/HBDB-V-5073 | HYDROCYCLONE VESSEL |  | A |  | PRD | DK50
2026-W13-14 | 4 | NOSD | WGN | PRODTECH | MTN-RIGG | 2200013549 | Replace Liners in V-5071/5072/5073 when | Rigging of plate | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT | 8 | 0 |  | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2026-01-26 | 2023-08-10 | 70 | PCNF REL | APPR OPND | HB /D /27/HBDB-V-5073 | HYDROCYCLONE VESSEL |  | A |  | PRD | DK50
2026-W13-14 | 4 | NOSD | WGN | PRODTECH | MTN-RIGG | 2200013549 | Replace Liners in V-5071/5072/5073 when | Remove rigging equipment | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT | 4 | 0 |  | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2026-01-26 | 2023-08-10 | 80 | PCNF REL | APPR OPND | HB /D /27/HBDB-V-5073 | HYDROCYCLONE VESSEL |  | A |  | PRD | DK50
2026-W13-14 | 4 | NOSD | WGN | PRODTECH | PRODTECH | 2200013549 | Replace Liners in V-5071/5072/5073 when | Additional liners 13/11, 1 kit 1203220 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT | 0 | 0 |  | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2026-01-26 | 2023-08-10 | 100 | REL | APPR OPND | HB /D /27/HBDB-V-5073 | HYDROCYCLONE VESSEL |  | A |  | PRD | DK50
2026-W13-14 | 4 | NOSD | WGN | PRODTECH | PRODTECH | 2200013549 | Replace Liners in V-5071/5072/5073 when | Additional liners 29/1-2024, 1203220 | REL PCNF GMPS MANC PRC SETC | APPR APOG SMAT | 0 | 0 |  | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2026-01-26 | 2023-08-10 | 110 | REL | INIT OPND | HB /D /27/HBDB-V-5073 | HYDROCYCLONE VESSEL |  | A |  | PRD | DK50
2026-W1-2 | 3 | HBBPWELL | WDF | MTN-MECH | PRODTECH | 2100053574 | Hydraulic leak in accumulator cabinet | Production isolation | REL PCNF PRT MANC NMAT PRC SETC | APPR APOG SCH RDBL | 3 | 0 | W07-W08 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2021-12-03 | 2021-09-04 | 70 | PCNF REL | APPR OPND | HB /B /07/HBBB-FP-5941 | MP ACCUMULATOR PANEL | 99000119 | A |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-RIGG | 2100053574 | Hydraulic leak in accumulator cabinet | Rigger assistance | REL PCNF PRT MANC NMAT PRC SETC | APPR APOG SCH RDBL | 4 | 0 | W07-W08 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2021-12-03 | 2021-09-04 | 80 | PCNF REL | APPR OPND | HB /B /07/HBBB-FP-5941 | MP ACCUMULATOR PANEL | 99000119 | A |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | HBBPWELL | WDF | MTN-MECH | MTN-MECH | 2100053574 | Hydraulic leak in accumulator cabinet | Install/charge ACC-5941A | REL PCNF PRT MANC NMAT PRC SETC | APPR APOG SCH RDBL | 12 | 0 | W07-W08 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2021-12-03 | 2021-09-04 | 90 | PCNF REL | APPR OPND | HB /B /07/HBBB-FP-5941 | MP ACCUMULATOR PANEL | 99000119 | A |  | MMS | DK50 |  | PROK
2026-W1-2 | 3 | HBBPWELL | WDF | MTN-MECH | PRODTECH | 2100053574 | Hydraulic leak in accumulator cabinet | Production deisolation w leak test | REL PCNF PRT MANC NMAT PRC SETC | APPR APOG SCH RDBL | 3 | 0 | W07-W08 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2021-12-03 | 2021-09-04 | 100 | PCNF REL | APPR OPND | HB /B /07/HBBB-FP-5941 | MP ACCUMULATOR PANEL | 99000119 | A |  | MMS | DK50 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100090453 | Dishwasher will not pump dirty water | FLM Dishwasher will not pump dirty water | REL PCNF MANC PRC SETC | APPR APOG SCH RDBL | 0 | 0 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-11-04 | 2023-06-22 | 10 | PCNF REL | APPR OPND | HD /B /82/HDBC-X-130024 | DISHWASHER |  | C |  | MEL | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100090453 | Dishwasher will not pump dirty water | Replace pump | REL PCNF MANC PRC SETC | APPR APOG SCH RDBL | 3 | 2 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-11-04 | 2023-06-22 | 20 | PCNF REL | APPR OPND | HD /B /82/HDBC-X-130024 | DISHWASHER |  | C |  | MEL | DK60 |  | PROK
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010505 | ANOC MPM Ad Hoc Work Capture_Halfdan B | Weekly check of scaffolding | REL PCNF MANC NMAT PPRT PRC SETC | APPR APOG SCH RDBL | 4 | 4 |  | 2024-04-04 | 2024-04-08 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 4670 | PCNF REL | INIT OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010505 | ANOC MPM Ad Hoc Work Capture_Halfdan B | Helicopter refueling | REL PCNF MANC NMAT PPRT PRC SETC | APPR APOG SCH RDBL | 3 | 3 |  | 2024-04-04 | 2024-04-08 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 4680 | PCNF REL | INIT OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010505 | ANOC MPM Ad Hoc Work Capture_Halfdan B | Scaff for sealing roof under helideck | REL PCNF MANC NMAT PPRT PRC SETC | APPR APOG SCH RDBL | 10 | 10 |  | 2024-04-04 | 2024-04-08 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 4690 | PCNF REL | INIT OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010505 | ANOC MPM Ad Hoc Work Capture_Halfdan B | Shelf drilling vinner scaffolding | REL PCNF MANC NMAT PPRT PRC SETC | APPR APOG SCH RDBL | 4 | 4 |  | 2024-04-04 | 2024-04-08 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 4700 | PCNF REL | INIT OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010505 | ANOC MPM Ad Hoc Work Capture_Halfdan B | HBA flowline 05 found material | REL PCNF MANC NMAT PPRT PRC SETC | APPR APOG SCH RDBL | 3 | 3 |  | 2024-04-04 | 2024-04-08 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 4710 | PCNF REL | INIT OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010505 | ANOC MPM Ad Hoc Work Capture_Halfdan B | checking rigging equipment from well 27 | REL PCNF MANC NMAT PPRT PRC SETC | APPR APOG SCH RDBL | 3 | 3 |  | 2024-04-04 | 2024-04-08 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 4720 | PCNF REL | INIT OPND | HB /A /86/FABRIC-MAINTENANCE | HBA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W1-2 | 1 | HBD-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100095377 | WO HCV-038062 cannot open fully | Prepare rigging gear | REL PCNF MANC NMAT PPRT PRC SETC | APPR APOG SCH | 12 | 6 | W43-44 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-02-14 | 2023-01-30 | 10 | PCNF REL | APPR OPND | HB /D /01/HBDB-HCV-038062 | LO - BUTTERFLY VALVE |  | F |  | MMS | DK50 |  | PROK
2026-W1-2 | 1 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100095377 | WO HCV-038062 cannot open fully | Production to isolate | REL PCNF MANC NMAT PPRT PRC SETC | APPR APOG SCH | 3 | 0 | W43-44 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-02-14 | 2023-01-30 | 20 | PCNF REL | APPR OPND | HB /D /01/HBDB-HCV-038062 | LO - BUTTERFLY VALVE |  | F |  | MMS | DK50 |  | PROK
2026-W1-2 | 1 | HBD-IPHP | WDF | MTN-MECH | MTN-MECH | 2100095377 | WO HCV-038062 cannot open fully | Replace HCV-038062 | REL PCNF MANC NMAT PPRT PRC SETC | APPR APOG SCH | 10 | 0 | W43-44 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-02-14 | 2023-01-30 | 30 | PCNF REL | APPR OPND | HB /D /01/HBDB-HCV-038062 | LO - BUTTERFLY VALVE |  | F |  | MMS | DK50 |  | PROK
2026-W1-2 | 1 | HBD-IPHP | WDF | MTN-MECH | PRODTECH | 2100095377 | WO HCV-038062 cannot open fully | Production De-isolate and leak test | REL PCNF MANC NMAT PPRT PRC SETC | APPR APOG SCH | 3 | 0 | W43-44 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2023-02-14 | 2023-01-30 | 40 | PCNF REL | APPR OPND | HB /D /01/HBDB-HCV-038062 | LO - BUTTERFLY VALVE |  | F |  | MMS | DK50 |  | PROK
0 | 3 | HDAFLARE | WDF | MTN-ROPE | CON-WELD | 2100023683 | ANOPR Clash ml. flarerør og cls drainrør | R4 Clash ml. flarerør og cls drainrør | REL PCNF PRT MANC PRC SETC | APPR APOG RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2018-10-16 | 2018-07-18 | 10 | REL | APPR OPND | HD /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000087 | C |  | MFM | DK60
0 | 3 | HDAFLARE | WDF | MTN-ROPE | MTN-PIPF | 2100023683 | ANOPR Clash ml. flarerør og cls drainrør | Insert spacer and evaluate corrosion | REL PCNF PRT MANC PRC SETC | APPR APOG RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2018-10-16 | 2018-07-18 | 170 | REL | APPR OPND | HD /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000087 | C |  | MFM | DK60
0 | 3 | HDAFLARE | WDF | MTN-ROPE | MTN-ROPE | 2100023683 | ANOPR Clash ml. flarerør og cls drainrør | Move SS pipe. | REL PCNF PRT MANC PRC SETC | APPR APOG RDBL | 36 | 0 |  | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2018-10-16 | 2018-07-18 | 180 | REL | APPR OPND | HD /A /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | 99000087 | C |  | MFM | DK60
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100026251 | Bad Heat T. and missing lagging | Isolate HT | REL PRT CSER MANC NMAT PRC SETC | APPR APOG RDBL | 0.5 | 0 | BL-Team | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2020-04-30 | 2020-01-31 | 10 | REL | APPR OPND | HB /B /28/HBBA-S-50261 | STRAINER |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ROPE | 2100026251 | Bad Heat T. and missing lagging | Remove piping insulation | REL PRT CSER MANC NMAT PRC SETC | APPR APOG RDBL | 2 | 0 | BL-Team | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2020-04-30 | 2020-01-31 | 20 | REL | APPR OPND | HB /B /28/HBBA-S-50261 | STRAINER |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100026251 | Bad Heat T. and missing lagging | Replace HT cable - megger test new cable | REL PRT CSER MANC NMAT PRC SETC | APPR APOG RDBL | 8 | 0 | BL-Team | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2020-04-30 | 2020-01-31 | 30 | REL | APPR OPND | HB /B /28/HBBA-S-50261 | STRAINER |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ROPE | 2100026251 | Bad Heat T. and missing lagging | Re-establish piping and strainer insulat | REL PRT CSER MANC NMAT PRC SETC | APPR APOG RDBL | 12 | 0 | BL-Team | 2023-04-24 | 2023-04-27 | 2023-04-26 | 2020-04-30 | 2020-01-31 | 40 | REL | APPR OPND | HB /B /28/HBBA-S-50261 | STRAINER |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100026251 | Bad Heat T. and missing lagging | Megger test after insulation job. | REL PRT CSER MANC NMAT PRC SETC | APPR APOG RDBL | 0.5 | 0 | BL-Team | 2023-04-24 | 2023-04-27 | 2023-04-27 | 2020-04-30 | 2020-01-31 | 50 | REL | APPR OPND | HB /B /28/HBBA-S-50261 | STRAINER |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-LAGG | MTN-ELEC | 2100026251 | Bad Heat T. and missing lagging | De-isolate | REL PRT CSER MANC NMAT PRC SETC | APPR APOG RDBL | 0.5 | 0 | BL-Team | 2023-04-24 | 2023-04-27 | 2023-04-27 | 2020-04-30 | 2020-01-31 | 60 | REL | APPR OPND | HB /B /28/HBBA-S-50261 | STRAINER |  | C |  | MEL | DK50
0 | 4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100062365 | DWESR HDA - Replace of Handrail EL +1850 | Replace handrail | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 25 | 0 |  | 2024-07-30 | 2024-08-06 | 2024-07-30 | 2022-09-21 | 2022-04-24 | 30 | REL | INIT OPND | HD /A /86/18500 - HANDRAILS | 18500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100062365 | DWESR HDA - Replace of Handrail EL +1850 | Replace handrail Cuffs | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 25 | 0 |  | 2024-07-30 | 2024-08-06 | 2024-07-31 | 2022-09-21 | 2022-04-24 | 40 | REL | INIT OPND | HD /A /86/18500 - HANDRAILS | 18500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100062365 | DWESR HDA - Replace of Handrail EL +1850 | Prep and painting of sockets | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 50 | 0 |  | 2024-07-30 | 2024-08-06 | 2024-08-01 | 2022-09-21 | 2022-04-24 | 50 | REL | INIT OPND | HD /A /86/18500 - HANDRAILS | 18500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100062365 | DWESR HDA - Replace of Handrail EL +1850 | Repair to bent handrail | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 25 | 0 |  | 2024-07-30 | 2024-08-06 | 2024-08-04 | 2022-09-21 | 2022-04-24 | 60 | REL | INIT OPND | HD /A /86/18500 - HANDRAILS | 18500 - HANDRAILS |  | A |  | MFM | DK60
0 | 4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100062365 | DWESR HDA - Replace of Handrail EL +1850 | Close-out report | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 5 | 2 |  | 2024-07-30 | 2024-08-06 | 2024-08-05 | 2022-09-21 | 2022-04-24 | 70 | PCNF REL | INIT OPND | HD /A /86/18500 - HANDRAILS | 18500 - HANDRAILS |  | A |  | MFM | DK60
2026-W13-14 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100066133 | Hydr. hoses HBAA-LCV-34115 | Isolation/deisolation of LCV-34115 | REL MANC NMAT PRC SETC | APPR APOG RDBL | 3 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2022-04-30 | 2022-04-10 | 10 | REL | APPR OPND | HB /A /11/HBAA-LCV-34115 | LEVEL CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100066133 | Hydr. hoses HBAA-LCV-34115 | Disconnect hydraulic Hose | REL MANC NMAT PRC SETC | APPR APOG RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2022-04-30 | 2022-04-10 | 20 | REL | APPR OPND | HB /A /11/HBAA-LCV-34115 | LEVEL CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100066133 | Hydr. hoses HBAA-LCV-34115 | Mount New Hydraulic hose | REL MANC NMAT PRC SETC | APPR APOG RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2022-04-30 | 2022-04-10 | 30 | REL | APPR OPND | HB /A /11/HBAA-LCV-34115 | LEVEL CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086906 | Trip on 1838-QF10/E Emg. light | Isolate and prove dead. | REL MANC PRC SETC | APPR APOG RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-16 | 2024-03-09 | 2023-08-31 | 2023-04-18 | 10 | REL | APPR OPND | HB /C /05/HBCA-LP-1838-QF10-E | EMERG. LIGHTING (LE20) E2 LEVEL 4 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086906 | Trip on 1838-QF10/E Emg. light | Replace cable between | REL MANC PRC SETC | APPR APOG RDBL | 30 | 0 |  | 2024-03-09 | 2024-03-16 | 2024-03-09 | 2023-08-31 | 2023-04-18 | 20 | REL | APPR OPND | HB /C /05/HBCA-LP-1838-QF10-E | EMERG. LIGHTING (LE20) E2 LEVEL 4 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100086906 | Trip on 1838-QF10/E Emg. light | HBCC-LE-18430 & HBCC-LE-18431 | REL MANC PRC SETC | APPR APOG RDBL | 10 | 0 |  | 2024-03-09 | 2024-03-16 | 2024-03-15 | 2023-08-31 | 2023-04-18 | 30 | REL | APPR OPND | HB /C /05/HBCA-LP-1838-QF10-E | EMERG. LIGHTING (LE20) E2 LEVEL 4 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086906 | Trip on 1838-QF10/E Emg. light | De-isolate and test. | REL MANC PRC SETC | APPR APOG RDBL | 1 | 0 |  | 2024-03-09 | 2024-03-16 | 2024-03-16 | 2023-08-31 | 2023-04-18 | 40 | REL | APPR OPND | HB /C /05/HBCA-LP-1838-QF10-E | EMERG. LIGHTING (LE20) E2 LEVEL 4 |  | C |  | MEL | DK50
2024-W45-46 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100087271 | FCV-29253 hydr. weep from actuator stem | FCV-29253 hydr. weep from actuator stem | REL MANC NMAT PRC SETC | APPR APOG RDBL | 4 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2023-09-07 | 2023-04-25 | 10 | REL | APPR OPND | HB /A /37/HBAA-FCV-29253 | LIFT GAS FLOW CONTROL VALVE |  | A |  | MMS | DK50
2024-W45-46 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100087271 | FCV-29253 hydr. weep from actuator stem | Isolate FCV-29254 | REL MANC NMAT PRC SETC | APPR APOG RDBL | 4 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2023-09-07 | 2023-04-25 | 20 | REL | APPR OPND | HB /A /37/HBAA-FCV-29253 | LIFT GAS FLOW CONTROL VALVE |  | A |  | MMS | DK50
2024-W45-46 | 3 | NE | WDF | MTN-MECH | MTN-INST | 2100087271 | FCV-29253 hydr. weep from actuator stem | Isolate hydraulic and controls | REL MANC NMAT PRC SETC | APPR APOG RDBL | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-17 | 2023-09-07 | 2023-04-25 | 30 | REL | APPR OPND | HB /A /37/HBAA-FCV-29253 | LIFT GAS FLOW CONTROL VALVE |  | A |  | MMS | DK50
2024-W45-46 | 3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100087271 | FCV-29253 hydr. weep from actuator stem | Rigging assist. Rig in/out | REL MANC NMAT PRC SETC | APPR APOG RDBL | 5 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-17 | 2023-09-07 | 2023-04-25 | 40 | REL | APPR OPND | HB /A /37/HBAA-FCV-29253 | LIFT GAS FLOW CONTROL VALVE |  | A |  | MMS | DK50
2024-W45-46 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100087271 | FCV-29253 hydr. weep from actuator stem | Demount Actuator | REL MANC NMAT PRC SETC | APPR APOG RDBL | 3 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-18 | 2023-09-07 | 2023-04-25 | 50 | REL | APPR OPND | HB /A /37/HBAA-FCV-29253 | LIFT GAS FLOW CONTROL VALVE |  | A |  | MMS | DK50
2024-W45-46 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100087271 | FCV-29253 hydr. weep from actuator stem | Mount blinds if necessary | REL MANC NMAT PRC SETC | APPR APOG RDBL | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2023-09-07 | 2023-04-25 | 60 | REL | APPR OPND | HB /A /37/HBAA-FCV-29253 | LIFT GAS FLOW CONTROL VALVE |  | A |  | MMS | DK50
2024-W45-46 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100087271 | FCV-29253 hydr. weep from actuator stem | Change trim/stem seals | REL MANC NMAT PRC SETC | APPR APOG RDBL | 4 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2023-09-07 | 2023-04-25 | 70 | REL | APPR OPND | HB /A /37/HBAA-FCV-29253 | LIFT GAS FLOW CONTROL VALVE |  | A |  | MMS | DK50
2024-W45-46 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100087271 | FCV-29253 hydr. weep from actuator stem | Remove blinds | REL MANC NMAT PRC SETC | APPR APOG RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2023-09-07 | 2023-04-25 | 80 | REL | APPR OPND | HB /A /37/HBAA-FCV-29253 | LIFT GAS FLOW CONTROL VALVE |  | A |  | MMS | DK50
2024-W45-46 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100087271 | FCV-29253 hydr. weep from actuator stem | Mount Actuator | REL MANC NMAT PRC SETC | APPR APOG RDBL | 3 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2023-09-07 | 2023-04-25 | 90 | REL | APPR OPND | HB /A /37/HBAA-FCV-29253 | LIFT GAS FLOW CONTROL VALVE |  | A |  | MMS | DK50
2024-W45-46 | 3 | NE | WDF | MTN-MECH | MTN-INST | 2100087271 | FCV-29253 hydr. weep from actuator stem | De-Isolate Hydraulic and Controls | REL MANC NMAT PRC SETC | APPR APOG RDBL | 1 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2023-09-07 | 2023-04-25 | 100 | REL | APPR OPND | HB /A /37/HBAA-FCV-29253 | LIFT GAS FLOW CONTROL VALVE |  | A |  | MMS | DK50
2024-W45-46 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100087271 | FCV-29253 hydr. weep from actuator stem | Functionaltest / callibration FCV | REL MANC NMAT PRC SETC | APPR APOG RDBL | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2023-09-07 | 2023-04-25 | 110 | REL | APPR OPND | HB /A /37/HBAA-FCV-29253 | LIFT GAS FLOW CONTROL VALVE |  | A |  | MMS | DK50
2024-W45-46 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100087271 | FCV-29253 hydr. weep from actuator stem | De-Isolate FCV | REL MANC NMAT PRC SETC | APPR APOG RDBL | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2023-09-07 | 2023-04-25 | 120 | REL | APPR OPND | HB /A /37/HBAA-FCV-29253 | LIFT GAS FLOW CONTROL VALVE |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100093150 | Noisey fan in XE-5052 Oil pump VFD | Noisey fan in XE-5052 Oil pump VFD | REL MANC NMAT PRC SETC | APPR APOG RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-12-13 | 2023-07-31 | 10 | REL | APPR OPND | HB /D /28/HBDD-XE-5052 | PUMP MOTOR VFD |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100093150 | Noisey fan in XE-5052 Oil pump VFD | Isolate equipment and prove dead. | REL MANC NMAT PRC SETC | APPR APOG RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-12-13 | 2023-07-31 | 20 | REL | APPR OPND | HB /D /28/HBDD-XE-5052 | PUMP MOTOR VFD |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100093150 | Noisey fan in XE-5052 Oil pump VFD | Replace old fans with new ones | REL MANC NMAT PRC SETC | APPR APOG RDBL | 4 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2023-12-13 | 2023-07-31 | 30 | REL | APPR OPND | HB /D /28/HBDD-XE-5052 | PUMP MOTOR VFD |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100093150 | Noisey fan in XE-5052 Oil pump VFD | De-Isolate and put back in service | REL MANC NMAT PRC SETC | APPR APOG RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2023-12-13 | 2023-07-31 | 40 | REL | APPR OPND | HB /D /28/HBDD-XE-5052 | PUMP MOTOR VFD |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100093150 | Noisey fan in XE-5052 Oil pump VFD | Test equipment. | REL MANC NMAT PRC SETC | APPR APOG RDBL | 1 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2023-12-13 | 2023-07-31 | 50 | REL | APPR OPND | HB /D /28/HBDD-XE-5052 | PUMP MOTOR VFD |  | C |  | MEL | DK50
2024-W23-24 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106591 | HP-unit external leaking from pump | Isolate | REL PCNF PRT NMAT PRC SETC | APPR APOG RDBL | 2 | 10 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-07-26 | 2024-03-13 | 10 | PCNF REL | APPR OPND | HB /D /72/HBDB-A-1152 | PRESSURISATION UNIT |  | C |  | MMS | DK50 |  |  | 2024-05-10
2024-W23-24 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100106591 | HP-unit external leaking from pump | Replace two HP motor pump units | REL PCNF PRT NMAT PRC SETC | APPR APOG RDBL | 3 | 3 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-07-26 | 2024-03-13 | 20 | PCNF REL | APPR OPND | HB /D /72/HBDB-A-1152 | PRESSURISATION UNIT |  | C |  | MMS | DK50 |  |  | 2024-05-11
2024-W23-24 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106591 | HP-unit external leaking from pump | Replace two HP motor pump units | REL PCNF PRT NMAT PRC SETC | APPR APOG RDBL | 3 | 12 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-26 | 2024-07-26 | 2024-03-13 | 30 | PCNF REL | APPR OPND | HB /D /72/HBDB-A-1152 | PRESSURISATION UNIT |  | C |  | MMS | DK50 |  |  | 2024-05-12
2024-W23-24 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106591 | HP-unit external leaking from pump | De-isolate | REL PCNF PRT NMAT PRC SETC | APPR APOG RDBL | 2 | 1 | W13-W14 | 2024-03-25 | 2024-03-26 | 2024-03-26 | 2024-07-26 | 2024-03-13 | 40 | PCNF REL | APPR OPND | HB /D /72/HBDB-A-1152 | PRESSURISATION UNIT |  | C |  | MMS | DK50 |  |  | 2024-05-13
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | MPM Ad Hoc Work Capture_Halfdan A | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 0 | 0 |  | 2023-04-24 | 2024-04-20 | 2023-04-24 | 2023-04-06 | 2022-08-09 | 10 | PCNF REL | APPR OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | OBS-HDA-123124 remove net and cable tray | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 8 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 30 | PCNF REL | APPR OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | OBS-HDA 129048 fabricate install support | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 6 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 40 | PCNF REL | APPR OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | OBS-HDA 124097 remove broken clamp | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 2.5 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 50 | PCNF REL | APPR OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | OBS-HDA-132451 reinstall cable tray | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 4 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 60 | PCNF REL | APPR OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | OBS-HDA-130971 removal scaffolds | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 5 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 70 | PCNF REL | APPR OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Action Tr. mounting jobs roof deck HDB | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 8 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 80 | PCNF REL | APPR OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Action Tr. removal scaffold | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 2 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 90 | PCNF REL | APPR OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | OBS-HDA-134540 cable secured | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 9 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 100 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | OBS-HDA-134641 u bolt mounted | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 3 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 110 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | OBS-HDA-134634 wedges replaced | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 3 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 120 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Buidling scaffold for mainetenance | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 18 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 130 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Assisitng semco maintenance of lights | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 24 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 140 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Supporting inst. piping by wellhead 31 | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 3 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 150 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Alu stairs securing from movement | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 3 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 160 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | OBS HDA 120160 rivets | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 28 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 170 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Rigging and lifting roof HDB lvl 4 | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 12 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 180 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Exchange Gas Detector GD-016442 | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 18 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 600 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | OBS.card 321961-mech.prep.paint | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 4 | 4 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 680 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Rigging 3X wrap | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 0 | 8 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 690 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Install gratings HDB esc to sea lvl west | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 75 | 33 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 720 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Scaffold checks and storage HAL ALPHA | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 200 | 7 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 730 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Rigger loft check HAL ALPHA | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 200 | 7 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 740 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Transfer to sharepoint, orders, obs card | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 4 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 770 | PCNF REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
0 | 4 | NOSD | WGN | MTN-ROPE | MTN-LAGG | 2200010504 | ANOC MPM Ad Hoc Work Capture_Halfdan A | Replace insulation 1.5 fire water line | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 8 | 0 |  | 2023-04-24 | 2024-04-20 | 2024-04-04 | 2023-04-06 | 2022-08-09 | 820 | REL | INIT OPND | HD /A /86/FABRIC-MAINTENANCE | HDA PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK60
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | SCOPE #1 = 2174495-EP3822 | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 100 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Site-Inspector-Scan~NDT | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 115 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Paint; Barrier, Prep/Team/Gear/Test+POST | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 36 | 60 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 120 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Paint; Clean, SB, Inspect, Waste | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 72 | 39 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 125 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Paint; QC, Wencon, Primer, Waste | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 36 | 76 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 130 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Paint; QC, Recoat, Wast, Backload | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 4 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 135 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | SCOPE #2 = 2174496-16in-GPS-384027-FE | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 200 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Site-Inspector-Scan~NDT | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 215 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Paint; Barrier, Prep/Team/Gear/Test+POST | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 36 | 20 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 220 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Paint; Clean, SB, Inspect, Waste | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 72 | 33 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 225 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Paint; QC, Wencon, Primer, Waste | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 36 | 42 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 230 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Paint; QC, Recoat, Wast, Backload | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 4 | 2 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 235 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | SCOPE #3 = 2174497-14in-OCS-384034-FE | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 0 | 7 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 300 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Site-Inspector-Scan~NDT | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 0 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 315 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Paint; Barrier, Prep/Team/Gear/Test+POST | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 36 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 320 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Paint; Clean, SB, Inspect, Waste | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 72 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 325 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Paint; QC, Wencon, Primer, Waste | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 36 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 330 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | Paint; QC, Recoat, Wast, Backload | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 4 | 0 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 335 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | SCOPE#3 Prep, Paint | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 8 | 10 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 340 | PCNF REL | APPR OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WGN | MTN-ROPE | VEN-ROPE | 2200010678 | ANOC HBB CellarDeck Associat Pwk EP3822. | fabric ID 31134 prep, coating | REL PCNF MANC NMAT PRC SETC | APPR APOG RDBL | 0 | 48 |  | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-27 | 2022-08-30 | 350 | PCNF REL | INIT OPND | HB /B /86/FABRIC-MAINTENANCE | HBB PLATFORM FABRIC MAINTENANCE |  | A |  | MFM | DK50
2024-W29-30 | 4 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200012778 | Replacement of floor in laundry. | Vendor: Purchase materials | REL MANC PRC SETC | APPR APOG RDBL | 0 | 0 | W13-W14 | 2024-05-09 | 2024-05-09 | 2024-05-09 | 2025-11-22 | 2023-06-06 | 20 | REL | APPR OPND | HB /C /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK50 |  |  | 2024-06-02
2024-W29-30 | 4 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200012778 | Replacement of floor in laundry. | Vendor: Prepare scope onshore | REL MANC PRC SETC | APPR APOG RDBL | 0 | 0 | W13-W14 | 2024-05-09 | 2024-05-09 | 2024-05-09 | 2025-11-22 | 2023-06-06 | 30 | REL | APPR OPND | HB /C /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK50 |  |  | 2024-06-03
2024-W29-30 | 4 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200012778 | Replacement of floor in laundry. | Vendor: Execute offshore | REL MANC PRC SETC | APPR APOG RDBL | 0 | 0 | W13-W14 | 2024-05-09 | 2024-05-09 | 2024-05-09 | 2025-11-22 | 2023-06-06 | 40 | REL | APPR OPND | HB /C /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK50 |  |  | 2024-06-04
2024-W33-34 | 4 |  | WGN | MTN-LAGG | MTN-ELEC | 2200012786 | Maintenance of flooring in mess hall and | Maintenance of flooring in mess hall | REL MACM PRC SETC | APPR APOG RDBL | 0 | 0 |  | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2025-11-22 | 2023-06-06 | 10 | REL | APPR OPND | HB /C /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK50
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400222547 | 2Y STATIC SWITCH MAINT HBD | ISOLATION BY PRODUCTION | REL PCNF MANC PPRT PRC SETC | APPR APOG RDBL | 1 | 4 | W07-08 | 2024-09-15 | 2024-10-01 | 2024-09-15 | 2023-02-07 | 2022-12-14 | 5 | PCNF REL | APPR OPND | HB /D /61/HBDD-N-1854-B02-GA | IT-SWITCH B |  | A | DKHB-3001 | MEL | DK50 | EL0034
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400222547 | 2Y STATIC SWITCH MAINT HBD | STATIC SWITCH MAINT HBD | REL PCNF MANC PPRT PRC SETC | APPR APOG RDBL | 40 | 20 | W07-08 | 2024-09-15 | 2024-10-01 | 2024-09-15 | 2023-02-07 | 2022-12-14 | 10 | PCNF REL | APPR OPND | HB /D /61/HBDD-N-1854-B02-GA | IT-SWITCH B |  | A | DKHB-3001 | MEL | DK50 | EL0034
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400222547 | 2Y STATIC SWITCH MAINT HBD | DE-ISOLATION BY PRODUCTION | REL PCNF MANC PPRT PRC SETC | APPR APOG RDBL | 40 | 4 | W07-08 | 2024-09-15 | 2024-10-01 | 2024-09-19 | 2023-02-07 | 2022-12-14 | 15 | PCNF REL | APPR OPND | HB /D /61/HBDD-N-1854-B02-GA | IT-SWITCH B |  | A | DKHB-3001 | MEL | DK50 | EL0034
2026-W13-14 | C | NOSD | WPM | MTN-ELEC | MTN-TELE | 2400222547 | 2Y STATIC SWITCH MAINT HBD | Assist from Telecom | REL PCNF MANC PPRT PRC SETC | APPR APOG RDBL | 20 | 20 |  | 2024-09-15 | 2024-10-01 | 2024-09-28 | 2023-02-07 | 2022-12-14 | 20 | PCNF REL | INIT OPND | HB /D /61/HBDD-N-1854-B02-GA | IT-SWITCH B |  | A | DKHB-3001 | MEL | DK50 | EL0034
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071180 | HT replace Cable HBBA drain pump 5004 | Isolate and prove dead | REL PRT GMPS MANC PRC SETC | APPR APOG PMAT SCH RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2022-12-29 | 2022-08-16 | 10 | REL | APPR OPND | HB /B /61/HBBA-N-1811-Q19 | HEAT TRACING OPEN DRN HT-1811-7319-L1-A |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100071180 | HT replace Cable HBBA drain pump 5004 | Remove insulation | REL PRT GMPS MANC PRC SETC | APPR APOG PMAT SCH RDBL | 4 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2022-12-29 | 2022-08-16 | 20 | REL | APPR OPND | HB /B /61/HBBA-N-1811-Q19 | HEAT TRACING OPEN DRN HT-1811-7319-L1-A |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071180 | HT replace Cable HBBA drain pump 5004 | Change HT | REL PRT GMPS MANC PRC SETC | APPR APOG PMAT SCH RDBL | 2 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2022-12-29 | 2022-08-16 | 30 | REL | APPR OPND | HB /B /61/HBBA-N-1811-Q19 | HEAT TRACING OPEN DRN HT-1811-7319-L1-A |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071180 | HT replace Cable HBBA drain pump 5004 | Megger test installation | REL PRT GMPS MANC PRC SETC | APPR APOG PMAT SCH RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2022-12-29 | 2022-08-16 | 40 | REL | APPR OPND | HB /B /61/HBBA-N-1811-Q19 | HEAT TRACING OPEN DRN HT-1811-7319-L1-A |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100071180 | HT replace Cable HBBA drain pump 5004 | Insulate | REL PRT GMPS MANC PRC SETC | APPR APOG PMAT SCH RDBL | 4 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2022-12-29 | 2022-08-16 | 50 | REL | APPR OPND | HB /B /61/HBBA-N-1811-Q19 | HEAT TRACING OPEN DRN HT-1811-7319-L1-A |  | C |  | MEL | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071180 | HT replace Cable HBBA drain pump 5004 | De-Isolate above and test | REL PRT GMPS MANC PRC SETC | APPR APOG PMAT SCH RDBL | 1 | 0 |  | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2022-12-29 | 2022-08-16 | 60 | REL | APPR OPND | HB /B /61/HBBA-N-1811-Q19 | HEAT TRACING OPEN DRN HT-1811-7319-L1-A |  | C |  | MEL | DK50
2026-W1-2 | D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400259339 | 1Y HV TESTER/EARTHING EQUIP MAINT - HBD. | HV TESTER/EARTHING EQUIP MAINT - HBD | REL GMPS MANC PRC SETC | APPR APOG PMAT SCH RDBL | 2 | 0 | W45-46 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-06-16 | 2023-04-30 | 10 | REL | APPR OPND | HB /D /84/TEST-EQUIPMENT | TEST EQUIPMENT |  | A | DKHB-2044 | MEL | DK50 | EL0044
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100027043 | ANOPR Flanges and align in poor conditio | 2100027043-0002-COATING | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2023-03-27 | 2023-03-30 | 2023-03-27 | 2019-09-04 | 2019-06-06 | 2 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100027043 | ANOPR Flanges and align in poor conditio | 2100027043-0003-CONSUMER-GOODS | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2023-03-27 | 2023-03-30 | 2023-03-27 | 2019-09-04 | 2019-06-06 | 3 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100027043 | ANOPR Flanges and align in poor conditio | 2100027043-0004-DRAFT-RENT-ALTRAD | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2023-03-27 | 2023-03-30 | 2023-03-27 | 2019-09-04 | 2019-06-06 | 4 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100027043 | ANOPR Flanges and align in poor conditio | 2100027043-0005-DRAFT-RENT-MOURITSEN | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2023-03-27 | 2023-03-30 | 2023-03-27 | 2019-09-04 | 2019-06-06 | 5 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-INST | 2100027043 | ANOPR Flanges and align in poor conditio | Flanges and alignment in poor condition | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 8 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-27 | 2019-09-04 | 2019-06-06 | 10 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-INST | 2100027043 | ANOPR Flanges and align in poor conditio | . | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 13 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-27 | 2019-09-04 | 2019-06-06 | 170 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100027043 | ANOPR Flanges and align in poor conditio | Additional materials | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2023-03-27 | 2023-03-30 | 2023-03-27 | 2019-09-04 | 2019-06-06 | 190 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100027043 | ANOPR Flanges and align in poor conditio | Ordering materials. | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2023-03-27 | 2023-03-30 | 2023-03-27 | 2019-09-04 | 2019-06-06 | 195 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100027043 | ANOPR Flanges and align in poor conditio | Prepare rigging plan | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 12 | 8 |  | 2023-03-27 | 2023-03-30 | 2023-03-27 | 2019-09-04 | 2019-06-06 | 215 | PCNF REL | INIT OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100027043 | ANOPR Flanges and align in poor conditio | Build of scaffolding | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 16 | 18 |  | 2023-03-27 | 2023-03-30 | 2023-03-28 | 2019-09-04 | 2019-06-06 | 220 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100027043 | ANOPR Flanges and align in poor conditio | Build gallows for rigging | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 12 | 12 |  | 2023-03-27 | 2023-03-30 | 2023-03-28 | 2019-09-04 | 2019-06-06 | 225 | PCNF REL | INIT OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100027043 | ANOPR Flanges and align in poor conditio | Install Lifting gear | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2023-03-27 | 2023-03-30 | 2023-03-29 | 2019-09-04 | 2019-06-06 | 230 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100027043 | ANOPR Flanges and align in poor conditio | Isolation (Prod) | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 2 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 235 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ELEC | 2100027043 | ANOPR Flanges and align in poor conditio | Disconnect power | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 1 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 237 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100027043 | ANOPR Flanges and align in poor conditio | Dismantling FIT/FE-365112/spool | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 8 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 240 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100027043 | ANOPR Flanges and align in poor conditio | Install BLD HUBS | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 6 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 245 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100027043 | ANOPR Flanges and align in poor conditio | Rigging assistance | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 250 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | VEN-MECH | 2100027043 | ANOPR Flanges and align in poor conditio | Machining Hubs connection(Vendor) | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 270 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100027043 | ANOPR Flanges and align in poor conditio | Assistance to Vendor | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 10 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 280 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100027043 | ANOPR Flanges and align in poor conditio | Dismantling BLD HUBS | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 4 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 285 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100027043 | ANOPR Flanges and align in poor conditio | Reinstall FIT/FE-365112/spool | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 10 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 290 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100027043 | ANOPR Flanges and align in poor conditio | Paint; Prep/Team/Gear/Barrier+POST | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 12 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 291 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100027043 | ANOPR Flanges and align in poor conditio | Paint; Clean, SB, Inspect, Close Surface | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 12 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 292 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100027043 | ANOPR Flanges and align in poor conditio | Paint; QC, Repaint to Spec. | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 12 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 293 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100027043 | ANOPR Flanges and align in poor conditio | Paint; Clean-Up, Waist, Backload | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 3 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 294 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ELEC | 2100027043 | ANOPR Flanges and align in poor conditio | Reinstall power | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 2 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 295 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100027043 | ANOPR Flanges and align in poor conditio | Leak test and deisolation(prod) | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 2 | 0 | Before 2400050028 | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 300 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100027043 | ANOPR Flanges and align in poor conditio | Remove lifting gear | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 310 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100027043 | ANOPR Flanges and align in poor conditio | Demol Scaff | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2023-03-27 | 2023-03-30 | 2023-03-30 | 2019-09-04 | 2019-06-06 | 320 | PCNF REL | APPR OPND | HB /D /23/HBDC-FIT-365112 | FLOW INDICATOR TRANSMITTER (METERING) | 99000087 | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | P-1058 is stuck. Breaker trips instantly | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2024-03-23 | 2024-09-19 | 2024-03-23 | 2021-09-22 | 2021-04-25 | 10 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | Investigate if pump can crank manually | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 6 | 10 |  | 2024-03-23 | 2024-09-19 | 2024-03-23 | 2021-09-22 | 2021-04-25 | 20 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | Investigate if breaker is faulty | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 6 | 0 |  | 2024-03-23 | 2024-09-19 | 2024-03-23 | 2021-09-22 | 2021-04-25 | 30 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | Prepare Lifting equip/rig out | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 20 | 0 |  | 2024-03-23 | 2024-09-19 | 2024-03-23 | 2021-09-22 | 2021-04-25 | 50 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | Pump Overhaul | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2024-03-23 | 2024-09-19 | 2024-03-23 | 2021-09-22 | 2021-04-25 | 130 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | Prepare Lifting equip/rig in | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 20 | 0 |  | 2024-03-23 | 2024-09-19 | 2024-09-19 | 2021-09-22 | 2021-04-25 | 140 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | Production long term isolation | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 3 | 0 |  | 2024-03-23 | 2024-09-19 | 2024-03-23 | 2021-09-22 | 2021-04-25 | 160 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | Pump Installation | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 24 | 0 |  | 2024-03-23 | 2024-09-19 | 2024-03-23 | 2021-09-22 | 2021-04-25 | 180 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | Cable/cable trays installation | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 12 | 0 |  | 2024-03-23 | 2024-09-19 | 2024-03-23 | 2021-09-22 | 2021-04-25 | 190 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | Production de-isolation w leaktest | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 3 | 0 |  | 2024-03-23 | 2024-09-19 | 2024-03-23 | 2021-09-22 | 2021-04-25 | 200 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | Function Test | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 2 | 0 |  | 2024-03-23 | 2024-09-19 | 2024-03-23 | 2021-09-22 | 2021-04-25 | 210 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | Function Test | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 2 | 0 |  | 2024-03-23 | 2024-09-19 | 2024-03-23 | 2021-09-22 | 2021-04-25 | 220 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100045221 | LOTI: Seized HBDB-P-1058 Bckload pump fo | Mechanical prep of pump bracket | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 24 | 0 |  | 2024-03-23 | 2024-09-19 | 2024-03-23 | 2021-09-22 | 2021-04-25 | 230 | PCNF REL | APPR OPND | HB /D /85/HBDB-P-1058 | POTABLE WATER PUMP (100%) |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048089 | LOTI:Repair seeping acc from top fitting | Isolate accumulator | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2021-07-22 | 2021-04-23 | 80 | PCNF REL | APPR OPND | HB /A /07/HBAA-ACC-5960A | BLADDER ACCUM. IN HYDR. ACCUM. UNIT |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048089 | LOTI:Repair seeping acc from top fitting | Accumulator removal | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2021-07-22 | 2021-04-23 | 90 | PCNF REL | APPR OPND | HB /A /07/HBAA-ACC-5960A | BLADDER ACCUM. IN HYDR. ACCUM. UNIT |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048089 | LOTI:Repair seeping acc from top fitting | Install new PRV block on accum. | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2021-07-22 | 2021-04-23 | 100 | PCNF REL | APPR OPND | HB /A /07/HBAA-ACC-5960A | BLADDER ACCUM. IN HYDR. ACCUM. UNIT |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048089 | LOTI:Repair seeping acc from top fitting | Install accumulator and pre charge N2 | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 8 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2021-07-22 | 2021-04-23 | 110 | PCNF REL | APPR OPND | HB /A /07/HBAA-ACC-5960A | BLADDER ACCUM. IN HYDR. ACCUM. UNIT |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048089 | LOTI:Repair seeping acc from top fitting | De-isolate accumulator | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2021-07-22 | 2021-04-23 | 120 | PCNF REL | APPR OPND | HB /A /07/HBAA-ACC-5960A | BLADDER ACCUM. IN HYDR. ACCUM. UNIT |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048089 | LOTI:Repair seeping acc from top fitting | Functional/leak test | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 2 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2021-07-22 | 2021-04-23 | 130 | PCNF REL | APPR OPND | HB /A /07/HBAA-ACC-5960A | BLADDER ACCUM. IN HYDR. ACCUM. UNIT |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100048089 | LOTI:Repair seeping acc from top fitting | Rigger assist | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 4 | 0 | W17-W18 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2021-07-22 | 2021-04-23 | 140 | PCNF REL | APPR OPND | HB /A /07/HBAA-ACC-5960A | BLADDER ACCUM. IN HYDR. ACCUM. UNIT |  | C |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100050070 | LOTI:External leak on hyd. pump P-5952 | Isolate P-5952 | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 4 | 0 | 24-W09-10 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-07-07 | 2021-05-28 | 70 | PCNF REL | APPR OPND | HB /B /07/HBBB-P-5952 | HYDRAULIC PUMP | 99000121 | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050070 | LOTI:External leak on hyd. pump P-5952 | De-mount temporary pump 5952 | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 8 | 0 | 24-W09-10 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-07-07 | 2021-05-28 | 80 | PCNF REL | APPR OPND | HB /B /07/HBBB-P-5952 | HYDRAULIC PUMP | 99000121 | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050070 | LOTI:External leak on hyd. pump P-5952 | Mount new pump 5952 | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 12 | 0 | 24-W09-10 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-07-07 | 2021-05-28 | 90 | PCNF REL | APPR OPND | HB /B /07/HBBB-P-5952 | HYDRAULIC PUMP | 99000121 | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100050070 | LOTI:External leak on hyd. pump P-5952 | De-isolate P-5952 | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 4 | 0 | 24-W09-10 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-07-07 | 2021-05-28 | 100 | PCNF REL | APPR OPND | HB /B /07/HBBB-P-5952 | HYDRAULIC PUMP | 99000121 | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050070 | LOTI:External leak on hyd. pump P-5952 | Test run | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 4 | 0 | 24-W09-10 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-07-07 | 2021-05-28 | 110 | PCNF REL | APPR OPND | HB /B /07/HBBB-P-5952 | HYDRAULIC PUMP | 99000121 | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050070 | LOTI:External leak on hyd. pump P-5952 | Backload temporary pump. | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 1 | 0 | 24-W09-10 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-07-07 | 2021-05-28 | 120 | PCNF REL | APPR OPND | HB /B /07/HBBB-P-5952 | HYDRAULIC PUMP | 99000121 | A |  | MMR | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050070 | LOTI:External leak on hyd. pump P-5952 | New pump | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 | 24-W09-10 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2021-07-07 | 2021-05-28 | 140 | REL | APPR OPND | HB /B /07/HBBB-P-5952 | HYDRAULIC PUMP | 99000121 | A |  | MMR | DK50
2024-W23-24 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100099375 | Air start bottle is external leaking | Reinstall last bottle | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 15 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-04-02 | 2023-11-19 | 120 | REL | APPR OPND | HB /C /01/HBCM-A-0332-AIR-START | FIRE PUMP AIR START |  | A |  | MMS | DK50 |  |  | 2024-05-27
2024-W23-24 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100099375 | Air start bottle is external leaking | Additional materials | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-04-02 | 2023-11-19 | 130 | REL | APPR OPND | HB /C /01/HBCM-A-0332-AIR-START | FIRE PUMP AIR START |  | A |  | MMS | DK50 |  |  | 2024-05-29
2024-W21-22 | 1 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100105110 | New FE to G-1660. | Materiels to store offshore | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-07-09 | 2024-02-25 | 20 | PCNF REL | APPR OPND | HB /D /60/HBDC-FE-165284 | FM332, MASS FLOW METER |  | A |  | MMR | DK50 |  | CLOSED | 2024-05-25
2024-W21-22 | 1 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100105110 | New FE to G-1660. | New materiel warrenty Solar | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-07-09 | 2024-02-25 | 30 | PCNF REL | APPR OPND | HB /D /60/HBDC-FE-165284 | FM332, MASS FLOW METER |  | A |  | MMR | DK50 |  | CLOSED | 2024-05-26
2024-W21-22 | 1 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100105110 | New FE to G-1660. | Add new materiel | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-07-09 | 2024-02-25 | 40 | PCNF REL | APPR OPND | HB /D /60/HBDC-FE-165284 | FM332, MASS FLOW METER |  | A |  | MMR | DK50 |  | CLOSED | 2024-05-27
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100109618 | COMPRESSOR NDE HIGH VIB & BEARING DEFECT | Isolate HBDB-C-5450 | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 2 | 0 |  | 2024-03-25 | 2024-04-01 | 2024-03-25 | 2024-05-09 | 2024-03-25 | 10 | REL | APPR OPND | HB /D /07/HBDB-C-5450 | AIR COMPRESSOR (100%) |  | C |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100109618 | COMPRESSOR NDE HIGH VIB & BEARING DEFECT | Remove Air-End | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 16 | 0 |  | 2024-03-25 | 2024-04-01 | 2024-03-26 | 2024-05-09 | 2024-03-25 | 20 | REL | APPR OPND | HB /D /07/HBDB-C-5450 | AIR COMPRESSOR (100%) |  | C |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100109618 | COMPRESSOR NDE HIGH VIB & BEARING DEFECT | Rigging assistance | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 22 | 0 |  | 2024-03-25 | 2024-04-01 | 2024-03-27 | 2024-05-09 | 2024-03-25 | 30 | REL | APPR OPND | HB /D /07/HBDB-C-5450 | AIR COMPRESSOR (100%) |  | C |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100109618 | COMPRESSOR NDE HIGH VIB & BEARING DEFECT | Install new Air-End | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 16 | 0 |  | 2024-03-25 | 2024-04-01 | 2024-03-30 | 2024-05-09 | 2024-03-25 | 40 | REL | APPR OPND | HB /D /07/HBDB-C-5450 | AIR COMPRESSOR (100%) |  | C |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100109618 | COMPRESSOR NDE HIGH VIB & BEARING DEFECT | Alignment of HBDB-C-5450 | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 4 | 0 |  | 2024-03-25 | 2024-04-01 | 2024-03-31 | 2024-05-09 | 2024-03-25 | 50 | REL | APPR OPND | HB /D /07/HBDB-C-5450 | AIR COMPRESSOR (100%) |  | C |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100109618 | COMPRESSOR NDE HIGH VIB & BEARING DEFECT | Deisolate and test HBDB-C-5450 | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 2 | 0 |  | 2024-03-25 | 2024-04-01 | 2024-04-01 | 2024-05-09 | 2024-03-25 | 60 | REL | APPR OPND | HB /D /07/HBDB-C-5450 | AIR COMPRESSOR (100%) |  | C |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100109618 | COMPRESSOR NDE HIGH VIB & BEARING DEFECT | Cleanup | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 2 | 0 |  | 2024-03-25 | 2024-04-01 | 2024-04-01 | 2024-05-09 | 2024-03-25 | 70 | REL | APPR OPND | HB /D /07/HBDB-C-5450 | AIR COMPRESSOR (100%) |  | C |  | MMR | DK50
2026-W13-14 | 2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100109618 | COMPRESSOR NDE HIGH VIB & BEARING DEFECT | Sol. Valve | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2024-03-25 | 2024-04-01 | 2024-04-01 | 2024-05-09 | 2024-03-25 | 90 | REL | INIT OPND | HB /D /07/HBDB-C-5450 | AIR COMPRESSOR (100%) |  | C |  | MMR | DK50
0 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200011874 | Replace HPU Hyd. oil freefall LB2 HDB | Isolate accordingly | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2025-08-27 | 2023-03-11 | 10 | REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | A |  | MMS | DK60 |  | PROK
0 | 4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200011874 | Replace HPU Hyd. oil freefall LB2 HDB | Replace hyd. oil and filters in HPU | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 12 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2025-08-27 | 2023-03-11 | 20 | REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | A |  | MMS | DK60 |  | PROK
0 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200011874 | Replace HPU Hyd. oil freefall LB2 HDB | De-isolate above | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-09 | 2025-08-27 | 2023-03-11 | 30 | REL | APPR OPND | HD /B /02/HDBM-X-0702 | LIFEBOAT |  | A |  | MMS | DK60 |  | PROK
0 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200011875 | Replace HPU Hyd. oil freefall LB1 HDB | Isolate accordingly | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2025-08-27 | 2023-03-11 | 10 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A |  | MMS | DK60 |  | PROK
0 | 4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200011875 | Replace HPU Hyd. oil freefall LB1 HDB | Replace hyd. oil and filters in HPU | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 12 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2025-08-27 | 2023-03-11 | 20 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A |  | MMS | DK60 |  | PROK
0 | 4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200011875 | Replace HPU Hyd. oil freefall LB1 HDB | De-isolate above | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-09 | 2024-04-09 | 2025-08-27 | 2023-03-11 | 30 | REL | APPR OPND | HD /B /02/HDBM-X-0701 | LIFEBOAT |  | A |  | MMS | DK60 |  | PROK
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | DK48 EL/INSTR MATERIAL ORDER 2020 | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 10 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-02
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | EL MATERIAL | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 20 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-03
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | EL Oprigning V-5076 05.08.20 | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 30 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-04
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | 28000086100 05.01.2021 URGENT OPRINGNIN | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 40 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-05
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | 2300001492 25.01.21 MAT FLUSH RIG MUEHLH | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 50 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-06
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | Tape og Strips 28.01.2021 | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 60 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-07
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | 2300000582 12.04.21 MAT CALIBRATOR MUEHL | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 70 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-08
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | 2800008173 29.04 TMP297 CABLE TIE,MÆRKAT | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 80 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-09
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | 2800008173 29.04 TMP297 OPRIG.GREJ MUEHL | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 90 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-10
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | OFFSHORE TIMESHEETS BESTILLING | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 100 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-11
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | 2300000582 26-07 MAT INSTRUM. MUE | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 110 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-12
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | 2400116224 02.09 INST,OPR PVI3411 MUE | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 120 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-13
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | 2300000582 06.09 INSTRUM 1177162 TOT | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 130 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-14
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | 2300008177 07.09 EX PRO FAN TMP297 MUE | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 140 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-15
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | 2300008177 07.09 PRESSENG TMP297 MUE | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 150 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-16
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 | 2300008177 07.09 FIRE BLANKET TMP297 | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 160 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-17
2024-W43-44 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000582 | DK48 EL/INSTR MATERIAL ORDER 2020/21 |  | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2020-12-31 | 2020-01-01 | 170 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  |  | DK50 |  |  | 2024-06-18
2024-W33-34 | 4 | NE | WRO | PRODTECH | PRODTECH | 2300000637 | DK48 BACKLOAD OC MATERIAL ORDER 2020 | 2300000637 15.12.20 MAT BYGGETAVLE MUEHL | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2020-12-15 | 2020-12-15 | 2020-12-15 | 2020-12-31 | 2020-01-01 | 46 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50 |  |  | 2024-06-02
0 | 4 |  | WRO | PRODTECH | PRODTECH | 2300002631 | DK60 - CONSUMABLE PROD - OCEAN TEAM | DK60 - CONSUMABLE PROD - CHEMICALS | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2022-06-06 | 2021-08-10 | 10 | REL | APPR OPND | HD /A /75 | CHEMICAL STOR & INJECT (INCL METHANOL) |  | A |  | PRD | DK60
2024-W31-32 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002956 | DK50 SCAFF MATERIAL ORDER 2021/2022 | DK50 SCAFF MATERIAL ORDER 2021/2022 | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-08-02 | 2021-06-23 | 10 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W31-32 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002956 | DK50 SCAFF MATERIAL ORDER 2021/2022 | TMP297 TELT 5 | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-08-02 | 2021-06-23 | 20 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W31-32 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002956 | DK50 SCAFF MATERIAL ORDER 2021/2022 | TMP297 TELT 6 | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-08-02 | 2021-06-23 | 30 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W31-32 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002956 | DK50 SCAFF MATERIAL ORDER 2021/2022 | TMP297 TELT 7 | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-08-02 | 2021-06-23 | 40 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W31-32 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002956 | DK50 SCAFF MATERIAL ORDER 2021/2022 | TMP297 TAPE | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-08-02 | 2021-06-23 | 50 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W31-32 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002956 | DK50 SCAFF MATERIAL ORDER 2021/2022 | 2300002956 26.07 ALU BSK MUE | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-08-02 | 2021-06-23 | 60 | REL | APPR OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W31-32 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002956 | DK50 SCAFF MATERIAL ORDER 2021/2022 | TMP297 RAPID CLIPS | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-08-02 | 2021-06-23 | 70 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W31-32 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002956 | DK50 SCAFF MATERIAL ORDER 2021/2022 | Knive til teltbygning | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-08-02 | 2021-06-23 | 80 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W31-32 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002956 | DK50 SCAFF MATERIAL ORDER 2021/2022 | Knive til teltbygning 20 stk. | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-08-02 | 2021-06-23 | 90 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W31-32 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002956 | DK50 SCAFF MATERIAL ORDER 2021/2022 | 2700001666 30.08 L.HUBS HBDACOR MUE | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-08-02 | 2021-06-23 | 100 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
2024-W31-32 | 3 |  | WRO | PRODTECH | PRODTECH | 2300002956 | DK50 SCAFF MATERIAL ORDER 2021/2022 | 2300002956 TOOLS SCAFF | REL GMPS MANC PRC SETC | APPR APOG PMAT RDBL | 0 | 0 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-08-02 | 2021-06-23 | 110 | REL | INIT OPND | HB /D | HALFDAN BD |  | A |  | CON | DK50
0 | 3 | NOSD | WGN | MTN-ELEC | MTN-MECH | 2200014863 | Installation of 15 turnbeds | Installation of 15 turnbeds | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWSC RDBL | 168 | 13 | 24-W07-08 | 2024-09-03 | 2024-09-07 | 2024-09-03 | 2023-12-26 | 2023-08-13 | 10 | PCNF REL | APPR OPND | HD /B /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK60
0 | 3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200014863 | Installation of 15 turnbeds | Additional materials | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWSC RDBL | 0 | 0 | 24-W07-08 | 2024-09-03 | 2024-09-07 | 2024-09-03 | 2023-12-26 | 2023-08-13 | 40 | PCNF REL | APPR OPND | HD /B /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK60
0 | 3 | NOSD | WGN | MTN-ELEC | MTN-MECH | 2200014863 | Installation of 15 turnbeds | Installation of 15 turnbeds | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWSC RDBL | 168 | 23 | 24-W07-08 | 2024-09-03 | 2024-09-07 | 2024-09-03 | 2023-12-26 | 2023-08-13 | 50 | PCNF REL | APPR OPND | HD /B /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK60
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Genbestilling af:4"SPOOL ACC.TO HB-1199- | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 100 | REL | APPR OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Genbestilling af: EM ACC. TO HB-1199 | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 110 | REL | APPR OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Build of scaffolding. | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 18 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 160 | REL | APPR OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Isolation HBD-4"-WS-053-8265-AM | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 165 | REL | APPR OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Cutting of existing spool near elbow. | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 16 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 170 | REL | APPR OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | INP-SITE | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Check Wall thickness on exis spool. | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 180 | REL | APPR OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Marked new cut line on both spools. | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 190 | REL | APPR OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Install rigging epuipment | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 195 | REL | INIT OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Cut existing spool according to marked | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 8 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 200 | REL | APPR OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Rig out spool / Rig in new spool | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 205 | REL | INIT OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Cut new spool according to marked cut po | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 4 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 210 | REL | APPR OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Paint; Linewalk+release, MAT, Permit | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 6 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 211 | REL | INIT OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Paint; Prep, Gear, Team, Test, Clean | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 212 | REL | INIT OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Paint; Habitat, Blast, Clean, QC, Primer | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 213 | REL | INIT OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Paint; Paint, Waste, Clean, Report | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 24 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 214 | REL | INIT OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Assist install new spool/Pyplock. | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 220 | REL | APPR OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | De-Isolation/test HBD-4"-WS-053-8265- | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 225 | REL | APPR OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100024450 | FFSPR Replace temp. rep. HBD-4"-WS-053-8 | Demol. of Scaffolding. | REL GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 12 | 0 |  | 2022-12-01 | 2022-12-03 | 2022-12-01 | 2019-08-01 | 2019-07-12 | 230 | REL | APPR OPND | HB /D /50/HBD-4-WS-053-8265-AM-U | 4 SEA WATER SERVICE LINE |  | C |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064836 | ANOCR HBC - 90+ Corroded Window Frames. | 2100064836-0002-COATING | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-12-19 | 2023-01-31 | 2022-12-19 | 2023-03-02 | 2022-07-05 | 2 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064836 | ANOCR HBC - 90+ Corroded Window Frames. | 2100064836-0003-CONSUMER-GOODS | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-12-19 | 2023-01-31 | 2022-12-19 | 2023-03-02 | 2022-07-05 | 3 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064836 | ANOCR HBC - 90+ Corroded Window Frames. | 2100064836-0004-RENT-ALTRAD-WAREHOUSE | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-12-19 | 2023-01-31 | 2022-12-19 | 2023-03-02 | 2022-07-05 | 4 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064836 | ANOCR HBC - 90+ Corroded Window Frames. | 2100064836-0005-RENT-MOURITSEN | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-12-19 | 2023-01-31 | 2022-12-19 | 2023-03-02 | 2022-07-05 | 5 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064836 | ANOCR HBC - 90+ Corroded Window Frames. | 2100064836-0006-ALTRAD-GARNET-GRIT | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-12-19 | 2023-01-31 | 2022-12-19 | 2023-03-02 | 2022-07-05 | 6 | PCNF REL | INIT OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064836 | ANOCR HBC - 90+ Corroded Window Frames. | HBC - 90+Corroded Window Frames+Rope | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2022-12-19 | 2023-01-31 | 2022-12-19 | 2023-03-02 | 2022-07-05 | 10 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064836 | ANOCR HBC - 90+ Corroded Window Frames. | Paint; Prep/Site/Gear/Net/Barrier+Post | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 200 | 342 |  | 2022-12-19 | 2023-01-31 | 2022-12-19 | 2023-03-02 | 2022-07-05 | 20 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064836 | ANOCR HBC - 90+ Corroded Window Frames. | Paint; Clean, Waste, QC, Wencon, Primer | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 350 | 235 |  | 2022-12-19 | 2023-01-31 | 2022-12-25 | 2023-03-02 | 2022-07-05 | 30 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064836 | ANOCR HBC - 90+ Corroded Window Frames. | Paint; QC-Log, Recoat to Spec | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 250 | 205 |  | 2022-12-19 | 2023-01-31 | 2023-01-05 | 2023-03-02 | 2022-07-05 | 40 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064836 | ANOCR HBC - 90+ Corroded Window Frames. | Paint; Clean-Up+Backload | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 50 | 50 |  | 2022-12-19 | 2023-01-31 | 2023-01-12 | 2023-03-02 | 2022-07-05 | 50 | PCNF REL | APPR OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064836 | ANOCR HBC - 90+ Corroded Window Frames. | Erecting of scaffold | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 300 | 70 |  | 2022-12-19 | 2023-01-31 | 2023-01-13 | 2023-03-02 | 2022-07-05 | 60 | PCNF REL | INIT OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100064836 | ANOCR HBC - 90+ Corroded Window Frames. | Dismantling Of scaffold | REL PCNF GMPS MANC PRC SETC | APPR APOG PMAT AWDO RDBL RFRZ ROUT | 100 | 63 |  | 2022-12-19 | 2023-01-31 | 2023-01-27 | 2023-03-02 | 2022-07-05 | 70 | PCNF REL | INIT OPND | HB /C /02/FIRE AND BLAST-WALLS | FIRE AND BLAST WALLS |  | A |  | MFM | DK50
2026-W13-14 | A | NOSD | WPM | MTN-MECH | INP-SITE | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | Inspection of pad eyes / lifting points | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 | DK50-M-6920 | 2024-06-17 | 2024-08-27 | 2024-06-17 | 2022-07-22 | 2022-04-22 | 1 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | Scaff assistance | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 20 | 12 | DK50-M-6920 | 2024-06-17 | 2024-08-27 | 2024-06-17 | 2022-07-22 | 2022-04-22 | 2 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | ISOLATION BY PRODUCTION | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | DK50-M-6920 | 2024-06-17 | 2024-08-27 | 2024-06-20 | 2022-07-22 | 2022-04-22 | 10 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | FWP ANODE REPLACEMENT-HBDB-A-0352 | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 120 | 0 | DK50-M-6920 | 2024-06-17 | 2024-08-27 | 2024-06-20 | 2022-07-22 | 2022-04-22 | 20 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | FWP ANODE REPLACEMENT-HBDB-A-0352 | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 120 | 0 | DK50-M-6920 | 2024-06-17 | 2024-08-27 | 2024-07-02 | 2022-07-22 | 2022-04-22 | 30 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | PRODTECH | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | DE-ISOLATION BY PRODUCTION | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 | DK50-M-6920 | 2024-06-17 | 2024-08-27 | 2024-07-25 | 2022-07-22 | 2022-04-22 | 40 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | Rigger assistance | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 240 | 0 | DK50-M-6920 | 2024-06-17 | 2024-08-27 | 2024-07-25 | 2022-07-22 | 2022-04-22 | 50 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | Performance test | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 | DK50-M-6920 | 2024-06-17 | 2024-08-27 | 2024-08-18 | 2022-07-22 | 2022-04-22 | 70 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | Replace ALL hydr. oil til Total Oil | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 20 | 0 | DK50-M-6920 | 2024-06-17 | 2024-08-27 | 2024-08-19 | 2022-07-22 | 2022-04-22 | 80 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ROPE | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | Rope aasistance for mount of air hoist | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 36 | 0 | DK50-M-6920 | 2024-06-17 | 2024-08-27 | 2024-08-20 | 2022-07-22 | 2022-04-22 | 90 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | Crane assisstance | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 30 | 0 | DK50-M-6920 | 2024-06-17 | 2024-08-27 | 2024-08-21 | 2022-07-22 | 2022-04-22 | 100 | PCNF REL | APPR OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | Additional materials. | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-06-17 | 2024-08-27 | 2024-08-27 | 2022-07-22 | 2022-04-22 | 120 | PCNF REL | INIT OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | Filter element for OTS pump | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-06-17 | 2024-08-27 | 2024-08-27 | 2022-07-22 | 2022-04-22 | 130 | PCNF REL | INIT OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | Hose for OTS pump | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-06-17 | 2024-08-27 | 2024-08-27 | 2022-07-22 | 2022-04-22 | 140 | PCNF REL | INIT OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | Cradles for pipe stack | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-06-17 | 2024-08-27 | 2024-08-27 | 2022-07-22 | 2022-04-22 | 150 | PCNF REL | INIT OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400207463 | 8Y FWP ANODE REPLACEMENT-HBDB-A-0352 | Additional shims | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2024-06-17 | 2024-08-27 | 2024-08-27 | 2022-07-22 | 2022-04-22 | 160 | PCNF REL | INIT OPND | HB /D /01/HBDB-A-0352 | FIREWATER PUMP MODULE |  | D | DKHB-0652 | MMS | DK50 | MS0014
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001427 | HBA02, WL, TRSSSV React, SV19837 | HBA02, WL, TRSSSV React, SV19837 | REL GMPS MANC PRC SETC | APPR APOG PMAT | 0 | 0 |  | 2024-04-04 | 2024-05-03 | 2024-04-04 | 2024-09-09 | 2024-04-27 | 10 | REL | APPR OPND | HB /A /55/HBA02-WATER-INJECTION | HBA02 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | PRODTECH | 2900001427 | HBA02, WL, TRSSSV React, SV19837 | Safing well/well handover (production) | REL GMPS MANC PRC SETC | APPR APOG PMAT | 12 | 0 |  | 2024-04-04 | 2024-05-03 | 2024-04-04 | 2024-09-09 | 2024-04-27 | 20 | REL | APPR OPND | HB /A /55/HBA02-WATER-INJECTION | HBA02 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | MTN-ROUS | 2900001427 | HBA02, WL, TRSSSV React, SV19837 | Crane assist during WL R/U and RD | REL GMPS MANC PRC SETC | APPR APOG PMAT | 48 | 0 |  | 2024-04-04 | 2024-05-03 | 2024-04-04 | 2024-09-09 | 2024-04-27 | 30 | REL | APPR OPND | HB /A /55/HBA02-WATER-INJECTION | HBA02 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | MTN-SCAF | 2900001427 | HBA02, WL, TRSSSV React, SV19837 | Scaffolder assistance for RU and RD | REL GMPS MANC PRC SETC | APPR APOG PMAT | 48 | 0 |  | 2024-04-04 | 2024-05-03 | 2024-04-04 | 2024-09-09 | 2024-04-27 | 40 | REL | APPR OPND | HB /A /55/HBA02-WATER-INJECTION | HBA02 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | MTN-ELEC | 2900001427 | HBA02, WL, TRSSSV React, SV19837 | Electrician assistance for RU and RD | REL GMPS MANC PRC SETC | APPR APOG PMAT | 12 | 0 |  | 2024-04-04 | 2024-05-03 | 2024-04-08 | 2024-09-09 | 2024-04-27 | 50 | REL | APPR OPND | HB /A /55/HBA02-WATER-INJECTION | HBA02 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | MTN-TELE | 2900001427 | HBA02, WL, TRSSSV React, SV19837 | Tele assist during WL RRU and RD | REL GMPS MANC PRC SETC | APPR APOG PMAT | 24 | 0 |  | 2024-04-04 | 2024-05-03 | 2024-04-11 | 2024-09-09 | 2024-04-27 | 60 | REL | APPR OPND | HB /A /55/HBA02-WATER-INJECTION | HBA02 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | VEN-CRAN | 2900001427 | HBA02, WL, TRSSSV React, SV19837 | Crane support assitance for days | REL GMPS MANC PRC SETC | APPR APOG PMAT | 168 | 0 |  | 2024-04-04 | 2024-05-03 | 2024-04-16 | 2024-09-09 | 2024-04-27 | 70 | REL | APPR OPND | HB /A /55/HBA02-WATER-INJECTION | HBA02 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001427 | HBA02, WL, TRSSSV React, SV19837 | Oilenco tools | REL GMPS MANC PRC SETC | APPR APOG PMAT | 0 | 0 |  | 2024-04-04 | 2024-05-03 | 2024-05-03 | 2024-09-09 | 2024-04-27 | 80 | REL | APPR OPND | HB /A /55/HBA02-WATER-INJECTION | HBA02 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001427 | HBA02, WL, TRSSSV React, SV19837 | WRSSSV | REL GMPS MANC PRC SETC | APPR APOG PMAT | 0 | 0 |  | 2024-04-04 | 2024-05-03 | 2024-05-03 | 2024-09-09 | 2024-04-27 | 90 | REL | APPR OPND | HB /A /55/HBA02-WATER-INJECTION | HBA02 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001427 | HBA02, WL, TRSSSV React, SV19837 | Ocean Team chemicals | REL GMPS MANC PRC SETC | APPR APOG PMAT | 0 | 0 |  | 2024-04-04 | 2024-05-03 | 2024-05-03 | 2024-09-09 | 2024-04-27 | 100 | REL | APPR OPND | HB /A /55/HBA02-WATER-INJECTION | HBA02 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001427 | HBA02, WL, TRSSSV React, SV19837 | Semco spare parts | REL GMPS MANC PRC SETC | APPR APOG PMAT | 0 | 0 |  | 2024-04-04 | 2024-05-03 | 2024-05-03 | 2024-09-09 | 2024-04-27 | 110 | REL | INIT OPND | HB /A /55/HBA02-WATER-INJECTION | HBA02 WATER INJECTION |  | A |  | WLD | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024577 | LOTI:HBCM-LCP-5233 - Cal./rep of purge s | Cal./rep of purge system | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 0 | 8 | W01-02 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2019-10-03 | 2019-09-13 | 10 | PCNF REL | APPR OPND | HB /C /52/HBCM-LCP-5233 | SEAWATER ANTI-FOULING UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024577 | LOTI:HBCM-LCP-5233 - Cal./rep of purge s | Isolate equipment | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 3 | 0 | W37-38 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2019-10-03 | 2019-09-13 | 20 | PCNF REL | APPR OPND | HB /C /52/HBCM-LCP-5233 | SEAWATER ANTI-FOULING UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100024577 | LOTI:HBCM-LCP-5233 - Cal./rep of purge s | Troubleshooting, replace RLV25 & Cal. | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 15 | 7 | W37-38 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2019-10-03 | 2019-09-13 | 30 | PCNF REL | APPR OPND | HB /C /52/HBCM-LCP-5233 | SEAWATER ANTI-FOULING UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100024577 | LOTI:HBCM-LCP-5233 - Cal./rep of purge s | Troubleshooting, replace RLV25 & Cal. | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 15 | 9 | W37-38 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2019-10-03 | 2019-09-13 | 40 | PCNF REL | APPR OPND | HB /C /52/HBCM-LCP-5233 | SEAWATER ANTI-FOULING UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024577 | LOTI:HBCM-LCP-5233 - Cal./rep of purge s | Remove isolation - Ready to operate | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 3 | 0 |  | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2019-10-03 | 2019-09-13 | 50 | PCNF REL | APPR OPND | HB /C /52/HBCM-LCP-5233 | SEAWATER ANTI-FOULING UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024577 | LOTI:HBCM-LCP-5233 - Cal./rep of purge s | Order correct relief valve | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2019-10-03 | 2019-09-13 | 60 | PCNF REL | APPR OPND | HB /C /52/HBCM-LCP-5233 | SEAWATER ANTI-FOULING UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-TELE | 2100024577 | LOTI:HBCM-LCP-5233 - Cal./rep of purge s | Trobleshooting | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 20 | 33 | W01-02 | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2019-10-03 | 2019-09-13 | 70 | PCNF REL | APPR OPND | HB /C /52/HBCM-LCP-5233 | SEAWATER ANTI-FOULING UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024577 | LOTI:HBCM-LCP-5233 - Cal./rep of purge s | Assist base crew with outstandings | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 8 | 0 |  | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2019-10-03 | 2019-09-13 | 80 | REL | APPR OPND | HB /C /52/HBCM-LCP-5233 | SEAWATER ANTI-FOULING UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100024577 | LOTI:HBCM-LCP-5233 - Cal./rep of purge s | Trouble shoot and order sparesparts | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 18 | 0 |  | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2019-10-03 | 2019-09-13 | 90 | REL | INIT OPND | HB /C /52/HBCM-LCP-5233 | SEAWATER ANTI-FOULING UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024577 | LOTI:HBCM-LCP-5233 - Cal./rep of purge s | Isolate equipment | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 1 | 0 |  | 2024-03-11 | 2024-03-14 | 2024-03-11 | 2019-10-03 | 2019-09-13 | 100 | REL | INIT OPND | HB /C /52/HBCM-LCP-5233 | SEAWATER ANTI-FOULING UNIT |  | C |  | MIN | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100046783 | ANOPR Spring Hanger HBA flowlines batch | Spring Hanger failures on HBA flowlines | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-09-02 | 2024-07-30 | 2021-04-25 | 2021-03-16 | 10 | PCNF REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100046783 | ANOPR Spring Hanger HBA flowlines batch | additional materials | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-09-02 | 2024-07-30 | 2021-04-25 | 2021-03-16 | 30 | PCNF REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100046783 | ANOPR Spring Hanger HBA flowlines batch | SEMCO hrs | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 200 | 93 | W07-08 | 2024-07-30 | 2024-09-02 | 2024-07-30 | 2021-04-25 | 2021-03-16 | 60 | PCNF REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100046783 | ANOPR Spring Hanger HBA flowlines batch | Material handling Semco | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 0 | 0 |  | 2024-07-30 | 2024-09-02 | 2024-08-05 | 2021-04-25 | 2021-03-16 | 80 | REL | INIT OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100046783 | ANOPR Spring Hanger HBA flowlines batch | Remove spring Hangers | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 350 | 0 |  | 2024-07-30 | 2024-09-02 | 2024-08-05 | 2021-04-25 | 2021-03-16 | 90 | REL | INIT OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100046783 | ANOPR Spring Hanger HBA flowlines batch | Replace spring Hangers | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 450 | 0 |  | 2024-07-30 | 2024-09-02 | 2024-08-18 | 2021-04-25 | 2021-03-16 | 100 | REL | INIT OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MFM | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100052178 | XCV-30198 is leaking internally | Prepare rigging plan | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 10 | 9 |  | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2022-02-20 | 2021-09-23 | 5 | PCNF REL | INIT OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100052178 | XCV-30198 is leaking internally | XCV-30198 is leaking internally | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 0 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-02-20 | 2021-09-23 | 10 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100052178 | XCV-30198 is leaking internally | Grease and exercise valve | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-02-20 | 2021-09-23 | 20 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100052178 | XCV-30198 is leaking internally | Prepare Lifting Equip. | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 12 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-02-20 | 2021-09-23 | 30 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100052178 | XCV-30198 is leaking internally | Prepare matr/tools | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-02-20 | 2021-09-23 | 40 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100052178 | XCV-30198 is leaking internally | Production isolation | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-02-20 | 2021-09-23 | 50 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100052178 | XCV-30198 is leaking internally | Rigger assistance | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 20 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2022-02-20 | 2021-09-23 | 60 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100052178 | XCV-30198 is leaking internally | Actuator removal | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2022-02-20 | 2021-09-23 | 70 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100052178 | XCV-30198 is leaking internally | XCV-30198 removal/installation | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 12 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2022-02-20 | 2021-09-23 | 80 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100052178 | XCV-30198 is leaking internally | Actuator installation | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 6 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2022-02-20 | 2021-09-23 | 90 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100052178 | XCV-30198 is leaking internally | Production de-isolation w leaktest | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 3 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2022-02-20 | 2021-09-23 | 100 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100052178 | XCV-30198 is leaking internally | Function test | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 2 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2022-02-20 | 2021-09-23 | 110 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-RIGG | 2100052178 | XCV-30198 is leaking internally | Lifting equip. removal | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT RDBL | 8 | 0 |  | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2022-02-20 | 2021-09-23 | 120 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30198 | 8" 2500# T PLUG VALVE FROM WELL 19 |  | F |  | MMS | DK50
2024-W27-28 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084871 | Sheared valve handle on HBA CI skid | Sheared valve handle on HBA CI skid | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2025-12-19 | 2023-07-03 | 10 | REL | APPR OPND | HB /A /75/HBAA-P-39441 | CORROSION INHIBITOR PUMP |  | A |  | MMR | DK50 |  | PROK | 2024-05-28
2024-W27-28 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084871 | Sheared valve handle on HBA CI skid | FLM Sheared valve handle on HBA CI skid | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2025-12-19 | 2023-07-03 | 20 | REL | APPR OPND | HB /A /75/HBAA-P-39441 | CORROSION INHIBITOR PUMP |  | A |  | MMR | DK50 |  | PROK | 2024-05-29
0 | 3 | NOSD | WGN | MTN-ROUS | MTN-ROUS | 2200006759 | Replace all mattresses in cabins. | Rigging in new mattresses (16 PCS) | REL PCNF GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 3 | 0 | Wrong mat | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2021-04-11 | 2021-03-22 | 50 | REL | APPR OPND | HD /B /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK60
0 | 3 | NOSD | WGN | MTN-ROUS | MTN-ROUS | 2200006759 | Replace all mattresses in cabins. | Place new mattresses in cabins (16 PCS) | REL PCNF GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 4 | 0 | Wrong mat | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2021-04-11 | 2021-03-22 | 60 | REL | APPR OPND | HD /B /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK60
2026-W13-14 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010131 | ANOPR HBA replacement spring supports ba | HBA replacement spring supports batch 2 | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-06-25 | 2022-03-27 | 10 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010131 | ANOPR HBA replacement spring supports ba | Additional materials | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 0 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-06-25 | 2022-03-27 | 20 | REL | APPR OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200010131 | ANOPR HBA replacement spring supports ba | Check ID plate and take photos | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 30 | 0 |  | 2024-03-11 | 2024-03-12 | 2024-03-11 | 2022-06-25 | 2022-03-27 | 40 | REL | INIT OPND | HB /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING |  | A |  | MFM | DK50
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001233 | HDA-06/14, set plug, GLV replacement | HDA14, set plug, GLV replacement | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 0 | 0 |  | 2024-02-04 | 2024-03-22 | 2024-02-04 | 2024-06-18 | 2024-02-04 | 10 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | PRODTECH | 2900001233 | HDA-06/14, set plug, GLV replacement | Safing well/well handover (production) | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 12 | 0 |  | 2024-02-04 | 2024-03-22 | 2024-02-04 | 2024-06-18 | 2024-02-04 | 20 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-ROUS | 2900001233 | HDA-06/14, set plug, GLV replacement | Crane assist during WL R/U and RD | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 48 | 0 |  | 2024-02-04 | 2024-03-22 | 2024-02-07 | 2024-06-18 | 2024-02-04 | 30 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-SCAF | 2900001233 | HDA-06/14, set plug, GLV replacement | Scaffolder assistance for RU and RD | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 50 | 0 |  | 2024-02-04 | 2024-03-22 | 2024-02-13 | 2024-06-18 | 2024-02-04 | 40 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-ELEC | 2900001233 | HDA-06/14, set plug, GLV replacement | Electrician assistance for RU and RD | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 12 | 0 |  | 2024-02-04 | 2024-03-22 | 2024-02-18 | 2024-06-18 | 2024-02-04 | 50 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-TELE | 2900001233 | HDA-06/14, set plug, GLV replacement | Tele assist during WL RRU and RD | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 24 | 0 |  | 2024-02-04 | 2024-03-22 | 2024-02-20 | 2024-06-18 | 2024-02-04 | 60 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | VEN-CRAN | 2900001233 | HDA-06/14, set plug, GLV replacement | Crane support assitance for days/nights | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 240 | 0 |  | 2024-02-04 | 2024-03-22 | 2024-02-25 | 2024-06-18 | 2024-02-04 | 70 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001233 | HDA-06/14, set plug, GLV replacement | H2S equipment 60 days | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 0 | 0 |  | 2024-02-04 | 2024-03-22 | 2024-03-21 | 2024-06-18 | 2024-02-04 | 80 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001233 | HDA-06/14, set plug, GLV replacement | Plug service | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 0 | 0 |  | 2024-02-04 | 2024-03-22 | 2024-03-21 | 2024-06-18 | 2024-02-04 | 90 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001233 | HDA-06/14, set plug, GLV replacement | Gas lift valves | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 0 | 0 |  | 2024-02-04 | 2024-03-22 | 2024-03-21 | 2024-06-18 | 2024-02-04 | 100 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-PIPF | 2900001233 | HDA-06/14, set plug, GLV replacement | Pipe fitter assistance | REL GMPS MANC PRC SETC | APPR APOG CMAT RDBL | 12 | 0 |  | 2024-02-04 | 2024-03-22 | 2024-03-21 | 2024-06-18 | 2024-02-04 | 110 | REL | INIT OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100043615 | HBDB-HCV-365361 Malfun. outlet P-3653 | Prepare for rig out the valve approx. 95 | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 3 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-08-18 | 2021-03-21 | 10 | PCNF REL | APPR OPND | HB /D /23/HBDB-HCV-365361 | DBB BALL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100043615 | HBDB-HCV-365361 Malfun. outlet P-3653 | Rig out old valve for backload onshore - | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 3 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-08-18 | 2021-03-21 | 40 | PCNF REL | APPR OPND | HB /D /23/HBDB-HCV-365361 | DBB BALL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100043615 | HBDB-HCV-365361 Malfun. outlet P-3653 | Rig in new valve fon installation | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 3 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-08-18 | 2021-03-21 | 50 | PCNF REL | APPR OPND | HB /D /23/HBDB-HCV-365361 | DBB BALL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043615 | HBDB-HCV-365361 Malfun. outlet P-3653 | Install new valve | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 2 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-08-18 | 2021-03-21 | 60 | PCNF REL | APPR OPND | HB /D /23/HBDB-HCV-365361 | DBB BALL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100043615 | HBDB-HCV-365361 Malfun. outlet P-3653 | Pressure test system and leak detection | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 2 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-08-18 | 2021-03-21 | 70 | PCNF REL | APPR OPND | HB /D /23/HBDB-HCV-365361 | DBB BALL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100043615 | HBDB-HCV-365361 Malfun. outlet P-3653 | Backload valve to User Resp. for repair | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 2 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-08-18 | 2021-03-21 | 80 | PCNF REL | APPR OPND | HB /D /23/HBDB-HCV-365361 | DBB BALL VALVE | 99000119 | C |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043615 | HBDB-HCV-365361 Malfun. outlet P-3653 | Add. Matr. New Gearbox | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 6 | 24-W01-02 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-08-18 | 2021-03-21 | 90 | PCNF REL | APPR OPND | HB /D /23/HBDB-HCV-365361 | DBB BALL VALVE | 99000119 | C |  | MMS | DK50
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | HDA - Grating/Handrail Rep. on Jacket | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 10 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | BIS-DK-TEPDK-GVI 591Rev1 - Gratings | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 20 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Build scaffold | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 30 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Prepare rigging | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 40 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Remove grating in bundles acc. dwg591 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 50 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | INP-SITE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Inspect surfaces on underlying structure | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 60 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Sandblast badly conditioned structure | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 70 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Paint sandblasted areas | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 80 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Install new grating section 1 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 90 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Dismantle scaff & secure & clean up area | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 100 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | BIS-DK-TEPDK-GVI 593 - Stair Treads | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 110 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Build scaffold | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 120 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Dismantle stair treads from stair | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 130 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Sandblast and prep for new treads | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 140 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Install new treads | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 150 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Paint staircase | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 160 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Dismantle scaff & secure & clean up area | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 170 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | BIS-DK-TEPDK-GVI 597 - Handrails | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 180 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Build scaffold | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 190 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Prepare rigging | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 200 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Remove old handrail | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 210 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Prepare for new handrail | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 220 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Install new handrail | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 230 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Dismantle scaff & secure & clean up area | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 240 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | BIS-DK-TEPDK-GVI 345 - Gratings | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 250 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Build scaffold | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 260 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Prepare rigging | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 270 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Remove grating section 2 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 280 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | INP-SITE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Inspect surfaces on underlying structure | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 290 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Sandblast badly conditioned structure | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 300 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Paint sandblasted areas | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 310 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Install new grating section 2 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 320 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Dismantle scaff & secure & clean up area | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 330 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | BIS-DK-TEPDK-GVI 340 - Grating | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 340 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Build scaffold | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 350 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Prepare rigging | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 360 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Remove grating section 3 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 370 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Inspect surfaces on underlying structure | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 380 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Sandblast badly conditioned structure | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 390 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Paint sandblasted areas | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 400 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Install new grating section 3 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 410 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Dismantle scaff & secure & clean up area | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 420 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | BIS-DK-TEPDK-GVI 339 - Grating | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 430 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Build scaffold | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 440 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Prepare rigging | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 450 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Remove grating section 4 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 460 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Inspect surfaces on underlying structure | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 470 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Sandblast badly conditioned structure | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 480 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Paint sandblasted areas | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 490 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Install new grating section 4 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 500 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Dismantle scaff & secure & clean up area | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 510 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | BIS-DK-TEPDK-GVI 337 - Handrail | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 520 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Build scaffold | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 530 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Prepare rigging | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 540 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Remove old handrail | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 550 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Prepare for new handrail | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 560 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Install new handrail | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 570 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Dismantle scaff & secure & clean up area | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 580 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Material handling | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 590 | REL | APPR OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Remove grating section 5 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 600 | REL | INIT OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Install new grating section 5 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 610 | REL | INIT OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Remove grating section 6 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 620 | REL | INIT OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077619 | TOPSR HDA - Grating/Handrail Rep. on LVL | Install new grating section 6 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWSC RDBL | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-05-06 | 2022-12-22 | 630 | REL | INIT OPND | HD /A /86/JACKET - GRATINGS | JACKET - GRATINGS |  | A |  | MFM | DK60
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100045906 | LOTI: Recharge & replace bottle HBCM-A-0 | Isolate HBCM-A-0338 | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 3 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2021-04-08 | 2021-02-27 | 10 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0338 | FIREWATER MIST SKID | 99000121 | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100045906 | LOTI: Recharge & replace bottle HBCM-A-0 | Replace bottle HBCM-A-0338 | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 6 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2021-04-08 | 2021-02-27 | 20 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0338 | FIREWATER MIST SKID | 99000121 | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-INST | 2100045906 | LOTI: Recharge & replace bottle HBCM-A-0 | Troubleshoot PSL and replace | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 10 | 73 |  | 2024-03-13 | 2024-03-13 | 2023-01-02 | 2021-04-08 | 2021-02-27 | 50 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0338 | FIREWATER MIST SKID | 99000121 | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100045906 | LOTI: Recharge & replace bottle HBCM-A-0 | N2 cylinder 11. Replace bottle valve. | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 5 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2021-04-08 | 2021-02-27 | 70 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0338 | FIREWATER MIST SKID | 99000121 | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100045906 | LOTI: Recharge & replace bottle HBCM-A-0 | N2 cylinder 12. Repair PSL line | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 3 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2021-04-08 | 2021-02-27 | 80 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0338 | FIREWATER MIST SKID | 99000121 | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100045906 | LOTI: Recharge & replace bottle HBCM-A-0 | N2 cylinder 13. Repair PSL line | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 3 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2021-04-08 | 2021-02-27 | 90 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0338 | FIREWATER MIST SKID | 99000121 | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100045906 | LOTI: Recharge & replace bottle HBCM-A-0 | N2 cylinder 14. Replace bottle valve | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 5 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2021-04-08 | 2021-02-27 | 100 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0338 | FIREWATER MIST SKID | 99000121 | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-RIGG | 2100045906 | LOTI: Recharge & replace bottle HBCM-A-0 | Rigging assist | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 18 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2021-04-08 | 2021-02-27 | 110 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0338 | FIREWATER MIST SKID | 99000121 | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100045906 | LOTI: Recharge & replace bottle HBCM-A-0 | Discharge of skid for repair | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 4 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2021-04-08 | 2021-02-27 | 120 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0338 | FIREWATER MIST SKID | 99000121 | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100045906 | LOTI: Recharge & replace bottle HBCM-A-0 | Recharge of N2 and water | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 10 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2021-04-08 | 2021-02-27 | 130 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0338 | FIREWATER MIST SKID | 99000121 | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100045906 | LOTI: Recharge & replace bottle HBCM-A-0 | De-Isolate/Test HBCM-A-0338 | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 3 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2021-04-08 | 2021-02-27 | 135 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0338 | FIREWATER MIST SKID | 99000121 | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100045906 | LOTI: Recharge & replace bottle HBCM-A-0 | Extra spare parts - check & backload | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2021-04-08 | 2021-02-27 | 140 | PCNF REL | APPR OPND | HB /C /01/HBCM-A-0338 | FIREWATER MIST SKID | 99000121 | C |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100055072 | HBD/78: Corroded bolts on hyd. motor mai | Rig motor off and on | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 12 | 0 | W11-W12 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2021-12-29 | 2021-09-30 | 40 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055072 | HBD/78: Corroded bolts on hyd. motor mai | QC, functioncheck ,report, clean-up | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 1 | 6 | W11-W12 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2021-12-29 | 2021-09-30 | 70 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055072 | HBD/78: Corroded bolts on hyd. motor mai | Isolate crane | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W11-W12 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2021-12-29 | 2021-09-30 | 80 | REL | INIT OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055072 | HBD/78: Corroded bolts on hyd. motor mai | Replace bolts on SAE flanger | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | W11-W12 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2021-12-29 | 2021-09-30 | 90 | REL | INIT OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055072 | HBD/78: Corroded bolts on hyd. motor mai | De-Isolate crane | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W11-W12 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2021-12-29 | 2021-09-30 | 100 | REL | INIT OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055072 | HBD/78: Corroded bolts on hyd. motor mai | QC, functioncheck ,report, clean-up | REL PCNF PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | W11-W12 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2021-12-29 | 2021-09-30 | 110 | REL | INIT OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100097398 | Broken pre-fuel filter cover FWP-0331 | Broken pre-fuel filter cover FWP-0331 | REL GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 0 | 0 | 24-W05-06 | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-02-26 | 2023-10-14 | 10 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | A |  | MMS | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | PRODTECH | 2100097398 | Broken pre-fuel filter cover FWP-0331 | Isolate FWP from start | REL GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | 24-W05-06 | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-02-26 | 2023-10-14 | 20 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | A |  | MMS | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100097398 | Broken pre-fuel filter cover FWP-0331 | Replace lid | REL GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 2 | 0 | 24-W05-06 | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-02-26 | 2023-10-14 | 30 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | A |  | MMS | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100097398 | Broken pre-fuel filter cover FWP-0331 | De-isolate | REL GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 1 | 0 | 24-W05-06 | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-02-26 | 2023-10-14 | 40 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | A |  | MMS | DK50
2026-W1-2 | 3 | NE | WDF | MTN-MECH | MTN-MECH | 2100097398 | Broken pre-fuel filter cover FWP-0331 | Additional materials | REL GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 0 | 0 |  | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-02-26 | 2023-10-14 | 50 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | A |  | MMS | DK50
0 | 2 | NOSD | WDF | MTN-ROUS | PRODTECH | 2100097586 | Replace firehoses in all hosereel | Isolate hosereels 1 at a time | REL GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 5 | 0 | 23-W51-52 | 2024-03-28 | 2024-04-03 | 2024-03-28 | 2023-10-19 | 2023-09-04 | 10 | REL | APPR OPND | HD /B /01/HDBC-FHR-0301 | HOSE REEL FOAM |  | C |  | MMS | DK60
0 | 2 | NOSD | WDF | MTN-ROUS | MTN-ROUS | 2100097586 | Replace firehoses in all hosereel | Replace hoses on all hosereels | REL GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 15 | 0 | 23-W51-52 | 2024-03-28 | 2024-04-03 | 2024-03-29 | 2023-10-19 | 2023-09-04 | 20 | REL | APPR OPND | HD /B /01/HDBC-FHR-0301 | HOSE REEL FOAM |  | C |  | MMS | DK60
0 | 2 | NOSD | WDF | MTN-ROUS | PRODTECH | 2100097586 | Replace firehoses in all hosereel | De-isolate accordingly | REL GMPS MANC PRC SETC | APPR APOG CMAT AWDO SCH RDBL RFRZ ROUT | 5 | 0 | 23-W51-52 | 2024-03-28 | 2024-04-03 | 2024-04-02 | 2023-10-19 | 2023-09-04 | 30 | REL | APPR OPND | HD /B /01/HDBC-FHR-0301 | HOSE REEL FOAM |  | C |  | MMS | DK60
2024-W19-20 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026515 | Change out hose reel station -> HBBA-HRS | Isolate the hose reel station | REL GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL ROUT | 1 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2019-08-18 | 2019-05-20 | 10 | REL | APPR OPND | HB /B /01/HBBA-HRS-0328 | HOSE REEL STATION |  | C |  | MMS | DK50 |  |  | 2024-05-19
2024-W19-20 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026515 | Change out hose reel station -> HBBA-HRS | Prepare tools & equipment | REL GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL ROUT | 1 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2019-08-18 | 2019-05-20 | 20 | REL | APPR OPND | HB /B /01/HBBA-HRS-0328 | HOSE REEL STATION |  | C |  | MMS | DK50 |  |  | 2024-05-20
2024-W19-20 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026515 | Change out hose reel station -> HBBA-HRS | Change out hose reel station | REL GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL ROUT | 6 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2019-08-18 | 2019-05-20 | 30 | REL | APPR OPND | HB /B /01/HBBA-HRS-0328 | HOSE REEL STATION |  | C |  | MMS | DK50 |  |  | 2024-05-22
2024-W19-20 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026515 | Change out hose reel station -> HBBA-HRS | De-Isolate the hose reel station | REL GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL ROUT | 1 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2019-08-18 | 2019-05-20 | 40 | REL | APPR OPND | HB /B /01/HBBA-HRS-0328 | HOSE REEL STATION |  | C |  | MMS | DK50 |  |  | 2024-05-24
2024-W19-20 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026515 | Change out hose reel station -> HBBA-HRS | Clean up and disposal of old station | REL GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL ROUT | 2 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2019-08-18 | 2019-05-20 | 50 | REL | APPR OPND | HB /B /01/HBBA-HRS-0328 | HOSE REEL STATION |  | C |  | MMS | DK50 |  |  | 2024-05-26
2024-W19-20 | 3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100026515 | Change out hose reel station -> HBBA-HRS | Rigger assistance. | REL GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL ROUT | 0 | 0 |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2019-08-18 | 2019-05-20 | 70 | REL | APPR OPND | HB /B /01/HBBA-HRS-0328 | HOSE REEL STATION |  | C |  | MMS | DK50 |  |  | 2024-05-27
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100045217 | FFSP Corroded flange HBD-16”-OCS-036-252 | Corroded flange HBD-16”-OCS-036-2527-ED | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 0 | 40.5 | W01-02 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2021-03-24 | 2021-02-12 | 10 | PCNF REL | APPR OPND | HB /D /23/HBD-16-OCS-036-2527-ED-U | 16 CRUDE OIL SOUR LINE |  | D |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100045217 | FFSP Corroded flange HBD-16”-OCS-036-252 | New spools | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W01-02 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2021-03-24 | 2021-02-12 | 30 | REL | APPR OPND | HB /D /23/HBD-16-OCS-036-2527-ED-U | 16 CRUDE OIL SOUR LINE |  | D |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100045217 | FFSP Corroded flange HBD-16”-OCS-036-252 | 2100045217 MAT 30.08 CLAMP.GSK,BOLTS | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W01-02 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2021-03-24 | 2021-02-12 | 60 | REL | APPR OPND | HB /D /23/HBD-16-OCS-036-2527-ED-U | 16 CRUDE OIL SOUR LINE |  | D |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045217 | FFSP Corroded flange HBD-16”-OCS-036-252 | Leak test and deisolation | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 4 | 0 | W01-02 RCE | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2021-03-24 | 2021-02-12 | 140 | REL | APPR OPND | HB /D /23/HBD-16-OCS-036-2527-ED-U | 16 CRUDE OIL SOUR LINE |  | D |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100045217 | FFSP Corroded flange HBD-16”-OCS-036-252 | Install/remove scaff. for lifting gear | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 60 | 83.5 | W01-02 RCE | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2021-03-24 | 2021-02-12 | 150 | PCNF REL | APPR OPND | HB /D /23/HBD-16-OCS-036-2527-ED-U | 16 CRUDE OIL SOUR LINE |  | D |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100045217 | FFSP Corroded flange HBD-16”-OCS-036-252 | Remove lifting gear | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 14 | 16 | W01-02 RCE | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2021-03-24 | 2021-02-12 | 160 | PCNF REL | APPR OPND | HB /D /23/HBD-16-OCS-036-2527-ED-U | 16 CRUDE OIL SOUR LINE |  | D |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | CON-SCAF | 2100045217 | FFSP Corroded flange HBD-16”-OCS-036-252 | 2100045217 03.09 STUD GASKET NUTS MM | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W01-02 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2021-03-24 | 2021-02-12 | 170 | REL | APPR OPND | HB /D /23/HBD-16-OCS-036-2527-ED-U | 16 CRUDE OIL SOUR LINE |  | D |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | CON-SCAF | 2100045217 | FFSP Corroded flange HBD-16”-OCS-036-252 | 2100045217 08.09 NUTS | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W01-02 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2021-03-24 | 2021-02-12 | 171 | REL | APPR OPND | HB /D /23/HBD-16-OCS-036-2527-ED-U | 16 CRUDE OIL SOUR LINE |  | D |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | CON-SCAF | 2100045217 | FFSP Corroded flange HBD-16”-OCS-036-252 | New blind | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W01-02 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2021-03-24 | 2021-02-12 | 180 | REL | APPR OPND | HB /D /23/HBD-16-OCS-036-2527-ED-U | 16 CRUDE OIL SOUR LINE |  | D |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | CON-WELD | 2100045217 | FFSP Corroded flange HBD-16”-OCS-036-252 |  | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 0 | 0 | W01-02 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2021-03-24 | 2021-02-12 | 181 | REL | APPR OPND | HB /D /23/HBD-16-OCS-036-2527-ED-U | 16 CRUDE OIL SOUR LINE |  | D |  | MFM | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045217 | FFSP Corroded flange HBD-16”-OCS-036-252 | Extra materials | REL PCNF CSER GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2021-03-24 | 2021-02-12 | 201 | REL | INIT OPND | HB /D /23/HBD-16-OCS-036-2527-ED-U | 16 CRUDE OIL SOUR LINE |  | D |  | MFM | DK50
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079233 | HDB/78: Flush slew bearing w. grease | Flush slew bearing under rotation | REL GMPS MANC PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-09-15 | 2024-12-15 | 2024-09-15 | 2023-06-06 | 2023-01-22 | 10 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100079233 | HDB/78: Flush slew bearing w. grease | Operation of crane | REL GMPS MANC PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 3 | 0 |  | 2024-09-15 | 2024-12-15 | 2024-09-15 | 2023-06-06 | 2023-01-22 | 20 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079233 | HDB/78: Flush slew bearing w. grease | Isolate/de-isolate of crane HDBR-A-6102 | REL GMPS MANC PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-09-15 | 2024-12-15 | 2024-09-15 | 2023-06-06 | 2023-01-22 | 25 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079233 | HDB/78: Flush slew bearing w. grease | Check sealing and clean excess grease | REL GMPS MANC PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 2 | 0 |  | 2024-09-15 | 2024-12-15 | 2024-09-16 | 2023-06-06 | 2023-01-22 | 30 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079233 | HDB/78: Flush slew bearing w. grease | Take new slew sample after 3 month | REL GMPS MANC PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 1 | 0 |  | 2024-09-15 | 2024-12-15 | 2024-12-15 | 2023-06-06 | 2023-01-22 | 40 | REL | APPR OPND | HD /B /78/HDBR-A-6102 | CRANE - 6 T |  | A |  | MMS | DK60
2024-W47-48 | 3 | NOSD | WGN | MTN-ELEC | VEN-HVAC | 2200011350 | Air in let in CCR Room | Demount old inlet diffussors | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 8 | 0 | W47-47 IOP 08-21/11-22 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-05-24 | 2022-02-23 | 10 | PCNF REL | APPR OPND | HB /D /09/HBDC-A-1253 | HVAC AHU FOR LEVELS 1, 2 & LEVEL 2 MEZZ. |  | A |  | MEL | DK50
2024-W47-48 | 3 | NOSD | WGN | MTN-ELEC | VEN-HVAC | 2200011350 | Air in let in CCR Room | Mount plate for inlet | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 16 | 0 | W47-47 IOP 08-21/11-22 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-05-24 | 2022-02-23 | 20 | PCNF REL | APPR OPND | HB /D /09/HBDC-A-1253 | HVAC AHU FOR LEVELS 1, 2 & LEVEL 2 MEZZ. |  | A |  | MEL | DK50
2024-W47-48 | 3 | NOSD | WGN | MTN-ELEC | VEN-HVAC | 2200011350 | Air in let in CCR Room | Mount guide rails for fabricair diffuss. | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 24 | 0 | W47-47 IOP 08-21/11-22 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-05-24 | 2022-02-23 | 30 | PCNF REL | APPR OPND | HB /D /09/HBDC-A-1253 | HVAC AHU FOR LEVELS 1, 2 & LEVEL 2 MEZZ. |  | A |  | MEL | DK50
2024-W47-48 | 3 | NOSD | WGN | MTN-ELEC | VEN-HVAC | 2200011350 | Air in let in CCR Room | Mount fabricair diffussors | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 24 | 0 | W47-47 IOP 08-21/11-22 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-05-24 | 2022-02-23 | 40 | PCNF REL | APPR OPND | HB /D /09/HBDC-A-1253 | HVAC AHU FOR LEVELS 1, 2 & LEVEL 2 MEZZ. |  | A |  | MEL | DK50
2024-W47-48 | 3 | NOSD | WGN | MTN-ELEC | VEN-HVAC | 2200011350 | Air in let in CCR Room | Mount diffussor in runner area | REL PCNF GMPS MANC PPRT PRC SETC | APPR APOG CMAT AWDO RDBL RFRZ ROUT | 10 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-05-24 | 2022-02-23 | 45 | REL | INIT OPND | HB /D /09/HBDC-A-1253 | HVAC AHU FOR LEVELS 1, 2 & LEVEL 2 MEZZ. |  | A |  | MEL | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-MECH | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | SO til Ramboll Survey | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-01 | 2020-12-30 | 2020-08-02 | 10 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-MECH | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Offshore PA asist to ECOW for 3D survey | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-01 | 2020-12-30 | 2020-08-02 | 20 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-MECH | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | additional materials | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 0 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-01 | 2020-12-30 | 2020-08-02 | 30 | REL | APPR OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-ROPE | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Preapre rigging of spool | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 18 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-01 | 2020-12-30 | 2020-08-02 | 40 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-SCAF | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Prepare scaffolding | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 32 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-02 | 2020-12-30 | 2020-08-02 | 50 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | PRODTECH | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Isolate line | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-04 | 2020-12-30 | 2020-08-02 | 60 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-PIPF | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | BoC + removal of bolts and gasket | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 18 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-04 | 2020-12-30 | 2020-08-02 | 70 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-RIGG | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Rigging of old spool | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-05 | 2020-12-30 | 2020-08-02 | 80 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-PIPF | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Cleaning of gasket surface | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-07 | 2020-12-30 | 2020-08-02 | 90 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | INP-SITE | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | SI to decide if flanges needs machining | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 2 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-07 | 2020-12-30 | 2020-08-02 | 100 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-PIPF | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Possible machining of flange face | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 18 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-07 | 2020-12-30 | 2020-08-02 | 110 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-RIGG | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Rigging of new spool | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 24 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-08 | 2020-12-30 | 2020-08-02 | 120 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-PIPF | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Insert gaskets and torque bolts | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 14 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-10 | 2020-12-30 | 2020-08-02 | 130 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | PRODTECH | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Handover to PRODTECH | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 1 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-11 | 2020-12-30 | 2020-08-02 | 140 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-ROPE | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Removal of rigging equipment | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 12 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-11 | 2020-12-30 | 2020-08-02 | 150 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-SCAF | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Removal of scaffolding | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 18 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-11 | 2020-12-30 | 2020-08-02 | 160 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2026-W13-14 | 4 | HBA09-GL | WDF | MTN-PIPF | MTN-RIGG | 2100031944 | FFSPR HBA-09 Replace well flowline Choke | Clean up workspace | REL PRT GMPS MANC PRC SETC | APPR APOG CMAT AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-13 | 2025-01-12 | 2020-12-30 | 2020-08-02 | 170 | REL | INIT OPND | HB /A /10/HBA-6-PHS-030-4092-FE-U | 6 HIGH PRESS WELL SOUR LINE | 99000119 | E |  | MFM | DK50
2024-W27-28 | 4 |  | WGN | PRODTECH | PRODTECH | 2200017582 | Replace cyclone liners 5071/-5072/-5073 | Replace cyclone liners 5071/-5072/-5073 | REL GMPS MANC PRC SETC | APPR APOG CMAT | 0 | 0 |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2027-01-30 | 2024-08-13 | 10 | REL | APPR OPND | HB /D /27/HBDB-A-5070 | HYDROCYCLONE SKID (3 X 50%) |  | E |  | PRD | DK50
2024-W27-28 | 4 |  | WGN | PRODTECH | PRODTECH | 2200017582 | Replace cyclone liners 5071/-5072/-5073 | Replace cyclone liners 5071/-5072/-5073 | REL GMPS MANC PRC SETC | APPR APOG CMAT | 0 | 0 |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2027-01-30 | 2024-08-13 | 20 | REL | INIT OPND | HB /D /27/HBDB-A-5070 | HYDROCYCLONE SKID (3 X 50%) |  | E |  | PRD | DK50
2024-W27-28 | 4 |  | WGN | PRODTECH | PRODTECH | 2200017582 | Replace cyclone liners 5071/-5072/-5073 | Replace cyclone liners 8/4-2024 | REL GMPS MANC PRC SETC | APPR APOG CMAT | 0 | 0 |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2027-01-30 | 2024-08-13 | 30 | REL | INIT OPND | HB /D /27/HBDB-A-5070 | HYDROCYCLONE SKID (3 X 50%) |  | E |  | PRD | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-MECH | 2100026273 | LOTI:CMAT:Replacement of 8" XCV-30208 | Material line | REL PCNF PRT CSER MANC PRC SETC | APPR APOG AWSC RDBL | 12 | 12 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-03-26 | 2017-02-14 | 10 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30208 | 8" 2500# T PLUG VALVE FROM WELL 20 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-SCAF | 2100026273 | LOTI:CMAT:Replacement of 8" XCV-30208 | Preparation for rigging of the valve | REL PCNF PRT CSER MANC PRC SETC | APPR APOG AWSC RDBL | 8.7 | 0 | LOTI | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-03-26 | 2017-02-14 | 20 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30208 | 8" 2500# T PLUG VALVE FROM WELL 20 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | PRODTECH | 2100026273 | LOTI:CMAT:Replacement of 8" XCV-30208 | Safing | REL PCNF PRT CSER MANC PRC SETC | APPR APOG AWSC RDBL | 0.1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-03-26 | 2017-02-14 | 30 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30208 | 8" 2500# T PLUG VALVE FROM WELL 20 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-INST | 2100026273 | LOTI:CMAT:Replacement of 8" XCV-30208 | Remove hydr lines&positnr from actuator | REL PCNF PRT CSER MANC PRC SETC | APPR APOG AWSC RDBL | 2.7 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-03-26 | 2017-02-14 | 40 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30208 | 8" 2500# T PLUG VALVE FROM WELL 20 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-RIGG | 2100026273 | LOTI:CMAT:Replacement of 8" XCV-30208 | Rigging assistance for removal of the va | REL PCNF PRT CSER MANC PRC SETC | APPR APOG AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-03-26 | 2017-02-14 | 50 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30208 | 8" 2500# T PLUG VALVE FROM WELL 20 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-MECH | 2100026273 | LOTI:CMAT:Replacement of 8" XCV-30208 | Removal of defective valve | REL PCNF PRT CSER MANC PRC SETC | APPR APOG AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-03-26 | 2017-02-14 | 60 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30208 | 8" 2500# T PLUG VALVE FROM WELL 20 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-RIGG | 2100026273 | LOTI:CMAT:Replacement of 8" XCV-30208 | Rigging assistance for installation of t | REL PCNF PRT CSER MANC PRC SETC | APPR APOG AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-03-26 | 2017-02-14 | 70 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30208 | 8" 2500# T PLUG VALVE FROM WELL 20 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-MECH | 2100026273 | LOTI:CMAT:Replacement of 8" XCV-30208 | Mounting of the new valve | REL PCNF PRT CSER MANC PRC SETC | APPR APOG AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-03-26 | 2017-02-14 | 80 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30208 | 8" 2500# T PLUG VALVE FROM WELL 20 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-INST | 2100026273 | LOTI:CMAT:Replacement of 8" XCV-30208 | Remount hydr lines+positnior to actuator | REL PCNF PRT CSER MANC PRC SETC | APPR APOG AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2017-03-26 | 2017-02-14 | 90 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30208 | 8" 2500# T PLUG VALVE FROM WELL 20 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | PRODTECH | 2100026273 | LOTI:CMAT:Replacement of 8" XCV-30208 | Desafing and leak test | REL PCNF PRT CSER MANC PRC SETC | APPR APOG AWSC RDBL | 0.1 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2017-03-26 | 2017-02-14 | 100 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30208 | 8" 2500# T PLUG VALVE FROM WELL 20 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | PRODTECH | 2100026273 | LOTI:CMAT:Replacement of 8" XCV-30208 | Function test | REL PCNF PRT CSER MANC PRC SETC | APPR APOG AWSC RDBL | 4 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2017-03-26 | 2017-02-14 | 110 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30208 | 8" 2500# T PLUG VALVE FROM WELL 20 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 3 | HBA20-GL | WDF | MTN-MECH | MTN-SCAF | 2100026273 | LOTI:CMAT:Replacement of 8" XCV-30208 | Removal of rigging equipment | REL PCNF PRT CSER MANC PRC SETC | APPR APOG AWSC RDBL | 8.7 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2017-03-26 | 2017-02-14 | 120 | PCNF REL | APPR OPND | HB /A /10/HBAA-XCV-30208 | 8" 2500# T PLUG VALVE FROM WELL 20 | 99000119 | F |  | MMS | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100071447 | FLM ANOS HBD - Install Handrail Join Lin | HBD - Install Handrail Join Link EL35000 | REL MANC NMAT PRC SETC | APPR APOG AWSC RDBL | 0 | 0 |  | 2023-08-07 | 2023-08-08 | 2023-08-07 | 2023-12-31 | 2023-01-04 | 10 | REL | APPR OPND | HB /D /86/35000 - HANDRAILS | 35000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100071447 | FLM ANOS HBD - Install Handrail Join Lin | Survey number of missing handrail links | REL MANC NMAT PRC SETC | APPR APOG AWSC RDBL | 3 | 0 |  | 2023-08-07 | 2023-08-08 | 2023-08-07 | 2023-12-31 | 2023-01-04 | 20 | REL | INIT OPND | HB /D /86/35000 - HANDRAILS | 35000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100071447 | FLM ANOS HBD - Install Handrail Join Lin | Order materials | REL MANC NMAT PRC SETC | APPR APOG AWSC RDBL | 1 | 0 |  | 2023-08-07 | 2023-08-08 | 2023-08-07 | 2023-12-31 | 2023-01-04 | 30 | REL | INIT OPND | HB /D /86/35000 - HANDRAILS | 35000 - HANDRAILS |  | A |  | MFM | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100071447 | FLM ANOS HBD - Install Handrail Join Lin | Install missing handrail links | REL MANC NMAT PRC SETC | APPR APOG AWSC RDBL | 12 | 0 |  | 2023-08-07 | 2023-08-08 | 2023-08-07 | 2023-12-31 | 2023-01-04 | 40 | REL | INIT OPND | HB /D /86/35000 - HANDRAILS | 35000 - HANDRAILS |  | A |  | MFM | DK50
0 | 3 | NOSD | WGN | MTN-TURB | MTN-TURB | 2200015859 | NOX messurements Haldfan A 2023. | NOX messurements Haldfan A 2023 | REL MANC NMAT PRC SETC | APPR APOG AWSC RDBL | 0 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-24 | 2023-11-10 | 10 | REL | APPR OPND | HD /A | HALFDAN DA |  | B |  | MMR | DK60
0 | 3 | NOSD | WGN | MTN-TURB | MTN-TURB | 2200015859 | NOX messurements Haldfan A 2023. | Support vendor | REL MANC NMAT PRC SETC | APPR APOG AWSC RDBL | 8 | 0 |  | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-03-24 | 2023-11-10 | 20 | REL | INIT OPND | HD /A | HALFDAN DA |  | B |  | MMR | DK60
2024-W29-30 | D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259611 | 2Y REMOTE WELL PANEL MAINT-HBBB-FP-3141B | REMOTE WELL PANEL MAINT-HBBB-FP-3141B | REL PCNF MANC NMAT PRC SETC | APPR APOG AWSC RDBL | 5 | 1.5 | W29-30 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-06-24 | 2023-04-12 | 10 | PCNF REL | APPR OPND | HB /B /07/HBBB-FP-3141B | FIELD PANEL |  | A | DKHB-2063 | MMS | DK50 | MS0064
2024-W29-30 | D | NOSD | WPM | MTN-MECH | MTN-INST | 2400259611 | 2Y REMOTE WELL PANEL MAINT-HBBB-FP-3141B | REMOTE WELL PANEL MAINT-HBBB-FP-3141B | REL PCNF MANC NMAT PRC SETC | APPR APOG AWSC RDBL | 1.5 | 1.5 | W29-30 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2023-06-24 | 2023-04-12 | 20 | PCNF REL | APPR OPND | HB /B /07/HBBB-FP-3141B | FIELD PANEL |  | A | DKHB-2063 | MMS | DK50 | MS0064
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093818 | Sewage tank inspection | Sewage tank inspection | REL MANC NMAT PRC SETC | APPR APOG AWSC | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2023-11-27 | 2023-07-15 | 10 | REL | APPR OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | C |  | MMS | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093818 | Sewage tank inspection | Isolate and verifification by production | REL MANC NMAT PRC SETC | APPR APOG AWSC | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2023-11-27 | 2023-07-15 | 20 | REL | INIT OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | C |  | MMS | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093818 | Sewage tank inspection | Inspection of sewage tank | REL MANC NMAT PRC SETC | APPR APOG AWSC | 16 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2023-11-27 | 2023-07-15 | 30 | REL | INIT OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | C |  | MMS | DK60 |  | PROK
0 | 3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093818 | Sewage tank inspection | De-isolate | REL MANC NMAT PRC SETC | APPR APOG AWSC | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-10 | 2024-04-10 | 2023-11-27 | 2023-07-15 | 40 | REL | INIT OPND | HD /B /82/HDBC-A-5150 | SEWAGE UNIT |  | C |  | MMS | DK60 |  | PROK
2026-W1-2 | 4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025867 | Cleaning of HBBA-T-5003 (open drain) | L3 Isolation of HBBA-T-5003 | REL PRT MANC PRC SETC | APPR APOG AWDO SCH RFRZ ROUT | 3 | 0 | W45-46 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2019-09-14 | 2019-04-17 | 10 | REL | APPR OPND | HB /B /28/HBBA-T-5003 | OPEN DRAIN TANK |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025867 | Cleaning of HBBA-T-5003 (open drain) | L2 Build Kofferdam | REL PRT MANC PRC SETC | APPR APOG AWDO SCH RFRZ ROUT | 16 | 0 | W45-46 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2019-09-14 | 2019-04-17 | 15 | REL | APPR OPND | HB /B /28/HBBA-T-5003 | OPEN DRAIN TANK |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025867 | Cleaning of HBBA-T-5003 (open drain) | L2 Cleaning of HBBA-T-5003 | REL PRT MANC PRC SETC | APPR APOG AWDO SCH RFRZ ROUT | 5 | 0 | W45-46 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2019-09-14 | 2019-04-17 | 20 | REL | APPR OPND | HB /B /28/HBBA-T-5003 | OPEN DRAIN TANK |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025867 | Cleaning of HBBA-T-5003 (open drain) | L3 Clean up chemical spill (if any) | REL PRT MANC PRC SETC | APPR APOG AWDO SCH RFRZ ROUT | 6 | 0 | W45-46 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2019-09-14 | 2019-04-17 | 25 | REL | APPR OPND | HB /B /28/HBBA-T-5003 | OPEN DRAIN TANK |  | A |  | MMS | DK50
2026-W1-2 | 4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025867 | Cleaning of HBBA-T-5003 (open drain) | L3 De-Isolation/test suction HBBA-T-5003 | REL PRT MANC PRC SETC | APPR APOG AWDO SCH RFRZ ROUT | 3 | 0 | W45-46 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2019-09-14 | 2019-04-17 | 30 | REL | APPR OPND | HB /B /28/HBBA-T-5003 | OPEN DRAIN TANK |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100059597 | HBC/78: Replace wood in boom rest | Build scaffoldng repo around boom rest | REL MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 50 | 0 | W07-W08 | 2024-09-18 | 2025-01-01 | 2024-09-18 | 2022-03-29 | 2021-12-29 | 10 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059597 | HBC/78: Replace wood in boom rest | Measure dimensions of wood blocks in boo | REL MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 12 | 0 | W07-W08 | 2024-09-18 | 2025-01-01 | 2024-09-23 | 2022-03-29 | 2021-12-29 | 20 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059597 | HBC/78: Replace wood in boom rest | Check new materials is correct and drill | REL MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 6 | 0 | W07-W08 | 2024-09-18 | 2025-01-01 | 2024-12-24 | 2022-03-29 | 2021-12-29 | 30 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059597 | HBC/78: Replace wood in boom rest | Replace wood blocks, bolts and nuts | REL MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 12 | 0 | W07-W08 | 2024-09-18 | 2025-01-01 | 2024-12-25 | 2022-03-29 | 2021-12-29 | 40 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100059597 | HBC/78: Replace wood in boom rest | Assist MTN-CRAN with lifting wood blocks | REL MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 6 | 0 | W07-W08 | 2024-09-18 | 2025-01-01 | 2024-12-25 | 2022-03-29 | 2021-12-29 | 50 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100059597 | HBC/78: Replace wood in boom rest | Remove scaffolding repo | REL MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 50 | 0 | W07-W08 | 2024-09-18 | 2025-01-01 | 2024-12-27 | 2022-03-29 | 2021-12-29 | 60 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059597 | HBC/78: Replace wood in boom rest | Cleanup, upload pictures, scrap old mats | REL MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 2 | 0 | W07-W08 | 2024-09-18 | 2025-01-01 | 2025-01-01 | 2022-03-29 | 2021-12-29 | 70 | REL | APPR OPND | HB /C /78/HBCO-A-6101 | CRANE - 16 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100059598 | HBD/78: Replace wood in boom rest | Build scaffoldng repo around boom rest | REL PCNF PRT MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 100 | 0 | W07-W08 | 2024-09-16 | 2024-12-28 | 2024-09-16 | 2022-03-29 | 2021-12-29 | 10 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059598 | HBD/78: Replace wood in boom rest | Measure dimensions of wood blocks in boo | REL PCNF PRT MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 12 | 5 | W07-W08 | 2024-09-16 | 2024-12-28 | 2024-09-17 | 2022-03-29 | 2021-12-29 | 20 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059598 | HBD/78: Replace wood in boom rest | Check new materials is correct and drill | REL PCNF PRT MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 6 | 0 | W07-W08 | 2024-09-16 | 2024-12-28 | 2024-12-18 | 2022-03-29 | 2021-12-29 | 30 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059598 | HBD/78: Replace wood in boom rest | Replace wood blocks, bolts and nuts | REL PCNF PRT MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 12 | 0 | W07-W08 | 2024-09-16 | 2024-12-28 | 2024-12-19 | 2022-03-29 | 2021-12-29 | 40 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100059598 | HBD/78: Replace wood in boom rest | Assist MTN-CRAN with lifting wood blocks | REL PCNF PRT MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 12 | 0 | W07-W08 | 2024-09-16 | 2024-12-28 | 2024-12-19 | 2022-03-29 | 2021-12-29 | 50 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100059598 | HBD/78: Replace wood in boom rest | Remove scaffolding repo | REL PCNF PRT MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 100 | 0 | W07-W08 | 2024-09-16 | 2024-12-28 | 2024-12-21 | 2022-03-29 | 2021-12-29 | 60 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059598 | HBD/78: Replace wood in boom rest | Cleanup, upload pictures, scrap old mats | REL PCNF PRT MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 2 | 0 | W07-W08 | 2024-09-16 | 2024-12-28 | 2024-12-28 | 2022-03-29 | 2021-12-29 | 70 | PCNF REL | APPR OPND | HB /D /78/HBDE-A-6150 | CRANE - 60 T |  | A |  | MMS | DK50
2024-W15-16 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100074268 | Defect Eexd JB-4201 needs replacement. | Defect Eexd JB-4201 needs replacement. | REL MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2025-08-23 | 2023-03-07 | 10 | REL | APPR OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | A |  | MEL | DK50 |  |  | 2024-04-21
2024-W15-16 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100074268 | Defect Eexd JB-4201 needs replacement. | Additionat materials | REL MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 0 | 0 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2025-08-23 | 2023-03-07 | 20 | REL | INIT OPND | HB /C /01/HBCM-A-0331 | FIREWATER PUMP PACKAGE |  | A |  | MEL | DK50 |  |  | 2024-04-22
2024-W27-28 | 1 | NE | WDF | MTN-PIPF | MTN-MECH | 2100109317 | ANOPR: Replace 1" Bypass spool. | HBA - Pinhole on 14"-WI-354002-GFW | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-03-31 | 2024-03-16 | 10 | PCNF REL | APPR OPND | HB /A /50/HBA-14-WI-035-4002-GFW-U | 14 INJECTION WATER LINE |  | F |  | MFM | DK50 |  |  | 2024-06-02
2024-W27-28 | 1 | NE | WDF | MTN-PIPF | MTN-MECH | 2100109317 | ANOPR: Replace 1" Bypass spool. | EMS Materials - 01 (Boat) | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-03-31 | 2024-03-16 | 20 | PCNF REL | APPR OPND | HB /A /50/HBA-14-WI-035-4002-GFW-U | 14 INJECTION WATER LINE |  | F |  | MFM | DK50 |  |  | 2024-06-03
2024-W27-28 | 1 | NE | WDF | MTN-PIPF | MTN-MECH | 2100109317 | ANOPR: Replace 1" Bypass spool. | EMS Materials - 02 (Heli) | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 0 | 0 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-03-31 | 2024-03-16 | 30 | PCNF REL | APPR OPND | HB /A /50/HBA-14-WI-035-4002-GFW-U | 14 INJECTION WATER LINE |  | F |  | MFM | DK50 |  |  | 2024-06-04
2024-W27-28 | 1 | NE | WDF | MTN-PIPF | MTN-SCAF | 2100109317 | ANOPR: Replace 1" Bypass spool. | Build Hbitat | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 0 | 10 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-03-31 | 2024-03-16 | 40 | PCNF REL | APPR OPND | HB /A /50/HBA-14-WI-035-4002-GFW-U | 14 INJECTION WATER LINE |  | F |  | MFM | DK50 |  |  | 2024-06-05
2024-W27-28 | 1 | NE | WDF | MTN-PIPF | MTN-SCAF | 2100109317 | ANOPR: Replace 1" Bypass spool. | Remove Habitat | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO RDBL RFRZ ROUT | 0 | 8 | W15-W16 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-03-31 | 2024-03-16 | 50 | PCNF REL | APPR OPND | HB /A /50/HBA-14-WI-035-4002-GFW-U | 14 INJECTION WATER LINE |  | F |  | MFM | DK50 |  |  | 2024-06-06
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100035441 | ANOCR Corroded beam HDC | Corroded beam HDC | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO AWSC RFRZ ROUT | 80 | 61 |  | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2020-09-08 | 2020-07-30 | 10 | PCNF REL | APPR OPND | HD /C /78/HDCZ-X-6120 | RUNWAY BEAM SWL. HDCZ-01-00022-0000 |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100035441 | ANOCR Corroded beam HDC | Extended handrails | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO AWSC RFRZ ROUT | 60 | 32 |  | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2020-09-08 | 2020-07-30 | 20 | PCNF REL | INIT OPND | HD /C /78/HDCZ-X-6120 | RUNWAY BEAM SWL. HDCZ-01-00022-0000 |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100035441 | ANOCR Corroded beam HDC | Dismantling extended handrail | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO AWSC RFRZ ROUT | 18 | 36 |  | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2020-09-08 | 2020-07-30 | 30 | PCNF REL | INIT OPND | HD /C /78/HDCZ-X-6120 | RUNWAY BEAM SWL. HDCZ-01-00022-0000 |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100035441 | ANOCR Corroded beam HDC | Erect scaffold Access | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO AWSC RFRZ ROUT | 100 | 0 |  | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2020-09-08 | 2020-07-30 | 40 | PCNF REL | INIT OPND | HD /C /78/HDCZ-X-6120 | RUNWAY BEAM SWL. HDCZ-01-00022-0000 |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100035441 | ANOCR Corroded beam HDC | Prep and prime corroded areas | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO AWSC RFRZ ROUT | 380 | 0 |  | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2020-09-08 | 2020-07-30 | 50 | PCNF REL | INIT OPND | HD /C /78/HDCZ-X-6120 | RUNWAY BEAM SWL. HDCZ-01-00022-0000 |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100035441 | ANOCR Corroded beam HDC | Coat to paint spec | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO AWSC RFRZ ROUT | 460 | 0 |  | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2020-09-08 | 2020-07-30 | 60 | PCNF REL | INIT OPND | HD /C /78/HDCZ-X-6120 | RUNWAY BEAM SWL. HDCZ-01-00022-0000 |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100035441 | ANOCR Corroded beam HDC | QC Paint report | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO AWSC RFRZ ROUT | 15 | 0 |  | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2020-09-08 | 2020-07-30 | 70 | PCNF REL | INIT OPND | HD /C /78/HDCZ-X-6120 | RUNWAY BEAM SWL. HDCZ-01-00022-0000 |  | A |  | MFM | DK60
0 | 3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100035441 | ANOCR Corroded beam HDC | Dismantle scaffold access | REL PCNF MANC NMAT PRC SETC | APPR APOG AWDO AWSC RFRZ ROUT | 100 | 9 |  | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2020-09-08 | 2020-07-30 | 80 | PCNF REL | INIT OPND | HD /C /78/HDCZ-X-6120 | RUNWAY BEAM SWL. HDCZ-01-00022-0000 |  | A |  | MFM | DK60
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100026212 | Retighten hydraulic connections on 600 B | Prep of scope | REL PRT MANC NMAT PRC SETC | APPR APOG AWDO AWSC RDBL RFRZ ROUT | 5 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-06-10 | 2019-01-11 | 8 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | D |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100026212 | Retighten hydraulic connections on 600 B | L3 Isolate equipment | REL PRT MANC NMAT PRC SETC | APPR APOG AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-06-10 | 2019-01-11 | 10 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | D |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | MTN-MECH | 2100026212 | Retighten hydraulic connections on 600 B | L3 Tighten hydraulic connections | REL PRT MANC NMAT PRC SETC | APPR APOG AWDO AWSC RDBL RFRZ ROUT | 8 | 0 | IOP | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2019-06-10 | 2019-01-11 | 20 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | D |  | MMS | DK50
2026-W13-14 | 4 | HBAPWELL | WDF | MTN-MECH | PRODTECH | 2100026212 | Retighten hydraulic connections on 600 B | L3 Remove isolation | REL PRT MANC NMAT PRC SETC | APPR APOG AWDO AWSC RDBL RFRZ ROUT | 4 | 0 |  | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2019-06-10 | 2019-01-11 | 30 | REL | APPR OPND | HB /A /07/HBAA-A-3112 | WELLHEAD CONTROL PANEL | 99000119 | D |  | MMS | DK50
2024-W27-28 | 3 | NE | WDF | MTN-TURB | MTN-TURB | 2100107682 | Potential Liq. fuel leak at filterA-1650 | Potential Liq. fuel leak at filterA-1650 | REL NMAT PRC SETC | APPR APOG | 0 | 0 |  | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-08-13 | 2024-03-31 | 10 | REL | APPR OPND | HB /D /60/HBDC-FIL-16050 | LIQUID FUEL FILTERS ASSY |  | A |  | MMR | DK50 |  | AW-INFO | 2024-04-22
2026-W13-14 | 3 | HB-DIFF | WDF | MTN-ELEC | VEN-ELEC | 2100024790 | Investigation-Hz reader N-1851 BUS B | L3 Investigation HBDC-N-1851B | REL PRT MANC NMAT PRC SETC | APPR | 24 | 0 | W17-W18 | 2024-04-26 | 2024-04-27 | 2024-04-26 | 2019-04-06 | 2019-01-06 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100026043 | Troubleshoot on Def. amp meassurement N- | Isolate | REL MANC PPRT PRC SETC | APPR | 2 | 0 | W13 DK50-M-6110 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2020-01-25 | 2019-12-16 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100026043 | Troubleshoot on Def. amp meassurement N- | Troubleshoot and correct or order spares | REL MANC PPRT PRC SETC | APPR | 3 | 0 | W13 DK50-M-6110 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2020-01-25 | 2019-12-16 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100026043 | Troubleshoot on Def. amp meassurement N- | De-isolate | REL MANC PPRT PRC SETC | APPR | 2 | 0 | W13 DK50-M-6110 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2020-01-25 | 2019-12-16 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1851 | 11KV MAIN HV SWITCHBOARD |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100027090 | SMAT:Replace Voltmeter FOR HBDB-PM-3653 | Isolate and pull out drawer | REL MANC PRC SETC | APPR | 2 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2020-07-13 | 2020-02-14 | 10 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M12-02 | O & E RELAY FOR HBDB-PM-3653 |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027090 | SMAT:Replace Voltmeter FOR HBDB-PM-3653 | Replace voltmeter | REL MANC PRC SETC | APPR | 1 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2020-07-13 | 2020-02-14 | 20 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M12-02 | O & E RELAY FOR HBDB-PM-3653 |  | C |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100027090 | SMAT:Replace Voltmeter FOR HBDB-PM-3653 | De-isolate | REL MANC PRC SETC | APPR | 2 | 0 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2020-07-13 | 2020-02-14 | 30 | REL | APPR OPND | HB /D /61/HBDC-N-1852-M12-02 | O & E RELAY FOR HBDB-PM-3653 |  | C |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073049 | Replace vibration dampers on HBCM-A-1235 | Recover refrigerant into receiver | REL PCNF MANC PRC SETC | APPR | 8 | 0 | W | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 10 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073049 | Replace vibration dampers on HBCM-A-1235 | Isolate compressor breaker | REL PCNF MANC PRC SETC | APPR | 1 | 0 | W | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 20 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100073049 | Replace vibration dampers on HBCM-A-1235 | Cut out / weld in flex pipes in system | REL PCNF MANC PRC SETC | APPR | 24 | 0 | W | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 40 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | CON-NDTI | 2100073049 | Replace vibration dampers on HBCM-A-1235 | X-ray (100%) of 4 welds | REL PCNF MANC PRC SETC | APPR | 12 | 0 |  | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 45 | REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073049 | Replace vibration dampers on HBCM-A-1235 | Leak test @10 bar with N2 | REL PCNF MANC PRC SETC | APPR | 12 | 0 | W | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 50 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073049 | Replace vibration dampers on HBCM-A-1235 | Apply vacuum, recharge refrigerant | REL PCNF MANC PRC SETC | APPR | 8 | 0 | W | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 60 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073049 | Replace vibration dampers on HBCM-A-1235 | Deisolate / test / top up refrigerant | REL PCNF MANC PRC SETC | APPR | 8 | 0 | W | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 70 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | MTN-PAIN | 2100073049 | Replace vibration dampers on HBCM-A-1235 | Paint | REL PCNF MANC PRC SETC | APPR | 2 | 0 | W | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2023-02-13 | 2022-10-01 | 80 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100073049 | Replace vibration dampers on HBCM-A-1235 | Insulate | REL PCNF MANC PRC SETC | APPR | 2 | 0 | W | 2024-04-19 | 2024-04-20 | 2024-04-20 | 2023-02-13 | 2022-10-01 | 90 | PCNF REL | APPR OPND | HB /C /09/HBCM-A-1235 | 1 UTILITY CONDENSING UNIT |  | A |  | MEL | DK50
2026-W13-14 | 4 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100107402 | FLM Install bolts in top deck holes HBA | Install bolts in top deck holes HBA | REL MANC NMAT PRC SETC | APPR | 16 | 0 |  | 2024-08-13 | 2024-08-15 | 2024-08-13 | 2027-01-30 | 2024-08-13 | 10 | REL | APPR OPND | HB /A /86/STRUCTURE | HBA PLATFORM STRUCTURES |  | A |  | MFM | DK50
2024-W37-38 | 2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100107406 | Flowtrend looks odd - FI-507601 | Replace Hart 09 Module 345102 | REL PCNF MANC PRC SETC | APPR | 20 | 0 |  | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2024-02-23 | 2024-01-09 | 20 | PCNF REL | APPR OPND | HB /D /27/HBDB-FIT-507601 | VORTEX FLOW TRANSM. (WATER)(METERING) |  | A |  | MIN | DK50
2024-W15-16 | 3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200013783 | Handheld vib meas. on rotating Eq | Handheld vib meas. on rotating Eq | REL MANC NMAT PRC SETC | APPR | 60 | 0 | W07-W08 | 2024-09-18 | 2024-09-30 | 2024-09-18 | 2023-09-04 | 2023-04-22 | 10 | REL | APPR OPND | HB /B /9 | SPECIFIC APPLICATION |  | A |  | MMT | DK50 |  |  | 2024-04-10
0 | 2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015797 | Locks on wardrobedoors in cabins | Locks on wardrobedoors in cabins | REL MANC NMAT PRC SETC | APPR | 10 | 0 | W47-48 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2023-10-30 | 2023-09-15 | 10 | REL | APPR OPND | HD /B /82 | LIVING AND WELFARE QTRS |  | A |  | MEL | DK60 |  | CC PROK
2024-W31-32 | 1 | NE | WGN | MTN-INST | MTN-MECH | 2200017718 | New icemachine in the mess hall | Replace 2 cylinders for the ice machine | REL MANC NMAT PRC SETC | APPR | 0 | 0 | W11-W12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-02-27 | 10 | REL | APPR OPND | HB /D /82/CATERING-EQUIPMENT | CATERING EQUIPMENT |  | A |  | MEL | DK50 |  |  | 2024-04-11
2024-W49-50 | 4 | NOSD | WRO | VEN-INST | MTN-TELE | 2300000877 | SIM F03. Feedbackfejl Ovr.key | F03. Feedbackfejl Ovr.key | REL PRT MANC NMAT PRC SETC | APPR | 36 | 0 | W49-50 | 2023-12-04 | 2023-12-04 | 2023-12-04 | 2014-03-18 | 2014-03-18 | 10 | REL | APPR OPND | HB /A /03/HBAA-FP-0120A | FIRE AND GAS PANEL |  | A |  | MIN | DK50
2024-W15-16 | 2 | NE | WRO | MTN-TELE | MTN-MECH | 2300007832 | HBA02/11 Rotary switch installation | HBA02/11 Rotary switch installation | REL PCNF MANC NMAT PRC SETC | APPR | 4 | 0 |  | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-03-21 | 2024-02-05 | 10 | PCNF REL | APPR OPND | HB /A /55/HBAA-MCV-30022 | MASTER CONTROL VALVE (WS) |  | A |  | MIN | DK50 |  |  | 2024-04-09
2024-W25-26 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001043 | HBA18, WL, Leaking tub, GLV, LI19708 | HBA18, WL, Leaking tub, GLV, LI19708 | REL MANC PRC SETC | APPR | 0 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 10 | REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2024-W25-26 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001043 | HBA18, WL, Leaking tub, GLV, LI19708 | Bennet WE tool | REL MANC PRC SETC | APPR | 0 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 20 | REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2024-W25-26 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001043 | HBA18, WL, Leaking tub, GLV, LI19708 | Well Sense | REL MANC PRC SETC | APPR | 0 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 30 | REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
2024-W25-26 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001043 | HBA18, WL, Leaking tub, GLV, LI19708 | HBA18, WL, Leaking tub, GLV, LI19708 | REL MANC PRC SETC | APPR | 0 | 0 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-03-10 | 2023-10-27 | 40 | REL | APPR OPND | HB /A | HALFDAN BA |  | A |  | WLD | DK50
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001244 | HDA15, wl, MFC, CA19779 | HDA15, wl, MFC, CA19779 | REL MACM PRC SETC | APPR | 0 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-02-18 | 2024-07-02 | 2024-02-18 | 10 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | PRODTECH | 2900001244 | HDA15, wl, MFC, CA19779 | Safing well/well handover (production) | REL MACM PRC SETC | APPR | 12 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-02-18 | 2024-07-02 | 2024-02-18 | 20 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-ROUS | 2900001244 | HDA15, wl, MFC, CA19779 | Crane assist during WL R/U and RD | REL MACM PRC SETC | APPR | 48 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-02-21 | 2024-07-02 | 2024-02-18 | 30 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-SCAF | 2900001244 | HDA15, wl, MFC, CA19779 | Scaffolder assistance for RU and RD | REL MACM PRC SETC | APPR | 50 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-02-27 | 2024-07-02 | 2024-02-18 | 40 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-ELEC | 2900001244 | HDA15, wl, MFC, CA19779 | Electrician assistance for RU and RD | REL MACM PRC SETC | APPR | 12 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-03-03 | 2024-07-02 | 2024-02-18 | 50 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-TELE | 2900001244 | HDA15, wl, MFC, CA19779 | Tele assist during WL RRU and RD | REL MACM PRC SETC | APPR | 24 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-03-05 | 2024-07-02 | 2024-02-18 | 60 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | VEN-CRAN | 2900001244 | HDA15, wl, MFC, CA19779 | Crane support assitance for days/nights | REL MACM PRC SETC | APPR | 240 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-03-10 | 2024-07-02 | 2024-02-18 | 70 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001244 | HDA15, wl, MFC, CA19779 | HDA15 slickline service | REL MACM PRC SETC | APPR | 0 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-04-04 | 2024-07-02 | 2024-02-18 | 80 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001244 | HDA15, wl, MFC, CA19779 | Oilenco tools | REL MACM PRC SETC | APPR | 0 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-04-04 | 2024-07-02 | 2024-02-18 | 90 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001244 | HDA15, wl, MFC, CA19779 | Ocean Team chemicals | REL MACM PRC SETC | APPR | 0 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-04-04 | 2024-07-02 | 2024-02-18 | 100 | REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001245 | HDA19, wl, logging, EL19780 | HDA19, wl, logging, EL19780 | REL PCNF MACM PRC SETC | APPR | 0 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-02-18 | 2024-07-02 | 2024-02-18 | 10 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | PRODTECH | 2900001245 | HDA19, wl, logging, EL19780 | Safing well/well handover (production) | REL PCNF MACM PRC SETC | APPR | 12 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-02-18 | 2024-07-02 | 2024-02-18 | 20 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-ROUS | 2900001245 | HDA19, wl, logging, EL19780 | Crane assist during WL R/U and RD | REL PCNF MACM PRC SETC | APPR | 48 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-02-21 | 2024-07-02 | 2024-02-18 | 30 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-SCAF | 2900001245 | HDA19, wl, logging, EL19780 | Scaffolder assistance for RU and RD | REL PCNF MACM PRC SETC | APPR | 50 | 47 |  | 2024-02-18 | 2024-04-04 | 2024-02-27 | 2024-07-02 | 2024-02-18 | 40 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-ELEC | 2900001245 | HDA19, wl, logging, EL19780 | Electrician assistance for RU and RD | REL PCNF MACM PRC SETC | APPR | 12 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-03-03 | 2024-07-02 | 2024-02-18 | 50 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | MTN-TELE | 2900001245 | HDA19, wl, logging, EL19780 | Tele assist during WL RRU and RD | REL PCNF MACM PRC SETC | APPR | 24 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-03-05 | 2024-07-02 | 2024-02-18 | 60 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | VEN-CRAN | 2900001245 | HDA19, wl, logging, EL19780 | Crane support assitance for days/nights | REL PCNF MACM PRC SETC | APPR | 240 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-03-10 | 2024-07-02 | 2024-02-18 | 70 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60
0 | 3 |  | WSO | WELLSUPV | WELLSUPV | 2900001245 | HDA19, wl, logging, EL19780 | WL logging | REL PCNF MACM PRC SETC | APPR | 0 | 0 |  | 2024-02-18 | 2024-04-04 | 2024-04-04 | 2024-07-02 | 2024-02-18 | 80 | PCNF REL | APPR OPND | HD /A | HALFDAN DA |  | A |  | WLD | DK60